## Contract
CONTRACT PRICE AND PROGRESS PAYMENT
NO | DESCRIPTION | CONTRACT PRICE (WIKA PORTION) | PROGRESS-1 | PROGRESS-2 | PROGRESS-3 | PROGRESS-4 | PROGRESS-5 | PROGRESS-6 | PROGRESS-7 | PROGRESS-8 | PROGRESS-9 | PROGRESS-10 | PROGRESS-11 | PROGRESS-12 | PROGRESS-13 | PROGRESS-14 | PROGRESS-15 | PROGRESS-16 | PROGRESS-17 | RUMUS CONTRACT PRICE |  | Until Last Month | This Month | Up to this month
[21 empty] | Print A | 253188670930 | 2810408948 | 255999079877
A | WIKA ONSHORE PORTION | [19 empty] | Print B | 1599040344254 | 164543219611 | 1.7636e+12
[21 empty] | Print C | 108519034477 | 4221242603 | 112740277081
A-1 | Engineering Services by WIKA | 327737902800.844 | 8713329240 | 14198081783 | 8876092995 | 15887157825 | 12511900748 | 47729345318 | 23232113520 | 41734749788 | 46772062837.5 | 27797862015.5 | 8213457945.5 | 5500835917.5 | 4566070162.5 | 3651247792.5 | 9912184012.5 | 3229541700.5 | 3229541700.5 | 327737687393 | Print D | 0 | 0 | 0
[22 empty] | 1960748049661 | 171574871162 | 2.1323e+12
A-2 | Onshore Equipments and/or Materials by WIKA | 787873603103.5609 | 21078871275 | 28281006600 | 64262089815 | 0 | 27627378240 | 32842573418 | 24388186515 | 111760156200 | 37178972985.5 | 8088650955.5 | 13883169300.5 | 4319351190.5 | 30669066120.5 | 50627891160.5 | 31862452545.5 | 19798634625.5 | 24946279628.5 | 787874361119.5
A-3 | Construction Services by WIKA | 435014441202.4615 | 756561960 | 756561960 | 0 | 1559444040 | 2051273648 | 3637416090 | 9690233438 | 4530043403 | 2123970503 | 3595277648 | 6030300623 | 4869724283 | 3724266315 | 9673185060 | 7793360190 | 18387800970 | 3802109850 | 435012833640
A-4 | Supervisory Services by WIKA | 2711783222.8106 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2711978693
B | WIKA OFFSHORE PORTION
B-1 | Offshore Equipments and/or Materials by KHI | 691014999999.9915 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115067863102.5 | 166631806687.5 | 79923437055 | 173063548349.5 | 26544967102.5 | 17364576652.5 | 9562531440 | 34948530540 | 691015130190
B-2 | Transportation Services for Equipment/Material by WIKA | 109192843168.345 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355120920 | 5127058283 | 11013251865 | 2465903055 | 0 | 1690041045 | 722465205 | 235138943 | 29560921583 | 109193571218
B-3 | Offshore Equipments and/or Materials by WIKA | 863129426501.9894 | 92317285830 | 0 | 21796511468 | 5018656335 | 9488869583 | 1039307693 | 52229473643 | 25178845230 | 21789434783 | 586078185 | 14097399855 | 11732822063 | 0 | 137329184108 | 82620940710 | 7379374118 | 75087487860 | 863129437747
| TOTAL | 3.2167e+12 | 122866048305 | 43235650343 | 94934694278 | 22465258200 | 51679422219 | 85248642519 | 109540007116 | 183203794621 | 108221813701 | 160262790189.5 | 219869386276.5 | 108812073564 | 212022950947.5 | 229516516268.5 | 150275979315.5 | 58593021797 | 171574871162 |  | TOTAL Progress | 2.1323e+12 | FALSE | -1
[22 empty] | 171574871162 | TRUE | 0
Jakarta, 2018
| Mengetahui, | [17 empty] | Dibuat Oleh,
(Baka Kusuma)

## SumProgres
No. | Description | Contract Amount - IDR | Weight Factor | Progress up to Last Month |  | Progress in This Month (M16) |  | Progress up to This Month
|  |  |  | Weight Progress |  | Weight Progress |  | Progress |  | Weight Progres
|  |  |  | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
|  |  | WF | PL' | AL' |  |  | PP | AP | PP' | AP'
[6 empty] | PP'-PL' | AL'-AP' |  |  | PP*WF | AP*WF
A | Project Management and Engineering | 430362902737.909 | 10.49% | 9.715% | 9.331% | 0.05456% | 0.08214% | 93.17% | 89.76% | 9.77% | 9.413%
B | Procurement and Transportation | 2.5533e+12 | 73.04% | 50.73% | 48.38% | 4.579% | 5.434% | 75.73% | 73.68% | 55.31% | 53.82%
C | Construction | 437726224424.8856 | 14.81% | 4.816% | 3.259% | 0.5622% | 0.1272% | 36.32% | 22.87% | 5.378% | 3.386%
D | Commissioning | 57075527565 | 1.668%
| Overall | 3.4214e+12 | 100% | 65.26% | 60.97% | 5.196% | 5.643% |  |  | 70.46% | 66.62%
No. | Description | Contract Amount - IDR | Weight Factor | Progress up to Last Month |  | Progress in This Month (M16) |  | Progress up to This Month |  |  |  | 2.4107e+12
|  |  |  | Weight Progress |  | Weight Progress |  | Progress |  | Weight Progress
|  |  |  | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | 2.2792e+12
|  |  | WF | PL' | AL' |  |  | PP | AP | PP' | AP'
[6 empty] | PP'-PL' | AL'-AP' |  |  | PP*WF | AP*WF
A | Project Management and Engineering | 430362902737.909 | 10.49% | 9.715% | 9.331% | 0.05456% | 0.08214% |  |  | 9.77% | 9.413%
| - WIKA Portion |  | 8.55% | 7.786% | 7.4% | 0.05456% | 0.08214% | 91.71% | 87.51% | 7.841% | 7.482% | -131428567092.5991
| - KHI Portion |  | 1.936% | 1.929% | 1.93% | 0% | 0% | 99.63% | 99.7% | 1.929% | 1.93%
B | Procurement and Transportation | 2.5533e+12 | 73.04% | 50.73% | 48.38% | 4.579% | 5.434% |  |  | 55.31% | 53.82%
| - WIKA Portion |  | 70.16% | 48.66% | 46.74% | 4.579% | 4.809% | 75.89% | 73.47% | 53.24% | 51.55%
| - KHI Portion |  | 2.881% | 2.068% | 1.647% | 0% | 0.6249% | 71.8% | 78.88% | 2.068% | 2.272%
C | Construction | 437726224424.8856 | 14.81% | 4.816% | 3.259% | 0.5622% | 0.1272% |  |  | 5.378% | 3.386%
| - WIKA Portion |  | 13.74% | 4.759% | 3.172% | 0.5622% | 0.1234% | 38.72% | 23.98% | 5.321% | 3.295%
| - KHI Portion |  | 1.063% | 0.05696% | 0.08728% | 0% | 0.003827% | 5.358% | 8.57% | 0.05696% | 0.09111%
D | Commissioning | 57075527565 | 1.668%
| - WIKA Portion | 53512455570 | 1.564%
| - KHI Portion |  | 0.1041%
| Total WIKA Portion |  | 94.02% | 61.21% | 57.31% | 5.196% | 5.015% |  |  | 66.4% | 62.32%
| Total KHI Portion |  | 5.984% | 4.055% | 3.665% | 0% | 0.6287% |  |  | 4.055% | 4.294%
| Total Overall (WIKA & KHI Portion) | 3421425000000 | 100% | 65.26% | 60.97% | 5.196% | 5.643% |  |  | 70.46% | 66.62% |  | -3.841%
[5 empty] | 60.97% | [5 empty] | 66.62%
[5 empty] | -1.289e-06% | [5 empty] | 2.167e-06%

## SumCommercial
| No. | Description | Overall | WIKA Portion |  | Ammount
A | A | Project Management and Engineering by WIKA | 8.55% | 9.094% |  | 292532466188 | 8.55% | 0
| 1 | Project Management and Engineering | 8.55% | 9.094% |  | 292532466188 | 8.55% | 0
B | B | Procurement and Transportation by WIKA | 70.16% | 74.62% |  | 2400411873667 | 70.16% | 0
| 1 | Onshore Equipments and/or Materials | 22.52% | 23.96% |  | 770599529700 | 22.52% | 0
| 2 | Offshore Equipments and/or Materials System 1 | 19.47% | 20.7% |  | 666010307077 | 19.47% | 0
| 3 | Offshore Equipments and/or Materials System 2, 3, 4 | 24.98% | 26.57% |  | 854608465672 | 24.98% | 0
| 4 | Transportation Services for Equipment/Material System 1 | 3.191% | 3.395% |  | 109193571218 | 3.191% | 0
C | C | Construction by WIKA | 13.74% | 14.62% |  | 470218054845 | 13.74% | 0
| 1 | Construction Services | 12.71% | 13.52% |  | 435012833640 | 12.71% | 0
| 2 | Insurance and other fee | 1.029% | 1.094% |  | 35205221205 | 1.029% | 0
D | D | Commissioning | 1.564% | 1.664% |  | 53512605300 | 1.564% | 0
| 1 | Supervisory Services | 0.07926% | 0.08431% |  | 2711978693 | 0.07926% | 0
| 2 | Spare Part for 1 year operation | 1.485% | 1.579% |  | 50800626607 | 1.485% | 0
0
| Total Overall Progress |  | 94.02% | 100% |  | 3216675000000 | 94.02% | 0
0
| No. | Description | Overall | WIKA Portion | % Progress | Ammount
A | A | Project Management and Engineering by WIKA | 0.08214% | 0.08737% | 0.9607% | 2810408948 | 0.08214% | 0
| 1 | Project Management and Engineering | 0.08214% | 0.08737% | 0.9607% | 2810408948 | 0.08214% | 0
B | B | Procurement and Transportation by WIKA | 4.809% | 5.115% | 6.855% | 164543219611 | 4.809% | 0
| 1 | Onshore Equipments and/or Materials | 0.7291% | 0.7755% | 3.237% | 24946279628 | 0.7291% | 0
| 2 | Offshore Equipments and/or Materials System 1 | 1.021% | 1.086% | 5.247% | 34948530540 | 1.021% | 0
| 3 | Offshore Equipments and/or Materials System 2, 3, 4 | 2.195% | 2.334% | 8.786% | 75087487860 | 2.195% | 0
| 4 | Transportation Services for Equipment/Material System 1 | 0.864% | 0.919% | 27.07% | 29560921583 | 0.864% | 0
C | C | Construction by WIKA | 0.1234% | 0.1312% | 0.8977% | 4221242603 | 0.1234% | 0
| 1 | Construction Services | 0.1111% | 0.1182% | 0.874% | 3802109850 | 0.1111% | 0
| 2 | Insurance and other fee | 0.01225% | 0.01303% | 1.191% | 419132753 | 0.01225% | 0
D | D | Commissioning | 0% | 0% | 0% | 0 | 0% | 0
| 1 | Supervisory Services | 0% | 0% | 0% | 0 | 0% | 0
| 2 | Spare Part for 1 year operation | 0% | 0% | 0% | 0 | 0% | 0
[7 empty] | 0% | 0
| Total Overall Progress May 31, 2018 |  | 5.015% | 5.334% |  | 171574871162 | 5.015% | 0
|  | Print A |  |  |  | 292532466188 | 253188670930 | 2810408948 | 255999079877
|  | Print B |  |  |  | 2.4004e+12 | 1599040344254 | 164543219611 | 1.7636e+12
|  | Print C |  |  |  | 470218054845 | 108519034477 | 4221242603 | 112740277081
|  | Print D |  |  |  | 53512605300 | 0 | 0 | 0
|  | TOTAL |  |  |  | 3.2167e+12 | 1960748049661 | 171574871162 | 2.1323e+12
0

## Print A
| Attachment 1 - Project Management and Engineering | [19 empty] | 2018-05-31
[13 empty] | 28267174898 | [7 empty] | 31077583846
| NO | DESCRIPTION |  |  | CONTRACT - IDR |  |  |  |  | PROGRESS
[5 empty] | FOREIGN PORTION | DOMESTIC PORTION | TOTAL |  |  | UNTIL PREVIOUS MONTH |  |  |  | THIS MONTH |  |  |  | UNTIL THIS MONTH
[7 empty] | % WEIGHT FACTOR (OVERALL) | % WEIGHT FACTOR (WIKA PORTION) | IDR | % WEIGHT FACTOR (OVERALL) | % WEIGHT FACTOR (WIKA PORTION) | % PROGRESS | IDR | % WEIGHT FACTOR (OVERALL) | % WEIGHT FACTOR (WIKA PORTION) | % PROGRESS | IDR | % WEIGHT FACTOR (OVERALL) | % WEIGHT FACTOR (WIKA PORTION) | % PROGRESS | IDR
| TOTAL |  |  |  | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! |  | #REF!
x | A. | WIKA Onshore Portion |  |  | #REF! | #REF! | #REF! |  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF! | #REF! |  |  | #REF!
A | A | PROJECT MANAGEMENT & ENGINEERING |  |  |  |  | 8.55% | 9.094% | 292532466188 | 7.4% | 7.871% |  | 253188670930 | 0.08214% | 0.08737% |  | 2810408948 | 7.482% | 7.958% |  | 255999079877 | 87.51% | 3.2167e+12
A.1 | A.1 | Engineering Services by WIKA |  |  | 1.979% | 6.571% | 8.55% | 9.094% | 292532466188 | 7.4% | 7.871% |  | 253188670930 | 0.08214% | 0.08737% |  | 2810408948 | 7.482% | 7.958% |  | 255999079877 | 87.51%
PROJECT MANAGEMENT & ENGINEERING
|  |  | Project Management |  |  | 1.637% | 1.637% | 1.741% | 55999738410 | 0.8729% | 0.9285% | 53.33% | 29866184040.5 | 0.05456% | 0.05803% | 3.333% | 1866636502.5 | 0.9275% | 0.9865% | 56.67% | 31732820543
Temporary Facility
|  |  |  | Mess |  | 0.1539% | 0.1539% | 0.1637% | 5266983645 | 0.08213% | 0.08736% | 53.33% | 2810087280 | 0.005133% | 0.00546% | 3.333% | 175630455 | 0.08727% | 0.09282% | 56.67% | 2985717735
|  |  |  | Camp |  | 0.712% | 0.712% | 0.7573% | 24360844777.5 | 0.712% | 0.7573% | 100% | 24360844779 |  |  |  |  | 0.712% | 0.7573% | 100% | 24360844779
|  |  |  | Warehouse |  | 0.09622% | 0.09622% | 0.1023% | 3291945195 | 0.09622% | 0.1023% | 100% | 3291945195 |  |  |  |  | 0.09622% | 0.1023% | 100% | 3291945195
|  |  |  | Site Office |  | 0.07697% | 0.07697% | 0.08187% | 2633491822.5 | 0.07698% | 0.08188% | 100% | 2633813490 |  |  |  |  | 0.07698% | 0.08188% | 100% | 2633813490
|  |  |  | Workshop |  | 0.05773% | 0.05773% | 0.0614% | 1975038450 | 0.05773% | 0.0614% | 100% | 1975038450 |  |  |  |  | 0.05773% | 0.0614% | 100% | 1975038450
|  |  |  | Storage Yard |  | 0.07697% | 0.07697% | 0.08187% | 2633491822.5 | 0.07697% | 0.08187% | 100% | 2633491823 |  |  |  |  | 0.07697% | 0.08187% | 100% | 2633491823
|  |  |  | Acces Road |  | 0.05773% | 0.05773% | 0.0614% | 1975038450 | 0.05773% | 0.0614% | 100% | 1975038450 |  |  |  |  | 0.05773% | 0.0614% | 100% | 1975038450
|  |  |  | Temporary Fencing |  | 0.01924% | 0.01924% | 0.02046% | 658131705 | 0.01924% | 0.02046% | 100% | 658131705 |  |  |  |  | 0.01924% | 0.02046% | 100% | 658131705
|  |  |  | Internet |  | 0.03849% | 0.03849% | 0.04094% | 1316906745 | 0.02046% | 0.02176% | 53.33% | 699948480 | 0.001279% | 0.00136% | 3.333% | 43746780 | 0.02174% | 0.02312% | 56.67% | 743695260
|  |  |  | Electricity Distribution |  | 0.5773% | 0.5773% | 0.614% | 19751671170 | 0.3079% | 0.3275% | 53.33% | 10535253959.5 | 0.01925% | 0.02047% | 3.333% | 658453372.5 | 0.3272% | 0.348% | 56.67% | 11193707332
|  |  |  | Water Distribution |  | 0.05773% | 0.05773% | 0.0614% | 1975038450 | 0.03083% | 0.03279% | 53.33% | 1054747732.5 | 0.001927% | 0.00205% | 3.333% | 65941837.5 | 0.03276% | 0.03484% | 56.67% | 1120689570
|  |  | Engineering |  | 1.979% | 3.01% | 4.989% | 5.307% | 170694145545 | 4.989% | 5.307% | 100% | 170694145545 | 0% | 0% | 0% | 0 | 4.989% | 5.307% | 100% | 170694145545

## Print B
| Attachment 2 - Procurement and Transporation | [21 empty] | 2018-05-31
| NO | DESCRIPTION |  |  |  |  | CONTRACT - IDR |  |  |  |  | PROGRESS
[7 empty] | FOREIGN PORTION | DOMESTIC PORTION | TOTAL |  |  | UNTIL PREVIOUS MONTH |  |  |  | THIS MONTH |  |  |  | UNTIL THIS MONTH |  |  |  | THIS MONTH
[9 empty] | % WEIGHT FACTOR (OVERALL) | % WEIGHT FACTOR (WIKA PORTION) | IDR | % WEIGHT FACTOR (OVERALL) | % WEIGHT FACTOR (WIKA PORTION) | % PROGRESS | IDR | % WEIGHT FACTOR (OVERALL) | % WEIGHT FACTOR (WIKA PORTION) | % PROGRESS | IDR | % WEIGHT FACTOR (OVERALL) | % WEIGHT FACTOR (WIKA PORTION) | % PROGRESS | IDR | % WEIGHT FACTOR (OVERALL)
B | B | PROCUREMENT & TRANSPORTATION | [6 empty] | 70.16% | 74.62% | 2.4004e+12 | 46.74% | 49.71% |  | 1599040344254 | 4.809% | 5.115% |  | 164543219611 | 51.55% | 54.83% |  | 1.7636e+12 | 1.044% | 73.47%
B.1 | B.1 | Onshore Equipments and/or Materials by WIKA | [5 empty] | 23.03% | 22.52% | 23.96% | 770599529700 | 14.81% | 15.75% |  | 506668450944 | 0.7291% | 0.7755% |  | 24946279628 | 15.54% | 16.53% |  | 531614730572 | 0.5417%
|  | B.1.1 | MECHANICAL EQUIPMENT |  |  |  |  | 4.634% | 4.634% | 4.929% | 158559560775 | 3.918% | 4.167% |  | 134041742261 | 0.1649% | 0.1754% |  | 5643334620 | 4.083% | 4.343% |  | 139685076881 | 0.2013%
|  | 1 | System 2
|  |  |  | Top Bin Covers |  |  |  | 0.1086% | 0.1087% | 0.1156% | 3717511297.5 | 0.1086% | 0.1156% | 100% | 3717189629 |  |  |  |  | 0.1086% | 0.1156% | 100% | 3717189629
|  |  |  | Container |  |  |  | 0.1261% | 0.1261% | 0.1341% | 4315169512.5 | 0.1009% | 0.1073% | 80% | 3452135610 |  |  |  |  | 0.1009% | 0.1073% | 80% | 3452135610 | 0.07567%
|  |  |  | Transfer Car |  |  |  | 0.1628% | 0.1628% | 0.1732% | 5571602767.5 | 0.1628% | 0.1732% | 100% | 5571602767.5 |  |  |  |  | 0.1628% | 0.1732% | 100% | 5571602767.5
|  |  |  | Furnace Top Bin |  |  |  | 0.2596% | 0.2596% | 0.2761% | 8880918007.5 | 0.2596% | 0.2761% | 100% | 8880918007.5 |  |  |  |  | 0.2596% | 0.2761% | 100% | 8880918007.5
|  |  |  | Charging tubes |  |  |  | 0.2394% | 0.2394% | 0.2547% | 8191906222.5 | 0.2394% | 0.2547% | 100% | 8191584555.5 |  |  |  |  | 0.2394% | 0.2547% | 100% | 8191584555.5
|  |  |  | Dust Collection Equipment |  |  |  | 0.1612% | 0.1612% | 0.1715% | 5516275957.5 | 0.1612% | 0.1715% | 100% | 5516275957.5 |  |  |  |  | 0.1612% | 0.1715% | 100% | 5516275957.5
|  |  |  | Auxiliaries |  |  |  | 0.02153% | 0.02153% | 0.0229% | 736618575 | 0.004306% | 0.00458% | 20% | 147323715 |  |  |  |  | 0.004306% | 0.00458% | 20% | 147323715
|  |  |  | Clamping frames |  |  |  | 0.02001% | 0.02001% | 0.02128% | 684508440 | 0.005002% | 0.00532% | 25% | 171127110 |  |  |  |  | 0.005002% | 0.00532% | 25% | 171127110
|  |  |  | Working Deck for Electrode |  |  |  | 0.01156% | 0.01156% | 0.0123% | 395651025
|  |  |  | Tapping Deck |  |  |  | 0.04265% | 0.04265% | 0.04536% | 1459083780 | 0.008527% | 0.00907% | 20% | 291752423 |  |  |  |  | 0.008527% | 0.00907% | 20% | 291752423
|  |  |  | Heat Prevention Board for Tapping Runner |  |  |  | 0.00149% | 0.001485% | 0.00158% | 50823465
|  |  |  | Hoist for Paste Charge and Mud Kneader |  |  |  | 0.05987% | 0.05987% | 0.06368% | 2048378640 | 0.05089% | 0.05413% | 85% | 1741186178 |  |  |  |  | 0.05089% | 0.05413% | 85% | 1741186178
|  | 2 | System 3
Desulphurizing System
|  |  |  | Stirrer Unit |  |  |  | 0.03267% | 0.03267% | 0.03475% | 1117794562.5 | 0.03267% | 0.03475% | 100% | 1117794563 |  |  |  |  | 0.03267% | 0.03475% | 100% | 1117794563
|  |  |  | Lifting Device |  |  |  | 0.02661% | 0.02661% | 0.0283% | 910319025 | 0.02661% | 0.0283% | 100% | 910319025 |  |  |  |  | 0.02661% | 0.0283% | 100% | 910319025
|  |  |  | Shifting Device and Swinging Part |  |  |  | 0.03728% | 0.03728% | 0.03965% | 1275411637.5 | 0.03728% | 0.03965% | 100% | 1275411637.5 |  |  |  |  | 0.03728% | 0.03965% | 100% | 1275411637.5
|  |  |  | Hoist |  |  |  | 0.01196% | 0.01196% | 0.01272% | 409161060 | 0.01195% | 0.01271% | 100% | 408839392.5 |  |  |  |  | 0.01195% | 0.01271% | 100% | 408839392.5
|  |  |  | Exhaust Gas Duct |  |  |  | 0.01729% | 0.01729% | 0.01839% | 591546532.5 | 0.01729% | 0.01839% | 100% | 591546532.5 |  |  |  |  | 0.01729% | 0.01839% | 100% | 591546532.5
|  |  |  | Work Stage |  |  |  | 0.07439% | 0.07439% | 0.07913% | 2545354927.5 | 0.0744% | 0.07914% | 100% | 2545676595 |  |  |  |  | 0.0744% | 0.07914% | 100% | 2545676595
Shot Making Equipment
|  |  |  | Ladle Tilting Machine |  |  |  | 0.1549% | 0.1549% | 0.1648% | 5300437065 | 0.1549% | 0.1648% | 100% | 5300758732.5 |  |  |  |  | 0.1549% | 0.1648% | 100% | 5300758732.5
|  |  |  | Runner |  |  |  | 0.01521% | 0.01521% | 0.01618% | 520458015 | 0.01522% | 0.01619% | 100% | 520779682.5 |  |  |  |  | 0.01522% | 0.01619% | 100% | 520779682.5
|  |  |  | Spray Head |  |  |  | 0.00292% | 0.002924% | 0.00311% | 100038592.5 | 0.002924% | 0.00311% | 100% | 100038592.5 |  |  |  |  | 0.002924% | 0.00311% | 100% | 100038592.5
|  |  |  | Shot Making Tank |  |  |  | 0.08764% | 0.08764% | 0.09322% | 2998584435 | 0.08763% | 0.09321% | 100% | 2998262767.5 |  |  |  |  | 0.08763% | 0.09321% | 100% | 2998262767.5
|  |  |  | No.1 Net Conveyor |  |  |  | 0.06563% | 0.06563% | 0.06981% | 2245560817.5 | 0.06563% | 0.06981% | 100% | 2245560817.5 |  |  |  |  | 0.06563% | 0.06981% | 100% | 2245560817.5
|  |  |  | Jet Water Pump |  |  |  | 0.00909% | 0.009091% | 0.00967% | 311052472.5 | 0.009082% | 0.00966% | 100% | 310730805 |  |  |  |  | 0.009082% | 0.00966% | 100% | 310730805
|  |  |  | Surge Hopper |  |  |  | 0.01364% | 0.01364% | 0.01451% | 466739542.5 | 0.01364% | 0.01451% | 100% | 466739542.5 |  |  |  |  | 0.01364% | 0.01451% | 100% | 466739542.5
|  |  |  | No.2 Net Conveyor |  |  |  | 0.07728% | 0.07728% | 0.0822% | 2644106850 | 0.07728% | 0.0822% | 100% | 2644106850 |  |  |  |  | 0.07728% | 0.0822% | 100% | 2644106850
|  |  |  | Hot Stove |  |  |  | 0.00674% | 0.006741% | 0.00717% | 230635597.5 | 0.006732% | 0.00716% | 100% | 230313930 |  |  |  |  | 0.006732% | 0.00716% | 100% | 230313930
|  |  |  | Burner Dilution Fan |  |  |  | 0.00486% | 0.004861% | 0.00517% | 166302097.5 | 0.004851% | 0.00516% | 100% | 165980430 |  |  |  |  | 0.004851% | 0.00516% | 100% | 165980430
|  |  |  | Hot Gas Circulation Fan |  |  |  | 0.00997% | 0.009966% | 0.0106% | 340967550 | 0.009966% | 0.0106% | 100% | 340967550 |  |  |  |  | 0.009966% | 0.0106% | 100% | 340967550
|  |  |  | Ducting |  |  |  | 0.01701% | 0.01701% | 0.01809% | 581896507.5 | 0.01701% | 0.01809% | 100% | 581896507.5 |  |  |  |  | 0.01701% | 0.01809% | 100% | 581896507.5
|  |  |  | Trommel |  |  |  | 0.02212% | 0.02212% | 0.02353% | 756883627.5 | 0.02213% | 0.02354% | 100% | 757205295 |  |  |  |  | 0.02213% | 0.02354% | 100% | 757205295
|  |  |  | Soundproof Box |  |  |  | 0.01631% | 0.01631% | 0.01735% | 558093112.5 | 0.01631% | 0.01735% | 100% | 558093112.5 |  |  |  |  | 0.01631% | 0.01735% | 100% | 558093112.5
|  |  |  | Container |  |  |  | 0.05569% | 0.05569% | 0.05923% | 1905236602.5 | 0.05569% | 0.05924% | 100% | 1905558270 |  |  |  |  | 0.05569% | 0.05924% | 100% | 1905558270
|  |  |  | Container Car |  |  |  | 0.0379% | 0.0379% | 0.04031% | 1296641692.5 | 0.0379% | 0.04031% | 100% | 1296641692.5 |  |  |  |  | 0.0379% | 0.04031% | 100% | 1296641692.5
|  |  |  | Shot Cooling Pump |  |  |  | 0.01987% | 0.01987% | 0.02113% | 679683427.5 | 0.01987% | 0.02114% | 100% | 680005095 |  |  |  |  | 0.01987% | 0.02114% | 100% | 680005095
|  |  |  | Cooling Tower |  |  |  | 0.04946% | 0.04946% | 0.05261% | 1692292717.5 | 0.04946% | 0.05261% | 100% | 1692292717.5 |  |  |  |  | 0.04946% | 0.05261% | 100% | 1692292717.5
|  |  |  | Cooling Tower Feed Pump |  |  |  | 0.01987% | 0.01987% | 0.02113% | 679683427.5 | 0.01987% | 0.02114% | 100% | 680005095 |  |  |  |  | 0.01987% | 0.02114% | 100% | 680005095
|  |  |  | Ladle Handling Crane |  |  |  | 0.7778% | 0.7778% | 0.8273% | 26610908940 | 0.7778% | 0.8273% | 100% | 26610908940 |  |  |  |  | 0.7778% | 0.8273% | 100% | 26610908940
|  |  |  | Ladles |  |  |  | 0.1578% | 0.1578% | 0.1679% | 5399510655 | 0.1578% | 0.1679% | 100% | 5399510655 |  |  |  |  | 0.1578% | 0.1679% | 100% | 5399510655 | 0.03156%
|  |  |  | Slag Pot |  |  |  | 0.03074% | 0.03074% | 0.0327% | 1051852725 | 0.03074% | 0.0327% | 100% | 1051852725 |  |  |  |  | 0.03074% | 0.0327% | 100% | 1051852725 | 0.006149%
|  |  |  | Hanger |  |  |  | 0.02597% | 0.02597% | 0.02762% | 888445635 | 0.00519% | 0.00552% | 20% | 177560460 |  |  |  |  | 0.00519% | 0.00552% | 20% | 177560460
|  |  |  | Service Tank |  |  |  | 0.00589% | 0.005885% | 0.00626% | 201363855 | 0.005885% | 0.00626% | 100% | 201363855 |  |  |  |  | 0.005885% | 0.00626% | 100% | 201363855
|  |  |  | Pump Unit |  |  |  | 0.00539% | 0.005387% | 0.00573% | 184315477.5 | 0.005396% | 0.00574% | 100% | 184637145 |  |  |  |  | 0.005396% | 0.00574% | 100% | 184637145
|  |  |  | Valve Unit |  |  |  | 0.01617% | 0.01617% | 0.0172% | 553268100 | 0.01617% | 0.0172% | 100% | 553268100 |  |  |  |  | 0.01617% | 0.0172% | 100% | 553268100
|  |  |  | Burner |  |  |  | 0.00735% | 0.007352% | 0.00782% | 251543985 | 0.007343% | 0.00781% | 100% | 251222317.5 |  |  |  |  | 0.007343% | 0.00781% | 100% | 251222317.5
|  |  |  | Blower |  |  |  | 0.00735% | 0.007352% | 0.00782% | 251543985 | 0.007343% | 0.00781% | 100% | 251222317.5 |  |  |  |  | 0.007343% | 0.00781% | 100% | 251222317.5
|  |  |  | Ladle Heating Unit |  |  |  | 0.06731% | 0.06731% | 0.07159% | 2302817632.5 | 0.06731% | 0.07159% | 100% | 2302817632.5 |  |  |  |  | 0.06731% | 0.07159% | 100% | 2302817632.5
|  |  |  | Casting Storage Crane |  |  |  | 0.077% | 0.07701% | 0.08191% | 2634778492.5 | 0.07701% | 0.08191% | 100% | 2634778492.5 |  |  |  |  | 0.07701% | 0.08191% | 100% | 2634778492.5
|  | 3 | System 4
|  |  |  | Raw Water Intake Pump |  |  |  | 0.00494% | 0.004936% | 0.00525% | 168875437.5 | 0.003949% | 0.0042% | 80% | 135100350 |  |  |  |  | 0.003949% | 0.0042% | 80% | 135100350 | 0.002961%
|  |  |  | Raw Water Intake Pump |  |  |  | 0.0124% | 0.0124% | 0.01319% | 424279432.5 | 0.009919% | 0.01055% | 80% | 339359212.5 |  |  |  |  | 0.009919% | 0.01055% | 80% | 339359212.5 | 0.007437%
|  |  |  | Clarifier |  |  |  | 0.03646% | 0.03646% | 0.03878% | 1247426565 | 0.03646% | 0.03878% | 100% | 1247426565 |  |  |  |  | 0.03646% | 0.03878% | 100% | 1247426565
|  |  |  | Water Transfer Pump |  |  |  | 0.00429% | 0.004287% | 0.00456% | 146680380 | 0.003432% | 0.00365% | 80% | 117408637.5 |  |  |  |  | 0.003432% | 0.00365% | 80% | 117408637.5 | 0.002576% |  | 0.002576%
|  |  |  | Water Transfer Pump |  |  |  | 0.03031% | 0.03031% | 0.03224% | 1037056020 | 0.02425% | 0.02579% | 80% | 829580482.5 |  |  |  |  | 0.02425% | 0.02579% | 80% | 829580482.5 | 0.01818% |  | 0.01818%
|  |  |  | No.1 Dosing Tank |  |  |  | 0.00207% | 0.002068% | 0.0022% | 70766850 | 0.0004137% | 0.00044% | 20% | 14153370 | 0.001655% | 0.00176% | 80% | 56613480 | 0.002068% | 0.0022% | 100% | 70766850 | 0.001241%
|  |  |  | Dosing Pump for No.1 Tank |  |  |  | 0.00239% | 0.002388% | 0.00254% | 81703545 | 0.001909% | 0.00203% | 80% | 65298502.5 |  |  |  |  | 0.001909% | 0.00203% | 80% | 65298502.5
|  |  |  | No.2 Dosing Tank |  |  |  | 0.00165% | 0.001655% | 0.00176% | 56613480 | 0.0003291% | 0.00035% | 20% | 11258362.5 | 0.001326% | 0.00141% | 80% | 45355117.5 | 0.001655% | 0.00176% | 100% | 56613480 | 0.0009966%
|  |  |  | Dosing Pump for No.2 Tank |  |  |  | 0.00239% | 0.002388% | 0.00254% | 81703545 | 0.001909% | 0.00203% | 80% | 65298502.5 |  |  |  |  | 0.001909% | 0.00203% | 80% | 65298502.5
|  |  |  | Receiving Water Pump |  |  |  | 0.00254% | 0.002538% | 0.0027% | 86850225 | 0.002538% | 0.0027% | 100% | 86850225 |  |  |  |  | 0.002538% | 0.0027% | 100% | 86850225
|  |  |  | Receiving Water Pump |  |  |  | 0.01072% | 0.01072% | 0.0114% | 366700950 | 0.01072% | 0.0114% | 100% | 366700950 |  |  |  |  | 0.01072% | 0.0114% | 100% | 366700950
|  |  |  | Sand Filter |  |  |  | 0.04986% | 0.04986% | 0.05303% | 1705802752.5 | 0.03989% | 0.04243% | 80% | 1364835202.5 | 0.009975% | 0.01061% | 20% | 341289217.5 | 0.04987% | 0.05304% | 100% | 1706124420 |  |  | -0.009975%
|  |  |  | Filtered Water Pond |  |  |  | 0% | 0% | 0% | 0
|  |  |  | Filtered Water Pump |  |  |  | 0.00344% | 0.003441% | 0.00366% | 117730305 | 0.003441% | 0.00366% | 100% | 117730305 |  |  |  |  | 0.003441% | 0.00366% | 100% | 117730305
|  |  |  | Filtered Water Pump |  |  |  | 0.01308% | 0.01308% | 0.01391% | 447439492.5 | 0.01308% | 0.01391% | 100% | 447439492.5 |  |  |  |  | 0.01308% | 0.01391% | 100% | 447439492.5
|  |  |  | Softener |  |  |  | 0.07203% | 0.07203% | 0.07661% | 2464294717.5 | 0.05762% | 0.06129% | 80% | 1971500107.5 | 0.0144% | 0.01532% | 20% | 492794610 | 0.07203% | 0.07661% | 100% | 2464294717.5 |  |  | -0.0144%
|  |  |  | NaCl Tank |  |  |  | 0.00286% | 0.002858% | 0.00304% | 97786920 | 0.002285% | 0.00243% | 80% | 78165202.5 |  |  |  |  | 0.002285% | 0.00243% | 80% | 78165202.5 | 0.001711%
|  |  |  | NSW- Circulation Pump |  |  |  | 0.00755% | 0.007549% | 0.00803% | 258299002.5 | 0.001514% | 0.00161% | 20% | 51788467.5 |  |  |  |  | 0.001514% | 0.00161% | 20% | 51788467.5
|  |  |  | NSW- Circulation Pump |  |  |  | 0.03357% | 0.03357% | 0.03571% | 1148674642.5 | 0.006713% | 0.00714% | 20% | 229670595 |  |  |  |  | 0.006713% | 0.00714% | 20% | 229670595
|  |  |  | NSW - Head Tank |  |  |  | 0.05051% | 0.05051% | 0.05373% | 1728319477.5 | 0.05051% | 0.05373% | 100% | 1728319477.5 |  |  |  |  | 0.05051% | 0.05373% | 100% | 1728319477.5
|  |  |  | NSW - Return Water Pump |  |  |  | 0.00282% | 0.00282% | 0.003% | 96500250 | 0.0005641% | 0.0006% | 20% | 19300050 |  |  |  |  | 0.0005641% | 0.0006% | 20% | 19300050
|  |  |  | NSW - Return Water Pump |  |  |  | 0.01538% | 0.01538% | 0.01636% | 526248030 | 0.003074% | 0.00327% | 20% | 105185272.5 |  |  |  |  | 0.003074% | 0.00327% | 20% | 105185272.5
|  |  |  | NSW - Cooling Tower |  |  |  | 0.0151% | 0.0151% | 0.01606% | 516598005 | 0.0151% | 0.01606% | 100% | 516598005.5 |  |  |  |  | 0.0151% | 0.01606% | 100% | 516598005.5
|  |  |  | SW - Circulation Pump |  |  |  | 0.00736% | 0.007361% | 0.00783% | 251865652.5 | 0.001476% | 0.00157% | 20% | 50501797.5 |  |  |  |  | 0.001476% | 0.00157% | 20% | 50501797.5
|  |  |  | SW - Circulation Pump |  |  |  | 0.03211% | 0.03211% | 0.03415% | 1098494512.5 | 0.006421% | 0.00683% | 20% | 219698902.5 |  |  |  |  | 0.006421% | 0.00683% | 20% | 219698902.5
|  |  |  | SW - Head Tank |  |  |  | 0.05942% | 0.05942% | 0.0632% | 2032938600 | 0.05942% | 0.0632% | 100% | 2032938600 |  |  |  |  | 0.05942% | 0.0632% | 100% | 2032938600
|  |  |  | SW - Return Water Pump |  |  |  | 0.00842% | 0.008424% | 0.00896% | 288214080 | 0.001683% | 0.00179% | 20% | 57578482.5 |  |  |  |  | 0.001683% | 0.00179% | 20% | 57578482.5
|  |  |  | SW - Return Water Pump |  |  |  | 0.02216% | 0.02216% | 0.02357% | 758170297.5 | 0.004428% | 0.00471% | 20% | 151505392.5 |  |  |  |  | 0.004428% | 0.00471% | 20% | 151505392.5
|  |  |  | SW - Cooling Tower |  |  |  | 0.03164% | 0.03164% | 0.03365% | 1082411137.5 | 0.03164% | 0.03365% | 100% | 1082411138 |  |  |  |  | 0.03164% | 0.03365% | 100% | 1082411138
|  |  |  | SW - Inline Filter |  |  |  | 0.00202% | 0.002021% | 0.00215% | 69158512.5 | 0.001617% | 0.00172% | 80% | 55326810 |  |  |  |  | 0.001617% | 0.00172% | 80% | 55326810 | 0.001213%
|  |  |  | SW - Circulation Pump |  |  |  | 0.00736% | 0.007361% | 0.00783% | 251865652.5 | 0.001476% | 0.00157% | 20% | 50501797.5 |  |  |  |  | 0.001476% | 0.00157% | 20% | 50501797.5
|  |  |  | SW - Circulation Pump |  |  |  | 0.03884% | 0.03884% | 0.04131% | 1328808442.5 | 0.007766% | 0.00826% | 20% | 265697355 |  |  |  |  | 0.007766% | 0.00826% | 20% | 265697355
|  |  |  | SW - Head Tank |  |  |  | 0.05051% | 0.05051% | 0.05373% | 1728319477.5 | 0.05051% | 0.05373% | 100% | 1728319478 |  |  |  |  | 0.05051% | 0.05373% | 100% | 1728319478
|  |  |  | SW - Return Water Pump |  |  |  | 0.00569% | 0.005688% | 0.00605% | 194608837.5 | 0.001138% | 0.00121% | 20% | 38921767.5 |  |  |  |  | 0.001138% | 0.00121% | 20% | 38921767.5
|  |  |  | SW - Return Water Pump |  |  |  | 0.02762% | 0.02762% | 0.02938% | 945059115 | 0.005528% | 0.00588% | 20% | 189140490 |  |  |  |  | 0.005528% | 0.00588% | 20% | 189140490
|  |  |  | SW - Cooling Tower |  |  |  | 0.04314% | 0.04314% | 0.04589% | 1476132157.5 | 0.04314% | 0.04589% | 100% | 1476132157.5 |  |  |  |  | 0.04314% | 0.04589% | 100% | 1476132157.5
|  |  |  | SW - Inline Filter; Auto Cleaning Type; Accessories. |  |  |  | 0.00172% | 0.00172% | 0.00183% | 58865152.5 | 0.001382% | 0.00147% | 80% | 47285122.5 |  |  |  |  | 0.001382% | 0.00147% | 80% | 47285122.5 | 0.001034%
|  |  |  | Air compressors |  |  |  | 0.1134% | 0.1134% | 0.1206% | 3880596720 | 0.02269% | 0.02413% | 20% | 776183677.5 | 0.06805% | 0.07238% | 60% | 2328229365 | 0.09073% | 0.09651% | 80% | 3104413042.5
|  |  |  | Air Receiver Tank |  |  |  | 0.00472% | 0.00472% | 0.00502% | 161477085 | 0.0009402% | 0.001% | 20% | 32166750 |  |  |  |  | 0.0009402% | 0.001% | 20% | 32166750
|  |  |  | Air Receiver Tank |  |  |  | 0.01394% | 0.01394% | 0.01483% | 477032902.5 | 0.002792% | 0.00297% | 20% | 95535247.5 |  |  |  |  | 0.002792% | 0.00297% | 20% | 95535247.5
|  |  |  | Air Receiver Tank |  |  |  | 0.00129% | 0.001288% | 0.00137% | 44068447.5 | 0.0002538% | 0.00027% | 20% | 8685022.5 |  |  |  |  | 0.0002538% | 0.00027% | 20% | 8685022.5
|  |  |  | Air Dryer for HAG Instrument |  |  |  | 0.00042% | 0.0004231% | 0.00045% | 14475037.5 | 8.461e-05% | 9e-05% | 20% | 2895007.5 | 0.0002538% | 0.00027% | 60% | 8685022.5 | 0.0003385% | 0.00036% | 80% | 11580030
|  |  |  | Air Dryer for Instrument for Kiln |  |  |  | 0.00042% | 0.0004231% | 0.00045% | 14475037.5 | 8.461e-05% | 9e-05% | 20% | 2895007.5 | 0.0002538% | 0.00027% | 60% | 8685022.5 | 0.0003385% | 0.00036% | 80% | 11580030
|  |  |  | Air Dryer for DE-S System and Others (System-3) |  |  |  | 0.00042% | 0.0004231% | 0.00045% | 14475037.5 | 8.461e-05% | 9e-05% | 20% | 2895007.5 | 0.0002538% | 0.00027% | 60% | 8685022.5 | 0.0003385% | 0.00036% | 80% | 11580030
|  |  |  | Air compressor for Mud Gun |  |  |  | 0.01386% | 0.01386% | 0.01474% | 474137895 | 0.002773% | 0.00295% | 20% | 94891912.5 | 0.008311% | 0.00884% | 60% | 284354070 | 0.01108% | 0.01179% | 80% | 379245982.5
|  |  |  | Air Compressor for ESF & Refinery System |  |  |  | 0.07352% | 0.07352% | 0.0782% | 2515439850 | 0.0147% | 0.01564% | 20% | 503087970 | 0.04411% | 0.04692% | 60% | 1509263910 | 0.05882% | 0.06256% | 80% | 2012351880
|  |  |  | Air Receiver Tank |  |  |  | 0.00303% | 0.003027% | 0.00322% | 103576935 | 0.0006017% | 0.00064% | 20% | 20586720 |  |  |  |  | 0.0006017% | 0.00064% | 20% | 20586720
|  |  |  | Air Receiver Tank |  |  |  | 0.00202% | 0.002021% | 0.00215% | 69158512.5 | 0.0004043% | 0.00043% | 20% | 13831702.5 |  |  |  |  | 0.0004043% | 0.00043% | 20% | 13831702.5
|  |  |  | Air Receiver Tank |  |  |  | 0.00101% | 0.001006% | 0.00107% | 34418422.5 | 0.0001974% | 0.00021% | 20% | 6755017.5 |  |  |  |  | 0.0001974% | 0.00021% | 20% | 6755017.5
|  |  |  | Air Dryer for Instrument Air System-1 |  |  |  | 0.00727% | 0.007267% | 0.00773% | 248648977.5 | 0.001457% | 0.00155% | 20% | 49858462.5 | 0.004362% | 0.00464% | 60% | 149253720 | 0.00582% | 0.00619% | 80% | 199112182.5
|  |  |  | Feed Pump for MFO Fuel |  |  |  | 0.00561% | 0.005613% | 0.00597% | 192035497.5 | 0.005603% | 0.00596% | 100% | 191713830 |  |  |  |  | 0.005603% | 0.00596% | 100% | 191713830
|  |  |  | Feed Pump for MFO Fuel |  |  |  | 0.01116% | 0.01116% | 0.01187% | 381819322.5 | 0.01115% | 0.01186% | 100% | 381497655 |  |  |  |  | 0.01115% | 0.01186% | 100% | 381497655
|  |  |  | Feed Pump for HSD Fuel |  |  |  | 0.00561% | 0.005613% | 0.00597% | 192035497.5 | 0.001119% | 0.00119% | 20% | 38278432.5 |  |  |  |  | 0.001119% | 0.00119% | 20% | 38278432.5
|  |  |  | Feed Pump for HSD Fuel |  |  |  | 0.01116% | 0.01116% | 0.01187% | 381819322.5 | 0.002228% | 0.00237% | 20% | 76235197.5 |  |  |  |  | 0.002228% | 0.00237% | 20% | 76235197.5
|  |  |  | Fixed Screen Bar & Rotary Screen |  |  |  | 0.08421% | 0.08421% | 0.08957% | 2881175797.5 | 0.06736% | 0.07165% | 80% | 2304747637.5 |  |  |  |  | 0.06736% | 0.07165% | 80% | 2304747637.5 | 0.05052%
|  |  |  | Sea Water Intake Pump |  |  |  | 0.1807% | 0.1807% | 0.1922% | 6181162680 | 0.03613% | 0.03843% | 20% | 1236168202.5 |  |  |  |  | 0.03613% | 0.03843% | 20% | 1236168202.5
|  |  |  | Fire Water Tank |  |  |  | 0.04623% | 0.04623% | 0.04917% | 1581639097.5 | 0.04623% | 0.04917% | 100% | 1581639097.5 |  |  |  |  | 0.04623% | 0.04917% | 100% | 1581639097.5
|  |  |  | Fire Water Pump |  |  |  | 0.04813% | 0.04813% | 0.05119% | 1646615932.5 | 0.0385% | 0.04095% | 80% | 1317228413 | 0.009627% | 0.01024% | 20% | 329387520 | 0.04813% | 0.05119% | 100% | 1646615933
|  |  |  | Jockey Pump |  |  |  | 0.01181% | 0.01182% | 0.01257% | 404336047.5 | 0.009449% | 0.01005% | 80% | 323275838 | 0.00236% | 0.00251% | 20% | 80738542.5 | 0.01181% | 0.01256% | 100% | 404014380.5
|  | B.1.2 | ELECTRICAL EQUIPMENT |  |  |  | 0% | 1.892% | 1.892% | 2.013% | 64745877735 | 0.4407% | 0.4688% |  | 15079772400 | 0.04889% | 0.052% |  | 1672671000 | 0.4896% | 0.5208% |  | 16752443400 | 0.06101%
|  | 1 | System 2
|  |  |  | MV Switchgear 6.6 kV |  |  |  | 0.07741% | 0.07741% | 0.08234% | 2648610195 | 0.01548% | 0.01647% | 20% | 529786372.5 |  |  |  |  | 0.01548% | 0.01647% | 20% | 529786372.5
|  |  |  | Power Transformer 6.6 / 0.4 kV |  |  |  | 0.00979% | 0.009787% | 0.01041% | 334855867.5 | 0.007832% | 0.00833% | 80% | 267949027.5 |  |  |  |  | 0.007832% | 0.00833% | 80% | 267949027.5
|  |  |  | LV Switchgear 400 V |  |  |  | 0.1007% | 0.1007% | 0.1071% | 3444093922.5 | 0.02013% | 0.02141% | 20% | 688690117.5 |  |  |  |  | 0.02013% | 0.02141% | 20% | 688690117.5
|  |  |  | Capacitor Bank Panel |  |  |  | 0.0434% | 0.0434% | 0.04616% | 1484817180 | 0.03472% | 0.03693% | 80% | 1187918077.5 |  |  |  |  | 0.03472% | 0.03693% | 80% | 1187918077.5 | 0.02604%
|  |  |  | Lighting and Small Power Panel |  |  |  | 0.00067% | 0.0006675% | 0.00071% | 22838392.5
|  |  |  | Indoor and Outdoor Lighting |  |  |  | 0.0213% | 0.0213% | 0.02266% | 728898555
|  |  |  | DC UPS |  |  |  | 0.04821% | 0.04821% | 0.05128% | 1649510940 | 0.009646% | 0.01026% | 20% | 330030855 |  |  |  |  | 0.009646% | 0.01026% | 20% | 330030855
|  |  |  | MV Power Cable |  |  |  | 0.0049% | 0.004898% | 0.00521% | 167588767.5
|  |  |  | LV Power Cable |  |  |  | 0.08935% | 0.08935% | 0.09504% | 3057127920
|  |  |  | Control Cable |  |  |  | 0.01161% | 0.01161% | 0.01235% | 397259362.5
|  |  |  | Cable Ladder and Cable Tray |  |  |  | 0.0366% | 0.0366% | 0.03893% | 1252251577.5
|  |  |  | Bulk Material |  |  |  | 0.0222% | 0.0222% | 0.02361% | 759456967.5
|  |  |  | Grounding and Lightning Protection |  |  |  | 0.01205% | 0.01204% | 0.01281% | 412056067.5
|  | 2 | System 3
|  |  |  | MV Switchgear 6.6 kV |  |  |  | 0.04769% | 0.04769% | 0.05073% | 1631819227.5 | 0.009543% | 0.01015% | 20% | 326492512.5 |  |  |  |  | 0.009543% | 0.01015% | 20% | 326492512.5
|  |  |  | Power Transformer 6.6 / 0.4 kV |  |  |  | 0.00515% | 0.005152% | 0.00548% | 176273790 | 0.004127% | 0.00439% | 80% | 141212032.5 |  |  |  |  | 0.004127% | 0.00439% | 80% | 141212032.5
|  |  |  | LV Switchgear 400 V |  |  |  | 0.06358% | 0.06358% | 0.06763% | 2175437302.5 | 0.01272% | 0.01353% | 20% | 435216128 |  |  |  |  | 0.01272% | 0.01353% | 20% | 435216128 |  |  | 0%
|  |  |  | Capacitor Bank Panel |  |  |  | 0.0217% | 0.0217% | 0.02308% | 742408590 | 0.01736% | 0.01847% | 80% | 594119872.5 |  |  |  |  | 0.01736% | 0.01847% | 80% | 594119872.5 | 0.01302%
|  |  |  | Lighting and Small Power Panel |  |  |  | 0.0002% | 0.0001974% | 0.00021% | 6755017.5
|  |  |  | Indoor and Outdoor Lighting |  |  |  | 0.00197% | 0.001974% | 0.0021% | 67550175 | 0.0003949% | 0.00042% | 20% | 13510035 |  |  |  |  | 0.0003949% | 0.00042% | 20% | 13510035
|  |  |  | AC UPS |  |  |  | 0.03348% | 0.03348% | 0.03561% | 1145457967.5 | 0.006694% | 0.00712% | 20% | 229027260 |  |  |  |  | 0.006694% | 0.00712% | 20% | 229027260 |  |  | 0%
|  |  |  | MV Power Cable |  |  |  | 0.00598% | 0.005979% | 0.00636% | 204580530
|  |  |  | LV Power Cable |  |  |  | 0.00715% | 0.007155% | 0.00761% | 244788967.5 | 0.007155% | 0.00761% | 100% | 244788967.5 |  |  |  |  | 0.007155% | 0.00761% | 100% | 244788967.5
|  |  |  | Control Cable |  |  |  | 0.00285% | 0.002849% | 0.00303% | 97465252.5 | 0.002849% | 0.00303% | 100% | 97465252.5 |  |  |  |  | 0.002849% | 0.00303% | 100% | 97465252.5
|  |  |  | Cable Ladder and Cable Tray |  |  |  | 0.02022% | 0.02022% | 0.02151% | 691906792.5 | 0.01618% | 0.01721% | 80% | 553589767 |  |  |  |  | 0.01618% | 0.01721% | 80% | 553589767
|  |  |  | Bulk Material |  |  |  | 0.0118% | 0.0118% | 0.01255% | 403692712.5 | [14 empty] | 0%
|  |  |  | Grounding and Lightning Protection |  |  |  | 0.0087% | 0.008696% | 0.00925% | 297542437.5
|  | 3 | System 4
|  |  |  | Power Transformer 6.6 / 0.4 kV for Main Substation |  |  |  | 0.1503% | 0.1503% | 0.1598% | 5140889985 | 0.1202% | 0.1279% | 80% | 4112518987.5 |  |  |  |  | 0.1202% | 0.1279% | 80% | 4112518987.5
|  |  |  | MV Switchgear 6.6 kV |  |  |  | 0.1386% | 0.1386% | 0.1474% | 4741057282.5 | 0.02772% | 0.02948% | 20% | 948275790 |  |  |  |  | 0.02772% | 0.02948% | 20% | 948275790
|  |  |  | Power Transformer 6.6 / 0.4 kV |  |  |  | 0.01813% | 0.01813% | 0.01928% | 620174940 | 0.01451% | 0.01543% | 80% | 496332952.5 |  |  |  |  | 0.01451% | 0.01543% | 80% | 496332952.5
|  |  |  | LV Switchgear 400 V |  |  |  | 0.1642% | 0.1642% | 0.1747% | 5619209557.5 | 0.03285% | 0.03494% | 20% | 1123906245 |  |  |  |  | 0.03285% | 0.03494% | 20% | 1123906245
|  |  |  | Capacitor Bank Panel |  |  |  | 0.0217% | 0.0217% | 0.02308% | 742408590 | 0.01736% | 0.01847% | 80% | 594119872.5 |  |  |  |  | 0.01736% | 0.01847% | 80% | 594119872.5 | 0.01302%
|  |  |  | Distribution Board |  |  |  | 0.0003% | 0.0003009% | 0.00032% | 10293360
|  |  |  | Lighting and Small Power Panel |  |  |  | 0.00579% | 0.005791% | 0.00616% | 198147180
|  |  |  | Indoor and Outdoor Lighting |  |  |  | 0.1187% | 0.1186% | 0.1262% | 4059443850 | 0.02373% | 0.02524% | 20% | 811888770 |  |  |  |  | 0.02373% | 0.02524% | 20% | 811888770
|  |  |  | AC UPS |  |  |  | 0.08729% | 0.08729% | 0.09285% | 2986682737.5 | 0.01746% | 0.01857% | 20% | 597336547.5 |  |  |  |  | 0.01746% | 0.01857% | 20% | 597336547.5
|  |  |  | MV Power Cable |  |  |  | 0.1456% | 0.1456% | 0.1549% | 4982951242.5 |  |  |  |  | 0.02913% | 0.03098% | 20% | 996525915 | 0.02913% | 0.03098% | 20% | 996525915
|  |  |  | LV Power Cable |  |  |  | 0.0988% | 0.0988% | 0.1051% | 3380403757.5 |  |  |  |  | 0.01976% | 0.02102% | 20% | 676145085 | 0.01976% | 0.02102% | 20% | 676145085
|  |  |  | Control Cable |  |  |  | 0.01197% | 0.01197% | 0.01273% | 409482727.5
|  |  |  | Cable Ladder and Cable Tray |  |  |  | 0.04461% | 0.04461% | 0.04745% | 1526312287.5 | 0.008922% | 0.00949% | 20% | 30526245750% |  |  |  |  | 0.008922% | 0.00949% | 20% | 305262457.5 | 0.008922%
|  |  |  | Bulk '('( Material )) |  |  |  | 0.112% | 0.112% | 0.1191% | 3831381592.5
|  |  |  | Grounding and Lightning Protection |  |  |  | 0.06582% | 0.06582% | 0.07001% | 2251994167.5 | 0.01316% | 0.014% | 20% | 450334500 |  |  |  |  | 0.01316% | 0.014% | 20% | 450334500
|  | B.1.3 | INSTRUMENT EQUIPMENT |  |  |  |  | 1.781% | 1.781% | 1.894% | 60926397840 | 0.365% | 0.3882% |  | 12487454018 | 0.03753% | 0.03992% |  | 1284096660 | 0.4025% | 0.4281% |  | 13771550678 | 0.1165%
|  | 1 | System 2
|  |  |  | Field Devices (Instrument and logic sensor) |  |  |  | 0.3766% | 0.3766% | 0.4006% | 12884713380
|  |  |  | Actuator |  |  |  | 0.05725% | 0.05725% | 0.06089% | 1958633407.5
|  |  |  | Local Control Panel/Local Operation Box |  |  |  | 0.00491% | 0.004908% | 0.00522% | 167910435
|  |  |  | Process Control System (PCS) and Uninterupted Power Supply (UPS System) |  |  |  | 0.272% | 0.272% | 0.2893% | 9306805777.5 | 0.05441% | 0.05787% | 20% | 1861489822.5 |  |  |  |  | 0.05441% | 0.05787% | 20% | 1861489822.5
|  |  |  | CCTV for System-2 Area |  |  |  | 0.01882% | 0.01882% | 0.02002% | 643978335 | 0.003761% | 0.004% | 20% | 128667000 |  |  |  |  | 0.003761% | 0.004% | 20% | 128667000 | 0.01129%
|  |  |  | PA/GA for System-2 Area |  |  |  | 0.0336% | 0.0336% | 0.03574% | 1149639645 | 0.006722% | 0.00715% | 20% | 229992262.5 |  |  |  |  | 0.006722% | 0.00715% | 20% | 229992262.5 | 0.02016%
|  |  |  | Telephone for System-2 Area |  |  |  | 0.00203% | 0.002031% | 0.00216% | 69480180 | 0.0004043% | 0.00043% | 20% | 13831702.5 |  |  |  |  | 0.0004043% | 0.00043% | 20% | 13831702.5 | 0.001222%
|  |  |  | Fire Detection for System-2 Area |  |  |  | 0.01266% | 0.01266% | 0.01347% | 433286122.5 | 0.01013% | 0.01077% | 80% | 346435897.5 |  |  |  |  | 0.01013% | 0.01077% | 80% | 346435897.5
|  |  |  | Instrument & Control Cables |  |  |  | 0.1536% | 0.1536% | 0.1633% | 5254438612.5 | [8 empty] | 0% | 0% | 0% | 0
|  |  |  | Bulk Material |  |  |  | 0.2631% | 0.2631% | 0.2798% | 9000256650
|  | 2 | System 3
|  |  |  | Field Devices (Instrument and logic sensor) |  |  |  | 0.03394% | 0.03394% | 0.0361% | 1161219675 | 0.006788% | 0.00722% | 20% | 232243935 |  |  |  |  | 0.006788% | 0.00722% | 20% | 232243935
|  |  |  | Actuator |  |  |  | 0.002% | 0.002003% | 0.00213% | 68515177.5 | 0.0004043% | 0.00043% | 20% | 13831702.5 |  |  |  |  | 0.0004043% | 0.00043% | 20% | 13831702.5
|  |  |  | Local Control Panel/Local Operation Box |  |  |  | 0.00529% | 0.005293% | 0.00563% | 181098802.5 | 0.001062% | 0.00113% | 20% | 36348427.5 |  |  |  |  | 0.001062% | 0.00113% | 20% | 36348427.5
|  |  |  | Process Control System (PCS) and Uninterupted Power Supply (UPS System) |  |  |  | 0.06539% | 0.06539% | 0.06955% | 2237197462.5 | 0.01308% | 0.01391% | 20% | 447439492.5 |  |  |  |  | 0.01308% | 0.01391% | 20% | 447439492.5
|  |  |  | CCTV for System-3 Area |  |  |  | 0.0251% | 0.0251% | 0.0267% | 858852225 | 0.00502% | 0.00534% | 20% | 171770445 |  |  |  |  | 0.00502% | 0.00534% | 20% | 171770445 | 0.01506%
|  |  |  | PA/GA for System-3 Area |  |  |  | 0.0448% | 0.0448% | 0.04765% | 1532745637.5 | 0.00896% | 0.00953% | 20% | 306549127.5 |  |  |  |  | 0.00896% | 0.00953% | 20% | 306549127.5 | 0.02688%
|  |  |  | Telephone for System-3 Area |  |  |  | 0.0027% | 0.002698% | 0.00287% | 92318572.5 | 0.0005359% | 0.00057% | 20% | 18335048 |  |  |  |  | 0.0005359% | 0.00057% | 20% | 18335048 | 0.001617%
|  |  |  | Fire Detection for System-3 Area |  |  |  | 0.01688% | 0.01688% | 0.01795% | 577393162.5 | 0.0135% | 0.01436% | 80% | 461914530 |  |  |  |  | 0.0135% | 0.01436% | 80% | 461914530
|  |  |  | Instrument & Control Cables |  |  |  | 0.02027% | 0.02027% | 0.02156% | 693515130 | 0.004052% | 0.00431% | 20% | 138638692.5 |  |  |  |  | 0.004052% | 0.00431% | 20% | 138638692.5
|  |  |  | Bulk Material |  |  |  | 0.05402% | 0.05401% | 0.05745% | 1847979787.5 | 0.04321% | 0.04596% | 80% | 1478383830 |  |  |  |  | 0.04321% | 0.04596% | 80% | 1478383830
|  | 3 | System 4
|  |  |  | Field Devices (Instrument and logic sensor) |  |  |  | 0.04535% | 0.04535% | 0.04824% | 1551724020 |  |  |  |  | 0.009073% | 0.00965% | 20% | 310409137.5 | 0.009073% | 0.00965% | 20% | 310409137.5
|  |  |  | Actuator |  |  |  | 0.00126% | 0.00126% | 0.00134% | 43103445
|  |  |  | Local Control Panel/Local Operation Box |  |  |  | 0.00516% | 0.005161% | 0.00549% | 176595457.5
|  |  |  | Process Control System (PCS) and Uninterupted Power Supply (UPS System) for Water treatment and Oxygen Plant |  |  |  | 0.0459% | 0.0459% | 0.04882% | 1570380735 | 0.03671% | 0.03905% | 80% | 1256111587.5 |  |  |  |  | 0.03671% | 0.03905% | 80% | 1256111587.5
|  |  |  | CCTV for System-4 Area |  |  |  | 0.01882% | 0.01882% | 0.02002% | 643978335 | 0.003761% | 0.004% | 20% | 128667000 |  |  |  |  | 0.003761% | 0.004% | 20% | 128667000 | 0.01129%
|  |  |  | PA/GA for System-4 Area |  |  |  | 0.0336% | 0.0336% | 0.03574% | 1149639645 | 0.02688% | 0.02859% | 80% | 919647382.5 |  |  |  |  | 0.02688% | 0.02859% | 80% | 919647382.5 | 0.02016%
|  |  |  | Telephone for System-4 Area |  |  |  | 0.00203% | 0.002031% | 0.00216% | 69480180 | 0.001626% | 0.00173% | 80% | 55648477.5 |  |  |  |  | 0.001626% | 0.00173% | 80% | 55648477.5 | 0.001222%
|  |  |  | Fire Detection for System-4 Area |  |  |  | 0.01266% | 0.01266% | 0.01347% | 433286122.5 | 0.01013% | 0.01077% | 80% | 346435897.5 |  |  |  |  | 0.01013% | 0.01077% | 80% | 346435897.5 | 0.007596%
|  |  |  | Instrument & Control Cables |  |  |  | 0.00875% | 0.008753% | 0.00931% | 299472442.5
|  |  |  | Bulk Material |  |  |  | 0.1423% | 0.1423% | 0.1514% | 4868759280 | 0.1138% | 0.1211% | 80% | 3895071757.5 | 0.02846% | 0.03027% | 20% | 973687522.5 | 0.1423% | 0.1514% | 100% | 4868759280
|  | B.1.4 | PIPING MATERIAL |  |  |  |  | 1.453% | 1.453% | 1.546% | 49722397147.5 | 0.2065% | 0.2196% |  | 7063818300 | 0.08383% | 0.08917% |  | 2868309097.5 | 0.2903% | 0.3088% |  | 9932127397.5 | 0%
|  | 1 | System 2
|  |  |  | Piping, Fitting, Support & Accesories to accomodate 16JL08-PID-10-002-A3 (Slag Granulation) |  |  |  | 0.7053% | 0.7053% | 0.7502% | 24130209180
|  | 2 | System 3
|  |  |  | Piping, Fitting, Support & Accesories to accomodate 16JL08-PID-10-004-A3 (Shot Making Equipment) |  |  |  | 0.00969% | 0.009693% | 0.01031% | 331639192.5 | [14 empty] | 0%
|  |  |  | Piping, Fitting, Support & Accesories to accomodate 16JL08-PID-10-005-A3 (Ladle Preheating) |  |  |  | 0.01251% | 0.01251% | 0.01331% | 428139442.5 | [14 empty] | 0%
|  | 3 | System 4
|  |  |  | Piping, Fitting, Support & Accesories to accomodate 16JL08-PID-10-006-A3 (Fuel Oil Pumping & DS) |  |  |  | 0.04599% | 0.04599% | 0.04892% | 1573597410 | 0.01308% | 0.01391% | 28.45% | 447439492.5 | 0.005312% | 0.00565% | 11.55% | 181742137.5 | 0.01839% | 0.01956% | 40% | 629181630
|  |  |  | Piping, Fitting, Support & Accesories to accomodate 16JL08-PID-10-007-A3 Compressed Air System) |  |  |  | 0.02763% | 0.02763% | 0.02939% | 945380782.5 | 0.00786% | 0.00836% | 28.45% | 268914030 | 0.003187% | 0.00339% | 11.55% | 109045282.5 | 0.01105% | 0.01175% | 40% | 377959312.5
|  |  |  | Piping, Fitting, Support & Accesories to accomodate 16JL08-PID-10-008-A3 (Water Intake Treatment & Calculation) |  |  |  | 0.1323% | 0.1323% | 0.1408% | 4528113397.5 | 0.03764% | 0.04004% | 28.45% | 1287956670 | 0.01529% | 0.01626% | 11.55% | 523031355 | 0.05293% | 0.0563% | 40% | 1810988025
|  |  |  | Piping, Fitting, Support & Accesories to accomodate 16JL08-PID-10-009-A3 (Water Intake Treatment & Calculation) |  |  |  | 0.4585% | 0.4585% | 0.4877% | 15686437305 | 0.1304% | 0.1387% | 28.45% | 4462493227.5 | 0.05296% | 0.05633% | 11.55% | 1811953027.5 | 0.1834% | 0.1951% | 40% | 6274446255
|  |  |  | Piping, Fitting, Support & Accesories to accomodate16JL08-PID-10-010-A3 (Fire Water Supply System) |  |  |  | 0.02649% | 0.02649% | 0.02818% | 906459015 | 0.00754% | 0.00802% | 28.45% | 257977335 | 0.003065% | 0.00326% | 11.55% | 104863605 | 0.0106% | 0.01128% | 40% | 362840940
|  |  |  | Piping, Fitting, Support & Accesories to accomodate16JL08-PID-10-011-A3 (Fire Water Distribution) |  |  |  | 0.03486% | 0.03485% | 0.03707% | 1192421422.5 | 0.009909% | 0.01054% | 28.45% | 339037545 | 0.004024% | 0.00428% | 11.55% | 137673690 | 0.01393% | 0.01482% | 40% | 476711235
|  | B.1.6 | EARTH WORK, CIVIL WORK AND STRUCTURAL WORK ( PROCUREMENT ) |  |  |  |  | 12.76% | 12.76% | 13.57% | 436645296202.5 | 9.879% | 10.51% |  | 337995663965 | 0.3939% | 0.419% |  | 13477868250 | 10.27% | 10.93% |  | 351473532215 | 0.1629%
|  | 1 | Earth Work |  |  |  |  | 0.05841% | 0.05841% | 0.06213% | 1998520177.5 | 0.05841% | 0.06213% |  | 1998520177.5 | 0% | 0% |  | 0 | 0.05841% | 0.06213% |  | 1998520177.5 | 0%
|  |  |  | Ground Improvement |  |  |  | 0.05841% | 0.05841% | 0.06213% | 1998520177.5 | 0.05841% | 0.06213% | 100% | 1998520177.5 |  |  |  |  | 0.05841% | 0.06213% | 100% | 1998520177.5
|  | 2 | Civil Work |  |  |  |  | 1.673% | 1.673% | 1.779% | 57224969917.5 | 1.673% | 1.779% |  | 57224969917.5 | 0% | 0% |  | 0 | 1.673% | 1.779% |  | 57224969917.5 | 0%
Fence & Gates
[6 empty] | Reinforcement Bar |  | 0.07999% | 0.07999% | 0.08508% | 2736747090 | 0.07999% | 0.08508% | 100% | 2736747090 |  |  |  |  | 0.07999% | 0.08508% | 100% | 2736747090
Storm Water Drainage System
a. Concrete ditch 50x50
[6 empty] | Reinforcement Bar |  | 0.1313% | 0.1313% | 0.1397% | 4493694975 | 0.1313% | 0.1397% | 100% | 4493694975 |  |  |  |  | 0.1313% | 0.1397% | 100% | 4493694975
b. Concrete ditch 80x70
[6 empty] | Reinforcement Bar |  | 0.08461% | 0.08461% | 0.09% | 2895007500 | 0.08461% | 0.09% | 100% | 2895007500 |  |  |  |  | 0.08461% | 0.09% | 100% | 2895007500
c. Box Culvert 80x80
[6 empty] | Reinforcement Bar |  | 0.00623% | 0.006233% | 0.00663% | 213265552.5 | 0.006233% | 0.00663% | 100% | 213265552.5 |  |  |  |  | 0.006233% | 0.00663% | 100% | 213265552.5
d. Control Box 80x80
[6 empty] | Reinforcement Bar |  | 0.00426% | 0.004259% | 0.00453% | 145715377.5 | 0.004259% | 0.00453% | 100% | 145715377.5 |  |  |  |  | 0.004259% | 0.00453% | 100% | 145715377.5
e. Control Box 100x100
[6 empty] | Reinforcement Bar |  | 0.01617% | 0.01617% | 0.0172% | 553268100 | 0.01617% | 0.0172% | 100% | 553268100 |  |  |  |  | 0.01617% | 0.0172% | 100% | 553268100
Sewage Drainage system
[6 empty] | Reinforcement Bar |  | 0.02954% | 0.02954% | 0.03142% | 1010679285 | 0.02954% | 0.03142% | 100% | 1010679285 |  |  |  |  | 0.02954% | 0.03142% | 100% | 1010679285
Road & Pavement
[6 empty] | Reinforcement Bar |  | 0.2952% | 0.2952% | 0.3139% | 10098429495 | 0.2952% | 0.3139% | 100% | 10098429495 |  |  |  |  | 0.2952% | 0.3139% | 100% | 10098429495
Road Lighting & Site Outdoor Lighting
[6 empty] | Reinforcement Bar |  | 0.01388% | 0.01388% | 0.01476% | 474781230 | 0.01388% | 0.01476% | 100% | 474781230 |  |  |  |  | 0.01388% | 0.01476% | 100% | 474781230
Parking & Vehicle Shed
[6 empty] | Reinforcement Bar |  | 0.1757% | 0.1757% | 0.1869% | 6012608910 | 0.1757% | 0.1869% | 100% | 6012608910 |  |  |  |  | 0.1757% | 0.1869% | 100% | 6012608910
Toilets & Other Sanitary Facilities
[6 empty] | Reinforcement Bar |  | 0.00627% | 0.006271% | 0.00667% | 214552222.5 | 0.006271% | 0.00667% | 100% | 214552222.5 |  |  |  |  | 0.006271% | 0.00667% | 100% | 214552222.5
Retainning Wall
[6 empty] | Reinforcement Bar |  | 0.7619% | 0.7619% | 0.8104% | 26069220870 | 0.7619% | 0.8104% | 100% | 26069220870 |  |  |  |  | 0.7619% | 0.8104% | 100% | 26069220870
Trenches & Duct Support
[6 empty] | Reinforcement Bar |  | 0.06744% | 0.06743% | 0.07172% | 2306999310 | 0.06743% | 0.07172% | 100% | 2306999310 |  |  |  |  | 0.06743% | 0.07172% | 100% | 2306999310
|  | 3 | Structural Work |  |  |  |  | 9.709% | 9.709% | 10.33% | 332203075627.5 | 7.141% | 7.595% |  | 244312899598.5 | 0.3939% | 0.419% |  | 13477868250 | 7.535% | 8.014% |  | 257790767848.5 | 0.09821%
|  |  | 2.1 | System 1
Electrical Room for Ore Dryer Area
[6 empty] | Reinforcement Bar |  | 0.03614% | 0.03613% | 0.03843% | 1236168202.5 | 0.03614% | 0.03844% | 100% | 1236489870 |  |  |  |  | 0.03614% | 0.03844% | 100% | 1236489870
Electrical Room for Ore Mixing Area inside Ore Mixing and Briquetting Building
[6 empty] | Reinforcement Bar |  | 0.02972% | 0.02972% | 0.03161% | 1016790967.5 | 0.02972% | 0.03161% | 100% | 1016790967.5 |  |  |  |  | 0.02972% | 0.03161% | 100% | 1016790967.5
Electrical Room for Rotary Kiln Area and Coal Firing Area
[6 empty] | Reinforcement Bar |  | 0.06725% | 0.06725% | 0.07153% | 2300887627.5 | 0.06726% | 0.07154% | 100% | 2301209295 |  |  |  |  | 0.06726% | 0.07154% | 100% | 2301209295
Raw Ore Storage
[6 empty] | Piles |  | 0.04174% | 0.04174% | 0.0444% | 1428203700 | 0.04174% | 0.0444% | 100% | 1428203700 |  |  |  |  | 0.04174% | 0.0444% | 100% | 1428203700
[6 empty] | Reinforcement Bar |  | 0.3282% | 0.3282% | 0.3491% | 11227804087.5 | 0.3282% | 0.3491% | 100% | 11227804087.5 |  |  |  |  | 0.3282% | 0.3491% | 100% | 11227804087.5
[6 empty] | Steel Structure & Roof Siding |  | 0.5693% | 0.5693% | 0.6055% | 19477610460 | 0.4124% | 0.4387% | 72.45% | 14111231557 |  |  |  |  | 0.4124% | 0.4387% | 72.45% | 14111231557
Ore Drying Equipment & Ore Sizing Equipment
[6 empty] | Piles |  | 0.1858% | 0.1859% | 0.1977% | 6358723140 | 0.1859% | 0.1977% | 100% | 6359044807.5 |  |  |  |  | 0.1859% | 0.1977% | 100% | 6359044807.5
[6 empty] | Reinforcement Bar |  | 0.09105% | 0.09105% | 0.09685% | 3115349737.5 | 0.09105% | 0.09685% | 100% | 3115349737.5 |  |  |  |  | 0.09105% | 0.09685% | 100% | 3115349737.5
[6 empty] | Steel Structure & Roof Siding |  | 0.2751% | 0.2751% | 0.2926% | 9411991050 | 0.09628% | 0.1024% | 35% | 3294196867.5 |  |  |  |  | 0.09628% | 0.1024% | 35% | 3294196867.5
Conditioned Ore Storage
[6 empty] | Piles |  | 0.02568% | 0.02568% | 0.02731% | 878473942.5 | 0.02568% | 0.02731% | 100% | 878473942.5 |  |  |  |  | 0.02568% | 0.02731% | 100% | 878473942.5
[6 empty] | Reinforcement Bar |  | 0.1119% | 0.1119% | 0.119% | 3828808252.5 | 0.1119% | 0.119% | 100% | 3829129920 |  |  |  |  | 0.1119% | 0.119% | 100% | 3829129920
[6 empty] | Steel Structure & Roof Siding |  | 0.2305% | 0.2305% | 0.2451% | 7884713760 | 0.2212% | 0.2353% | 96% | 7568836274 |  |  |  |  | 0.2212% | 0.2353% | 96% | 7568836274 | 0.02466%
Ore Mixing Equipment & Dust Treatment Equipment
[6 empty] | Piles |  | 0.05398% | 0.05398% | 0.05742% | 1847014785 | 0.05398% | 0.05742% | 100% | 1847014785 |  |  |  |  | 0.05398% | 0.05742% | 100% | 1847014785
[6 empty] | Reinforcement Bar |  | 0.04256% | 0.04256% | 0.04527% | 1456188772.5 | 0.04255% | 0.04526% | 100% | 1455867105 |  |  |  |  | 0.04255% | 0.04526% | 100% | 1455867105
[6 empty] | Steel Structure & Roof Siding |  | 0.3702% | 0.3702% | 0.3937% | 12665014477.5 | 0.1296% | 0.1378% | 35% | 4432578150 |  |  |  |  | 0.1296% | 0.1378% | 35% | 4432578150
Rotary Kiln & Exhaust Gas Treatment Equipment
[6 empty] | Piles |  | 0.238% | 0.238% | 0.2531% | 8141404425 | 0.238% | 0.2531% | 100% | 8141404425 |  |  |  |  | 0.238% | 0.2531% | 100% | 8141404425
[6 empty] | Reinforcement Bar |  | 0.3096% | 0.3096% | 0.3293% | 10593475777.5 | 0.3096% | 0.3293% | 100% | 10593797445 |  |  |  |  | 0.3096% | 0.3293% | 100% | 10593797445
[6 empty] | Steel Structure & Roof Siding |  | 0.8754% | 0.8754% | 0.9311% | 29950782592.5 | 0.3502% | 0.3725% | 40.01% | 11982757710 | 0.3939% | 0.419% | 45% | 13477868250 | 0.7442% | 0.7915% | 85.01% | 25460625960 | 0.01313%
Coal Firing Equipment
[6 empty] | Piles |  | 0.04875% | 0.04875% | 0.05185% | 1667845987.5 | 0.04875% | 0.05185% | 100% | 1667845987.5 |  |  |  |  | 0.04875% | 0.05185% | 100% | 1667845987.5
[6 empty] | Reinforcement Bar |  | 0.03754% | 0.03754% | 0.03993% | 1284418327.5 | 0.03755% | 0.03994% | 100% | 1284739995 |  |  |  |  | 0.03755% | 0.03994% | 100% | 1284739995
[6 empty] | Steel Structure & Roof Siding |  | 0.1909% | 0.1909% | 0.2031% | 6532745257.5 | 0.06683% | 0.07108% | 35% | 2286412590 |  |  |  |  | 0.06683% | 0.07108% | 35% | 2286412590
Fuel Coal Storage
[6 empty] | Piles |  | 0.2034% | 0.2033% | 0.2163% | 6957346357.5 | 0.2033% | 0.2163% | 100% | 6957346357.5 |  |  |  |  | 0.2033% | 0.2163% | 100% | 6957346357.5
[6 empty] | Reinforcement Bar |  | 0.06734% | 0.06734% | 0.07163% | 2304104302.5 | 0.06735% | 0.07164% | 100% | 2304425970 |  |  |  |  | 0.06735% | 0.07164% | 100% | 2304425970
[6 empty] | Steel Structure & Roof Siding |  | 0.2065% | 0.2065% | 0.2196% | 7065104970 | 0.2065% | 0.2196% | 100% | 7064783302.5 |  |  |  |  | 0.2065% | 0.2196% | 100% | 7064783302.5
Reductant Coal Storage
[6 empty] | Reinforcement Bar |  | 0.0665% | 0.0665% | 0.07073% | 2275154227.5 | 0.06651% | 0.07074% | 100% | 2275475895 |  |  |  |  | 0.06651% | 0.07074% | 100% | 2275475895
[6 empty] | Steel Structure & Roof Siding |  | 0.2194% | 0.2194% | 0.2333% | 7505789445 | 0.2194% | 0.2333% | 100% | 7505467777.5 |  |  |  |  | 0.2194% | 0.2333% | 100% | 7505467777.5
Belt Conveyor / Transfer Towe, Girder & Support.
[6 empty] | Piles |  | 0.06447% | 0.06447% | 0.06857% | 2205674047.5 | 0.06446% | 0.06856% | 100% | 2205352380 |  |  |  |  | 0.06446% | 0.06856% | 100% | 2205352380
[6 empty] | Reinforcement Bar |  | 0.05713% | 0.05713% | 0.06077% | 1954773397.5 | 0.05712% | 0.06076% | 100% | 1954451730 |  |  |  |  | 0.05712% | 0.06076% | 100% | 1954451730
[6 empty] | Steel Structure & Roof Siding |  | 0.5011% | 0.5012% | 0.5331% | 17146486087.5 | 0.1804% | 0.1918% | 35.99% | 6170869320 |  |  |  |  | 0.1804% | 0.1918% | 35.99% | 6170869320
|  |  | 2.2 | System 2
ESF Building
[6 empty] | Piles |  | 0.3268% | 0.3268% | 0.3476% | 11182127302.5 | 0.3268% | 0.3476% | 100% | 11182127302.5 |  |  |  |  | 0.3268% | 0.3476% | 100% | 11182127302.5
[6 empty] | Reinforcement Bar |  | 0.1896% | 0.1896% | 0.2016% | 6486425137.5 | 0.1896% | 0.2016% | 100% | 6486425137.5 |  |  |  |  | 0.1896% | 0.2016% | 100% | 6486425137.5
[6 empty] | Steel Structure & Roof Siding |  | 1.237% | 1.237% | 1.316% | 42323079645 | 0.6499% | 0.6913% | 52.54% | 22235909272.5 |  |  |  |  | 0.6499% | 0.6913% | 52.54% | 22235909272.5 | 0.0481%
ESF Equipments Support & Foundation :
a. Furnace Foundation
[6 empty] | Piles |  | 0.07071% | 0.07071% | 0.07521% | 2419261267.5 | 0.07071% | 0.07521% | 100% | 2419261267.5 |  |  |  |  | 0.07071% | 0.07521% | 100% | 2419261267.5
[6 empty] | Reinforcement Bar |  | 0.02479% | 0.02479% | 0.02637% | 848237197.5 | 0.02478% | 0.02636% | 100% | 847915530 |  |  |  |  | 0.02478% | 0.02636% | 100% | 847915530
b. Tapping Deck Structure & Foundation
[6 empty] | Reinforcement Bar |  | 0.00222% | 0.002219% | 0.00236% | 75913530 | 0.002219% | 0.00236% | 100% | 75913530 |  |  |  |  | 0.002219% | 0.00236% | 100% | 75913530
[6 empty] | Steel Structure & Roof Siding |  | 0.06539% | 0.06539% | 0.06955% | 2237197462.5 | 0.02289% | 0.02435% | 35% | 783260362.5 |  |  |  |  | 0.02289% | 0.02435% | 35% | 783260362.5
c. Furnace Fan Foundation
[6 empty] | Reinforcement Bar |  | 0.00359% | 0.003591% | 0.00382% | 122876985 | 0.003582% | 0.00381% | 100% | 122555317.5 |  |  |  |  | 0.003582% | 0.00381% | 100% | 122555317.5
d. Spray Chamber Support Foundation
[6 empty] | Piles |  | 0.00232% | 0.002322% | 0.00247% | 79451872.5 | 0.002322% | 0.00247% | 100% | 79451872.5 |  |  |  |  | 0.002322% | 0.00247% | 100% | 79451872.5
[6 empty] | Reinforcement Bar |  | 0.00069% | 0.0006863% | 0.00073% | 23481727.5 | 0.0006957% | 0.00074% | 100% | 23803395 |  |  |  |  | 0.0006957% | 0.00074% | 100% | 23803395
[6 empty] | Steel Structure & Roof Siding |  | 0.00392% | 0.00392% | 0.00417% | 134135347.5 | 0.001373% | 0.00146% | 35% | 46963455 |  |  |  |  | 0.001373% | 0.00146% | 35% | 46963455
e. Bag House Inlet Duct Support Foundation
[6 empty] | Reinforcement Bar |  | 0.00033% | 0.0003291% | 0.00035% | 11258362.5 | 0.0003291% | 0.00035% | 100% | 11258362.5 |  |  |  |  | 0.0003291% | 0.00035% | 100% | 11258362.5
[6 empty] | Steel Structure & Roof Siding |  | 0.00531% | 0.005312% | 0.00565% | 181742137.5 | 0.001862% | 0.00198% | 35% | 63690165 |  |  |  |  | 0.001862% | 0.00198% | 35% | 63690165
f. Bag House Foundation
[6 empty] | Piles |  | 0.03263% | 0.03263% | 0.03471% | 1116507892.5 | 0.03263% | 0.03471% | 100% | 1116507892.5 |  |  |  |  | 0.03263% | 0.03471% | 100% | 1116507892.5
[6 empty] | Reinforcement Bar |  | 0.03571% | 0.03571% | 0.03798% | 1221693165 | 0.03572% | 0.03799% | 100% | 1222014832.5 |  |  |  |  | 0.03572% | 0.03799% | 100% | 1222014832.5
g. Blowpots Foundation
[6 empty] | Reinforcement Bar |  | 0.00041% | 0.0004137% | 0.00044% | 14153370 | 0.0004137% | 0.00044% | 100% | 14153370 |  |  |  |  | 0.0004137% | 0.00044% | 100% | 14153370
h. Bag House Fan Foundation
[6 empty] | Reinforcement Bar |  | 0.00218% | 0.002181% | 0.00232% | 74626860 | 0.002172% | 0.00231% | 100% | 74305192.5 |  |  |  |  | 0.002172% | 0.00231% | 100% | 74305192.5
i. Bag House Outlet Duct Support Foundation
[6 empty] | Reinforcement Bar |  | 0.00068% | 0.0006769% | 0.00072% | 23160060 | 0.0006675% | 0.00071% | 100% | 22838392.5 |  |  |  |  | 0.0006675% | 0.00071% | 100% | 22838392.5
[6 empty] | Steel Structure & Roof Siding |  | 0.0071% | 0.007098% | 0.00755% | 242858962.5 | 0.002491% | 0.00265% | 35% | 85241887.5 |  |  |  |  | 0.002491% | 0.00265% | 35% | 85241887.5
j. Bag House Stack Foundation
[6 empty] | Piles |  | 0.00364% | 0.003638% | 0.00387% | 124485322.5 | 0.003638% | 0.00387% | 100% | 124485322.5 |  |  |  |  | 0.003638% | 0.00387% | 100% | 124485322.5
[6 empty] | Reinforcement Bar |  | 0.00351% | 0.003507% | 0.00373% | 119981977.5 | 0.003516% | 0.00374% | 100% | 120303645 |  |  |  |  | 0.003516% | 0.00374% | 100% | 120303645
Main Substation Building
[6 empty] | Reinforcement Bar |  | 0.03599% | 0.03599% | 0.03828% | 1231343190 | 0.036% | 0.03829% | 100% | 1231664857.5 |  |  |  |  | 0.036% | 0.03829% | 100% | 1231664857.5
Electrical Room for ESF Area
[6 empty] | Reinforcement Bar |  | 0.00107% | 0.001072% | 0.00114% | 36670095 | 0.001072% | 0.00114% | 100% | 36670095 |  |  |  |  | 0.001072% | 0.00114% | 100% | 36670095
[6 empty] | Steel Structure & Roof Siding |  | 0.01893% | 0.01893% | 0.02013% | 647516677.5 | 0.006619% | 0.00704% | 35% | 226453920 |  |  |  |  | 0.006619% | 0.00704% | 35% | 226453920
Center Control Room at ESF Building
[6 empty] | Reinforcement Bar |  | 0.00151% | 0.001514% | 0.00161% | 51788467.5 | 0.001514% | 0.00161% | 100% | 51788467.5 |  |  |  |  | 0.001514% | 0.00161% | 100% | 51788467.5
[6 empty] | Steel Structure & Roof Siding |  | 0.02898% | 0.02898% | 0.03082% | 991379235 | 0.01014% | 0.01079% | 35% | 347079232.5 |  |  |  |  | 0.01014% | 0.01079% | 35% | 347079232.5
Crane Control Room at ESF Building
[6 empty] | Reinforcement Bar |  | 0.00044% | 0.0004419% | 0.00047% | 15118372.5 | 0.0004419% | 0.00047% | 100% | 15118372.5 |  |  |  |  | 0.0004419% | 0.00047% | 100% | 15118372.5
[6 empty] | Steel Structure & Roof Siding |  | 0.01052% | 0.01052% | 0.01119% | 359945932.5 | 0.003685% | 0.00392% | 35% | 126093660 |  |  |  |  | 0.003685% | 0.00392% | 35% | 126093660
Emergency Pit
[6 empty] | Reinforcement Bar |  | 0.00065% | 0.0006487% | 0.00069% | 22195057.5 | 0.0006487% | 0.00069% | 100% | 22195057.5 |  |  |  |  | 0.0006487% | 0.00069% | 100% | 22195057.5
[6 empty] | Steel Structure & Roof Siding |  | 0.00328% | 0.003281% | 0.00349% | 112261957.5 | 0.001147% | 0.00122% | 35% | 39243435 |  |  |  |  | 0.001147% | 0.00122% | 35% | 39243435
|  |  | 2.3 | System 3
Refining Shot Making Building
[6 empty] | Piles |  | 0.00468% | 0.004682% | 0.00498% | 160190415 | 0.004682% | 0.00498% | 100% | 160190415 |  |  |  |  | 0.004682% | 0.00498% | 100% | 160190415
[6 empty] | Reinforcement Bar |  | 0.00671% | 0.006713% | 0.00714% | 229670595 | 0.006713% | 0.00714% | 100% | 229670595 |  |  |  |  | 0.006713% | 0.00714% | 100% | 229670595
[6 empty] | Steel Structure & Roof Siding |  | 0.04095% | 0.04095% | 0.04356% | 1401183630 | 0.01434% | 0.01525% | 35% | 490542937.5 |  |  |  |  | 0.01434% | 0.01525% | 35% | 490542937.5
Shot Making Equipment Support & Foundation
[6 empty] | Reinforcement Bar |  | 0.01809% | 0.01809% | 0.01924% | 618888270 | 0.01809% | 0.01924% | 100% | 618888270 |  |  |  |  | 0.01809% | 0.01924% | 100% | 618888270
Desulphurizing Equipment Support & Foundation
[6 empty] | Piles |  | 0.02309% | 0.02309% | 0.02456% | 790015380 | 0.0231% | 0.02457% | 100% | 790337047.5 |  |  |  |  | 0.0231% | 0.02457% | 100% | 790337047.5
[6 empty] | Reinforcement Bar |  |  | 0.003676% | 0.00391% | 125771992.5 | 0.003676% | 0.00391% | 100% | 125771992.5 |  |  |  |  | 0.003676% | 0.00391% | 100% | 125771992.5
|  |  |  | Product Storage Building & Handling Crane |  |  |  | 0.00368%
[6 empty] | Reinforcement Bar |  | 0.03071% | 0.03071% | 0.03266% | 1050566055 | 0.03071% | 0.03266% | 100% | 1050566055 |  |  |  |  | 0.03071% | 0.03266% | 100% | 1050566055
[6 empty] | Steel Structure & Roof Siding |  | 0.1578% | 0.1578% | 0.1678% | 5397902317.5 | 0.05522% | 0.05873% | 35% | 1889153227.5 |  |  |  |  | 0.05522% | 0.05873% | 35% | 1889153227.5
Electrical Room for Shot Making Area
[6 empty] | Reinforcement Bar |  | 0.02071% | 0.02071% | 0.02203% | 708633502.5 | 0.02072% | 0.02204% | 100% | 708955170 |  |  |  |  | 0.02072% | 0.02204% | 100% | 708955170
Control Room for Shot Making
[6 empty] | Reinforcement Bar |  | 0.00038% | 0.0003761% | 0.0004% | 12866700 | 0.0003761% | 0.0004% | 100% | 12866700 |  |  |  |  | 0.0003761% | 0.0004% | 100% | 12866700
[6 empty] | Steel Structure & Roof Siding |  | 0.00732% | 0.007324% | 0.00779% | 250578982.5 | 0.002567% | 0.00273% | 35% | 87815227.5 |  |  |  |  | 0.002567% | 0.00273% | 35% | 87815227.5
Ladle Preheating Equipment Foundation
[6 empty] | Reinforcement Bar |  | 0.00049% | 0.0004889% | 0.00052% | 16726710 | 0.0004795% | 0.00051% | 100% | 16405042.5 |  |  |  |  | 0.0004795% | 0.00051% | 100% | 16405042.5
Ladle Foundation
[6 empty] | Reinforcement Bar |  | 0.00126% | 0.00126% | 0.00134% | 43103445 | 0.00126% | 0.00134% | 100% | 43103445 |  |  |  |  | 0.00126% | 0.00134% | 100% | 43103445
Turbo Blower Foundation
[6 empty] | Reinforcement Bar |  | 0.00017% | 0.0001692% | 0.00018% | 5790015 | 0.0001786% | 0.00019% | 100% | 6111682.5 |  |  |  |  | 0.0001786% | 0.00019% | 100% | 6111682.5
Oil Tank Foundation
[6 empty] | Reinforcement Bar |  | 0.00015% | 0.0001504% | 0.00016% | 5146680 | 0.0001504% | 0.00016% | 100% | 5146680 |  |  |  |  | 0.0001504% | 0.00016% | 100% | 5146680
Pump Unit Foundation
[6 empty] | Reinforcement Bar |  | 0.0003% | 0.0003009% | 0.00032% | 10293360 | 0.0002914% | 0.00031% | 100% | 9971692.5 |  |  |  |  | 0.0002914% | 0.00031% | 100% | 9971692.5
Maintenance Deck for Ladle Preheating
[6 empty] | Reinforcement Bar |  | 0.00056% | 0.0005641% | 0.0006% | 19300050 | 0.0005641% | 0.0006% | 100% | 19300050 |  |  |  |  | 0.0005641% | 0.0006% | 100% | 19300050
[6 empty] | Steel Structure & Roof Siding |  | 0.00367% | 0.003667% | 0.0039% | 125450325 | 0.001288% | 0.00137% | 35% | 44068447.5 |  |  |  |  | 0.001288% | 0.00137% | 35% | 44068447.5
|  |  | 2.4 | System 4
Emergency Generator Room
[6 empty] | Reinforcement Bar |  | 0.02537% | 0.02537% | 0.02698% | 867858915 | 0.02537% | 0.02699% | 100% | 868180582.5 |  |  |  |  | 0.02537% | 0.02699% | 100% | 868180582.5
Oxygen Plant Building
[6 empty] | Reinforcement Bar |  | 0.00199% | 0.001993% | 0.00212% | 68193510 | 0.001984% | 0.00211% | 100% | 67871842.5 |  |  |  |  | 0.001984% | 0.00211% | 100% | 67871842.5
[6 empty] | Steel Structure & Roof Siding |  | 0.01239% | 0.01239% | 0.01318% | 423957765 | 0.004344% | 0.00462% | 35% | 148610385 |  |  |  |  | 0.004344% | 0.00462% | 35% | 148610385
Oxygen Plant Equipments Support & Foundation
[6 empty] | Reinforcement Bar |  | 0.00256% | 0.002557% | 0.00272% | 87493560 | 0.002548% | 0.00271% | 100% | 87171892.5 |  |  |  |  | 0.002548% | 0.00271% | 100% | 87171892.5
Compressor Room
[6 empty] | Reinforcement Bar |  | 0.03349% | 0.03349% | 0.03562% | 1145779635 | 0.03348% | 0.03561% | 100% | 1145457967.5 |  |  |  |  | 0.03348% | 0.03561% | 100% | 1145457967.5
Electrical Room for Utility
[6 empty] | Reinforcement Bar |  | 0.01166% | 0.01166% | 0.0124% | 398867700 | 0.01166% | 0.0124% | 100% | 398867700 |  |  |  |  | 0.01166% | 0.0124% | 100% | 398867700
Pump Room for Water Intake (Wayanof river)
[6 empty] | Reinforcement Bar |  | 0.00132% | 0.001316% | 0.0014% | 45033450 | 0.001316% | 0.0014% | 100% | 45033450 |  |  |  |  | 0.001316% | 0.0014% | 100% | 45033450
[6 empty] | Steel Structure & Roof Siding |  | 0.00404% | 0.004043% | 0.0043% | 138317025 | 0.00142% | 0.00151% | 35% | 48571792.5 |  |  |  |  | 0.00142% | 0.00151% | 35% | 48571792.5
Pump Room for Water Intake (sea)
[6 empty] | Reinforcement Bar |  | 0.0023% | 0.002303% | 0.00245% | 78808537.5
[6 empty] | Steel Structure & Roof Siding |  | 0.00893% | 0.008931% | 0.0095% | 305584125 | 0.003131% | 0.00333% | 35% | 107115277.5 |  |  |  |  | 0.003131% | 0.00333% | 35% | 107115277.5
Pump Room for MFO/HSD transfer
[6 empty] | Reinforcement Bar |  | 0.00104% | 0.001044% | 0.00111% | 35705092.5 | 0.001044% | 0.00111% | 100% | 35705092.5 |  |  |  |  | 0.001044% | 0.00111% | 100% | 35705092.5
[6 empty] | Steel Structure & Roof Siding |  | 0.00387% | 0.003873% | 0.00412% | 132527010 | 0.001354% | 0.00144% | 35% | 46320120 |  |  |  |  | 0.001354% | 0.00144% | 35% | 46320120
Cable Rack Structure
[6 empty] | Piles |  | 0.08907% | 0.08907% | 0.09474% | 3047477895 | 0.08907% | 0.09474% | 100% | 3047477895 |  |  |  |  | 0.08907% | 0.09474% | 100% | 3047477895
[6 empty] | Reinforcement Bar |  | 0.01613% | 0.01613% | 0.01716% | 551981430 | 0.01613% | 0.01716% | 100% | 551981430 |  |  |  |  | 0.01613% | 0.01716% | 100% | 551981430
[6 empty] | Steel Structure & Roof Siding |  | 0.2034% | 0.2034% | 0.2164% | 6960884700 | 0.1188% | 0.1264% | 58.42% | 4066198867.5 |  |  |  |  | 0.1188% | 0.1264% | 58.42% | 4066198867.5 | 0.01232%
Water Treatment Equipments Support & Foundation
a. Clarifier & Tank Foundation
[6 empty] | Piles |  | 0.02008% | 0.02008% | 0.02136% | 687081780 | 0.02008% | 0.02136% | 100% | 687081780 |  |  |  |  | 0.02008% | 0.02136% | 100% | 687081780
[6 empty] | Reinforcement Bar |  | 0.00389% | 0.003892% | 0.00414% | 133170345 | 0.003892% | 0.00414% | 100% | 133170345 |  |  |  |  | 0.003892% | 0.00414% | 100% | 133170345
b. Pump Room (Str. & Fdn.)
[6 empty] | Reinforcement Bar |  | 0.00104% | 0.001044% | 0.00111% | 35705092.5 | 0.001044% | 0.00111% | 100% | 35705092.5 |  |  |  |  | 0.001044% | 0.00111% | 100% | 35705092.5
[6 empty] | Steel Structure & Roof Siding |  | 0.00388% | 0.003883% | 0.00413% | 132848677.5 | 0.001354% | 0.00144% | 35% | 46320120 |  |  |  |  | 0.001354% | 0.00144% | 35% | 46320120
c. Warehouse for Chemical
[6 empty] | Reinforcement Bar |  | 0.00427% | 0.004268% | 0.00454% | 146037045 | 0.004268% | 0.00454% | 100% | 146037045 |  |  |  |  | 0.004268% | 0.00454% | 100% | 146037045
[6 empty] | Steel Structure & Roof Siding |  | 0.00753% | 0.007531% | 0.00801% | 257655667.5 | 0.002632% | 0.0028% | 35% | 90066900 |  |  |  |  | 0.002632% | 0.0028% | 35% | 90066900
d. Operator Room (Str. & Fdn.)
[6 empty] | Reinforcement Bar |  | 0.00096% | 0.000959% | 0.00102% | 32810085 | 0.0009496% | 0.00101% | 100% | 32488417.5 |  |  |  |  | 0.0009496% | 0.00101% | 100% | 32488417.5
[6 empty] | Steel Structure & Roof Siding |  | 0.00324% | 0.003244% | 0.00345% | 110975287.5 | 0.001138% | 0.00121% | 35% | 38921767.5 |  |  |  |  | 0.001138% | 0.00121% | 35% | 38921767.5
e. Piping Support (Str. & Fdn.)
[6 empty] | Reinforcement Bar |  | 0.00238% | 0.002379% | 0.00253% | 81381877.5 | 0.002388% | 0.00254% | 100% | 81703545 |  |  |  |  | 0.002388% | 0.00254% | 100% | 81703545
[6 empty] | Steel Structure & Roof Siding |  | 0.01974% | 0.01974% | 0.021% | 675501750 | 0.00691% | 0.00735% | 35% | 236425612.5 |  |  |  |  | 0.00691% | 0.00735% | 35% | 236425612.5
f. WTP Shelter (Str. & Fdn.)
[6 empty] | Reinforcement Bar |  | 0.00628% | 0.00628% | 0.00668% | 214873890 | 0.00629% | 0.00669% | 100% | 215195557.5 |  |  |  |  | 0.00629% | 0.00669% | 100% | 215195557.5
[6 empty] | Steel Structure & Roof Siding |  | 0.0139% | 0.0139% | 0.01478% | 475424565 | 0.00487% | 0.00518% | 35% | 166623765 |  |  |  |  | 0.00487% | 0.00518% | 35% | 166623765
g. Softener Foundation
[6 empty] | Reinforcement Bar |  | 0.00737% | 0.007371% | 0.00784% | 252187320 | 0.007371% | 0.00784% | 100% | 252187320 |  |  |  |  | 0.007371% | 0.00784% | 100% | 252187320
h. Sand Filter Foundation
[6 empty] | Reinforcement Bar |  | 0.00737% | 0.007371% | 0.00784% | 252187320 | 0.007371% | 0.00784% | 100% | 252187320 |  |  |  |  | 0.007371% | 0.00784% | 100% | 252187320
i. NaCL Tank Foundation
[6 empty] | Reinforcement Bar |  | 0.0027% | 0.002698% | 0.00287% | 92318572.5 | 0.002689% | 0.00286% | 100% | 91996905 |  |  |  |  | 0.002689% | 0.00286% | 100% | 91996905
Intake Water Pond (Wayanof River)
[6 empty] | Reinforcement Bar |  | 0.00336% | 0.003356% | 0.00357% | 114835297.5 | 0.003347% | 0.00356% | 100% | 114513630 |  |  |  |  | 0.003347% | 0.00356% | 100% | 114513630
Receiving Water Pond
[6 empty] | Reinforcement Bar |  | 0.0044% | 0.0044% | 0.00468% | 150540390 | 0.004409% | 0.00469% | 100% | 150862057.5 |  |  |  |  | 0.004409% | 0.00469% | 100% | 150862057.5
Filtered Water Pond
[6 empty] | Reinforcement Bar |  | 0.0044% | 0.0044% | 0.00468% | 150540390 | 0.004409% | 0.00469% | 100% | 150862057.5 |  |  |  |  | 0.004409% | 0.00469% | 100% | 150862057.5
Circulation Water Pond Non Softened Water
[6 empty] | Reinforcement Bar |  | 0.01176% | 0.01176% | 0.01251% | 402406042.5 | 0.01176% | 0.01251% | 100% | 402406042.5 |  |  |  |  | 0.01176% | 0.01251% | 100% | 402406042.5
Circulation Water Pond Softened Water
[6 empty] | Reinforcement Bar |  | 0.01332% | 0.01332% | 0.01417% | 455802847.5 | 0.01331% | 0.01416% | 100% | 455481180 |  |  |  |  | 0.01331% | 0.01416% | 100% | 455481180
Circulation Water Pond for Coper Cooler
[6 empty] | Reinforcement Bar |  | 0.01736% | 0.01736% | 0.01847% | 594119872.5 | 0.01736% | 0.01846% | 100% | 593798205 |  |  |  |  | 0.01736% | 0.01846% | 100% | 593798205
Non Softened Water Return Water Pond
[6 empty] | Reinforcement Bar |  | 0.00932% | 0.009317% | 0.00991% | 318772492.5 | 0.009317% | 0.00991% | 100% | 318772492.5 |  |  |  |  | 0.009317% | 0.00991% | 100% | 318772492.5
Softened Water Return Water Pond
[6 empty] | Reinforcement Bar |  | 0.01033% | 0.01033% | 0.01099% | 353512582.5 | 0.01033% | 0.01099% | 100% | 353512582.5 |  |  |  |  | 0.01033% | 0.01099% | 100% | 353512582.5
Softened Water for Cooper Cooler Return Pond
[6 empty] | Reinforcement Bar |  | 0.0102% | 0.0102% | 0.01085% | 349009237.5 | 0.0102% | 0.01085% | 100% | 349009237.5 |  |  |  |  | 0.0102% | 0.01085% | 100% | 349009237.5
Concrete Work for Water Intake (Canal) near the sea
[6 empty] | Piles |  | 0.03911% | 0.03911% | 0.0416% | 1338136800 | 0.03911% | 0.0416% | 100% | 1338136800 |  |  |  |  | 0.03911% | 0.0416% | 100% | 1338136800
[6 empty] | Reinforcement Bar |  | 0.3159% | 0.3159% | 0.336% | 10807062997.5 | 0.3159% | 0.336% | 100% | 10807062997.5 |  |  |  |  | 0.3159% | 0.336% | 100% | 10807062997.5
Transfer Sea Water Pond
[6 empty] | Reinforcement Bar |  | 0.06806% | 0.06806% | 0.07239% | 2328551032.5 | 0.06806% | 0.07239% | 100% | 2328551032.5 |  |  |  |  | 0.06806% | 0.07239% | 100% | 2328551032.5
Slag Granulation Pond
[6 empty] | Reinforcement Bar |  | 0.1216% | 0.1216% | 0.1293% | 4160769112.5 | 0.1216% | 0.1293% | 100% | 4160769112.5 |  |  |  |  | 0.1216% | 0.1293% | 100% | 4160769112.5
Settling Water Pond
[6 empty] | Reinforcement Bar |  | 0.05116% | 0.05116% | 0.05442% | 1750514535 | 0.05115% | 0.05441% | 100% | 1750192867.5 |  |  |  |  | 0.05115% | 0.05441% | 100% | 1750192867.5
Cooling Tower Basin Pond
[6 empty] | Reinforcement Bar |  | 0.05116% | 0.05116% | 0.05442% | 1750514535 | 0.05116% | 0.05442% | 100% | 1750514535 |  |  |  |  | 0.05116% | 0.05442% | 100% | 1750514535
Head Tanks Support & Foundation
[6 empty] | Piles |  | 0.1012% | 0.1012% | 0.1076% | 3461785635 | 0.1012% | 0.1076% | 100% | 3461463967.5 |  |  |  |  | 0.1012% | 0.1076% | 100% | 3461463967.5
[6 empty] | Reinforcement Bar |  | 0.01062% | 0.01062% | 0.0113% | 363484275 | 0.01062% | 0.0113% | 100% | 363484275 |  |  |  |  | 0.01062% | 0.0113% | 100% | 363484275
[6 empty] | Steel Structure & Roof Siding |  | 0.07601% | 0.07601% | 0.08085% | 2600681737.5 | 0.02661% | 0.0283% | 35% | 910319025 |  |  |  |  | 0.02661% | 0.0283% | 35% | 910319025
Softened Water Making Equipment
a. Shot Return Pond
[6 empty] | Reinforcement Bar |  | 0.02081% | 0.02081% | 0.02213% | 711850177.5 | 0.02082% | 0.02214% | 100% | 712171845 |  |  |  |  | 0.02082% | 0.02214% | 100% | 712171845
b. Shot Cooling Pond
[6 empty] | Reinforcement Bar |  | 0.02081% | 0.02081% | 0.02213% | 711850177.5 | 0.02082% | 0.02214% | 100% | 712171845 |  |  |  |  | 0.02082% | 0.02214% | 100% | 712171845
MFO / HSD Main Tank Support & Foundation
a. MFO Tank Foundation
[6 empty] | Reinforcement Bar |  | 0.01078% | 0.01078% | 0.01147% | 368952622.5 | 0.01077% | 0.01146% | 100% | 368630955 |  |  |  |  | 0.01077% | 0.01146% | 100% | 368630955
b. HSD Tank Foundation
[6 empty] | Reinforcement Bar |  | 0.00891% | 0.008913% | 0.00948% | 304940790 | 0.008922% | 0.00949% | 100% | 305262457.5 |  |  |  |  | 0.008922% | 0.00949% | 100% | 305262457.5
MFO / HSD Transfer Pump House
[6 empty] | Reinforcement Bar |  | 0.00104% | 0.001044% | 0.00111% | 35705092.5 | 0.001044% | 0.00111% | 100% | 35705092.5 |  |  |  |  | 0.001044% | 0.00111% | 100% | 35705092.5
[6 empty] | Steel Structure & Roof Siding |  | 0.00387% | 0.003873% | 0.00412% | 132527010 | 0.001354% | 0.00144% | 35% | 46320120 |  |  |  |  | 0.001354% | 0.00144% | 35% | 46320120
MFO Service Tank for Dryer Support & Foundation
[6 empty] | Reinforcement Bar |  | 0.0021% | 0.002097% | 0.00223% | 71731852.5 | 0.002097% | 0.00223% | 100% | 71731852.5 |  |  |  |  | 0.002097% | 0.00223% | 100% | 71731852.5
MFO Service Tank for Kiln Support & Foundation
[6 empty] | Reinforcement Bar |  | 0.0021% | 0.002097% | 0.00223% | 71731852.5 | 0.002106% | 0.00224% | 100% | 72053520 |  |  |  |  | 0.002106% | 0.00224% | 100% | 72053520
HSD Service Tank for Coal mill Support & Foundation
[6 empty] | Reinforcement Bar |  | 0.00084% | 0.0008367% | 0.00089% | 28628407.5 | 0.0008367% | 0.00089% | 100% | 28628407.5 |  |  |  |  | 0.0008367% | 0.00089% | 100% | 28628407.5
HSD Service Tank for Shot making & Ladle Heating Support & Foundation
[6 empty] | Reinforcement Bar |  | 0.00263% | 0.002632% | 0.0028% | 90066900 | 0.002632% | 0.0028% | 100% | 90066900 |  |  |  |  | 0.002632% | 0.0028% | 100% | 90066900
Fire Water Storage Tank Foundation
[6 empty] | Piles |  | 0.02577% | 0.02577% | 0.02741% | 881690617.5 | 0.02577% | 0.02741% | 100% | 881690617.5 |  |  |  |  | 0.02577% | 0.02741% | 100% | 881690617.5
[6 empty] | Reinforcement Bar |  | 0.00743% | 0.007427% | 0.0079% | 254117325 | 0.007427% | 0.0079% | 100% | 254117325 |  |  |  |  | 0.007427% | 0.0079% | 100% | 254117325
Electrical Room for River Water Intake (No.52)
[6 empty] | Reinforcement Bar |  | 0.0121% | 0.0121% | 0.01287% | 413986072.5 | 0.01209% | 0.01286% | 100% | 413664405 |  |  |  |  | 0.01209% | 0.01286% | 100% | 413664405
[6 empty] | Steel Structure & Roof Siding |  | 0.00575% | 0.005754% | 0.00612% | 196860510 | 0.002012% | 0.00214% | 35% | 68836845 |  |  |  |  | 0.002012% | 0.00214% | 35% | 68836845
Electrical Room for Sea Water Intake (No.53)
[6 empty] | Reinforcement Bar |  | 0.01161% | 0.01161% | 0.01235% | 397259362.5 | 0.01161% | 0.01235% | 100% | 397259362.5 |  |  |  |  | 0.01161% | 0.01235% | 100% | 397259362.5
[6 empty] | Steel Structure & Roof Siding |  | 0.0057% | 0.005697% | 0.00606% | 194930505 | 0.002003% | 0.00213% | 35% | 68515177.5 |  |  |  |  | 0.002003% | 0.00213% | 35% | 68515177.5
Cooling Tower Non Softened Water Foundation
[6 empty] | Reinforcement Bar |  | 0.03234% | 0.03234% | 0.0344% | 1106536200 | 0.03234% | 0.0344% | 100% | 1106536200 |  |  |  |  | 0.03234% | 0.0344% | 100% | 1106536200
Cooling Tower Softened Water Foundation
[6 empty] | Reinforcement Bar |  | 0.0539% | 0.0539% | 0.05733% | 1844119777.5 | 0.0539% | 0.05733% | 100% | 1844119777.5 |  |  |  |  | 0.0539% | 0.05733% | 100% | 1844119777.5
Cooling Tower Softened Water Cooper Cooler Foundation
[6 empty] | Reinforcement Bar |  | 0.0539% | 0.0539% | 0.05733% | 1844119777.5 | 0.0539% | 0.05733% | 100% | 1844119777.5 |  |  |  |  | 0.0539% | 0.05733% | 100% | 1844119777.5
|  | 4 | Civil Building |  |  |  |  | 1.322% | 1.322% | 1.406% | 45218730480 | 1.007% | 1.071% |  | 34459274271.5 | 0% | 0% |  | 0 | 1.007% | 1.071% |  | 34459274271.5 | 0.0647%
Administration Office Building 12mW x 50mL x 4mH
[6 empty] | Reinforcement Bar |  | 0.02641% | 0.02641% | 0.02809% | 903564007.5 | 0.02641% | 0.02809% | 100% | 903564007.5 |  |  |  |  | 0.02641% | 0.02809% | 100% | 903564007.5
[6 empty] | Steel Structure & Roof Siding |  | 0.0383% | 0.0383% | 0.04074% | 1310473395 | 0.003826% | 0.00407% | 10% | 130918672.5 |  |  |  |  | 0.003826% | 0.00407% | 10% | 130918672.5
Warehouse 20mW x 90mL x 12mH
[6 empty] | Reinforcement Bar |  | 0.00863% | 0.008631% | 0.00918% | 295290765 | 0.008631% | 0.00918% | 100% | 295290765 |  |  |  |  | 0.008631% | 0.00918% | 100% | 295290765
[6 empty] | Steel Structure & Roof Siding |  | 0.09816% | 0.09816% | 0.1044% | 3358530367.5 | 0.04118% | 0.0438% | 41.95% | 1408903650 |  |  |  |  | 0.04118% | 0.0438% | 41.95% | 1408903650 | 0.006826%
Laboratory 11mW x 24,5mL x 4mH
[6 empty] | Piles |  | 0.03901% | 0.03901% | 0.04149% | 1334598457.5 | 0.03901% | 0.04149% | 100% | 1334598457.5 |  |  |  |  | 0.03901% | 0.04149% | 100% | 1334598457.5
[6 empty] | Reinforcement Bar |  | 0.02587% | 0.02587% | 0.02752% | 885228960 | 0.02587% | 0.02752% | 100% | 885228960 |  |  |  |  | 0.02587% | 0.02752% | 100% | 885228960
Workshop 24mW x 30mL x 12mH
[6 empty] | Reinforcement Bar |  | 0.02932% | 0.02932% | 0.03119% | 1003280932.5 | 0.02932% | 0.03119% | 100% | 1003280932.5 |  |  |  |  | 0.02932% | 0.03119% | 100% | 1003280932.5
[6 empty] | Steel Structure & Roof Siding |  | 0.204% | 0.204% | 0.217% | 6978576412.5 | 0.149% | 0.1585% | 73.05% | 5098108207.5 |  |  |  |  | 0.149% | 0.1585% | 73.05% | 5098108207.5 | 0.01897%
Fire Station House 9mW x 12mL x 5mH
a. Fire Station House
[6 empty] | Reinforcement Bar |  | 0.01324% | 0.01324% | 0.01408% | 452907840 | 0.01324% | 0.01408% | 100% | 452907840 |  |  |  |  | 0.01324% | 0.01408% | 100% | 452907840
b. Fire Station Shelter
[6 empty] | Reinforcement Bar |  | 0.00355% | 0.003554% | 0.00378% | 121590315 | 0.003554% | 0.00378% | 100% | 121590315 |  |  |  |  | 0.003554% | 0.00378% | 100% | 121590315
[6 empty] | Steel Structure & Roof Siding |  | 0.00655% | 0.006553% | 0.00697% | 224202247.5 | 0.002294% | 0.00244% | 35% | 78486870 |  |  |  |  | 0.002294% | 0.00244% | 35% | 78486870
Pump House for Fire Station
[6 empty] | Reinforcement Bar |  | 0.01326% | 0.01326% | 0.0141% | 453551175 | 0.01326% | 0.0141% | 100% | 453551175 |  |  |  |  | 0.01326% | 0.0141% | 100% | 453551175
Weight Bridge & Control Room
[6 empty] | Piles |  | 0.00621% | 0.006214% | 0.00661% | 212622217.5 | 0.006214% | 0.00661% | 100% | 212622217.5 |  |  |  |  | 0.006214% | 0.00661% | 100% | 212622217.5
[6 empty] | Reinforcement Bar |  | 0.01369% | 0.01369% | 0.01456% | 468347880 | 0.01369% | 0.01456% | 100% | 468347880 |  |  |  |  | 0.01369% | 0.01456% | 100% | 468347880
Gate House 2,75mW x 2,5mL x 4mH
[6 empty] | Reinforcement Bar |  | 0.00737% | 0.007371% | 0.00784% | 252187320 | 0.007371% | 0.00784% | 100% | 252187320 |  |  |  |  | 0.007371% | 0.00784% | 100% | 252187320
Outdoor Lavatory
[6 empty] | Reinforcement Bar |  | 0.00065% | 0.0006487% | 0.00069% | 22195057.5 | 0.0006487% | 0.00069% | 100% | 22195057.5 |  |  |  |  | 0.0006487% | 0.00069% | 100% | 22195057.5
[6 empty] | Roof Siding |  | 0.00355% | 0.003554% | 0.00378% | 121590315 | 0.0003573% | 0.00038% | 10% | 12223365 |  |  |  |  | 0.0003573% | 0.00038% | 10% | 12223365
Chemical Laboratory
[6 empty] | Reinforcement Bar |  | 0.0354% | 0.0354% | 0.03765% | 1211078137.5 | 0.0354% | 0.03765% | 100% | 1211078137 |  |  |  |  | 0.0354% | 0.03765% | 100% | 1211078137
Ore Preparation Sample Laboratory
[6 empty] | Reinforcement Bar |  | 0.052% | 0.052% | 0.05531% | 1779142942.5 | 0.052% | 0.05531% | 100% | 1779142942 |  |  |  |  | 0.052% | 0.05531% | 100% | 1779142942
Musholla
[6 empty] | Reinforcement Bar |  | 0.01275% | 0.01275% | 0.01356% | 436181130 | 0.01275% | 0.01356% | 100% | 436181130 |  |  |  |  | 0.01275% | 0.01356% | 100% | 436181130
[6 empty] | Steel Structure & Roof Siding |  | 0.02506% | 0.02506% | 0.02666% | 857565555 | 0.008781% | 0.00934% | 35% | 300437445 |  |  |  |  | 0.008781% | 0.00934% | 35% | 300437445
Mechanical Maintenance & Heavy Equipment Workshop
[6 empty] | Reinforcement Bar |  | 0.01882% | 0.01882% | 0.02002% | 643978335 | 0.01882% | 0.02002% | 100% | 643978335 |  |  |  |  | 0.01882% | 0.02002% | 100% | 643978335
[6 empty] | Steel Structure & Roof Siding |  | 0.1435% | 0.1435% | 0.1526% | 4909289385 | 0.1131% | 0.1203% | 78.85% | 3870946695 |  |  |  |  | 0.1131% | 0.1203% | 78.85% | 3870946695 | 0.02525%
Electrical Maintenance & Instrument Control Workshop
[6 empty] | Reinforcement Bar |  | 0.01452% | 0.01452% | 0.01544% | 496654620 | 0.01452% | 0.01544% | 100% | 496654620 |  |  |  |  | 0.01452% | 0.01544% | 100% | 496654620
[6 empty] | Steel Structure & Roof Siding |  | 0.1072% | 0.1072% | 0.114% | 3667009500 | 0.1072% | 0.114% | 100% | 3667009500 |  |  |  |  | 0.1072% | 0.114% | 100% | 3667009500
Electrical & Instrument Warehouse
[6 empty] | Reinforcement Bar |  | 0.00863% | 0.008631% | 0.00918% | 295290765 | 0.008631% | 0.00918% | 100% | 295290765 |  |  |  |  | 0.008631% | 0.00918% | 100% | 295290765
[6 empty] | Steel Structure & Roof Siding |  | 0.09816% | 0.09816% | 0.1044% | 3358530367.5 | 0.04118% | 0.0438% | 41.95% | 1408903650 |  |  |  |  | 0.04118% | 0.0438% | 41.95% | 1408903650 | 0.006826%
Chemical Warehouse
[6 empty] | Reinforcement Bar |  | 0.00863% | 0.008631% | 0.00918% | 295290765 | 0.008631% | 0.00918% | 100% | 295290765 |  |  |  |  | 0.008631% | 0.00918% | 100% | 295290765
[6 empty] | Steel Structure & Roof Siding |  | 0.09816% | 0.09816% | 0.1044% | 3358530367.5 | 0.04118% | 0.0438% | 41.95% | 1408903650 |  |  |  |  | 0.04118% | 0.0438% | 41.95% | 1408903650 | 0.006826%
Concrete Pipe Sleeper Sea Water Intake
[6 empty] | Reinforcement Bar |  | 0.02327% | 0.02327% | 0.02475% | 796127062.5 | 0.02327% | 0.02475% | 100% | 796127062.5 |  |  |  |  | 0.02327% | 0.02475% | 100% | 796127062.5
Concrete Pipe Sleeper River Water Intake
[6 empty] | Reinforcement Bar |  | 0.1246% | 0.1246% | 0.1325% | 4262094375 | 0.1246% | 0.1325% | 100% | 4262094375 |  |  |  |  | 0.1246% | 0.1325% | 100% | 4262094375
Inject Water Pond
[6 empty] | Reinforcement Bar |  | 0.01325% | 0.01325% | 0.01409% | 453229507.5 | 0.01325% | 0.01409% | 100% | 453229507.5 |  |  |  |  | 0.01325% | 0.01409% | 100% | 453229507.5
B.2 | B.2 | Offshore Equipments and/or Materials System 1 |  |  |  |  | 19.47% | 0% | 19.47% | 20.7% | 666010307077.5 | 17.19% | 18.28% |  | 588158730391 | 1.021% | 1.086% |  | 34948530540 | 18.21% | 19.37% |  | 623107260930.5 | 0.2795% | 93.56%
|  | B.2.1 | MECHANICAL EQUIPMENT
|  | 1 | System 1
|  |  |  | Ore Receiving Equipment (1100) |  |  | 0.3398% |  | 0.3398% | 0.3614% | 11625063450 | 0.3393% | 0.3609% | 99.87% | 11609945077.5 | 0.0004419% | 0.00047% | 10% | 15118372.5 | 0.3398% | 0.3614% | 109.9% | 11625063450 | 0%
|  |  |  | Belt Weigher (Belt Scale) |  |  |  |  | 0.00438% | 0.004659% | 149858415 | 0.003939% | 0.00419% | 90% | 134778682 | 0.0004419% | 0.00047% | 10% | 15118372.5 | 0.004381% | 0.00466% | 100% | 149897055
|  |  |  | Shake Out Machine |  |  |  |  | 0.3288% | 0.3497% | 11250075269.5 | 0.3288% | 0.3497% | 100% | 11249999145 |  |  |  |  | 0.3288% | 0.3497% | 100% | 11249999145
|  |  |  | Other Small Equipment |  |  |  |  | 0.00658% | 0.006999% | 225129765 | 0.006581% | 0.007% | 100% | 225167250 |  |  |  |  | 0.006581% | 0.007% | 100% | 225167250
|  |  |  | Ore Drying Equipment (1200) |  |  | 2.53% |  | 2.53% | 2.691% | 86552360895 | 2.53% | 2.691% | 100% | 86552039227 | 0% | 0% | 0% | 0 | 2.53% | 2.691% | 100% | 86552039227 | 0%
|  |  |  | Shell & Accessories with Lifter |  |  |  |  | 0.4415% | 0.4696% | 15105137617 | 0.4415% | 0.4696% | 100% | 15105184132.5 |  |  |  |  | 0.4415% | 0.4696% | 100% | 15105184132.5
|  |  |  | Tire Ore Drying |  |  |  |  | 0.06584% | 0.07003% | 2252666220 | 0.06584% | 0.07003% | 100% | 2252637502 |  |  |  |  | 0.06584% | 0.07003% | 100% | 2252637502
|  |  |  | Roller & Shaft Ore Drying |  |  |  |  | 0.0852% | 0.09062% | 2915054100 | 0.0852% | 0.09062% | 100% | 2914950885 |  |  |  |  | 0.0852% | 0.09062% | 100% | 2914950885
|  |  |  | Roller Bearing & Pinion Bearing Ore Drying |  |  |  |  | 0.03873% | 0.0412% | 1325117902.5 | 0.03873% | 0.0412% | 100% | 1325270100 |  |  |  |  | 0.03873% | 0.0412% | 100% | 1325270100
|  |  |  | Roller Bearing Bed, Motor Bed & Pinion Bearing Bed Ore Drying |  |  |  |  | 0.0426% | 0.04531% | 1457527050 | 0.0426% | 0.04531% | 100% | 1457475442 |  |  |  |  | 0.0426% | 0.04531% | 100% | 1457475442
|  |  |  | Thruster Ore Drying |  |  |  |  | 0.00775% | 0.008243% | 265160437.5 | 0.007747% | 0.00824% | 100% | 265054020 |  |  |  |  | 0.007747% | 0.00824% | 100% | 265054020
|  |  |  | Girth Gear & Pinion Ore Drying |  |  |  |  | 0.08133% | 0.08651% | 2782644952.5 | 0.08133% | 0.08651% | 100% | 2782745542 |  |  |  |  | 0.08133% | 0.08651% | 100% | 2782745542
|  |  |  | Gear Reducer Ore Drying |  |  |  |  | 0.1355% | 0.1442% | 4637399445 | 0.1355% | 0.1442% | 100% | 4637480347 |  |  |  |  | 0.1355% | 0.1442% | 100% | 4637480347
|  |  |  | Casing, Frame, Support Structure, Stair & Access, Weather Enclosure, Collecting Plate |  |  |  |  | 0.425% | 0.4521% | 14541056250 | 0.425% | 0.4521% | 100% | 14541301005 |  |  |  |  | 0.425% | 0.4521% | 100% | 14541301005
|  |  |  | Rapping Hammer, Electrode, Electrical Components |  |  |  |  | 0.7237% | 0.7697% | 24759142012.5 | 0.7236% | 0.7697% | 100% | 24758747475 |  |  |  |  | 0.7236% | 0.7697% | 100% | 24758747475
|  |  |  | Loop Feeder |  |  |  |  | 0.01583% | 0.01684% | 541611577.5 | 0.01582% | 0.01683% | 100% | 541366402.5 |  |  |  |  | 0.01582% | 0.01683% | 100% | 541366402.5
|  |  |  | Rotary Valve |  |  |  |  | 0.01754% | 0.01866% | 600117945 | 0.01754% | 0.01866% | 100% | 600231555 |  |  |  |  | 0.01754% | 0.01866% | 100% | 600231555
|  |  |  | Other Small Equipment |  |  |  |  | 0.4492% | 0.4778% | 15369725385 | 0.4492% | 0.4778% | 100% | 15369594817.5 |  |  |  |  | 0.4492% | 0.4778% | 100% | 15369594817.5
|  |  |  | Ore Sizing Equipment (1300) |  |  | 0.1754% |  | 0.1754% | 0.1865% | 6000063877.5 | 0.1754% | 0.1865% | 100% | 6000385545 | 0% | 0% | 0% | 0 | 0.1754% | 0.1865% | 100% | 6000385545 | 0%
|  |  |  | Impeller Breaker |  |  |  |  | 0.1644% | 0.1749% | 5625075697.5 | 0.1644% | 0.1749% | 100% | 5625321240 |  |  |  |  | 0.1644% | 0.1749% | 100% | 5625321240
|  |  |  | Other Small Equipment |  |  |  |  | 0.01096% | 0.01166% | 374988180 | 0.01096% | 0.01166% | 100% | 375064305 |  |  |  |  | 0.01096% | 0.01166% | 100% | 375064305
|  |  |  | Ore Mixing Equipment (1400) |  |  | 0.1644% |  | 0.1644% | 0.1749% | 5625321240 | 0.1091% | 0.116% | 66.33% | 3731343000 | 0.04587% | 0.04879% | 27.9% | 1569415732.5 | 0.1549% | 0.1648% | 94.23% | 5300758732.5 | 0%
|  |  |  | Weighing Feeder |  |  |  |  | 0.04384% | 0.04663% | 1499903832 | 0.03946% | 0.04197% | 90% | 1350038497 |  |  |  |  | 0.03946% | 0.04197% | 90% | 1350038497
|  |  |  | Grizzly Feeder (Vibrating Screen) |  |  |  |  | 0.02192% | 0.02332% | 749976360 | 0.02192% | 0.02331% | 100% | 749806942.5 |  |  |  |  | 0.02192% | 0.02331% | 100% | 749806942.5
|  |  |  | Other Small Equipment |  |  |  |  | 0.04768% | 0.05073% | 1631677582.5 | 0.04768% | 0.05072% | 100% | 1631497560 |  |  |  |  | 0.04768% | 0.05072% | 100% | 1631497560
|  |  |  | Piping & Fitting |  |  |  |  | 0.05097% | 0.05421% | 1743763465.5 |  |  |  |  | 0.04587% | 0.04879% | 90% | 1569415732.5 | 0.04587% | 0.04879% | 90% | 1569415732.5
|  |  |  | Dust Treatment Equipment (1500) |  |  | 2.472% |  | 2.472% | 2.629% | 84562525740 | 2.422% | 2.576% | 97.98% | 82850289637.5 | 0% | 0% | 0% | 0 | 2.422% | 2.576% | 97.98% | 82850289637.5 | 0.1151%
|  |  |  | Rod Mill |  |  |  |  | 0.833% | 0.886% | 28500082117.5 | 0.833% | 0.886% | 100% | 28500062167.5 |  |  |  |  | 0.833% | 0.886% | 100% | 28500062167.5
|  |  |  | Briquetting Machine |  |  |  |  | 0.9609% | 1.022% | 32875104255 | 0.9609% | 1.022% | 100% | 32875061835 |  |  |  |  | 0.9609% | 1.022% | 100% | 32875061835
|  |  |  | Load Cell |  |  |  |  | 0.08038% | 0.0855% | 2750141415 | 0.07235% | 0.07695% | 90% | 2475231413 |  |  |  |  | 0.07235% | 0.07695% | 90% | 2475231413
|  |  |  | Loop Feeder |  |  |  |  | 0.1723% | 0.1833% | 5895115275 | 0.1723% | 0.1833% | 100% | 5895200272.5 |  |  |  |  | 0.1723% | 0.1833% | 100% | 5895200272.5
|  |  |  | Pug Mill |  |  |  |  | 0.1279% | 0.136% | 4374976147.5 | 0.1151% | 0.1224% | 90% | 3937531867.5 |  |  |  |  | 0.1151% | 0.1224% | 90% | 3937531867.5 | 0.1151%
|  |  |  | Screw Conveyor |  |  |  |  | 0.02923% | 0.03109% | 1000082527.5
|  |  |  | Other Small Equipment |  |  |  |  | 0.2679% | 0.285% | 9167024002.5 | 0.2679% | 0.285% | 100% | 9167202082.5 |  |  |  |  | 0.2679% | 0.285% | 100% | 9167202082.5
|  |  |  | Rotary Kiln Equipment (1600) |  |  | 5.847% |  | 5.847% | 6.22% | 200067534975 | 4.452% | 4.735% | 76.13% | 152316959602.5 | 0.3757% | 0.3996% | 6.425% | 12855119970 | 4.828% | 5.135% | 82.56% | 165172079572.5 | 0.1644%
|  |  |  | Shell & Accessories with Nose Ring, Thermometer Case & Lifter |  |  |  |  | 1.623% | 1.726% | 55517495077 | 1.623% | 1.726% | 100% | 55517558827.5 |  |  |  |  | 1.623% | 1.726% | 100% | 55517558827.5
|  |  |  | Tire |  |  |  |  | 0.4531% | 0.4819% | 15502476675 | 0.4531% | 0.4819% | 100% | 15502443495 |  |  |  |  | 0.4531% | 0.4819% | 100% | 15502443495
|  |  |  | Roller & Shaft |  |  |  |  | 0.6816% | 0.725% | 23320090657.5 | 0.6816% | 0.725% | 100% | 23320250415 |  |  |  |  | 0.6816% | 0.725% | 100% | 23320250415
|  |  |  | Roller Bearing & Pinion Bearing |  |  |  |  | 0.2556% | 0.2719% | 8745162300 | 0.2556% | 0.2719% | 100% | 8745174322 |  |  |  |  | 0.2556% | 0.2719% | 100% | 8745174322
|  |  |  | Roller Bearing Bed, Motor Bed & Pinion Bearing Bed |  |  |  |  | 0.1781% | 0.1895% | 6094926495 | 0.1781% | 0.1895% | 100% | 6094955790 |  |  |  |  | 0.1781% | 0.1895% | 100% | 6094955790
|  |  |  | Thruster |  |  |  |  | 0.06196% | 0.0659% | 2119914930 | 0.06196% | 0.0659% | 100% | 2119788825 |  |  |  |  | 0.06196% | 0.0659% | 100% | 2119788825
|  |  |  | Girth Gear & Pinion |  |  |  |  | 0.1549% | 0.1648% | 5300129467.5 | 0.1549% | 0.1648% | 100% | 5300115397.5 |  |  |  |  | 0.1549% | 0.1648% | 100% | 5300115397.5
|  |  |  | Gear Reducer |  |  |  |  | 0.3021% | 0.3213% | 10335098497.5 | 0.3021% | 0.3213% | 100% | 10335176775 |  |  |  |  | 0.3021% | 0.3213% | 100% | 10335176775
|  |  |  | kiln burner |  |  |  |  | 0.1827% | 0.1943% | 6249917047.5 | 0.1644% | 0.1749% | 90% | 5624999572.5 |  |  |  |  | 0.1644% | 0.1749% | 90% | 5624999572.5 | 0.1644%
|  |  |  | Weighing Feeder |  |  |  |  | 0.08768% | 0.09326% | 2999905440 | 0.07891% | 0.08393% | 90% | 2699755327 | 0.008772% | 0.00933% | 10% | 300115777.5 | 0.08768% | 0.09326% | 100% | 2999871104
|  |  |  | Hoist |  |  |  |  | 0.03946% | 0.04197% | 1350094305 | 0.03946% | 0.04197% | 100% | 1350038497 |  |  |  |  | 0.03946% | 0.04197% | 100% | 1350038497
|  |  |  | Refractory |  |  |  |  | 0.9609% | 1.022% | 32875104255 | 0% | 0% | 0% | 0 |  |  |  |  | 0% | 0% | 0% | 0
|  |  |  | Other Small Equipment |  |  |  |  | 0.3042% | 0.3235% | 10406982636.75 | 0.3042% | 0.3235% | 100% | 10406586960 |  |  |  |  | 0.3042% | 0.3235% | 100% | 10406586960
|  |  |  | Piping & Fitting |  |  |  |  | 0.4077% | 0.4337% | 13950107724 |  |  |  |  | 0.367% | 0.3903% | 90% | 12555004192.5 | 0.367% | 0.3903% | 90% | 12555004192.5
|  |  |  | General Fan |  |  |  |  | 0.1549% | 0.1648% | 5300129467.5 | 0.1549% | 0.1648% | 100% | 5300115397 |  |  |  |  | 0.1549% | 0.1648% | 100% | 5300115397
|  |  |  | Kiln Exhaust Gas Treatment (1700) |  |  | 1.382% |  | 1.382% | 1.47% | 47272577467.5 | 1.3% | 1.383% | 94.12% | 44491440264 | 0.07619% | 0.08104% | 5.514% | 2606793420 | 1.377% | 1.464% | 99.63% | 47098233684 | 0%
|  |  |  | Pneumatic Conveyor |  |  |  |  | 0.1997% | 0.2124% | 6833295585 | 0.1997% | 0.2124% | 100% | 6833182702 |  |  |  |  | 0.1997% | 0.2124% | 100% | 6833182702
|  |  |  | Chain Conveyor |  |  |  |  | 0.3032% | 0.3225% | 10375129170 | 0.2729% | 0.2903% | 90% | 9337685857 | 0.03032% | 0.03225% | 10% | 1037377687.5 | 0.3032% | 0.3225% | 100% | 10375063544
|  |  |  | Roots Blower |  |  |  |  | 0.2192% | 0.2332% | 7500105742.5 | 0.2192% | 0.2332% | 100% | 7500321097 |  |  |  |  | 0.2192% | 0.2332% | 100% | 7500321097
|  |  |  | Screw Conveyor |  |  |  |  | 0.01461% | 0.01554% | 499984240 | 0.01461% | 0.01554% | 100% | 499871295 |  |  |  |  | 0.01461% | 0.01554% | 100% | 499871295
|  |  |  | Other Small Equipment |  |  |  |  | 0.1686% | 0.1794% | 5770233262.5 | 0.1687% | 0.1794% | 100% | 5770393282.5 |  |  |  |  | 0.1687% | 0.1794% | 100% | 5770393282.5
|  |  |  | Piping & Fitting |  |  |  |  | 0.05097% | 0.05421% | 1743763465.5 |  |  |  |  | 0.04587% | 0.04879% | 90% | 1569415732.5 | 0.04587% | 0.04879% | 90% | 1569415732.5
|  |  |  | Process Fan |  |  |  |  | 0.4253% | 0.4523% | 14550066002.5 | 0.4253% | 0.4523% | 100% | 14549986027.5 |  |  |  |  | 0.4253% | 0.4523% | 100% | 14549986027.5
|  |  |  | Coal Firing Equipment (1800) |  |  | 1.81% |  | 1.81% | 1.925% | 61912308727.5 | 1.739% | 1.85% | 96.11% | 59506235827.5 | 0.07033% | 0.07481% | 3.887% | 2406394567.5 | 1.81% | 1.925% | 100% | 61912630395 | 0%
|  |  |  | Hot Air Generator |  |  |  |  | 0.3215% | 0.342% | 10999794015 | 0.3215% | 0.342% | 100% | 11000063497.5 |  |  |  |  | 0.3215% | 0.342% | 100% | 11000063497.5
|  |  |  | Pneumatic Conveyor |  |  |  |  | 0.09986% | 0.1062% | 3416635005 | 0.09985% | 0.1062% | 100% | 3416430517 |  |  |  |  | 0.09985% | 0.1062% | 100% | 3416430517
|  |  |  | Loop Feeder |  |  |  |  | 0.1882% | 0.2002% | 6438437565 | 0.1882% | 0.2002% | 100% | 6438818347 |  |  |  |  | 0.1882% | 0.2002% | 100% | 6438818347
|  |  |  | Magnet Separator / Metal Detector |  |  |  |  | 0.02557% | 0.0272% | 874858372.5 | 0.02557% | 0.0272% | 100% | 874935600 |  |  |  |  | 0.02557% | 0.0272% | 100% | 874935600
|  |  |  | Bag Filter |  |  |  |  | 0.4492% | 0.4778% | 15370067527.5 | 0.4492% | 0.4778% | 100% | 15369916485 |  |  |  |  | 0.4492% | 0.4778% | 100% | 15369916485
|  |  |  | Coal Grinding Mill |  |  |  |  | 0.6288% | 0.6688% | 21512551830 | 0.5659% | 0.6019% | 90% | 19361166825 | 0.06288% | 0.06688% | 10% | 2151312240 | 0.6288% | 0.6688% | 100% | 21512479065
|  |  |  | Coal Weigher |  |  |  |  | 0.07453% | 0.07927% | 2549988052.5 | 0.06708% | 0.07135% | 90% | 2295097612 | 0.007455% | 0.00793% | 10% | 255082327.5 | 0.07454% | 0.07928% | 100% | 2550179939
|  |  |  | Grizzly Feeder (Vibrating Screen) |  |  |  |  | 0.02192% | 0.02332% | 749976360 | 0.02192% | 0.02331% | 100% | 749806943 |  |  |  |  | 0.02192% | 0.02331% | 100% | 749806943
|  |  |  | Surge Hopper Equipment (2100) |  |  | 0.02601% |  | 0.02601% | 0.02767% | 890053972.5 | 0.02601% | 0.02767% | 100% | 890053972.5 |  |  |  |  | 0.02601% | 0.02767% | 100% | 890053972.5
|  |  |  | Other Small Equipment |  |  |  |  | 0.02601% | 0.02767% | 890053972.5 | 0.02601% | 0.02767% | 100% | 890053972.5 |  |  |  |  | 0.02601% | 0.02767% | 100% | 890053972.5
|  |  |  | Fuel Oil Pumping & Distribution system (4400) |  |  | 0.02192% |  | 0.02192% | 0.02331% | 749806942.5 | 0.02192% | 0.02331% | 100% | 749806942.5 |  |  |  |  | 0.02192% | 0.02331% | 100% | 749806942.5
|  |  |  | Other Small Equipment |  |  |  |  | 0.02192% | 0.02331% | 749806942.5 | 0.02192% | 0.02331% | 100% | 749806942.5 |  |  |  |  | 0.02192% | 0.02331% | 100% | 749806942.5
|  | B.2.2 | ELECTRICAL EQUIPMENT | [8 empty] | 4.076% | 4.336% | 0% | 139460231295 | 0.4529% | 0.4817% |  | 15495688477.5 | 4.529% | 4.817% | 0% | 154955919772 | 0%
|  | 1 | System 1 | [8 empty] | 4.076% | 4.336% | 0% | 139460231295 | 0.4529% | 0.4817% |  | 15495688477.5 | 4.529% | 4.817% | 0% | 154955919772 | 0% |  | Harga Equipment KHI
|  |  |  | Electrical and Instrumentation |  |  | 4.698% |  | 4.698% | 4.997% | 160752689790 | 4.076% | 4.336% |  | 139460231295 | 0.4529% | 0.4817% |  | 15495688477.5 | 4.529% | 4.817% |  | 154955919772 | 0% |  | USD | IDR
|  |  |  | Electrical Equipment |  |  |  |  | 4.529% | 4.817% | 154955687090.3094 | 4.076% | 4.336% | 90% | 139460231295 | 0.4529% | 0.4817% | 10% | 15495688477.5 | 4.529% | 4.817% | 100% | 154955919772
|  |  |  | Field Instrument |  |  |  |  | 0.1694% | 0.1802% | 5797002699.6906 | [14 empty] | 0%
0
B.3 | B.3 | Offshore Equipments and/or Materials System 2, 3, 4 by WIKA |  |  |  |  | 24.98% | 0.249% | 24.98% | 26.57% | 854608465672 | 14.11% | 15% |  | 482604183602 | 2.195% | 2.334% |  | 75087487860 | 16.3% | 17.34% |  | 557691671463 | 0.2157% | 65.26%
|  | B.3.1 | MECHANICAL EQUIPMENT |  |  |  | 24.98% | 0% | 24.98% | 26.57% | 854608465672.5 | 14.11% | 15% |  | 482604183601.5 | 2.195% | 2.334% |  | 75087487860 | 16.3% | 17.34% |  | 557691671462.5 | 0.2157%
|  | 1 | System 2
|  |  |  | Hot Charge Crane |  |  | 0.5867% |  | 0.5867% | 0.6241% | 20074625340 | 0.1174% | 0.1248% | 20% | 4015053735 |  |  |  |  | 0.1174% | 0.1248% | 20% | 4015053735
|  |  |  | Refraction for Furnace Crucible & Calcine Transfer Equipment |  |  | 10.79% |  | 10.79% | 11.48% | 369268499985 | 8.843% | 9.406% | 81.93% | 302546618798 | 0.4317% | 0.4592% | 4% | 14770649932.5 | 9.274% | 9.865% | 85.93% | 317317268731 | copper cooler on site
|  |  |  | Electrode Equipment |  |  | 1.299% |  | 1.299% | 1.381% | 44428071765 | 1.104% | 1.174% | 85% | 37764086168 |  |  |  |  | 1.104% | 1.174% | 85% | 37764086168 |  | 11107017941.25
|  |  |  | Secondary Current Supply Equipment |  |  | 0.6692% |  | 0.6692% | 0.7118% | 22897579320 | 0.5689% | 0.6051% | 85% | 19462813755 |  |  |  |  | 0.5689% | 0.6051% | 85% | 19462813755 |  | 5724394830
|  |  |  | Water Cooling Equipment |  |  | 0.04935% |  | 0.04935% | 0.05249% | 1688432707.5 | 0.01233% | 0.01312% | 25% | 422027760 |  |  |  |  | 0.01233% | 0.01312% | 25% | 422027760
|  |  |  | Electrical Panels |  |  | 0.2711% |  | 0.2711% | 0.2884% | 9276247365 | 0.06779% | 0.0721% | 25% | 2319222675 |  |  |  |  | 0.06779% | 0.0721% | 25% | 2319222675 |  | 2319061841.25
|  |  |  | Electrode Suspension Devices |  |  | 0.26% |  | 0.26% | 0.2765% | 8895071377.5 | 0.221% | 0.2351% | 85% | 7560794588 | 0.039% | 0.04148% | 15% | 1334276790 | 0.26% | 0.2765% | 100% | 8895071378 |  | 2223767844.375
|  |  |  | Tapping Equipment |  |  | 0.6576% |  | 0.6576% | 0.6994% | 22498711620 | 0.5589% | 0.5945% | 85% | 19123776210 |  |  |  |  | 0.5589% | 0.5945% | 85% | 19123776210
|  |  |  | Electric Smelting Furnace Equipment |  |  | 0.9241% |  | 0.9241% | 0.9829% | 31617341910 | 0.1848% | 0.1966% | 20% | 6323339715 | 0.5545% | 0.5897% | 60% | 18970340812.5 | 0.7393% | 0.7863% | 80% | 25293680527.5
|  |  |  | Cooling System for ESF |  |  | 0.5848% |  | 0.5848% | 0.622% | 20008361835 | 0.117% | 0.1244% | 20% | 4001543700 |  |  |  |  | 0.117% | 0.1244% | 20% | 4001543700
|  |  |  | Electrode Movement Equipment & Auxiliary |  |  | 0.1215% |  | 0.1215% | 0.1292% | 4157230770 | 0.1033% | 0.1099% | 85% | 3533517487 |  |  |  |  | 0.1033% | 0.1099% | 85% | 3533517487
|  |  |  | Furnace Transformer |  |  | 1.109% |  | 1.109% | 1.18% | 37955799997.5 | 0.9429% | 1.003% | 85% | 32262285247.5 |  |  |  |  | 0.9429% | 1.003% | 85% | 32262285247.5
|  |  |  | Off Gas Furnce Treatment System |  |  | 6.319% |  | 6.319% | 6.721% | 216185006730 | 0.9464% | 1.007% | 14.98% | 32379050550 | 0.4202% | 0.4469% | 6.65% | 14376285577.5 | 1.367% | 1.454% | 21.63% | 46755336128 | ladle hood, smoke hood, smoke stack & duct
|  |  |  | Slag Granulation System |  |  | 0.08566% |  | 0.08567% | 0.09112% | 2931034260 | 0.06853% | 0.07289% | 80% | 2344634408 |  |  |  |  | 0.06853% | 0.07289% | 80% | 2344634408 | 0.0514%
|  | 2 | System 4
|  |  |  | Oxygen Plant |  |  | 1.249% |  | 1.249% | 1.328% | 42726450690 | 0.2498% | 0.2657% | 20% | 8545418805 | 0.7493% | 0.797% | 60% | 25635934747.5 | 0.999% | 1.063% | 80% | 34181353552.5
B.4 | B.4 | Transportation Services for Equipment/Material by WIKA |  |  |  |  | 0% | 3.191% | 3.191% | 3.395% | 109193571218 | 0.6316% | 0.6718% |  | 21608979317 | 0.864% | 0.919% |  | 29560921583 | 1.496% | 1.591% |  | 51169900900 | 0.006873% | 46.86%
|  | B.4.1 | PACKAGING AND TRANSPORT
|  | 1 | System-1
Mechanical
[5 empty] | Rotary Klin |  |  | 0.3331% | 0.3331% | 0.3543% | 11397001192.5 | 0.2725% | 0.2899% | 81.82% | 9324819157.5 |  |  |  |  | 0.2725% | 0.2899% | 81.82% | 9324819157.5
[5 empty] | Rotary Dryer |  |  | 0.1007% | 0.1007% | 0.1072% | 3446988930 | 0.1007% | 0.1072% | 100% | 3446988930 |  |  |  |  | 0.1007% | 0.1072% | 100% | 3446988930
[5 empty] | Coal Mill |  |  | 0.00774% | 0.007737% | 0.00823% | 264732352.5 | 0.0002444% | 0.00026% | 3.2% | 8363355 |  |  |  |  | 0.0002444% | 0.00026% | 3.2% | 8363355
[5 empty] | EP |  |  | 0.0299% | 0.0299% | 0.0318% | 1022902650 | 0.0299% | 0.0318% | 100% | 1022902650 |  |  |  |  | 0.0299% | 0.0318% | 100% | 1022902650
[5 empty] | Impeller Breaker |  |  | 0.00229% | 0.002294% | 0.00244% | 78486870 | 0.002294% | 0.00244% | 100% | 78486870 |  |  |  |  | 0.002294% | 0.00244% | 100% | 78486870
[5 empty] | Briquetting Machine |  |  | 0.01024% | 0.01024% | 0.01089% | 350295907.5 | 0.01024% | 0.01089% | 100% | 350295907.5 |  |  |  |  | 0.01024% | 0.01089% | 100% | 350295907.5
[5 empty] | Rod Mill |  |  | 0.01953% | 0.01953% | 0.02077% | 668103397.5 | 0.01953% | 0.02077% | 100% | 668103397.5 |  |  |  |  | 0.01953% | 0.02077% | 100% | 668103397.5
[5 empty] | Fan |  |  | 0.00613% | 0.00613% | 0.00652% | 209727210 | 0.00613% | 0.00652% | 100% | 209727210 |  |  |  |  | 0.00613% | 0.00652% | 100% | 209727210
[5 empty] | Shake Out Machine |  |  | 0.00509% | 0.005086% | 0.00541% | 174022117.5 | 0.005086% | 0.00541% | 100% | 174022118 |  |  |  |  | 0.005086% | 0.00541% | 100% | 174022118
[5 empty] | Others |  |  | 0.1926% | 0.1926% | 0.2049% | 6590645407.5 | 0.1204% | 0.128% | 62.5% | 4118952338 |  |  |  |  | 0.1204% | 0.128% | 62.5% | 4118952338
[5 empty] | Electrical |  |  | 0.00437% | 0.004372% | 0.00465% | 149575387.5
[5 empty] | Refractory |  |  | 0.2919% | 0.2919% | 0.3105% | 9988419210 |  |  |  |  | 0.254% | 0.2702% | 87% | 8689847512.5 | 0.254% | 0.2702% | 87% | 8689847512.5 | 0.7287% |  | plan
[5 empty] | Machinery |  |  | 0.5456% | 0.5456% | 0.5803% | 18667973362.5 |  |  |  |  | 0.4747% | 0.5049% | 87% | 16240992075 | 0.4747% | 0.5049% | 87% | 16240992075
|  |  |  | Piping |  |  |  | 0.01732% | 0.01732% | 0.01842% | 592511535
|  |  |  | Instrument |  |  |  | 0.00562% | 0.005622% | 0.00598% | 192357165
|  |  |  | Electrical |  |  |  | 0.00606% | 0.006064% | 0.00645% | 207475537.5
|  | 2 | System-2
Mechanical
[5 empty] | Container and Transfer Car |  |  | 0.01641% | 0.01641% | 0.01745% | 561309787.5 |  |  |  |  | 0.01641% | 0.01745% | 100% | 561309787.5 | 0.01641% | 0.01745% | 100% | 561309787.5 | plan
[5 empty] | Top Bin Cover |  |  | 0.00387% | 0.003873% | 0.00412% | 132527010
[5 empty] | Dust Collecting Equipment |  |  | 0.00713% | 0.007126% | 0.00758% | 243823965
[5 empty] | Furnace Top Bin |  |  | 0.02686% | 0.02686% | 0.02857% | 919004047.5
[5 empty] | Auxillaries |  |  | 0.00166% | 0.001664% | 0.00177% | 56935147.5
[5 empty] | Surge Bin |  |  | 0.00371% | 0.003714% | 0.00395% | 127058662.5
[5 empty] | Container Shaft |  |  | 0.00198% | 0.001984% | 0.00211% | 67871842.5
[5 empty] | Hot Charge Crane |  |  | 0.00016% | 0.0001598% | 0.00017% | 5468347.5
[5 empty] | Furnace Charging System |  |  | 0.03166% | 0.03166% | 0.03368% | 1083376140
[5 empty] | Furnace Roof Equipment |  |  | 0.0002% | 0.0001974% | 0.00021% | 6755017.5
[5 empty] | Electrode Suspension Device |  |  | 0.0005% | 0.0004983% | 0.00053% | 17048377.5
[5 empty] | Electrode Equipment |  |  | 0.02308% | 0.02308% | 0.02455% | 789693712.5
[5 empty] | Secondary Current Supply Equipment |  |  | 0.00365% | 0.003648% | 0.00388% | 124806990
[5 empty] | Tapping Equipment |  |  | 0.00113% | 0.001128% | 0.0012% | 38600100
[5 empty] | Water Cooling for Electrode & Transformer |  |  | 0.00196% | 0.001956% | 0.00208% | 66906840
[5 empty] | Clinker Handling Equipment |  |  | 0.00024% | 0.0002444% | 0.00026% | 8363355
[5 empty] | Furnace Shell Assembly |  |  | 0.03845% | 0.03845% | 0.0409% | 1315620075
[5 empty] | Offgas Stack Assembly |  |  | 0.2847% | 0.2847% | 0.3028% | 9739770232.5
[5 empty] | Offgas Foundations |  |  | 0.00042% | 0.0004231% | 0.00045% | 14475037.5
[5 empty] | Tapping Launder for Metal and Slag |  |  | 0.0158% | 0.0158% | 0.01681% | 540723067.5
[5 empty] | Furnace Shell Lining |  |  | 0.6929% | 0.6929% | 0.737% | 23705929747.5
[5 empty] | Copper Coolers |  |  | 0.1018% | 0.1018% | 0.1083% | 3483015690
[5 empty] | Cooling Water System |  |  | 0.0001% | 0.0001034% | 0.00011% | 3538342.5
[5 empty] | Taping Fume System for Metal and Slag Tapholes |  |  | 0.00366% | 0.003657% | 0.00389% | 125128657.5
[5 empty] | Primary Offgas Dedusting System |  |  | 0.0061% | 0.006102% | 0.00649% | 208762207.5
|  |  |  | Piping |  |  |  | 0.02862% | 0.02862% | 0.03044% | 979155870
|  |  |  | Instrument |  |  |  | 0.00562% | 0.005622% | 0.00598% | 192357165
|  |  |  | Electrical |  |  |  | 0.00895% | 0.00895% | 0.00952% | 306227460
|  | 3 | System-3
|  |  |  | Mechanical |  |  |  | 0.05992% | 0.05992% | 0.06373% | 2049986977.5 | 0.04786% | 0.05091% | 79.88% | 1637609243 | 0.005989% | 0.00637% | 10% | 204902197.5 | 0.05385% | 0.05728% | 89.88% | 1842511441 | 0.006873%
|  |  |  | Piping |  |  |  | 0.00105% | 0.001053% | 0.00112% | 36026760
|  |  |  | Instrument |  |  |  | 0.00562% | 0.005622% | 0.00598% | 192357165
|  |  |  | Electrical |  |  |  | 0.00423% | 0.004231% | 0.0045% | 144750375
|  | 4 | System-4
|  |  |  | Mechanical |  |  |  | 0.1223% | 0.1222% | 0.13% | 4182642502.5 | 0.01662% | 0.01768% | 13.6% | 568708140 | 0.03301% | 0.03511% | 27% | 1129374592.5 | 0.04963% | 0.05279% | 40.6% | 1698082732.5 | plan
|  |  |  | Piping |  |  |  | 0.07992% | 0.07992% | 0.08501% | 2734495417.5 |  |  |  |  | 0.07992% | 0.08501% | 100% | 2734495417.5 | 0.07992% | 0.08501% | 100% | 2734495417.5 | plan
|  |  |  | Instrument |  |  |  | 0.00562% | 0.005622% | 0.00598% | 192357165
|  |  |  | Electrical |  |  |  | 0.02325% | 0.02325% | 0.02473% | 795483727.5
Note on F736: Windows User: Barata
Note on F740: Windows User: Refractory

## Print C
| Attachment 3 - Construction | [21 empty] | 2018-05-31
| NO | DESCRIPTION |  |  |  |  | CONTRACT - IDR |  |  |  |  | PROGRESS
[7 empty] | FOREIGN PORTION | DOMESTIC PORTION | TOTAL |  |  | UNTIL PREVIOUS MONTH |  |  |  | THIS MONTH |  |  |  | UNTIL THIS MONTH |  |  |  | THIS MONTH
[9 empty] | % WEIGHT FACTOR (OVERALL) | % WEIGHT FACTOR (WIKA PORTION) | IDR | % WEIGHT FACTOR (OVERALL) | % WEIGHT FACTOR (WIKA PORTION) | % PROGRESS | IDR | % WEIGHT FACTOR (OVERALL) | % WEIGHT FACTOR (WIKA PORTION) | % PROGRESS | IDR | % WEIGHT FACTOR (OVERALL) | % WEIGHT FACTOR (WIKA PORTION) | % PROGRESS | IDR | % WEIGHT FACTOR (OVERALL)
C | C | CONSTRUCTION | [6 empty] | 13.74% | 14.62% | 470218054845 | 3.172% | 3.374% |  | 108519034477 | 0.1234% | 0.1312% |  | 4221242603 | 3.295% | 3.505% |  | 112740277081 | 0.5446% | 23.98% | 0.0042121
C.1 | C.1 | Construction Services by WIKA |  |  |  |  | 1.981% | 10.73% | 12.71% | 13.52% | 435012833640 | 2.314% | 2.462% |  | 79181671807 | 0.1111% | 0.1182% |  | 3802109850 | 2.425% | 2.58% |  | 82983781658 | 0.5323% | 19.08% | 0.0042121
|  | C.1.1 | INSTALLATION |  |  |  | 1.981% | 7.357% | 9.338% | 9.933% | 319508467740 | 0.6082% | 0.6469% |  | 20809635577.5 | 0.08723% | 0.09278% |  | 2984431065 | 0.6954% | 0.7397% |  | 23794066642.5 | 0.4057% |  | 0.0031848
|  | A | PIPING WORK |  |  |  | 0% | 1.128% | 1.128% | 1.2% | 38594631652.5 | 0% | 0% |  | 0 | 0% | 0% |  | 0 | 0% | 0% |  | 0 | 0% |  | 0
|  |  | System-1 | [22 empty] | 0
|  |  |  | Piping, Fitting, Support, and Accessories |  |  |  | 0.179% | 0.179% | 0.1904% | 6124227532.5 | [14 empty] | 0
|  |  | System-2 | [22 empty] | 0
|  |  |  | Instalasi Piping Lokal |  |  |  | 0.08274% | 0.08274% | 0.08801% | 2830995667.5 | [14 empty] | 0
|  |  |  | Instalasi Piping KHI |  |  |  | 0.259% | 0.259% | 0.2755% | 8861617957.5 | [14 empty] | 0
|  |  | System-3 | [22 empty] | 0
|  |  |  | Piping, Fitting, Support & Accesories |  |  |  | 0.02754% | 0.02754% | 0.02929% | 942164107.5 | [14 empty] | 0
|  |  | System-4 | [22 empty] | 0
|  |  |  | Piping, Fitting, Support & Accesories |  |  |  | 0.5797% | 0.5797% | 0.6167% | 19835626387.5 | [14 empty] | 0
0
0
|  | B | MECHANICAL WORK |  |  |  | 1.981% | 4.869% | 6.85% | 7.287% | 234383667210 | 0.6082% | 0.6469% |  | 20809635577.5 | 0.08723% | 0.09278% |  | 2984431065 | 0.6954% | 0.7397% |  | 23794066642.5 | 0.4057% |  | 0.0031848
|  | 1 | Mechanical Work | [22 empty] | 0
|  |  | System-1 | [22 empty] | 0
|  |  |  | Ore Receiving Equipment |  |  |  | 0.04208% | 0.04208% | 0.04476% | 1439783730 | [14 empty] | 0
|  |  |  | Ore Drying Equipment |  |  |  | 0.3188% | 0.3189% | 0.3392% | 10909353262.5 | 0.1045% | 0.1111% | 32.76% | 3574047592.5 | 0.03329% | 0.03541% | 10.44% | 1139024617.5 | 0.1378% | 0.1465% | 43.2% | 4713072210 | 0.06373% |  | 0.00030442
|  |  |  | Ore Sizing Equipment |  |  |  | 0.0452% | 0.0452% | 0.04808% | 1546577340 | [14 empty] | 0
|  |  |  | Ore Mixing Equipment |  |  |  | 0.05685% | 0.05685% | 0.06047% | 1945123372.5 | [14 empty] | 0
|  |  |  | Dust Treatment Equipment |  |  |  | 0.06415% | 0.06415% | 0.06823% | 2194737352.5 | [14 empty] | 0
|  |  |  | Rotary Kiln Equipment |  |  |  | 0.7687% | 0.7687% | 0.8176% | 26301143137.5 | 0.2028% | 0.2157% | 26.38% | 6938367975 | 0.02519% | 0.02679% | 3.277% | 861747232.5 | 0.228% | 0.2425% | 29.66% | 7800115207.5 | 0.05321% |  | 0.00028026
|  |  |  | Kiln Exhaust Gas Treatment |  |  |  | 0.3918% | 0.3918% | 0.4168% | 13405814730 | 0.06246% | 0.06644% | 15.94% | 2137158870 | 0% | 0% |  | 0 | 0.06246% | 0.06644% | 15.94% | 2137158870 | 0.05728% |  | 0.00057284
|  |  |  | Coal Firing Equipment |  |  |  | 0.152% | 0.152% | 0.1617% | 5201041807.5 | [14 empty] | 0
|  |  |  | Surge Hopper Equipment |  |  |  | 0.08671% | 0.08671% | 0.09223% | 2966739352.5 | [14 empty] | 0
|  |  |  | Fuel Oil Pumping and Distribution system |  |  |  | 0.2527% | 0.2527% | 0.2688% | 8647387402.5 | 0.2264% | 0.2408% | 89.56% | 7744788397.5 | 0.02588% | 0.02753% | 10.24% | 885550627.5 | 0.2522% | 0.2683% | 99.8% | 8630339025 | 0.2264% |  | 0.0020048
0
0
|  |  | System-3 | [22 empty] | 0
|  |  |  | Stirrer Unit |  |  |  | 0.00236% | 0.00236% | 0.00251% | 80738542.5 | [14 empty] | 0
|  |  |  | Lifting Device |  |  |  | 0.00429% | 0.004287% | 0.00456% | 146680380 | [14 empty] | 0
|  |  |  | Shifting Device and Swinging Part |  |  |  | 0.00422% | 0.004221% | 0.00449% | 144428707.5 | [14 empty] | 0
|  |  |  | Hoist |  |  |  | 0.001% | 0.0009966% | 0.00106% | 34096755 | [14 empty] | 0
|  |  |  | Exhaust Gas Duct |  |  |  | 0.00267% | 0.00267% | 0.00284% | 91353570 | [14 empty] | 0
|  |  |  | Work Stage |  |  |  | 0.01637% | 0.01637% | 0.01741% | 560023117.5 | [14 empty] | 0
|  |  |  | Ladle Tilting Machine |  |  |  | 0.02324% | 0.02324% | 0.02472% | 795162060 | [14 empty] | 0
|  |  |  | Runner |  |  |  | 0.00341% | 0.003413% | 0.00363% | 116765302.5 | [14 empty] | 0
|  |  |  | Spray Head |  |  |  | 0.00018% | 0.0001786% | 0.00019% | 6111682.5 | [14 empty] | 0
|  |  |  | Shot Making Tank |  |  |  | 0.02417% | 0.02417% | 0.02571% | 827007142.5 | 0.009336% | 0.00993% | 38.63% | 319415827.5 | 0.0006487% | 0.00069% | 2.68% | 22195057.5 | 0.009984% | 0.01062% | 41.31% | 341610885 | 0.00267% |  | 2.0213e-05
|  |  |  | No. 1 Net Conveyor |  |  |  | 0.00568% | 0.005679% | 0.00604% | 194287170 | [14 empty] | 0
|  |  |  | Jet Water Pump |  |  |  | 0.0008% | 0.0007991% | 0.00085% | 27341737.5 | [14 empty] | 0
|  |  |  | Surge Hopper |  |  |  | 0.00291% | 0.002914% | 0.0031% | 99716925 | [14 empty] | 0
|  |  |  | No. 2 Net Conveyor |  |  |  | 0.00603% | 0.006026% | 0.00641% | 206188867.5 | [14 empty] | 0
|  |  |  | Hot Stove |  |  |  | 0.001% | 0.0009966% | 0.00106% | 34096755 | [14 empty] | 0
|  |  |  | Burner Dilution Fan |  |  |  | 0.00025% | 0.0002538% | 0.00027% | 8685022.5 | [14 empty] | 0
|  |  |  | Hot Gas Circulation Fan |  |  |  | 0.00036% | 0.0003573% | 0.00038% | 12223365 | [14 empty] | 0
|  |  |  | Ducting |  |  |  | 0.00436% | 0.004362% | 0.00464% | 149253720 | [14 empty] | 0
|  |  |  | Trommel |  |  |  | 0.00247% | 0.002473% | 0.00263% | 84598552.5 | [14 empty] | 0
|  |  |  | Soundproof Box |  |  |  | 0.00342% | 0.003422% | 0.00364% | 117086970 | [14 empty] | 0
|  |  |  | Container |  |  |  | 0.00604% | 0.006036% | 0.00642% | 206510535 | [14 empty] | 0
|  |  |  | Container Car |  |  |  | 0.00245% | 0.002454% | 0.00261% | 83955217.5 | [14 empty] | 0
|  |  |  | Shot Cooling Pump |  |  |  | 0.00177% | 0.001767% | 0.00188% | 60473490 | 0.0007051% | 0.00075% | 40% | 24125062.5 | 0.0008837% | 0.00094% | 50% | 30236745 | 0.001589% | 0.00169% | 90% | 54361807.5 | 0.0005265% |  | -3.5726e-06
|  |  |  | Cooling Tower |  |  |  | 0.00268% | 0.002679% | 0.00285% | 91675237.5 | 0.001391% | 0.00148% | 52% | 47606790 | 0.0004513% | 0.00048% | 16.8% | 15440040 | 0.001843% | 0.00196% | 68.8% | 63046830 | 0.001391% |  | 9.4016e-06
|  |  |  | Cooling Tower Feed Pump |  |  |  | 0.00177% | 0.001767% | 0.00188% | 60473490 | 0.0007051% | 0.00075% | 40% | 24125062.5 | 0.0008837% | 0.00094% | 50% | 30236745 | 0.001589% | 0.00169% | 90% | 54361807.5 | 0.0005265% |  | -3.5726e-06
|  |  |  | Ladle Handling Crane |  |  |  | 0.02186% | 0.02186% | 0.02325% | 747876937.5 | [14 empty] | 0
|  |  |  | Ladles |  |  |  | 0.03793% | 0.03793% | 0.04034% | 1297606695 | [14 empty] | 0
|  |  |  | Slag Pot |  |  |  | 0.00197% | 0.001974% | 0.0021% | 67550175 | [14 empty] | 0
|  |  |  | Hanger ( 5 Hanger +2 Stand ) |  |  |  | 0.00858% | 0.008584% | 0.00913% | 293682427.5 | [14 empty] | 0
|  |  |  | Service Tank |  |  |  | 0.00044% | 0.0004419% | 0.00047% | 15118372.5 | [14 empty] | 0
|  |  |  | Pump Unit |  |  |  | 0.00011% | 0.0001128% | 0.00012% | 3860010 | [14 empty] | 0
|  |  |  | Valve Unit |  |  |  | 0.0003% | 0.0003009% | 0.00032% | 10293360 | [14 empty] | 0
|  |  |  | Burner |  |  |  | 0.00011% | 0.0001128% | 0.00012% | 3860010 | [14 empty] | 0
|  |  |  | Blower |  |  |  | 0.00046% | 0.0004607% | 0.00049% | 15761707.5 | [14 empty] | 0
|  |  |  | Ladle Heating Unit |  |  |  | 0.00396% | 0.003958% | 0.00421% | 135422017.5 | [14 empty] | 0
|  |  |  | Casting Storage Crane |  |  |  | 0.00572% | 0.005707% | 0.00607% | 195252172.5 | [14 empty] | 0
0
|  |  | System-4 | [22 empty] | 0
|  |  |  | Raw Water Intake System | [21 empty] | 0
|  |  | 4102-1 | Raw Water Intake Pump | [21 empty] | 0
|  |  | 4102-2 | Raw Water Intake Pump |  |  |  | 0.00014% | 0.000141% | 0.00015% | 4825012.5 | [14 empty] | 0
|  |  | 4103 | Clarifier |  |  |  | 0.01329% | 0.01329% | 0.01414% | 454837845 | [14 empty] | 0
|  |  | 4104-1 | Water Transfer Pump |  |  |  | 0.00038% | 0.0003761% | 0.0004% | 12866700 | [14 empty] | 0
|  |  | 4104-2 | Water Transfer Pump |  |  |  | 0.00038% | 0.0003761% | 0.0004% | 12866700 | [14 empty] | 0
|  |  | 4105-1 | No.1 Dosing Tank |  |  |  | 0.00049% | 0.0004889% | 0.00052% | 16726710 | [14 empty] | 0
|  |  | 4106-1 | Dosing Pump for No.1 Tank |  |  |  | 0.00031% | 0.0003103% | 0.00033% | 10615027.5 | [14 empty] | 0
|  |  | 4105-2 | No.2 Dosing Tank |  |  |  | 3e-05% | 2.82e-05% | 3e-05% | 965002.5 | [14 empty] | 0
|  |  | 4106-2 | Dosing Pump for No.2 Tank |  |  |  | 2e-05% | 1.88e-05% | 2e-05% | 643335 | [14 empty] | 0
|  |  |  | Piping & Supports c/w Accessories; Used for Raw Water Intake Area. |  |  |  | 0.08346% | 0.08346% | 0.08877% | 2855442397.5 | [14 empty] | 0
|  |  |  | Piping to Filtration Receiving Water System; Used from Water Intake; Circulation water pond for Copper Cooler SW (emergency). |  |  |  | 0.00153% | 0.001532% | 0.00163% | 52431802.5 | [14 empty] | 0
|  |  | 4111-1 | Receiving Water Pump |  |  |  | 8e-05% | 8.461e-05% | 9e-05% | 2895007.5 | [14 empty] | 0
|  |  | 4111-2 | Receiving Water Pump |  |  |  | 8e-05% | 8.461e-05% | 9e-05% | 2895007.5 | [14 empty] | 0
|  |  | 4112 | Sand Filter |  |  |  | 0.0076% | 0.007596% | 0.00808% | 259907340 | [14 empty] | 0
|  |  | 4114-1 | Filtered Water Pump |  |  |  | 8e-05% | 8.461e-05% | 9e-05% | 2895007.5 | [14 empty] | 0
|  |  | 4114-2 | Filtered Water Pump |  |  |  | 8e-05% | 8.461e-05% | 9e-05% | 2895007.5 | [14 empty] | 0
|  |  | 4115-1/2 | Softener |  |  |  | 0.00435% | 0.004353% | 0.00463% | 148932052.5 | [14 empty] | 0
|  |  | 4116 | NaCl Tank |  |  |  | 0.00061% | 0.0006111% | 0.00065% | 20908387.5 | [14 empty] | 0
|  |  |  | Piping; Used from Water Filtered Pond to Circulation Water Pond and Circulation Water Pond Copper Cooler. |  |  |  | 0.00105% | 0.001053% | 0.00112% | 36026760 | [14 empty] | 0
|  |  |  | Circulation Water - NSW |  |  |  | 0% | 0% | 0% | 0 | [14 empty] | 0
|  |  | 4201-1 | NSW- Circulation Pump |  |  |  | 0.0004% | 0.0004043% | 0.00043% | 13831702.5 | [14 empty] | 0
|  |  | 4201-2 | NSW- Circulation Pump |  |  |  | 0.0004% | 0.0004043% | 0.00043% | 13831702.5 | [14 empty] | 0
|  |  | 4202 | NSW - Head Tank |  |  |  | 0.01851% | 0.01851% | 0.01969% | 633363307.5 | [14 empty] | 0
|  |  | 4204-1 | NSW - Return Water Pump |  |  |  | 0.00019% | 0.000188% | 0.0002% | 6433350 | [14 empty] | 0
|  |  | 4204-2 | NSW - Return Water Pump |  |  |  | 0.00019% | 0.000188% | 0.0002% | 6433350 | [14 empty] | 0
|  |  | 4205 | NSW - Cooling Water |  |  |  | 0.00196% | 0.001956% | 0.00208% | 66906840 | [14 empty] | 0
|  |  |  | Piping & Support; Pipe & Support for Water Circulation. |  |  |  | 0.00267% | 0.00267% | 0.00284% | 91353570 | [14 empty] | 0
|  |  |  | Circulation Water - SW |  |  |  | 0% | 0% | 0% | 0 | [14 empty] | 0
|  |  | 4211-1 | SW - Circulation Pump |  |  |  | 0.00031% | 0.0003103% | 0.00033% | 10615027.5 | [14 empty] | 0
|  |  | 4211-2 | SW - Circulation Pump |  |  |  | 0.00031% | 0.0003103% | 0.00033% | 10615027.5 | [14 empty] | 0
|  |  | 4212 | SW - Head Tank |  |  |  | 0.01851% | 0.01851% | 0.01969% | 633363307.5 | [14 empty] | 0
|  |  | 4214-1 | SW - Return Water Pump |  |  |  | 0.00028% | 0.000282% | 0.0003% | 9650025 | [14 empty] | 0
|  |  | 4214-2 | SW - Return Water Pump |  |  |  | 0.00028% | 0.000282% | 0.0003% | 9650025 | [14 empty] | 0
|  |  | 4215 | SW - Cooling Tower |  |  |  | 0.00652% | 0.006525% | 0.00694% | 223237245 | [14 empty] | 0
|  |  | 4216 | SW - Inline Filter |  |  |  | 8e-05% | 8.461e-05% | 9e-05% | 2895007.5 | [14 empty] | 0
|  |  |  | Piping & Support for Circulation Water - SW |  |  |  | 0.0025% | 0.002501% | 0.00266% | 85563555 | [14 empty] | 0
|  |  |  | Circulation Water SW (Copper Cooler) |  |  |  | 0% | 0% | 0% | 0 | [14 empty] | 0
|  |  | 4221-1 | SW - Circulation Pump |  |  |  | 0.0004% | 0.0004043% | 0.00043% | 13831702.5 | [14 empty] | 0
|  |  | 4221-2 | SW - Circulation Pump |  |  |  | 0.0004% | 0.0004043% | 0.00043% | 13831702.5 | [14 empty] | 0
|  |  | 4222 | SW - Head Tank |  |  |  | 0.01851% | 0.01851% | 0.01969% | 633363307.5 | [14 empty] | 0
|  |  | 4224-1 | SW - Return Water Pump |  |  |  | 0.00028% | 0.000282% | 0.0003% | 9650025 | [14 empty] | 0
|  |  | 4224-2 | SW - Return Water Pump |  |  |  | 0.00028% | 0.000282% | 0.0003% | 9650025 | [14 empty] | 0
|  |  | 4225 | SW - Cooling Tower |  |  |  | 0.00652% | 0.006525% | 0.00694% | 223237245 | [14 empty] | 0
|  |  | 4226 | SW - Inline Filter; Auto Cleaning Type; Accessories. |  |  |  | 8e-05% | 8.461e-05% | 9e-05% | 2895007.5 | [14 empty] | 0
|  |  |  | Piping & Support for Circulation Water SW (Copper Cooler) |  |  |  | 0.205% | 0.205% | 0.218% | 7013316502.5 | [14 empty] | 0
|  |  |  | Air Compressor |  |  |  | 0% | 0% | 0% | 0 | [14 empty] | 0
|  |  | 4701-1/2 | Air compressors |  |  |  | 0.00328% | 0.003281% | 0.00349% | 112261957.5 | [14 empty] | 0
|  |  | 4702 | Air Receiver Tank |  |  |  | 0.00098% | 0.0009778% | 0.00104% | 33453420 | [14 empty] | 0
|  |  | 4703-1/2/3/4/5 | Air Receiver Tank |  |  |  | 0.00489% | 0.004889% | 0.0052% | 167267100 | [14 empty] | 0
|  |  | 4703-6 | Air Receiver Tank |  |  |  | 0.00098% | 0.0009778% | 0.00104% | 33453420 | [14 empty] | 0
|  |  | 4704-2 | Air Dryer for HAG Instrument |  |  |  | 3e-05% | 2.82e-05% | 3e-05% | 965002.5 | [14 empty] | 0
|  |  | 4704-3 | Air Dryer for Instrument for Kiln |  |  |  | 3e-05% | 2.82e-05% | 3e-05% | 965002.5 | [14 empty] | 0
|  |  | 4704-4 | Air Dryer for DE-S System and Others (System-3) |  |  |  | 3e-05% | 2.82e-05% | 3e-05% | 965002.5 | [14 empty] | 0
|  |  | 4707-1/2 | Air compressor for Mud Gun (Tapping Drill ) |  |  |  | 0.00068% | 0.0006769% | 0.00072% | 23160060 | [14 empty] | 0
|  |  | 4705-1 | Air Compressor for ESF & Refinery System-1 |  |  |  | 0.00136% | 0.001363% | 0.00145% | 46641787.5 | [14 empty] | 0
|  |  |  | Air Compressor for ESF & Refinery System-2 |  |  |  | 0.00136% | 0.001363% | 0.00145% | 46641787.5 | [14 empty] | 0
|  |  | 4706 | Air Receiver Tank |  |  |  | 0.00033% | 0.0003291% | 0.00035% | 11258362.5 | [14 empty] | 0
|  |  | 4708-1/2 | Air Receiver Tank |  |  |  | 0.00033% | 0.0003291% | 0.00035% | 11258362.5 | [14 empty] | 0
|  |  | 4709-1 | Air Receiver Tank |  |  |  | 0.00033% | 0.0003291% | 0.00035% | 11258362.5 | [14 empty] | 0
|  |  | 4711-1 | Air Dryer for Instrument Air System-1 |  |  |  | 3e-05% | 2.82e-05% | 3e-05% | 965002.5 | [14 empty] | 0
|  |  |  | Air Dryer for Instrument Air System-2 |  |  |  | 3e-05% | 2.82e-05% | 3e-05% | 965002.5 | [14 empty] | 0
|  |  |  | Piping & Support: Used for Distribution Air Pipe & Support from Receiver Tank to Process Plant. |  |  |  | 0.0356% | 0.0356% | 0.03787% | 1218154822.5 | [14 empty] | 0
|  |  |  | Fuel Oil System |  |  |  | 0% | 0% | 0% | 0 | [14 empty] | 0
|  |  | 4302-1 | Feed Pump for MFO Fuel |  |  |  | 0.00013% | 0.0001316% | 0.00014% | 4503345 | [14 empty] | 0
|  |  | 4302-2 | Feed Pump for MFO Fuel |  |  |  | 0.00013% | 0.0001316% | 0.00014% | 4503345 | [14 empty] | 0
|  |  |  | MFO Fuel Oil Services Tank; Capacity 2m3; Mild Steel Material; Dimension 1.5mD x 2mH; Accessories. |  |  |  | 0.00027% | 0.0002726% | 0.00029% | 9328357.5 | [14 empty] | 0
|  |  |  | Piping & Support for MFO Fuel; Used for Distribution from Receiving Storage Tank to Tie-In Points at Process Plant Area. |  |  |  | 0.02409% | 0.02409% | 0.02562% | 824112135 | [14 empty] | 0
|  |  | 4401-1 | Feed Pump for HSD Fuel |  |  |  | 0.00013% | 0.0001316% | 0.00014% | 4503345 | [14 empty] | 0
|  |  | 4401-2 | Feed Pump for HSD Fuel |  |  |  | 0.00013% | 0.0001316% | 0.00014% | 4503345 | [14 empty] | 0
|  |  |  | Piping & Support for HSD Fuel; Used for Distribution from Receiving Storage Tank to Tie-In Points at Process Plant Area. |  |  |  | 0.02426% | 0.02426% | 0.0258% | 829902150 | [14 empty] | 0
|  |  |  | Sea Water Intake |  |  |  | 0% | 0% | 0% | 0 | [14 empty] | 0
|  |  | 4900 | Fixed Screen Bar & Rotary Screen |  |  |  | 0.00038% | 0.0003761% | 0.0004% | 12866700 | [14 empty] | 0
|  |  | 4901-1/2/3 | Sea Water Intake Pump |  |  |  | 0.00038% | 0.0003761% | 0.0004% | 12866700 | [14 empty] | 0
|  |  | 4901-4 | Sea Water Intake Pump |  |  |  | 0.04749% | 0.04749% | 0.05051% | 1624742542.5 | [14 empty] | 0
|  |  |  | Piping & Support; for Distribution from Intake Water Pump to Transfer Sea Water Pond (Slag System). |  |  |  | 0% | 0% | 0% | 0 | [14 empty] | 0
|  |  |  | Fire Water System |  |  |  | 0% | 0% | 0% | 0 | [14 empty] | 0
|  |  | 4801 | Fire Water Tank |  |  |  | 0% | 0% | 0% | 0 | [14 empty] | 0
|  |  | 4802-A/B | Fire Water Pump |  |  |  | 0% | 0% | 0% | 0 | [14 empty] | 0
|  |  | 4803 | Jockey Pump |  |  |  | 0% | 0% | 0% | 0 | [14 empty] | 0
|  |  |  | Oxygen Plant |  |  |  | 0% | 0% | 0% | 0 | [14 empty] | 0
|  |  | 4601 | 4601 Oxygen Plant |  |  |  | 0.03683% | 0.03682% | 0.03916% | 1259649930 | [14 empty] | 0
0
0
|  | 2 | Mechanical Work (Furnace) System 2 | [22 empty] | 0
|  |  |  | Instalasi Mechanical ( HTV ) |  |  | 1.981% |  | 1.981% | 2.107% | 67782097267.5 | [14 empty] | 0
|  |  |  | Top Bin Covers |  |  |  | 0.04272% | 0.04272% | 0.04544% | 1461657120 | [14 empty] | 0
|  |  |  | Container |  |  |  | 0.03158% | 0.03158% | 0.03359% | 1080481132.5 | [14 empty] | 0
|  |  |  | Transfer Car |  |  |  | 0.06277% | 0.06277% | 0.06677% | 2147773897.5 | [14 empty] | 0
|  |  |  | Hot Charge Crane |  |  |  | 0.05332% | 0.05332% | 0.05671% | 1824176392.5 | [14 empty] | 0
|  |  |  | Furnace Top Bin |  |  |  | 0.1127% | 0.1127% | 0.1199% | 3855828322.5 | [14 empty] | 0
|  |  |  | Charging tubes |  |  |  | 0.05574% | 0.05574% | 0.05929% | 1907166607.5 | [14 empty] | 0
|  |  |  | Dust Collection Equipment |  |  |  | 0.0447% | 0.0447% | 0.04755% | 1529528962.5 | [14 empty] | 0
|  |  |  | Refraction for Furnace Crucible & Calcine Transfer Equipment |  |  |  | 0.6556% | 0.6556% | 0.6973% | 22430839777.5 | [14 empty] | 0
|  |  |  | Auxiliaries |  |  |  | 0.00924% | 0.009242% | 0.00983% | 316199152.5 | [14 empty] | 0
|  |  |  | Electrode Equipment |  |  |  | 0.1146% | 0.1146% | 0.1219% | 3920483490 | [14 empty] | 0
|  |  |  | Clamping frames |  |  |  |  | 0% | 0% | 0 | [14 empty] | 0
|  |  |  | Secondary Current Supply Equipment |  |  |  | 0.0181% | 0.0181% | 0.01925% | 619209937.5 | [14 empty] | 0
|  |  |  | Water Cooling Equipment |  |  |  | 0.00972% | 0.009721% | 0.01034% | 332604195 | [14 empty] | 0
|  |  |  | Electrical Panels (Cooling Water Instruments) 30 KV MP Switch Gear |  |  |  |  | 0% | 0% | 0 | [14 empty] | 0
|  |  |  | Electrode Suspension Devices ( Main Hydraulic System ) |  |  |  | 0.00248% | 0.002482% | 0.00264% | 84920220 | [14 empty] | 0
|  |  |  | Tapping Equipment |  |  |  | 0.00559% | 0.005594% | 0.00595% | 191392162.5 | [14 empty] | 0
|  |  |  | Electric Smelting Furnace Equipment ( furnace roof & Cell ) |  |  |  | 0.1937% | 0.1937% | 0.206% | 6627958837.5 | [14 empty] | 0
|  |  |  | Cooling System for ESF |  |  |  |  | 0% | 0% | 0 | [14 empty] | 0
|  |  |  | Electrode Movement Equipment & Auxiliary |  |  |  | 0.1413% | 0.1413% | 0.1503% | 4835949195 | [14 empty] | 0
|  |  |  | Furnace Transformer |  |  |  |  | 0% | 0% | 0 | [14 empty] | 0
|  |  |  | Off Gas Furnace Treatment System |  |  |  | 0.3329% | 0.3329% | 0.3541% | 11390889510 | [14 empty] | 0
|  |  |  | Working Deck for Electrode'; Dimension 0.5mW x 20mL x 13.5mH; Accessories. |  |  |  |  | 0% | 0% | 0 | [14 empty] | 0
|  |  |  | Tapping Deck; Dimension 0.5mW x 20mL x 13,5mH; Accessories. |  |  |  |  | 0% | 0% | 0 | [14 empty] | 0
|  |  |  | Heat Prevention Board for Tapping Runner |  |  |  |  | 0% | 0% | 0 | [14 empty] | 0
|  |  |  | Hoist for Paste Charge; Monorail Type; Capacity 25ton; Dimension Lift 17m, Traveling 26m; Motor 1-30kW, 4P, IMB (Hoist), etc.; Accessories. |  |  |  | 0.00092% | 0.0009214% | 0.00098% | 31523415 | [14 empty] | 0
|  |  |  | Slag Granulation Launder; Spray Box Type, SS400 Install; Capacity 170t/h; Dimension 12mW x 12.7mL; Jet Box Size Inlet Dia 600A (0.274m2), Outlet 300 x 50mm x 6pcs (0.12m2) & 200 x 50mm x 6pcs (0.03m2). |  |  |  | 0.01409% | 0.01408% | 0.01498% | 481857915 | [14 empty] | 0
|  |  |  | Transfer Sea Water Pond; RC Construction Type; Capacity 1800m3; Dimension 20mW x 30mL x 3mH. |  |  |  |  | - | - | [15 empty] | 0
|  |  |  | Granulation Water Pump; Centrifugal Pump Type; Capacity 1000m3/h x 30mH, Wataer Temperature 400C; Motor 4-150kW, 4P, IM. |  |  |  |  | - | - | [15 empty] | 0
|  |  |  | Slag Granulation Pond (safety protect explosion); RC Construction Type; RC Construction Type; Dimension 25mW x 30mL x 4mH; Accessories. |  |  |  |  | - | - | [15 empty] | 0
|  |  |  | Settling Water Pond; RC Construction Type; Capacity 1500m3; Dimension 20mW x 25mL x 3mH. |  |  |  |  | - | - | [15 empty] | 0
|  |  |  | Cooling Tower Feed Pump; Centrifugal Pump Type; Capacity 900m3/h x 25mH, Wataer Temperature 700C; Motor 4-110kW, 4P, IM; Accessories. |  |  |  |  | - | - | [15 empty] | 0
|  |  |  | Cooling Tower; Shower Water Counter Flow Type with Filer Main Mataerial FRP/PP; Capacity 2700m3/h (900m3/h x 3 units) + 1 Unit Stndby; Water Temperature Input 700C / Output 400C; Motor 4-22kW, 4P, IM. |  |  |  |  | - | - | [15 empty] | 0
0
0
0
|  | C | ELECTRICAL WORK |  |  |  | 0% | 1.068% | 1.068% | 1.136% | 36554294700 | 0% | 0% |  |  | 0% | 0% |  |  | 0% | 0% |  |  | 0% |  | 0
|  |  | System-1 | [22 empty] | 0
|  |  |  | Power Transformer 6.6 / 0.4 kV |  |  |  | 0.3891% | 0.3891% | 0.4139% | 13313496157.5 | [14 empty] | 0
|  |  |  | Generator Unit Control Panel (GCP) |  |  |  | 0.0004% | 0.0004043% | 0.00043% | 13831702.5 | [14 empty] | 0
|  |  |  | Distribution Panel |  |  |  | 0.00152% | 0.001523% | 0.00162% | 52110135 | [14 empty] | 0
|  |  |  | Lighting and Small Power Panel |  |  |  | 0.00056% | 0.0005641% | 0.0006% | 19300050 | [14 empty] | 0
|  |  |  | Indoor and Outdoor Lighting |  |  |  | 0.0178% | 0.0178% | 0.01893% | 608916577.5 | [14 empty] | 0
|  |  |  | MV Power Cable (for Main Substation) |  |  |  | 0.00408% | 0.00408% | 0.00434% | 139603695 | [14 empty] | 0
|  |  |  | RTD Cable |  |  |  | 9e-05% | 9.402e-05% | 0.0001% | 3216675 | [14 empty] | 0
|  |  |  | LV Power Cable |  |  |  | 0.09871% | 0.09871% | 0.105% | 3377187082.5 | [14 empty] | 0
|  |  |  | Cable Ladder and Cable Tray |  |  |  | 0.03933% | 0.03933% | 0.04183% | 1345535152.5 | [14 empty] | 0
|  |  |  | Bulk Material |  |  |  | 0.03226% | 0.03226% | 0.03431% | 1103641192.5 | [14 empty] | 0
|  |  |  | Grounding and Lightning Protection |  |  |  | 0.0326% | 0.0326% | 0.03468% | 1115542890 | [14 empty] | 0
0
|  |  | System-2 | [22 empty] | 0
|  |  |  | Diesel Engine Generator | [21 empty] | 0
|  |  |  | Power Transformer 6.6 / 0.4 kV for Main Substation | [21 empty] | 0
|  |  |  | 30 kV MV Switchgear for ESF | [21 empty] | 0
|  |  |  | MV Switchgear 6.6 kV |  |  |  | 0.00609% | 0.006092% | 0.00648% | 208440540 | [14 empty] | 0
|  |  |  | Power Transformer 6.6 / 0.4 kV |  |  |  | 0.00095% | 0.0009496% | 0.00101% | 32488417.5 | [14 empty] | 0
|  |  |  | Power Transformer 6.6 / 0.69 kV |  |  |  | 0% | 0% | 0% | 0 | [14 empty] | 0
|  |  |  | LV Switchgear 400 V |  |  |  | 0.00246% | 0.002463% | 0.00262% | 84276885 | [14 empty] | 0
|  |  |  | Capacitor Bank Panel |  |  |  | 0.00121% | 0.001213% | 0.00129% | 41495107.5 | [14 empty] | 0
|  |  |  | Distribution Board |  |  |  | 0% | 0% | 0% | 0 | [14 empty] | 0
|  |  |  | Lighting and Small Power Panel |  |  |  | 0.00013% | 0.0001316% | 0.00014% | 4503345 | [14 empty] | 0
|  |  |  | Indoor and Outdoor Lighting |  |  |  | 0.00394% | 0.003939% | 0.00419% | 134778682.5 | [14 empty] | 0
|  |  |  | DC UPS |  |  |  | 0.00125% | 0.00125% | 0.00133% | 42781777.5 | [14 empty] | 0
|  |  |  | MV Power Cable |  |  |  | 0.00098% | 0.0009778% | 0.00104% | 33453420 | [14 empty] | 0
|  |  |  | LV Power Cable |  |  |  | 0.02363% | 0.02363% | 0.02513% | 808350427.5 | [14 empty] | 0
|  |  |  | Control Cable |  |  |  | 0.00808% | 0.008076% | 0.00859% | 276312382.5 | [14 empty] | 0
|  |  |  | Local Control Panel |  |  |  | 0% | 0% | 0% | 0 | [14 empty] | 0
|  |  |  | Cable Ladder and Cable Tray |  |  |  | 0.02869% | 0.02869% | 0.03052% | 981729210 | [14 empty] | 0
|  |  |  | Bulk Material |  |  |  | 0.01445% | 0.01445% | 0.01537% | 494402947.5 | [14 empty] | 0
|  |  |  | Grounding and Lightning Protection |  |  |  | 0.00615% | 0.006149% | 0.00654% | 210370545 | [14 empty] | 0
0
|  |  | System-3 | [22 empty] | 0
|  |  |  | Diesel Engine Generator | [21 empty] | 0
|  |  |  | Power Transformer 6.6 / 0.4 kV for Main Substation | [21 empty] | 0
|  |  |  | MV Switchgear 6.6 kV |  |  |  | 0.00193% | 0.001927% | 0.00205% | 65941837.5 | [14 empty] | 0
|  |  |  | Power Transformer 6.6 / 0.4 kV |  |  |  | 0.00273% | 0.002726% | 0.0029% | 93283575 | [14 empty] | 0
|  |  |  | LV Switchgear 400 V |  |  |  | 0.00246% | 0.002463% | 0.00262% | 84276885 | [14 empty] | 0
|  |  |  | Capacitor Bank Panel |  |  |  | 0.00068% | 0.0006769% | 0.00072% | 23160060 | [14 empty] | 0
|  |  |  | Distribution Board |  |  |  | 0% | 0% | 0% | 0 | [14 empty] | 0
|  |  |  | Lighting and Small Power Panel |  |  |  | 4e-05% | 3.761e-05% | 4e-05% | 1286670 | [14 empty] | 0
|  |  |  | Indoor and Outdoor Lighting |  |  |  | 0.00055% | 0.0005547% | 0.00059% | 18978382.5 | [14 empty] | 0
|  |  |  | DC UPS |  |  |  | 0.00092% | 0.0009214% | 0.00098% | 31523415 | [14 empty] | 0
|  |  |  | MV Power Cable |  |  |  | 0.0012% | 0.001203% | 0.00128% | 41173440 | [14 empty] | 0
|  |  |  | LV Power Cable |  |  |  | 0.00344% | 0.003441% | 0.00366% | 117730305 | [14 empty] | 0
|  |  |  | Control Cable |  |  |  | 0.00272% | 0.002717% | 0.00289% | 92961907.5 | [14 empty] | 0
|  |  |  | Local Control Panel |  |  |  | 0% | 0% | 0% | 0 | [14 empty] | 0
|  |  |  | Cable Ladder and Cable Tray |  |  |  | 0.01453% | 0.01453% | 0.01545% | 496976287.5 | [14 empty] | 0
|  |  |  | Bulk Material |  |  |  | 0.00948% | 0.009477% | 0.01008% | 324240840 | [14 empty] | 0
|  |  |  | Grounding and Lightning Protection |  |  |  | 0.00459% | 0.004588% | 0.00488% | 156973740 | [14 empty] | 0
0
|  |  | System-4 | [22 empty] | 0
|  |  |  | Diesel Engine Generator | [21 empty] | 0
|  |  |  | Power Transformer 6.6 / 0.4 kV for Main Substation |  |  |  | 0.02706% | 0.02706% | 0.02878% | 925759065 | [14 empty] | 0
|  |  |  | MV Switchgear 6.6 kV |  |  |  | 0.00167% | 0.001673% | 0.00178% | 57256815 | [14 empty] | 0
|  |  |  | Power Transformer 6.6 / 0.4 kV |  |  |  | 0.00195% | 0.001946% | 0.00207% | 66585172.5 | [14 empty] | 0
|  |  |  | LV Switchgear 400 V |  |  |  | 0.00277% | 0.002773% | 0.00295% | 94891912.5 | [14 empty] | 0
|  |  |  | Capacitor Bank Panel |  |  |  | 0.00068% | 0.0006769% | 0.00072% | 23160060 | [14 empty] | 0
|  |  |  | Distribution Board |  |  |  | 0.0036% | 0.003601% | 0.00383% | 123198652.5 | [14 empty] | 0
|  |  |  | Lighting and Small Power Panel |  |  |  | 0.00077% | 0.0007709% | 0.00082% | 26376735 | [14 empty] | 0
|  |  |  | Indoor and Outdoor Lighting |  |  |  | 0.02704% | 0.02704% | 0.02876% | 925115730 | [14 empty] | 0
|  |  |  | DC UPS |  |  |  | 0.00248% | 0.002482% | 0.00264% | 84920220 | [14 empty] | 0
|  |  |  | MV Power Cable |  |  |  | 0.02927% | 0.02927% | 0.03113% | 1001350927.5 | [14 empty] | 0
|  |  |  | LV Power Cable |  |  |  | 0.03161% | 0.03161% | 0.03362% | 1081446135 | [14 empty] | 0
|  |  |  | Control Cable |  |  |  | 0.0114% | 0.0114% | 0.01213% | 390182677.5 | [14 empty] | 0
|  |  |  | Local Control Panel |  |  |  | 0.00334% | 0.003338% | 0.00355% | 114191962.5 | [14 empty] | 0
|  |  |  | Cable Ladder and Cable Tray |  |  |  | 0.04295% | 0.04295% | 0.04568% | 1469377140 | [14 empty] | 0
|  |  |  | Bulk Material |  |  |  | 0.06546% | 0.06546% | 0.06963% | 2239770802.5 | [14 empty] | 0
|  |  |  | Grounding and Lightning Protection |  |  |  | 0.0566% | 0.0566% | 0.0602% | 1936438350 | [14 empty] | 0
0
0
|  | D | INSTRUMENTATION WORK |  |  |  | 0% | 0.2916% | 0.2916% | 0.3101% | 9975874177.5 | 0% | 0% |  |  | 0% | 0% |  |  | 0% | 0% |  |  | 0% |  | 0
|  |  | System-1 | [22 empty] | 0
|  |  |  | Actuator |  |  |  | 0.00336% | 0.003356% | 0.00357% | 114835297.5 | [14 empty] | 0
|  |  |  | Controll & Instrument Cable |  |  |  | 0.066% | 0.066% | 0.0702% | 2258105850 | [14 empty] | 0
|  |  |  | Instrument Piping |  |  |  | 0.00014% | 0.000141% | 0.00015% | 4825012.5 | [14 empty] | 0
0
|  |  | System-2 | [22 empty] | 0
|  |  |  | Local Instrument Installation |  |  |  | 0.01998% | 0.01998% | 0.02125% | 683543437.5 | [14 empty] | 0
|  |  |  | PLC-SCADA |  |  |  | 0.00202% | 0.002021% | 0.00215% | 69158512.5 | [14 empty] | 0
|  |  |  | Puliing and Instalasi Instrument Cable |  |  |  | 0.04008% | 0.04008% | 0.04263% | 1371268552.5 | [14 empty] | 0
|  |  |  | Termination |  |  |  | 0.01238% | 0.01238% | 0.01317% | 423636097.5 | [14 empty] | 0
|  |  |  | Instrument Bulk Material Installation |  |  |  | 0.0487% | 0.0487% | 0.0518% | 1666237650 | [14 empty] | 0
|  |  |  | Inspection and testion for Mechanical Completion |  |  |  | 0.00956% | 0.009561% | 0.01017% | 327135847.5 | [14 empty] | 0
0
|  |  | System-3 | [22 empty] | 0
|  |  |  | Local Instrument Installation |  |  |  | 0.00154% | 0.001542% | 0.00164% | 52753470 | [14 empty] | 0
|  |  |  | PLC-SCADA |  |  |  | 0.00154% | 0.001542% | 0.00164% | 52753470 | [14 empty] | 0
|  |  |  | Pulling and Installation Instrument Cable |  |  |  | 0.00454% | 0.004541% | 0.00483% | 155365402.5 | [14 empty] | 0
|  |  |  | Termination |  |  |  | 0.00134% | 0.001344% | 0.00143% | 45998452.5 | [14 empty] | 0
|  |  |  | Instrument Bulk Material Installation |  |  |  | 0.00739% | 0.00739% | 0.00786% | 252830655 | [14 empty] | 0
|  |  |  | Inspection and Testing Mechanical Completion |  |  |  | 0.00585% | 0.005848% | 0.00622% | 200077185 | [14 empty] | 0
0
|  |  | System-4 | [22 empty] | 0
|  |  |  | Local Instrument Installation |  |  |  | 0.00172% | 0.00172% | 0.00183% | 58865152.5 | [14 empty] | 0
|  |  |  | PLC-SCADA |  |  |  | 0.0019% | 0.001899% | 0.00202% | 64976835 | [14 empty] | 0
|  |  |  | Pulling and Installation Instrument Cable |  |  |  | 0.00551% | 0.005509% | 0.00586% | 188497155 | [14 empty] | 0
|  |  |  | Termination |  |  |  | 0.00225% | 0.002247% | 0.00239% | 76878532.5 | [14 empty] | 0
|  |  |  | Instrument Bulk Material Installation |  |  |  | 0.01015% | 0.01015% | 0.0108% | 347400900 | [14 empty] | 0
|  |  |  | Inspection and Testion for Mechanical Completion |  |  |  | 0.00596% | 0.005961% | 0.00634% | 203937195 | [14 empty] | 0
|  |  |  | Local Instrument Installation |  |  |  | 0.00079% | 0.0007897% | 0.00084% | 27020070 | [14 empty] | 0
|  |  |  | Process Control System |  |  |  | 0.00058% | 0.0005829% | 0.00062% | 19943385 | [14 empty] | 0
|  |  |  | Pulling and Installation Instrument Cable |  |  |  | 0.002% | 0.002003% | 0.00213% | 68515177.5 | [14 empty] | 0
|  |  |  | Termination |  |  |  | 0.0006% | 0.0006017% | 0.00064% | 20586720 | [14 empty] | 0
|  |  |  | Instrument Bulk Material Installation |  |  |  | 0.00976% | 0.009759% | 0.01038% | 333890865 | [14 empty] | 0
|  |  |  | Inspection and Testion for Mechanical Completion |  |  |  | 0.00616% | 0.006158% | 0.00655% | 210692212.5 | [14 empty] | 0
|  |  |  | Fire Detection System |  |  |  | 0.01034% | 0.01034% | 0.011% | 353834250 | [14 empty] | 0
|  |  |  | Telephone System |  |  |  | 0.00126% | 0.00126% | 0.00134% | 43103445 | [14 empty] | 0
|  |  |  | PAGA System |  |  |  | 0.00584% | 0.005838% | 0.00621% | 199755517.5 | [14 empty] | 0
|  |  |  | CCTV System |  |  |  | 0.00232% | 0.002322% | 0.00247% | 79451872.5 | [14 empty] | 0
0
0
0
|  | C.1.2 | CONSTRUCTION |  |  |  | 0% | 3.376% | 3.376% | 3.591% | 115504365900 | 1.706% | 1.815% |  | 58372036229.5 | 0.0239% | 0.02542% |  | 817678785 | 1.73% | 1.84% |  | 59189715015 | 0.1266% |  | 0.0010273
|  | 1 | Earth Work | [22 empty] | 0
|  |  |  | Site Clearing |  |  |  | 0.03365% | 0.03365% | 0.03579% | 1151247982.5 | 0.03197% | 0.03401% | 95% | 1093991168 | 0% | 0% |  | 0 | 0.03197% | 0.03401% | 95% | 1093991168 | 0.003366% |  | 3.3658e-05
|  |  |  | Cutting |  |  |  | 0.00791% | 0.007907% | 0.00841% | 270522367.5 | 0.007108% | 0.00756% | 90% | 243180630 | 0% | 0% |  | 0 | 0.007108% | 0.00756% | 90% | 243180630 | 0.0003949% |  | 3.9487e-06
|  |  |  | Backfilling |  |  |  | 0.00891% | 0.008913% | 0.00948% | 304940790 | 0.008029% | 0.00854% | 90% | 274704045 | 0% | 0% |  | 0 | 0.008029% | 0.00854% | 90% | 274704045 | 0.0004419% |  | 4.4187e-06
|  |  |  | Ground Improvement |  |  |  | 0.00584% | 0.005838% | 0.00621% | 199755517.5 | 0.005538% | 0.00589% | 95% | 189462157 | 0% | 0% |  | 0 | 0.005538% | 0.00589% | 95% | 189462157 | 0.0002914% |  | 2.9145e-06
0
|  | 2 | Civil Work | [22 empty] | 0
|  |  |  | Topographical Survey |  |  |  | 0.01935% | 0.01935% | 0.02058% | 661991715 | 0.01935% | 0.02058% | 100% | 661991715 |  |  |  |  | 0.01935% | 0.02058% | 100% | 661991715 |  |  | 0
|  |  |  | Soil Investigation Survey |  |  |  | 0.02488% | 0.02488% | 0.02646% | 851132205 | 0.02488% | 0.02646% | 100% | 851132205 |  |  |  |  | 0.02488% | 0.02646% | 100% | 851132205 |  |  | 0
|  |  |  | Fence & Gates | [21 empty] | 0
[6 empty] | Concrete |  | 0.00162% | 0.001617% | 0.00172% | 55326810 | 0.0003197% | 0.00034% | 19.74% | 10936694 | 0% | 0% |  | 0 | 0.0003197% | 0.00034% | 19.74% | 10936694 | 0.0001222% |  | 1.2222e-06
[6 empty] | Reinforcement Bar |  | 0.00383% | 0.003826% | 0.00407% | 130918672.5 | 0.0009026% | 0.00096% | 23.67% | 30880079 | 0% | 0% |  | 0 | 0.0009026% | 0.00096% | 23.67% | 30880079 |  |  | 0
[6 empty] | BRC |  | 0.01791% | 0.01791% | 0.01905% | 612776587.5 | 0% | 0% | 0% | 0 | 0.001344% | 0.00143% | 7.482% | 45998452.5 | 0.001344% | 0.00143% | 7.482% | 45998452 |  |  | -1.3444e-05
|  |  |  | Storm Water Drainage System | [21 empty] | 0
[5 empty] | a. Concrete ditch 50x50 | Concrete |  | 0.01513% | 0.01513% | 0.01609% | 517563007.5 | 0.002125% | 0.00226% | 14.03% | 72696854 | 0% | 0% |  | 0 | 0.002125% | 0.00226% | 14.03% | 72696854 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.02351% | 0.02351% | 0.02501% | 804490417.5 | 0.003902% | 0.00415% | 16.58% | 133492012 | 0% | 0% |  | 0 | 0.003902% | 0.00415% | 16.58% | 133492012 |  |  | 0
[5 empty] | b. Concrete ditch 80x70 | Concrete |  | 0.01055% | 0.01055% | 0.01122% | 360910935 | [14 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.01834% | 0.01834% | 0.01951% | 627573292.5 | [14 empty] | 0
[5 empty] | c. Box Culvert 80x80 | Concrete |  | 0.00091% | 0.000912% | 0.00097% | 31201747.5 | [14 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00115% | 0.001147% | 0.00122% | 39243435 | [14 empty] | 0
[5 empty] | d. Control Box 80x80 | Concrete |  | 0.00069% | 0.0006863% | 0.00073% | 23481727.5 | [14 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00087% | 0.0008743% | 0.00093% | 29915077.5 | [14 empty] | 0
[5 empty] | e. Control Box 100x100 | Concrete |  | 0.00328% | 0.003281% | 0.00349% | 112261957.5 | [14 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00313% | 0.003131% | 0.00333% | 107115277.5 | [14 empty] | 0
|  |  |  | Sewage Drainage system | [21 empty] | 0
[6 empty] | Concrete |  | 0.00363% | 0.003629% | 0.00386% | 124163655 | [14 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00568% | 0.005679% | 0.00604% | 194287170 | [14 empty] | 0
|  |  |  | Road & Pavement | [21 empty] | 0
[6 empty] | Concrete |  | 0.04196% | 0.04196% | 0.04463% | 1435602052.5 | 0.008076% | 0.00859% | 19.27% | 276312383 |  |  |  |  | 0.008076% | 0.00859% | 19.27% | 276312383 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.01256% | 0.01256% | 0.01336% | 429747780 | [14 empty] | 0
|  |  |  | Road Sign & Marking | [21 empty] | 0
[6 empty] | Concrete |  | 5e-05% | 4.701e-05% | 5e-05% | 1608337.5 | [14 empty] | 0
[6 empty] | Sign |  | 0.00015% | 0.0001504% | 0.00016% | 5146680 | [14 empty] | 0
|  |  |  | Road Lighting & Site Outdoor Lighting | [21 empty] | 0
[6 empty] | Concrete |  | 0.00172% | 0.00172% | 0.00183% | 58865152.5 | [14 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00217% | 0.002172% | 0.00231% | 74305192.5 | [14 empty] | 0
|  |  |  | Parking & Vehicle Shed | [21 empty] | 0
[6 empty] | Concrete |  | 0.02455% | 0.02455% | 0.02611% | 839873842.5 | [14 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00789% | 0.007888% | 0.00839% | 269879032.5 | [14 empty] | 0
|  |  |  | Toilets & Other Sanitary Facilities | [21 empty] | 0
[6 empty] | Concrete |  | 0.00101% | 0.001006% | 0.00107% | 34418422.5 | [14 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.0013% | 0.001297% | 0.00138% | 44390115 | [14 empty] | 0
|  |  |  | Retainning Wall | [21 empty] | 0
[6 empty] | Concrete |  | 0.03713% | 0.03713% | 0.03949% | 1270264957.5 | 0.03714% | 0.0395% | 100% | 1270586625 |  |  |  |  | 0.03714% | 0.0395% | 100% | 1270586625 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.08081% | 0.08081% | 0.08595% | 2764732162.5 | 0.0808% | 0.08594% | 100% | 2764410496 |  |  |  |  | 0.0808% | 0.08594% | 100% | 2764410496 |  |  | 0
|  |  |  | Grass Landscaping | [21 empty] | 0
[8 empty] | 0.01076% | 0.01076% | 0.01144% | 367987620 | [14 empty] | 0
|  |  |  | Trenches & Duct Support | [21 empty] | 0
[6 empty] | Concrete |  | 0.00086% | 0.0008555% | 0.00091% | 29271742.5 | [14 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00195% | 0.001946% | 0.00207% | 66585172.5 | [14 empty] | 0
[6 empty] | Compacted Sand |  | 0.02799% | 0.02799% | 0.02977% | 957604147.5 | [14 empty] | 0
0
0
|  | 3 | Structural Work | [22 empty] | 0
|  |  |  | System - 1 | [21 empty] | 0
|  |  |  | Electrical Room for Ore Dryer Area | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00466% | 0.004663% | 0.00496% | 159547080 | 0.003187% | 0.00339% | 68.24% | 109045282.5 | 0.0005641% | 0.0006% | 12% | 19300050 | 0.003751% | 0.00399% | 80.24% | 128345332.5 | 0.0002726% |  | -2.9145e-06
[6 empty] | Concrete |  | 0.00356% | 0.003563% | 0.00379% | 121911982.5 | 0.002426% | 0.00258% | 67.98% | 82990215 | 0.0003103% | 0.00033% | 8.788% | 10615027.5 | 0.002736% | 0.00291% | 76.77% | 93605242.5 |  |  | -3.1025e-06
|  |  |  | Electrical Room for Ore Mixing Area inside Ore Mixing and Briquetting Building |  |  |  |  | - | - | [15 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00392% | 0.00392% | 0.00417% | 134135347.5 | 0.001457% | 0.00155% | 37.22% | 49858462.5 | 0.001579% | 0.00168% | 40.19% | 54040140 | 0.003037% | 0.00323% | 77.41% | 103898602.5 | 0.001457% |  | -1.2222e-06
[6 empty] | Concrete |  | 0.00277% | 0.002773% | 0.00295% | 94891912.5 | 0.001344% | 0.00143% | 48.48% | 45998452.5 | 0.0007239% | 0.00077% | 26.26% | 24768397.5 | 0.002068% | 0.0022% | 74.75% | 70766850 |  |  | -7.2392e-06
|  |  |  | Electrical Room for Rotary Kiln Area and Coal Firing Area |  |  |  |  | - | - | [15 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00948% | 0.009477% | 0.01008% | 324240840 | 0.005406% | 0.00575% | 57.11% | 184958812.5 | 0.0009496% | 0.00101% | 10% | 32488417.5 | 0.006355% | 0.00676% | 67.11% | 217447230 | 0.002914% |  | 1.9649e-05
[6 empty] | Concrete |  | 0.00615% | 0.006149% | 0.00654% | 210370545 | 0.003441% | 0.00366% | 56.08% | 117730305 | 0.0005547% | 0.00059% | 8.997% | 18978382.5 | 0.003996% | 0.00425% | 65.08% | 136708687.5 |  |  | -5.5469e-06
|  |  |  | Raw Ore Storage | [21 empty] | 0
[6 empty] | Piles |  | 0.04681% | 0.04681% | 0.04979% | 1601582482.5 | 0.04681% | 0.04979% | 100% | 1601582483 |  |  |  |  | 0.04681% | 0.04979% | 100% | 1601582483 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.08051% | 0.08051% | 0.08563% | 2754438802.5 | 0.08028% | 0.08539% | 99.71% | 2746718783 | 0% | 0% |  | 0 | 0.08028% | 0.08539% | 99.71% | 2746718783 | 0.008123% |  | 8.123e-05
[6 empty] | Concrete |  | 0.0195% | 0.0195% | 0.02074% | 667138395 | 0.01939% | 0.02062% | 99.45% | 663278384.5 | 1.88e-05% | 2e-05% | 0.12% | 643335 | 0.0194% | 0.02064% | 99.57% | 663921719.5 | 0.002435% |  | 2.4162e-05
[6 empty] | Steel Structure & Roof Siding |  | 0.111% | 0.1111% | 0.1181% | 3799536510 |  |  |  |  | 0.007869% | 0.00837% | 7.083% | 269235697.5 | 0.007869% | 0.00837% | 7.083% | 269235697.5 |  |  | -7.8691e-05
|  |  |  | Ore Drying Equipment & Ore Sizing Equipment | [21 empty] | 0
[6 empty] | Piles |  | 0.02432% | 0.02432% | 0.02587% | 832153822.5 | 0.02432% | 0.02587% | 100% | 832153823 |  |  |  |  | 0.02432% | 0.02587% | 100% | 832153823 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.02136% | 0.02136% | 0.02272% | 730828560 | 0.02135% | 0.02271% | 100% | 730506892.5 |  |  |  |  | 0.02135% | 0.02271% | 100% | 730506892.5 | 9.402e-05% |  | 9.4016e-07
[6 empty] | Concrete |  | 0.00737% | 0.007371% | 0.00784% | 252187320 | 0.007371% | 0.00784% | 100% | 252187320 |  |  |  |  | 0.007371% | 0.00784% | 100% | 252187320 | 0.0004043% |  | 4.0427e-06
[6 empty] | Steel Structure & Roof Siding |  | 0.05592% | 0.05592% | 0.05948% | 1913278290 | [14 empty] | 0
|  |  |  | Conditioned Ore Storage | [21 empty] | 0
[6 empty] | Piles |  | 0.01194% | 0.01194% | 0.0127% | 408517725 | 0.01194% | 0.0127% | 100% | 408517725 |  |  |  |  | 0.01194% | 0.0127% | 100% | 408517725 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.02847% | 0.02847% | 0.03028% | 974009190 | 0.02847% | 0.03028% | 100% | 974009190 |  |  |  |  | 0.02847% | 0.03028% | 100% | 974009190 | 0.0004231% |  | 4.2307e-06
[6 empty] | Concrete |  | 0.0069% | 0.006901% | 0.00734% | 236103945 | 0.006901% | 0.00734% | 100% | 236103945 |  |  |  |  | 0.006901% | 0.00734% | 100% | 236103945 | 0.0001034% |  | 1.0342e-06
[6 empty] | Steel Structure & Roof Siding |  | 0.04669% | 0.04669% | 0.04966% | 1597400805 | 0.006543% | 0.00696% | 14.01% | 223880580 | 0% | 0% |  | 0 | 0.006543% | 0.00696% | 14.01% | 223880580 | 0.006543% |  | 6.5435e-05
|  |  |  | Ore Mixing Equipment & Dust Treatment Equipment | [21 empty] | 0
[6 empty] | Piles |  | 0.03001% | 0.03001% | 0.03192% | 1026762660 | 0.03001% | 0.03192% | 100% | 1026762660 |  |  |  |  | 0.03001% | 0.03192% | 100% | 1026762660 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.01354% | 0.01354% | 0.0144% | 463201200 | 0.01354% | 0.0144% | 100% | 463201201 | 0% | 0% |  | 0 | 0.01354% | 0.0144% | 100% | 463201201 | 0.0002444% |  | 2.4444e-06
[6 empty] | Concrete |  | 0.00357% | 0.003573% | 0.0038% | 122233650 | 0.003582% | 0.00381% | 100% | 122555317.5 | 0% | 0% |  | 0 | 0.003582% | 0.00381% | 100% | 122555317.5 | 7.521e-05% |  | 7.5213e-07
[6 empty] | Steel Structure & Roof Siding |  | 0.08547% | 0.08547% | 0.09091% | 2924279242.5 | [14 empty] | 0
|  |  |  | Rotary Kiln & Exhaust Gas Treatment Equipment | [21 empty] | 0
[6 empty] | Piles |  | 0.06945% | 0.06945% | 0.07387% | 2376157822.5 | 0.06945% | 0.07387% | 100% | 2376157822.5 |  |  |  |  | 0.06945% | 0.07387% | 100% | 2376157822.5 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.07166% | 0.07166% | 0.07622% | 2451749685 | 0.07079% | 0.0753% | 98.79% | 2422156275 | 0% | 0% |  | 0 | 0.07079% | 0.0753% | 98.79% | 2422156275 |  |  | 0
[6 empty] | Concrete |  | 0.02473% | 0.02473% | 0.0263% | 845985525 | 0.02454% | 0.0261% | 99.27% | 839552175 | 0% | 0% |  | 0 | 0.02454% | 0.0261% | 99.27% | 839552175 |  |  | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.1762% | 0.1762% | 0.1874% | 6027083947.5 | [14 empty] | 0
|  |  |  | Coal Firing Equipment | [21 empty] | 0
[6 empty] | Piles |  | 0.02173% | 0.02173% | 0.02311% | 743373592.5 | 0.02173% | 0.02311% | 100% | 743373592.5 |  |  |  |  | 0.02173% | 0.02311% | 100% | 743373592.5 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.01128% | 0.01128% | 0.012% | 386001000 | 0.01127% | 0.01199% | 100% | 385679332.5 |  |  |  |  | 0.01127% | 0.01199% | 100% | 385679332.5 | 0.0007427% |  | 7.4272e-06
[6 empty] | Concrete |  | 0.00297% | 0.002971% | 0.00316% | 101646930 | 0.00298% | 0.00317% | 100% | 101968597.5 |  |  |  |  | 0.00298% | 0.00317% | 100% | 101968597.5 | 0.0002444% |  | 2.4444e-06
[6 empty] | Steel Structure & Roof Siding |  | 0.04148% | 0.04148% | 0.04412% | 1419197010 | [14 empty] | 0
|  |  |  | Fuel Coal Storage | [21 empty] | 0
[6 empty] | Piles |  | 0.06004% | 0.06004% | 0.06386% | 2054168655 | 0.06004% | 0.06386% | 100% | 2054168655 |  |  |  |  | 0.06004% | 0.06386% | 100% | 2054168655 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.01846% | 0.01846% | 0.01964% | 631754970 | 0.01846% | 0.01964% | 100% | 631754970 |  |  |  |  | 0.01846% | 0.01964% | 100% | 631754970 |  |  | 0
[6 empty] | Concrete |  | 0.0044% | 0.0044% | 0.00468% | 150540390 | 0.004391% | 0.00467% | 100% | 150218722.5 |  |  |  |  | 0.004391% | 0.00467% | 100% | 150218722.5 |  |  | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.04484% | 0.04484% | 0.04769% | 1534032307.5 | 0.01253% | 0.01333% | 27.94% | 428782779 | 0.001401% | 0.00149% | 3.128% | 47928457.5 | 0.01393% | 0.01482% | 31.07% | 476711237 | 0.002473% |  | 1.0718e-05
|  |  |  | Reductant Coal Storage | [21 empty] | 0
[6 empty] | Piles | [19 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.01816% | 0.01816% | 0.01932% | 621461610 | 0.01817% | 0.01933% | 100% | 621783277.5 | 0% | 0% |  | 0 | 0.01817% | 0.01933% | 100% | 621783277.5 |  |  | 0
[6 empty] | Concrete |  | 0.0044% | 0.0044% | 0.00468% | 150540390 | 0.0044% | 0.00468% | 100% | 150540390 | 0% | 0% |  | 0 | 0.0044% | 0.00468% | 100% | 150540390 |  |  | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.04728% | 0.04728% | 0.05029% | 1617665857.5 | 0.0271% | 0.02883% | 57.33% | 927367404 | 0.005895% | 0.00627% | 12.46% | 201685522.5 | 0.033% | 0.0351% | 69.79% | 1129052927 | 0.006064% |  | 1.6923e-06
|  |  |  | Belt Conveyor / Transfer Towe, Girder & Support. | [21 empty] | 0
[6 empty] | Piles |  | 0.03582% | 0.03582% | 0.0381% | 1225553175 | 0.03582% | 0.0381% | 100% | 1225553175 |  |  |  |  | 0.03582% | 0.0381% | 100% | 1225553175 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.01816% | 0.01816% | 0.01932% | 621461610 | 0.01796% | 0.0191% | 98.91% | 614384925 | 0.0001974% | 0.00021% | 1.085% | 6755017.5 | 0.01815% | 0.01931% | 100% | 621139942.5 | 0.0005923% |  | 3.9487e-06
[6 empty] | Concrete |  | 0.00478% | 0.004776% | 0.00508% | 163407090 | 0.00472% | 0.00502% | 98.75% | 161477085 | 3.761e-05% | 4e-05% | 0.74% | 1286670 | 0.004757% | 0.00506% | 99.49% | 162763755 | 0.0002632% |  | 2.2564e-06
[6 empty] | Steel Structure & Roof Siding |  | 0.1146% | 0.1146% | 0.1218% | 3919518487.5 | [14 empty] | 0
0
|  |  |  | System - 2 | [21 empty] | 0
|  |  |  | ESF Building | [21 empty] | 0
[6 empty] | Piles |  | 0.1057% | 0.1057% | 0.1124% | 3615221032.5 | 0.1057% | 0.1124% | 100% | 3615221032.5 |  |  |  |  | 0.1057% | 0.1124% | 100% | 3615221032.5 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.05178% | 0.05178% | 0.05508% | 1771744590 | 0.03184% | 0.03387% | 61.5% | 1089487822.5 | 0% | 0% |  | 0 | 0.03184% | 0.03387% | 61.5% | 1089487822.5 | 0.01029% |  | 0.00010295
[6 empty] | Concrete |  | 0.01725% | 0.01725% | 0.01835% | 590259862.5 | 0.009223% | 0.00981% | 53.42% | 315555817.5 | 0.0004043% | 0.00043% | 2.36% | 13831702.5 | 0.009627% | 0.01024% | 55.78% | 329387520 | 0.002341% |  | 1.9367e-05
[6 empty] | Steel Structure & Roof Siding |  | 0.2767% | 0.2767% | 0.2943% | 9466996192.5 | 0.01422% | 0.01512% | 5.138% | 486361260 | 0.001232% | 0.00131% | 0.4459% | 42138442.5 | 0.01545% | 0.01643% | 5.584% | 528499702.5 | 0.01422% |  | 0.00012984
|  |  |  | ESF Equipments Support & Foundation : | [21 empty] | 0
[5 empty] | a. Furnace Foundation | Piles |  | 0.02849% | 0.02849% | 0.0303% | 974652525 | 0.02849% | 0.0303% | 100% | 974652525 |  |  |  |  | 0.02849% | 0.0303% | 100% | 974652525 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.00443% | 0.004428% | 0.00471% | 151505392.5 | 0.004438% | 0.00472% | 100% | 151827060 | 0% | 0% |  | 0 | 0.004438% | 0.00472% | 100% | 151827060 |  |  | 0
[6 empty] | Concrete |  | 0.00245% | 0.002454% | 0.00261% | 83955217.5 | 0.002444% | 0.0026% | 100% | 83633550 | 0% | 0% |  | 0 | 0.002444% | 0.0026% | 100% | 83633550 |  |  | 0
[5 empty] | b. Tapping Deck Structure & Foundation | Reinforcement Bar |  | 0.00079% | 0.0007897% | 0.00084% | 27020070 | 0.0007427% | 0.00079% | 93.82% | 25411732.5 | 0% | 0% |  | 0 | 0.0007427% | 0.00079% | 93.82% | 25411732.5 |  |  | 0
[6 empty] | Concrete |  | 0.0002% | 0.0001974% | 0.00021% | 6755017.5 | 0.0001786% | 0.00019% | 89.45% | 6111682.5 | 0% | 0% |  | 0 | 0.0001786% | 0.00019% | 89.45% | 6111682.5 |  |  | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.0168% | 0.0168% | 0.01787% | 574819822.5 | [14 empty] | 0
[5 empty] | c. Furnace Fan Foundation | Reinforcement Bar |  | 0.00033% | 0.0003291% | 0.00035% | 11258362.5 | [14 empty] | 0
[6 empty] | Concrete |  | 0.00017% | 0.0001692% | 0.00018% | 5790015 | [14 empty] | 0
[5 empty] | d. Spray Chamber Support Foundation | Piles |  | 0.00121% | 0.001213% | 0.00129% | 41495107.5 | 0.001213% | 0.00129% | 100% | 41495107.5 |  |  |  |  | 0.001213% | 0.00129% | 100% | 41495107.5 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.0002% | 0.0001974% | 0.00021% | 6755017.5 | [14 empty] | 0
[6 empty] | Concrete |  | 8e-05% | 8.461e-05% | 9e-05% | 2895007.5 | [14 empty] | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.00084% | 0.0008367% | 0.00089% | 28628407.5 | [14 empty] | 0
[5 empty] | e. Bag House Inlet Duct Support Foundation | Reinforcement Bar |  | 0.00012% | 0.0001222% | 0.00013% | 4181677.5 | [14 empty] | 0
[6 empty] | Concrete |  | 3e-05% | 2.82e-05% | 3e-05% | 965002.5 | [14 empty] | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.00123% | 0.001232% | 0.00131% | 42138442.5 | [14 empty] | 0
[5 empty] | f. Bag House Foundation | Piles |  | 0.01% | 0.01% | 0.01064% | 342254220 | 0.01% | 0.01064% | 100% | 342254220 | 0% | 0% |  | 0 | 0.01% | 0.01064% | 100% | 342254220 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.00469% | 0.004691% | 0.00499% | 160512082.5 | 0.004691% | 0.00499% | 100% | 160512082.5 | 0% | 0% |  | 0 | 0.004691% | 0.00499% | 100% | 160512082.5 |  |  | 0
[6 empty] | Concrete |  | 0.00251% | 0.00251% | 0.00267% | 85885222.5 | 0.00251% | 0.00267% | 100% | 85885222.5 | 0% | 0% |  | 0 | 0.00251% | 0.00267% | 100% | 85885222.5 |  |  | 0
[5 empty] | g. Blowpots Foundation | Reinforcement Bar |  | 5e-05% | 4.701e-05% | 5e-05% | 1608337.5 | [14 empty] | 0
[6 empty] | Concrete |  | 2e-05% | 1.88e-05% | 2e-05% | 643335 | [14 empty] | 0
[5 empty] | h. Bag House Fan Foundation | Reinforcement Bar |  | 0.00023% | 0.0002256% | 0.00024% | 7720020 | 8.461e-05% | 9e-05% | 38.5% | 2895007.5 | 0% | 0% |  | 0 | 8.461e-05% | 9e-05% | 38.5% | 2895007.5 | 8.461e-05% |  | 8.4614e-07
[6 empty] | Concrete |  | 0.0001% | 0.0001034% | 0.00011% | 3538342.5 | 3.761e-05% | 4e-05% | 33.19% | 1286670 | 0% | 0% |  | 0 | 3.761e-05% | 4e-05% | 33.19% | 1286670 | 3.761e-05% |  | 3.7606e-07
[5 empty] | i. Bag House Outlet Duct Support Foundation | Reinforcement Bar |  | 0.00021% | 0.0002068% | 0.00022% | 7076685 | [14 empty] | 0
[6 empty] | Concrete |  | 7e-05% | 6.581e-05% | 7e-05% | 2251672.5 | [14 empty] | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.00156% | 0.001561% | 0.00166% | 53396805 | [14 empty] | 0
[5 empty] | j. Bag House Stack Foundation | Piles |  | 0.00121% | 0.001213% | 0.00129% | 41495107.5 | 0.001213% | 0.00129% | 100% | 41495107.5 | 0% | 0% |  | 0 | 0.001213% | 0.00129% | 100% | 41495107.5 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.0006% | 0.0006017% | 0.00064% | 20586720 | [14 empty] | 0
[6 empty] | Concrete |  | 0.00023% | 0.0002256% | 0.00024% | 7720020 | 9.402e-06% | 1e-05% | 4.878% | 321667.5 | 0% | 0% |  | 0 | 9.402e-06% | 1e-05% | 4.878% | 321667.5 |  |  | 0
|  |  |  | Main Substaion Building | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00471% | 0.00471% | 0.00501% | 161155417.5 | 0.004297% | 0.00457% | 91.3% | 147002047.5 | 0.000188% | 0.0002% | 4% | 6433350 | 0.004485% | 0.00477% | 95.3% | 153435397.5 | 0.0007427% |  | 5.5469e-06
[6 empty] | Concrete |  | 0.0032% | 0.003197% | 0.0034% | 109366950 | 0.002604% | 0.00277% | 81.79% | 89101897.5 | 6.581e-05% | 7e-05% | 2.08% | 2251672.5 | 0.00267% | 0.00284% | 83.87% | 91353570 | 0.000282% |  | 2.1624e-06
|  |  |  | Electrical Room for ESF Area | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00025% | 0.0002538% | 0.00027% | 8685022.5 | [14 empty] | 0
[6 empty] | Concrete |  | 0.00056% | 0.0005641% | 0.0006% | 19300050 | [14 empty] | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.00395% | 0.003949% | 0.0042% | 135100350 | [14 empty] | 0
|  |  |  | Center Control Room at ESF Building | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00035% | 0.0003479% | 0.00037% | 11901697.5 | [14 empty] | 0
[6 empty] | Concrete |  | 0.00082% | 0.0008179% | 0.00087% | 27985072.5 | [14 empty] | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.00632% | 0.006318% | 0.00672% | 216160560 | [14 empty] | 0
|  |  |  | Crane Control Room at ESF Building | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00011% | 0.0001128% | 0.00012% | 3860010 | [14 empty] | 0
[6 empty] | Concrete |  | 0.00029% | 0.0002914% | 0.00031% | 9971692.5 | [14 empty] | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.00218% | 0.002181% | 0.00232% | 74626860 | [14 empty] | 0
|  |  |  | Emergency Pit | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00027% | 0.0002726% | 0.00029% | 9328357.5 | [14 empty] | 0
[6 empty] | Concrete |  | 4e-05% | 3.761e-05% | 4e-05% | 1286670 | [14 empty] | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.00074% | 0.0007427% | 0.00079% | 25411732.5 | [14 empty] | 0
0
|  |  |  | System - 3 | [21 empty] | 0
|  |  |  | Refining Shot Making Building | [21 empty] | 0
[6 empty] | Piles |  | 0.00242% | 0.002416% | 0.00257% | 82668547.5 | 0.002416% | 0.00257% | 100% | 82668547.5 |  |  |  |  | 0.002416% | 0.00257% | 100% | 82668547.5 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.00164% | 0.001636% | 0.00174% | 55970145 | 0.001279% | 0.00136% | 78.42% | 43746780 | 0% | 0% |  | 0 | 0.001279% | 0.00136% | 78.42% | 43746780 | 1.88e-05% |  | 1.8803e-07
[6 empty] | Concrete |  | 0.0007% | 0.0006957% | 0.00074% | 23803395 | 0.0005077% | 0.00054% | 72.97% | 17370045 | 0% | 0% |  | 0 | 0.0005077% | 0.00054% | 72.97% | 17370045 | 7.521e-05% |  | 7.5213e-07
[6 empty] | Steel Structure & Roof Siding |  | 0.00953% | 0.009533% | 0.01014% | 326170845 | [14 empty] | 0
|  |  |  | Shot Making Equipment Support & Foundation | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00244% | 0.002444% | 0.0026% | 83633550 | 0.002444% | 0.0026% | 100% | 83633550 | 0% | 0% |  | 0 | 0.002444% | 0.0026% | 100% | 83633550 |  |  | 0
[6 empty] | Concrete |  | 0.00092% | 0.0009214% | 0.00098% | 31523415 | 0.0009214% | 0.00098% | 100% | 31523415 | 0% | 0% |  | 0 | 0.0009214% | 0.00098% | 100% | 31523415 |  |  | 0
|  |  |  | Desulphurizing Equipment Support & Foundation | [21 empty] | 0
[6 empty] | Piles |  | 0.01211% | 0.01211% | 0.01288% | 414307740 | 0.01211% | 0.01288% | 100% | 414307740 |  |  |  |  | 0.01211% | 0.01288% | 100% | 414307740 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.00042% | 0.0004231% | 0.00045% | 14475037.5 | 0.0003197% | 0.00034% | 76.92% | 10936695 | 0% | 0% |  | 0 | 0.0003197% | 0.00034% | 76.92% | 10936695 | 2.82e-05% |  | 2.8205e-07
[6 empty] | Concrete |  | 0.00019% | 0.000188% | 0.0002% | 6433350 | 0.0001504% | 0.00016% | 76.87% | 5146680 | 0% | 0% |  | 0 | 0.0001504% | 0.00016% | 76.87% | 5146680 | 9.402e-06% |  | 9.4016e-08
|  |  |  | Product Storage Building & Handling Crane | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00704% | 0.007042% | 0.00749% | 240928957.5 | 0.005528% | 0.00588% | 78.45% | 189140490 | 0% | 0% |  | 0 | 0.005528% | 0.00588% | 78.45% | 189140490 |  |  | 0
[6 empty] | Concrete |  | 0.00267% | 0.00267% | 0.00284% | 91353570 | 0.001561% | 0.00166% | 58.28% | 53396805 | 0% | 0% |  | 0 | 0.001561% | 0.00166% | 58.28% | 53396805 |  |  | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.03642% | 0.03642% | 0.03874% | 1246139895 | [14 empty] | 0
|  |  |  | Electrical Room for Shot Making Area | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00233% | 0.002332% | 0.00248% | 79773540 | 0.001702% | 0.00181% | 73.09% | 58221817.5 | 0% | 0% |  | 0 | 0.001702% | 0.00181% | 73.09% | 58221817.5 |  |  | 0
[6 empty] | Concrete |  | 0.00227% | 0.002266% | 0.00241% | 77521867.5 | 0.001589% | 0.00169% | 70.04% | 54361807.5 | 0% | 0% |  | 0 | 0.001589% | 0.00169% | 70.04% | 54361807.5 | 8.461e-05% |  | 8.4614e-07
|  |  |  | Control Room for Shot Making | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00013% | 0.0001316% | 0.00014% | 4503345 | [14 empty] | 0
[6 empty] | Concrete |  | 4e-05% | 3.761e-05% | 4e-05% | 1286670 | [14 empty] | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.00167% | 0.001673% | 0.00178% | 57256815 | [14 empty] | 0
|  |  |  | Ladle Preheating Equipment Foundation | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 6e-05% | 5.641e-05% | 6e-05% | 1930005 | 5.641e-05% | 6e-05% | 100% | 1930005 | 0% | 0% |  | 0 | 5.641e-05% | 6e-05% | 100% | 1930005 |  |  | 0
[6 empty] | Concrete |  | 3e-05% | 2.82e-05% | 3e-05% | 965002.5 | 2.82e-05% | 3e-05% | 100% | 965002.5 | 0% | 0% |  | 0 | 2.82e-05% | 3e-05% | 100% | 965002.5 |  |  | 0
|  |  |  | Ladle Foundation | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00013% | 0.0001316% | 0.00014% | 4503345 | 0.0001316% | 0.00014% | 100% | 4503345 | 0% | 0% |  | 0 | 0.0001316% | 0.00014% | 100% | 4503345 |  |  | 0
[6 empty] | Concrete |  | 9e-05% | 9.402e-05% | 0.0001% | 3216675 | 9.402e-05% | 0.0001% | 100% | 3216675 | 0% | 0% |  | 0 | 9.402e-05% | 0.0001% | 100% | 3216675 |  |  | 0
|  |  |  | Turbo Blower Foundation | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 2e-05% | 1.88e-05% | 2e-05% | 643335 | [14 empty] | 0
[6 empty] | Concrete |  | 1e-05% | 9.402e-06% | 1e-05% | 321667.5 | [14 empty] | 0
|  |  |  | Oil Tank Foundation | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 1e-05% | 9.402e-06% | 1e-05% | 321667.5 | [14 empty] | 0
[6 empty] | Concrete |  | 1e-05% | 9.402e-06% | 1e-05% | 321667.5 | [14 empty] | 0
|  |  |  | Pump Unit Foundation | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 3e-05% | 2.82e-05% | 3e-05% | 965002.5 | 2.82e-05% | 3e-05% | 100% | 965002.5 |  |  |  |  | 2.82e-05% | 3e-05% | 100% | 965002.5 | 2.82e-05% |  | 2.8205e-07
[6 empty] | Concrete |  | 2e-05% | 1.88e-05% | 2e-05% | 643335 | 1.88e-05% | 2e-05% | 100% | 643335 |  |  |  |  | 1.88e-05% | 2e-05% | 100% | 643335 | 1.88e-05% |  | 1.8803e-07
|  |  |  | Maintenance Deck for Ladle Preheating | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00019% | 0.000188% | 0.0002% | 6433350 | 0.000188% | 0.0002% | 100% | 6433350 |  |  |  |  | 0.000188% | 0.0002% | 100% | 6433350 |  |  | 0
[6 empty] | Concrete |  | 5e-05% | 4.701e-05% | 5e-05% | 1608337.5 | 4.701e-05% | 5e-05% | 100% | 1608337.5 |  |  |  |  | 4.701e-05% | 5e-05% | 100% | 1608337.5 |  |  | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.00079% | 0.0007897% | 0.00084% | 27020070 | [14 empty] | 0
0
|  |  |  | System - 4 | [21 empty] | 0
|  |  |  | Emergency Generator Room | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00458% | 0.004579% | 0.00487% | 156652072.5 | 0.003356% | 0.00357% | 73.33% | 114835297.5 | 0% | 0% |  | 0 | 0.003356% | 0.00357% | 73.33% | 114835297.5 | 0.001081% |  | 1.0812e-05
[6 empty] | Concrete |  | 0.00216% | 0.002162% | 0.0023% | 73983525 | 0.001363% | 0.00145% | 63.11% | 46641787.5 | 0% | 0% |  | 0 | 0.001363% | 0.00145% | 63.11% | 46641787.5 | 0.0004231% |  | 4.2307e-06
|  |  |  | Oxygen Plant Building | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00062% | 0.0006205% | 0.00066% | 21230055 | [14 empty] | 0
[6 empty] | Concrete |  | 0.00028% | 0.000282% | 0.0003% | 9650025 | [14 empty] | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.00281% | 0.002811% | 0.00299% | 96178582.5 | [14 empty] | 0
|  |  |  | Oxygen Plant Equipments Support & Foundation | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00021% | 0.0002068% | 0.00022% | 7076685 | [14 empty] | 0
[6 empty] | Concrete |  | 0.00017% | 0.0001692% | 0.00018% | 5790015 | [14 empty] | 0
|  |  |  | Compressor Room | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00437% | 0.004372% | 0.00465% | 149575387.5 | 0.002303% | 0.00245% | 52.78% | 78808537.5 | 0% | 0% |  | 0 | 0.002303% | 0.00245% | 52.78% | 78808537.5 | 0.0002632% |  | 2.6324e-06
[6 empty] | Concrete |  | 0.00443% | 0.004428% | 0.00471% | 151505392.5 | 0.002068% | 0.0022% | 46.53% | 70766850 | 0% | 0% |  | 0 | 0.002068% | 0.0022% | 46.53% | 70766850 | 0.0003103% |  | 3.1025e-06
|  |  |  | Electrical Room for Utility | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00157% | 0.00157% | 0.00167% | 53718472.5 | 0.0007239% | 0.00077% | 46.36% | 24768397.5 | 4.701e-05% | 5e-05% | 3% | 1608337.5 | 0.0007709% | 0.00082% | 49.36% | 26376735 | 0.0001034% |  | 5.6409e-07
[6 empty] | Concrete |  | 0.00146% | 0.001457% | 0.00155% | 49858462.5 | 0.0006581% | 0.0007% | 44.83% | 22516725 | 4.701e-05% | 5e-05% | 3.16% | 1608337.5 | 0.0007051% | 0.00075% | 47.99% | 24125062.5 | 0.0001316% |  | 8.4614e-07
|  |  |  | Pump Room for Water Intake (Wayanof river) | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00045% | 0.0004513% | 0.00048% | 15440040 | [14 empty] | 0
[6 empty] | Concrete |  | 0.00016% | 0.0001598% | 0.00017% | 5468347.5 | [14 empty] | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.00108% | 0.001081% | 0.00115% | 36991762.5 | [14 empty] | 0
|  |  |  | Pump Room for Water Intake (sea) | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.0008% | 0.0007991% | 0.00085% | 27341737.5 | [14 empty] | 0
[6 empty] | Concrete |  | 0.00033% | 0.0003291% | 0.00035% | 11258362.5 | [14 empty] | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.00232% | 0.002322% | 0.00247% | 79451872.5 | [14 empty] | 0
|  |  |  | Pump Room for MFO/HSD transfer | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00036% | 0.0003573% | 0.00038% | 12223365 | [14 empty] | 0
[6 empty] | Concrete |  | 0.00016% | 0.0001598% | 0.00017% | 5468347.5 | [14 empty] | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.00097% | 0.0009684% | 0.00103% | 33131752.5 | [14 empty] | 0
|  |  |  | Cable Rack Structure | [21 empty] | 0
[6 empty] | Piles |  | 0.05431% | 0.05431% | 0.05777% | 1858273147.5 | 0.05431% | 0.05777% | 100% | 1858273147.5 |  |  |  |  | 0.05431% | 0.05777% | 100% | 1858273147.5 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.0061% | 0.006102% | 0.00649% | 208762207.5 | 0.004588% | 0.00488% | 75.12% | 156973740 | 0.0003009% | 0.00032% | 5% | 10293360 | 0.004889% | 0.0052% | 80.12% | 167267100 | 0.0005453% |  | 2.4444e-06
[6 empty] | Concrete |  | 0.00148% | 0.001476% | 0.00157% | 50501797.5 | 0.0011% | 0.00117% | 74.48% | 37635097.5 | 3.761e-05% | 4e-05% | 2.61% | 1286670 | 0.001138% | 0.00121% | 77.09% | 38921767.5 | 0.0002256% |  | 1.8803e-06
[6 empty] | Steel Structure & Roof Siding |  | 0.04823% | 0.04823% | 0.0513% | 1650154275 | [14 empty] | 0
|  |  |  | Water Treatment Equipments Support & Foundation | [21 empty] | 0
[5 empty] | a. Clarifier & Tank Foundation | Piles |  | 0.00561% | 0.005613% | 0.00597% | 192035497.5 | 0.005613% | 0.00597% | 100% | 192035497.5 |  |  |  |  | 0.005613% | 0.00597% | 100% | 192035497.5 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.00144% | 0.001438% | 0.00153% | 49215127.5 | 0.001438% | 0.00153% | 100% | 49215127.5 |  |  |  |  | 0.001438% | 0.00153% | 100% | 49215127.5 |  |  | 0
[6 empty] | Concrete |  | 0.00021% | 0.0002068% | 0.00022% | 7076685 | 0.0002068% | 0.00022% | 100% | 7076685 |  |  |  |  | 0.0002068% | 0.00022% | 100% | 7076685 |  |  | 0
[5 empty] | b. Pump Room (Str. & Fdn.) | Reinforcement Bar |  | 0.00036% | 0.0003573% | 0.00038% | 12223365 | [14 empty] | 0
[6 empty] | Concrete |  | 0.00016% | 0.0001598% | 0.00017% | 5468347.5 | [14 empty] | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.00097% | 0.0009684% | 0.00103% | 33131752.5 | [14 empty] | 0
[5 empty] | c. Warehouse for Chemical | Reinforcement Bar |  | 0.00109% | 0.001091% | 0.00116% | 37313430 | 0.001062% | 0.00113% | 97.54% | 36348427.5 | 0% | 0% |  | 0 | 0.001062% | 0.00113% | 97.54% | 36348427.5 |  |  | 0
[6 empty] | Concrete |  | 0.00033% | 0.0003291% | 0.00035% | 11258362.5 | 0.0003103% | 0.00033% | 94.74% | 10615027.5 | 0% | 0% |  | 0 | 0.0003103% | 0.00033% | 94.74% | 10615027.5 |  |  | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.00154% | 0.001542% | 0.00164% | 52753470 | [14 empty] | 0
[5 empty] | d. Operator Room (Str. & Fdn.) | Reinforcement Bar |  | 0.00033% | 0.0003291% | 0.00035% | 11258362.5 | 0.0003291% | 0.00035% | 97.54% | 11258362.5 | 0% | 0% |  | 0 | 0.0003291% | 0.00035% | 97.54% | 11258362.5 |  |  | 0
[6 empty] | Concrete |  | 0.00016% | 0.0001598% | 0.00017% | 5468347.5 | 0.000141% | 0.00015% | 94.74% | 4825012.5 | 0% | 0% |  | 0 | 0.000141% | 0.00015% | 94.74% | 4825012.5 |  |  | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.00078% | 0.0007803% | 0.00083% | 26698402.5 | [14 empty] | 0
[5 empty] | e. Piping Support (Str. & Fdn.) | Reinforcement Bar |  | 0.00117% | 0.001166% | 0.00124% | 39886770 | [14 empty] | 0
[6 empty] | Concrete |  | 0.0001% | 0.0001034% | 0.00011% | 3538342.5 | [14 empty] | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.00471% | 0.00471% | 0.00501% | 161155417.5 | [14 empty] | 0
[5 empty] | f. WTP Shelter (Str. & Fdn.) | Reinforcement Bar |  | 0.00205% | 0.00205% | 0.00218% | 70123515 | [14 empty] | 0
[6 empty] | Concrete |  | 0.00062% | 0.0006205% | 0.00066% | 21230055 | [14 empty] | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.00347% | 0.003469% | 0.00369% | 118695307.5 | [14 empty] | 0
[5 empty] | g. Softener Foundation | Reinforcement Bar |  | 0.00169% | 0.001692% | 0.0018% | 57900150 | 0.001692% | 0.0018% | 100% | 57900150 |  |  |  |  | 0.001692% | 0.0018% | 100% | 57900150 |  |  | 0
[6 empty] | Concrete |  | 0.00033% | 0.0003291% | 0.00035% | 11258362.5 | 0.0003291% | 0.00035% | 100% | 11258362.5 |  |  |  |  | 0.0003291% | 0.00035% | 100% | 11258362.5 |  |  | 0
[5 empty] | h. Sand Filter Foundation | Reinforcement Bar |  | 0.00169% | 0.001692% | 0.0018% | 57900150 | 0.001692% | 0.0018% | 100% | 57900150 |  |  |  |  | 0.001692% | 0.0018% | 100% | 57900150 |  |  | 0
[6 empty] | Concrete |  | 0.00033% | 0.0003291% | 0.00035% | 11258362.5 | 0.0003291% | 0.00035% | 100% | 11258362.5 |  |  |  |  | 0.0003291% | 0.00035% | 100% | 11258362.5 |  |  | 0
[5 empty] | i. NaCL Tank Foundation | Reinforcement Bar |  | 0.00065% | 0.0006487% | 0.00069% | 22195057.5 | 0.0006487% | 0.00069% | 100% | 22195057.5 |  |  |  |  | 0.0006487% | 0.00069% | 100% | 22195057.5 |  |  | 0
[6 empty] | Concrete |  | 0.00012% | 0.0001222% | 0.00013% | 4181677.5 | 0.0001222% | 0.00013% | 100% | 4181677.5 |  |  |  |  | 0.0001222% | 0.00013% | 100% | 4181677.5 |  |  | 0
|  |  |  | Intake Water Pond (Wayanof River) | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00065% | 0.0006487% | 0.00069% | 22195057.5 | 0.0006487% | 0.00069% | 100% | 22195057.5 | 0% | 0% |  | 0 | 0.0006487% | 0.00069% | 100% | 22195057.5 |  |  | 0
[6 empty] | Concrete |  | 0.00032% | 0.0003197% | 0.00034% | 10936695 | 0.0003103% | 0.00033% | 100% | 10615027.5 | 0% | 0% |  | 0 | 0.0003103% | 0.00033% | 100% | 10615027.5 |  |  | 0
|  |  |  | Receiving Water Pond | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00085% | 0.0008461% | 0.0009% | 28950075 | 0.0008461% | 0.0009% | 100% | 28950075 | 0% | 0% |  | 0 | 0.0008461% | 0.0009% | 100% | 28950075 | 7.521e-05% |  | 7.5213e-07
[6 empty] | Concrete |  | 0.00038% | 0.0003761% | 0.0004% | 12866700 | 0.0003667% | 0.00039% | 100% | 12545032.5 | 0% | 0% |  | 0 | 0.0003667% | 0.00039% | 100% | 12545032.5 | 4.701e-05% |  | 4.7008e-07
|  |  |  | Filtered Water Pond | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00085% | 0.0008461% | 0.0009% | 28950075 | 0.0008461% | 0.0009% | 100% | 28950075 | 0% | 0% |  | 0 | 0.0008461% | 0.0009% | 100% | 28950075 | 7.521e-05% |  | 7.5213e-07
[6 empty] | Concrete |  | 0.00038% | 0.0003761% | 0.0004% | 12866700 | 0.0003667% | 0.00039% | 100% | 12545032.5 | 0% | 0% |  | 0 | 0.0003667% | 0.00039% | 100% | 12545032.5 | 4.701e-05% |  | 4.7008e-07
|  |  |  | Circulation Water Pond Non Softened Water | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00238% | 0.002379% | 0.00253% | 81381877.5 | 0.002369% | 0.00252% | 100% | 81060210 | 0% | 0% |  | 0 | 0.002369% | 0.00252% | 100% | 81060210 | 0.0001316% |  | 1.3162e-06
[6 empty] | Concrete |  | 0.00096% | 0.000959% | 0.00102% | 32810085 | 0.000959% | 0.00102% | 100% | 32810085 | 0% | 0% |  | 0 | 0.000959% | 0.00102% | 100% | 32810085 | 0.0001316% |  | 1.3162e-06
|  |  |  | Circulation Water Pond Softened Water | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.0027% | 0.002698% | 0.00287% | 92318572.5 | 0.002698% | 0.00287% | 100% | 92318572.5 | 0% | 0% |  | 0 | 0.002698% | 0.00287% | 100% | 92318572.5 | 4.701e-05% |  | 4.7008e-07
[6 empty] | Concrete |  | 0.00108% | 0.001081% | 0.00115% | 36991762.5 | 0.001081% | 0.00115% | 100% | 36991762.5 | 0% | 0% |  | 0 | 0.001081% | 0.00115% | 100% | 36991762.5 | 0.0001316% |  | 1.3162e-06
|  |  |  | Circulation Water Pond for Coper Cooler | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00355% | 0.003554% | 0.00378% | 121590315 | 0.003544% | 0.00377% | 100% | 121268647.5 | 0% | 0% |  | 0 | 0.003544% | 0.00377% | 100% | 121268647.5 | 8.461e-05% |  | 8.4614e-07
[6 empty] | Concrete |  | 0.00134% | 0.001344% | 0.00143% | 45998452.5 | 0.001344% | 0.00143% | 100% | 45998452.5 | 0% | 0% |  | 0 | 0.001344% | 0.00143% | 100% | 45998452.5 | 0.0001504% |  | 1.5043e-06
|  |  |  | Non Softened Water Return Water Pond | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00187% | 0.001871% | 0.00199% | 64011832.5 | 0.00188% | 0.002% | 100% | 64333500 | 0% | 0% |  | 0 | 0.00188% | 0.002% | 100% | 64333500 | 8.461e-05% |  | 8.4614e-07
[6 empty] | Concrete |  | 0.00074% | 0.0007427% | 0.00079% | 25411732.5 | 0.0007427% | 0.00079% | 100% | 25411733 | 0% | 0% |  | 0 | 0.0007427% | 0.00079% | 100% | 25411733 | 9.402e-05% |  | 9.4016e-07
|  |  |  | Softened Water Return Water Pond | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00207% | 0.002068% | 0.0022% | 70766850 | 0.002068% | 0.0022% | 100% | 70766850 | 0% | 0% |  | 0 | 0.002068% | 0.0022% | 100% | 70766850 | 4.701e-05% |  | 4.7008e-07
[6 empty] | Concrete |  | 0.00081% | 0.0008085% | 0.00086% | 27663405 | 0.0008179% | 0.00087% | 100% | 27985072.5 | 0% | 0% |  | 0 | 0.0008179% | 0.00087% | 100% | 27985072.5 | 9.402e-05% |  | 9.4016e-07
|  |  |  | Softened Water for Cooper Cooler Return Pond | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.0021% | 0.002097% | 0.00223% | 71731852.5 | 0.002106% | 0.00224% | 100% | 72053520 | 0% | 0% |  | 0 | 0.002106% | 0.00224% | 100% | 72053520 | 0.0002162% |  | 2.1624e-06
[6 empty] | Concrete |  | 0.00094% | 0.0009402% | 0.001% | 32166750 | 0.0009402% | 0.001% | 100% | 32166750 | 0% | 0% |  | 0 | 0.0009402% | 0.001% | 100% | 32166750 | 0.0001222% |  | 1.2222e-06
|  |  |  | Concrete Work for Water Intake near the Sea | [21 empty] | 0
[6 empty] | Piles |  | 0.01514% | 0.01514% | 0.0161% | 517884675 | 0.01514% | 0.0161% | 100% | 517884675 |  |  |  |  | 0.01514% | 0.0161% | 100% | 517884675 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.062% | 0.062% | 0.06595% | 2121397162.5 | 0.05911% | 0.06287% | 95.32% | 2022323572.5 | 0% | 0% |  | 0 | 0.05911% | 0.06287% | 95.32% | 2022323572.5 |  |  | 0
[6 empty] | Concrete |  | 0.00878% | 0.008781% | 0.00934% | 300437445 | 0.008151% | 0.00867% | 92.86% | 278885722.5 | 0% | 0% |  | 0 | 0.008151% | 0.00867% | 92.86% | 278885722.5 |  |  | 0
|  |  |  | Transfer Sea Water Pond | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.01474% | 0.01474% | 0.01568% | 504374640 | [14 empty] | 0
[6 empty] | Concrete |  | 0.00495% | 0.004955% | 0.00527% | 169518772.5 | [14 empty] | 0
|  |  |  | Slag Granulation Pond | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.04211% | 0.04211% | 0.04479% | 1440748732.5 | 0.04182% | 0.04448% | 99.3% | 1430777040 | 0% | 0% |  | 0 | 0.04182% | 0.04448% | 99.3% | 1430777040 | 0.00896% |  | 8.9597e-05
[6 empty] | Concrete |  | 0.00599% | 0.005989% | 0.00637% | 204902197.5 | 0.005914% | 0.00629% | 98.77% | 202328857.5 | 0% | 0% |  | 0 | 0.005914% | 0.00629% | 98.77% | 202328857.5 | 0.001636% |  | 1.6359e-05
|  |  |  | Settling Water Pond | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.01118% | 0.01118% | 0.01189% | 382462657.5 | 0.01072% | 0.0114% | 95.85% | 366700950 | 0% | 0% |  | 0 | 0.01072% | 0.0114% | 95.85% | 366700950 |  |  | 0
[6 empty] | Concrete |  | 0.0039% | 0.003902% | 0.00415% | 133492012.5 | 0.003648% | 0.00388% | 93.37% | 124806990 | 0% | 0% |  | 0 | 0.003648% | 0.00388% | 93.37% | 124806990 |  |  | 0
|  |  |  | Cooling Tower Basin Pond | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.01118% | 0.01118% | 0.01189% | 382462657.5 | 0.01118% | 0.01189% | 100% | 382462657.5 |  |  |  |  | 0.01118% | 0.01189% | 100% | 382462657.5 |  |  | 0
[6 empty] | Concrete |  | 0.0039% | 0.003902% | 0.00415% | 133492012.5 | 0.003902% | 0.00415% | 100% | 133492012.5 |  |  |  |  | 0.003902% | 0.00415% | 100% | 133492012.5 |  |  | 0
|  |  |  | Head Tanks Support & Foundation | [21 empty] | 0
[6 empty] | Piles |  | 0.01547% | 0.01547% | 0.01645% | 529143037.5 | 0.01547% | 0.01645% | 100% | 529143037.5 |  |  |  |  | 0.01547% | 0.01645% | 100% | 529143037.5 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.00328% | 0.003281% | 0.00349% | 112261957.5 | 0.003281% | 0.00349% | 100% | 112261957.5 |  |  |  |  | 0.003281% | 0.00349% | 100% | 112261957.5 |  |  | 0
[6 empty] | Concrete |  | 0.00119% | 0.001194% | 0.00127% | 40851772.5 | 0.001194% | 0.00127% | 100% | 40851772.5 |  |  |  |  | 0.001194% | 0.00127% | 100% | 40851772.5 |  |  | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.01734% | 0.01734% | 0.01844% | 593154870 | [14 empty] | 0
|  |  |  | Softened Water Making Equipment | [21 empty] | 0
[5 empty] | a. Shot Return Pond | Reinforcement Bar |  | 0.00626% | 0.006261% | 0.00666% | 214230555 | 0.006261% | 0.00666% | 100% | 214230556 |  |  |  |  | 0.006261% | 0.00666% | 100% | 214230556 |  |  | 0
[6 empty] | Concrete |  | 0.0012% | 0.001203% | 0.00128% | 41173440 | 0.001194% | 0.00127% | 100% | 40851772.5 |  |  |  |  | 0.001194% | 0.00127% | 100% | 40851772.5 |  |  | 0
[5 empty] | b. Shot Cooling Pond | Reinforcement Bar |  | 0.00626% | 0.006261% | 0.00666% | 214230555 | 0.006261% | 0.00666% | 100% | 214230555 |  |  |  |  | 0.006261% | 0.00666% | 100% | 214230555 |  |  | 0
[6 empty] | Concrete |  | 0.0012% | 0.001203% | 0.00128% | 41173440 | 0.001194% | 0.00127% | 100% | 40851772.5 |  |  |  |  | 0.001194% | 0.00127% | 100% | 40851772.5 |  |  | 0
|  |  |  | MFO / HSD Main Tank Support & Foundation | [21 empty] | 0
[5 empty] | a. MFO Tank Foundation | Piles |  | 0.00936% | 0.009364% | 0.00996% | 320380830 | 0.009364% | 0.00996% | 100% | 320380830 |  |  |  |  | 0.009364% | 0.00996% | 100% | 320380830 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.00386% | 0.003864% | 0.00411% | 132205342.5 | [14 empty] | 0
[6 empty] | Concrete |  | 0.00055% | 0.0005547% | 0.00059% | 18978382.5 | [14 empty] | 0
[5 empty] | b. HSD Tank Foundation | Piles |  | 0.00687% | 0.006873% | 0.00731% | 235138942.5 | 0.006873% | 0.00731% | 100% | 235138942.5 |  |  |  |  | 0.006873% | 0.00731% | 100% | 235138942.5 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.00313% | 0.003131% | 0.00333% | 107115277.5 | [14 empty] | 0
[6 empty] | Concrete |  | 0.00045% | 0.0004513% | 0.00048% | 15440040 | [14 empty] | 0
|  |  |  | MFO / HSD Transfer Pump House | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00036% | 0.0003573% | 0.00038% | 12223365 | [14 empty] | 0
[6 empty] | Concrete |  | 0.00016% | 0.0001598% | 0.00017% | 5468347.5 | [14 empty] | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.00097% | 0.0009684% | 0.00103% | 33131752.5 | [14 empty] | 0
|  |  |  | MFO Service Tank for Dryer Support & Foundation | [21 empty] | 0
[6 empty] | Piles |  | 0.00303% | 0.003027% | 0.00322% | 103576935 | 0.003027% | 0.00322% | 100% | 103576935 |  |  |  |  | 0.003027% | 0.00322% | 100% | 103576935 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.00072% | 0.0007239% | 0.00077% | 24768397.5 | 0.0007239% | 0.00077% | 100% | 24768397.5 |  |  |  |  | 0.0007239% | 0.00077% | 100% | 24768397.5 |  |  | 0
[6 empty] | Concrete |  | 0.00011% | 0.0001128% | 0.00012% | 3860010 | 0.0001128% | 0.00012% | 100% | 3860010 |  |  |  |  | 0.0001128% | 0.00012% | 100% | 3860010 |  |  | 0
|  |  |  | MFO Service Tank for Kiln Support & Foundation | [21 empty] | 0
[6 empty] | Piles |  | 0.00303% | 0.003027% | 0.00322% | 103576935 | 0.003027% | 0.00322% | 100% | 103576935 |  |  |  |  | 0.003027% | 0.00322% | 100% | 103576935 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.00072% | 0.0007239% | 0.00077% | 24768397.5 | 0.0007239% | 0.00077% | 100% | 24768397.5 |  |  |  | 0 | 0.0007239% | 0.00077% | 100% | 24768397.5 | 0.0001316% |  | 1.3162e-06
[6 empty] | Concrete |  | 0.00011% | 0.0001128% | 0.00012% | 3860010 | 0.0001128% | 0.00012% | 100% | 3860010 |  |  |  | 0 | 0.0001128% | 0.00012% | 100% | 3860010 | 1.88e-05% |  | 1.8803e-07
|  |  |  | HSD Service Tank for Coal mill Support & Foundation | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00019% | 0.000188% | 0.0002% | 6433350 | 0.000188% | 0.0002% | 100% | 6433350 |  |  |  |  | 0.000188% | 0.0002% | 100% | 6433350 |  |  | 0
[6 empty] | Concrete |  | 3e-05% | 2.82e-05% | 3e-05% | 965002.5 | 2.82e-05% | 3e-05% | 100% | 965002.5 |  |  |  |  | 2.82e-05% | 3e-05% | 100% | 965002.5 |  |  | 0
|  |  |  | HSD Service Tank for Shot making & Ladle Heating Support & Foundation |  |  |  |  | - | - | [15 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.0006% | 0.0006017% | 0.00064% | 20586720 | [14 empty] | 0
[6 empty] | Concrete |  | 9e-05% | 9.402e-05% | 0.0001% | 3216675 | [14 empty] | 0
|  |  |  | Fire Water Storage Tank Foundation | [21 empty] | 0
[6 empty] | Piles |  | 0.00687% | 0.006873% | 0.00731% | 235138942.5 | 0.006873% | 0.00731% | 100% | 235138942.5 |  |  |  |  | 0.006873% | 0.00731% | 100% | 235138942.5 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.00263% | 0.002632% | 0.0028% | 90066900 | 0.002632% | 0.0028% | 100% | 90066900 |  |  |  |  | 0.002632% | 0.0028% | 100% | 90066900 |  |  | 0
[6 empty] | Concrete |  | 0.00038% | 0.0003761% | 0.0004% | 12866700 | 0.0003761% | 0.0004% | 100% | 12866700 |  |  |  |  | 0.0003761% | 0.0004% | 100% | 12866700 |  |  | 0
|  |  |  | Electrical Room for River Water Intake (No.52) | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00338% | 0.003385% | 0.0036% | 115800300 | 0.002341% | 0.00249% | 69.12% | 80095207.5 | 0% | 0% |  | 0 | 0.002341% | 0.00249% | 69.12% | 80095207.5 | 0.0003573% |  | 3.5726e-06
[6 empty] | Concrete |  | 0.00055% | 0.0005547% | 0.00059% | 18978382.5 | 0.0003103% | 0.00033% | 55.67% | 10615027.5 | 0% | 0% |  | 0 | 0.0003103% | 0.00033% | 55.67% | 10615027.5 | 9.402e-06% |  | 9.4016e-08
[6 empty] | Steel Structure & Roof Siding |  | 0.00104% | 0.001044% | 0.00111% | 35705092.5 | [14 empty] | 0
|  |  |  | Electrical Room for Sea Water Intake (No.53) | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00325% | 0.003253% | 0.00346% | 111296955 | 0.002106% | 0.00224% | 64.77% | 72053520 | 0% | 0% |  | 0 | 0.002106% | 0.00224% | 64.77% | 72053520 |  |  | 0
[6 empty] | Concrete |  | 0.00053% | 0.0005265% | 0.00056% | 18013380 | 0.0003291% | 0.00035% | 63.28% | 11258362.5 | 0% | 0% |  | 0 | 0.0003291% | 0.00035% | 63.28% | 11258362.5 | 3.761e-05% |  | 3.7606e-07
[6 empty] | Steel Structure & Roof Siding |  | 0.00104% | 0.001044% | 0.00111% | 35705092.5 | [14 empty] | 0
|  |  |  | Cooling Tower Non Softened Water Foundation | [21 empty] | 0
[6 empty] | Piles | [19 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.01158% | 0.01158% | 0.01232% | 396294360 | 0.01094% | 0.01164% | 94.44% | 374420970 | 0% | 0% |  | 0 | 0.01094% | 0.01164% | 94.44% | 374420970 | 0.01094% |  | 0.00010943
[6 empty] | Concrete |  | 0.00165% | 0.001655% | 0.00176% | 56613480 | 0.001561% | 0.00166% | 94.44% | 53396805 | 0% | 0% |  | 0 | 0.001561% | 0.00166% | 94.44% | 53396805 | 0.001561% |  | 1.5607e-05
|  |  |  | Cooling Tower Softened Water Foundation | [21 empty] | 0
[6 empty] | Piles | [19 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.0193% | 0.0193% | 0.02053% | 660383377.5 | 0.01819% | 0.01935% | 94.23% | 622426612.5 | 0% | 0% |  | 0 | 0.01819% | 0.01935% | 94.23% | 622426612.5 | 0.00455% |  | 4.5504e-05
[6 empty] | Concrete |  | 0.00275% | 0.002755% | 0.00293% | 94248577.5 | 0.002595% | 0.00276% | 94.23% | 88780230 | 0% | 0% |  | 0 | 0.002595% | 0.00276% | 94.23% | 88780230 | 0.0007427% |  | 7.4272e-06
|  |  |  | Cooling Tower Softened Water Cooper Cooler Foundation |  |  |  |  | - | - | [15 empty] | 0
[6 empty] | Piles | [19 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.0193% | 0.0193% | 0.02053% | 660383377.5 | 0.01854% | 0.01972% | 96.08% | 634328310 | 0% | 0% |  | 0 | 0.01854% | 0.01972% | 96.08% | 634328310 | 0.01854% |  | 0.0001854
[6 empty] | Concrete |  | 0.00279% | 0.002792% | 0.00297% | 95535247.5 | 0.002679% | 0.00285% | 96.08% | 91675237.5 | 0% | 0% |  | 0 | 0.002679% | 0.00285% | 96.08% | 91675237.5 | 0.002679% |  | 2.6794e-05
0
|  | 4 | Civil Building | [22 empty] | 0
|  |  |  | Administration Office Building 12mW x 50mL x 4mH | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00789% | 0.007888% | 0.00839% | 269879032.5 | 0.007314% | 0.00778% | 92.72% | 250257315 | 0% | 0% |  | 0 | 0.007314% | 0.00778% | 92.72% | 250257315 |  |  | 0
[6 empty] | Concrete |  | 0.00129% | 0.001288% | 0.00137% | 44068447.5 | 0.001185% | 0.00126% | 92.57% | 40530105 | 0% | 0% |  | 0 | 0.001185% | 0.00126% | 92.57% | 40530105 |  |  | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.00759% | 0.007587% | 0.00807% | 259585672.5 | [14 empty] | 0
|  |  |  | Warehouse 20mW x 90mL x 12mH | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00249% | 0.002491% | 0.00265% | 85241887.5 | 0.002407% | 0.00256% | 96.54% | 82346880 |  |  |  |  | 0.002407% | 0.00256% | 96.54% | 82346880 |  |  | 0
[6 empty] | Concrete |  | 0.00102% | 0.001015% | 0.00108% | 34740090 | 0.000282% | 0.0003% | 28.6% | 9650025 |  |  |  |  | 0.000282% | 0.0003% | 28.6% | 9650025 |  |  | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.02099% | 0.02099% | 0.02233% | 718283527.5 | [14 empty] | 0
|  |  |  | Laboratory 11mW x 24,5mL x 4mH | [21 empty] | 0
[6 empty] | Piles |  | 0% | 0% | 0% | 0 | [14 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00728% | 0.007277% | 0.00774% | 248970645 | 0.005171% | 0.0055% | 71.12% | 176917125 | 0% | 0% |  | 0 | 0.005171% | 0.0055% | 71.12% | 176917125 |  |  | 0
[6 empty] | Concrete |  | 0.00114% | 0.001138% | 0.00121% | 38921767.5 | 0.0007991% | 0.00085% | 70.16% | 27341737.5 | 0% | 0% |  | 0 | 0.0007991% | 0.00085% | 70.16% | 27341737.5 |  |  | 0
[6 empty] | Architectural |  | 0.00275% | 0.002755% | 0.00293% | 94248577.5 | [14 empty] | 0
|  |  |  | Workshop 24mW x 30mL x 12mH | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00741% | 0.007408% | 0.00788% | 253473990 | 0.007042% | 0.00749% | 95.04% | 240928957.5 |  |  |  |  | 0.007042% | 0.00749% | 95.04% | 240928957.5 |  |  | 0
[6 empty] | Concrete |  | 0.00783% | 0.007832% | 0.00833% | 267949027.5 | 0.002783% | 0.00296% | 35.58% | 95213580 |  |  |  |  | 0.002783% | 0.00296% | 35.58% | 95213580 |  |  | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.04285% | 0.04285% | 0.04558% | 1466160465 | [14 empty] | 0
|  |  |  | Fire Station House 9mW x 12mL x 5mH | [21 empty] | 0
[5 empty] | a. Fire Station House | Reinforcement Bar |  | 0.00171% | 0.001711% | 0.00182% | 58543485 | 0.001401% | 0.00149% | 81.69% | 47928457.5 | 0% | 0% |  | 0 | 0.001401% | 0.00149% | 81.69% | 47928457.5 |  |  | 0
[6 empty] | Concrete |  | 0.00178% | 0.001777% | 0.00189% | 60795157.5 | 0.001194% | 0.00127% | 67.34% | 40851772.5 | 0% | 0% |  | 0 | 0.001194% | 0.00127% | 67.34% | 40851772.5 |  |  | 0
[5 empty] | b. Fire Station Shelter | Reinforcement Bar |  | 0.00118% | 0.001185% | 0.00126% | 40530105 | 0.001185% | 0.00126% | 100% | 40530105.5 |  |  |  |  | 0.001185% | 0.00126% | 100% | 40530105.5 |  |  | 0
[6 empty] | Concrete |  | 0.00016% | 0.0001598% | 0.00017% | 5468347.5 | 0.0001598% | 0.00017% | 100% | 5468347.5 |  |  |  |  | 0.0001598% | 0.00017% | 100% | 5468347.5 |  |  | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.00174% | 0.001739% | 0.00185% | 59508487.5 | [14 empty] | 0
|  |  |  | Pump House for Fire Station | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00171% | 0.001711% | 0.00182% | 58543485 | [14 empty] | 0
[6 empty] | Concrete |  | 0.00178% | 0.001777% | 0.00189% | 60795157.5 | [14 empty] | 0
|  |  |  | Weight Bridge & Control Room | [21 empty] | 0
[6 empty] | Piles |  | 0.00932% | 0.009317% | 0.00991% | 318772492.5 | 0.009317% | 0.00991% | 100% | 318772492.5 | 0% | 0% |  |  | 0.009317% | 0.00991% | 100% | 318772492.5 |  |  | 0
[6 empty] | Reinforcement Bar |  | 0.00298% | 0.00298% | 0.00317% | 101968597.5 | 0.001786% | 0.0019% | 60.08% | 61116825 | 0% | 0% |  | 0 | 0.001786% | 0.0019% | 60.08% | 61116825 |  |  | 0
[6 empty] | Concrete |  | 0.00171% | 0.001711% | 0.00182% | 58543485 | 0.0009872% | 0.00105% | 57.84% | 33775087.5 | 0% | 0% |  | 0 | 0.0009872% | 0.00105% | 57.84% | 33775087.5 |  |  | 0
|  |  |  | Gate House 2,75mW x 2,5mL x 4mH | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00069% | 0.0006863% | 0.00073% | 23481727.5 | [14 empty] | 0
[6 empty] | Concrete |  | 0.00128% | 0.001279% | 0.00136% | 43746780 | [14 empty] | 0
|  |  |  | Outdoor Lavatory | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00014% | 0.000141% | 0.00015% | 4825012.5 | [14 empty] | 0
[6 empty] | Concrete |  | 5e-05% | 4.701e-05% | 5e-05% | 1608337.5 | [14 empty] | 0
[6 empty] | Roof Siding |  | 0.00082% | 0.0008179% | 0.00087% | 27985072.5 | [14 empty] | 0
|  |  |  | Chemical Laboratory | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00447% | 0.004466% | 0.00475% | 152792062.5 | 0.002736% | 0.00291% | 61.21% | 93605242.5 | 0% | 0% |  | 0 | 0.002736% | 0.00291% | 61.21% | 93605242.5 |  |  | 0
[6 empty] | Concrete |  | 0.0028% | 0.002802% | 0.00298% | 95856915 | 0.001673% | 0.00178% | 59.78% | 57256815 | 0% | 0% |  | 0 | 0.001673% | 0.00178% | 59.78% | 57256815 |  |  | 0
|  |  |  | Ore Preparation Sample Laboratory | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00661% | 0.006609% | 0.00703% | 226132252.5 | 0.003093% | 0.00329% | 46.92% | 105828607.5 | 0% | 0% |  | 0 | 0.003093% | 0.00329% | 46.92% | 105828607.5 |  |  | 0
[6 empty] | Concrete |  | 0.00405% | 0.004052% | 0.00431% | 138638692.5 | 0.001815% | 0.00193% | 44.56% | 62081827.5 | 0% | 0% |  | 0 | 0.001815% | 0.00193% | 44.56% | 62081827.5 |  |  | 0
|  |  |  | Musholla | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00293% | 0.002933% | 0.00312% | 100360260 | 0.002651% | 0.00282% | 90.44% | 90710235 | 0% | 0% |  | 0 | 0.002651% | 0.00282% | 90.44% | 90710235 |  |  | 0
[6 empty] | Concrete |  | 0.00099% | 0.0009872% | 0.00105% | 33775087.5 | 0.0008461% | 0.0009% | 86.02% | 28950075 | 0% | 0% |  | 0 | 0.0008461% | 0.0009% | 86.02% | 28950075 |  |  | 0
[6 empty] | Roof Siding |  | 0.00534% | 0.00534% | 0.00568% | 182707140 | [14 empty] | 0
|  |  |  | Mechanical Maintenance & Heavy Equipment Workshop | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00507% | 0.005067% | 0.00539% | 173378782.5 | 0.004814% | 0.00512% | 95.04% | 164693760 |  |  |  |  | 0.004814% | 0.00512% | 95.04% | 164693760 |  |  | 0
[6 empty] | Concrete |  | 0.00261% | 0.002614% | 0.00278% | 89423565 | 0.000959% | 0.00102% | 36.57% | 32810085 |  |  |  |  | 0.000959% | 0.00102% | 36.57% | 32810085 |  |  | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.03231% | 0.03231% | 0.03437% | 1105571197.5 | [14 empty] | 0
|  |  |  | Electrical Maintenance & Instrument Control Workshop | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.0039% | 0.003902% | 0.00415% | 133492012.5 | 0.003714% | 0.00395% | 95.02% | 127058663 |  |  |  |  | 0.003714% | 0.00395% | 95.02% | 127058663 |  |  | 0
[6 empty] | Concrete |  | 0.00202% | 0.002021% | 0.00215% | 69158512.5 | 0.0008367% | 0.00089% | 41.39% | 28628407.5 | 0% | 0% |  | 0 | 0.0008367% | 0.00089% | 41.39% | 28628407.5 |  |  | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.02404% | 0.02404% | 0.02557% | 822503797.5 | 0.0205% | 0.02181% | 85.28% | 701556817.5 | 0% | 0% |  | 0 | 0.0205% | 0.02181% | 85.28% | 701556817.5 | 0.004005% |  | 4.0051e-05
|  |  |  | Electrical & Instrument Warehouse | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00249% | 0.002491% | 0.00265% | 85241887.5 | 0.002407% | 0.00256% | 96.54% | 82346880 |  |  |  |  | 0.002407% | 0.00256% | 96.54% | 82346880 |  |  | 0
[6 empty] | Concrete |  | 0.00102% | 0.001015% | 0.00108% | 34740090 | 0.0002914% | 0.00031% | 28.6% | 9971692.5 |  |  |  |  | 0.0002914% | 0.00031% | 28.6% | 9971692.5 |  |  | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.02099% | 0.02099% | 0.02233% | 718283527.5 | [14 empty] | 0
|  |  |  | Chemical Warehouse | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00249% | 0.002491% | 0.00265% | 85241887.5 | 0.002407% | 0.00256% | 96.54% | 82346880 |  |  |  |  | 0.002407% | 0.00256% | 96.54% | 82346880 |  |  | 0
[6 empty] | Concrete |  | 0.00102% | 0.001015% | 0.00108% | 34740090 | 0.0002914% | 0.00031% | 28.6% | 9971692.5 |  |  |  |  | 0.0002914% | 0.00031% | 28.6% | 9971692.5 |  |  | 0
[6 empty] | Steel Structure & Roof Siding |  | 0.02099% | 0.02099% | 0.02233% | 718283527.5 | [14 empty] | 0
|  |  |  | Concrete Pipe Sleeper Sea Water Intake | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00387% | 0.003873% | 0.00412% | 132527010 | 0.001467% | 0.00156% | 37.91% | 50180130 | 0% | 0% |  | 0 | 0.001467% | 0.00156% | 37.91% | 50180130 |  |  | 0
[6 empty] | Concrete |  | 0.00099% | 0.0009872% | 0.00105% | 33775087.5 | 0.0002914% | 0.00031% | 29.44% | 9971693 | 0% | 0% |  | 0 | 0.0002914% | 0.00031% | 29.44% | 9971693 |  |  | 0
|  |  |  | Concrete Pipe Sleeper River Water Intake | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.02124% | 0.02124% | 0.02259% | 726646882.5 | 0.007126% | 0.00758% | 33.55% | 243823966 | 0% | 0% |  | 0 | 0.007126% | 0.00758% | 33.55% | 243823966 | 0.001119% |  | 1.1188e-05
[6 empty] | Concrete |  | 0.00524% | 0.005237% | 0.00557% | 179168797.5 | 0.001457% | 0.00155% | 27.68% | 49858462.5 | 0.0001316% | 0.00014% | 2.56% | 4503345 | 0.001589% | 0.00169% | 30.24% | 54361807.5 | 0.0003291% |  | 1.9743e-06
|  |  |  | Inject Water Pond | [21 empty] | 0
[6 empty] | Reinforcement Bar |  | 0.00273% | 0.002726% | 0.0029% | 93283575 | [14 empty] | 0
[6 empty] | Concrete |  | 0.00104% | 0.001044% | 0.00111% | 35705092.5 | [14 empty] | 0
0
C.2 | C.2 | Insurance | [6 empty] | 1.029% | 1.094% | 35205221205 | 0.8575% | 0.912% |  | 29337362670 | 0.01225% | 0.01303% |  | 419132753 | 0.8697% | 0.9251% |  | 29756495423 | 0.0001225 | 84.52% | 0
0
|  |  | Insurance and Other Fees |  |  |  |  | 1.029% | 1.029% | 1.094% | 35205221205 | 0.8575% | 0.912% | 83.33% | 29337362670 | 0.01225% | 0.01303% | 1.19% | 419132752.5 | 0.8697% | 0.9251% | 84.52% | 29756495422.5 | 0.0001225 |  | 0

## Print D
| Attachment 4 - Commissioning | [20 empty] | 2018-05-31
| NO | DESCRIPTION |  |  |  | CONTRACT - IDR |  |  |  |  | PROGRESS
[6 empty] | FOREIGN PORTION | DOMESTIC PORTION | TOTAL |  |  | UNTIL PREVIOUS MONTH |  |  |  | THIS MONTH |  |  |  | UNTIL THIS MONTH
[8 empty] | % WEIGHT FACTOR (OVERALL) | % WEIGHT FACTOR (WIKA PORTION) | IDR | % WEIGHT FACTOR (OVERALL) | % WEIGHT FACTOR (WIKA PORTION) | % PROGRESS | IDR | % WEIGHT FACTOR (OVERALL) | % WEIGHT FACTOR (WIKA PORTION) | % PROGRESS | IDR | % WEIGHT FACTOR (OVERALL) | % WEIGHT FACTOR (WIKA PORTION) | % PROGRESS | IDR
D | D | COMMISSIONING | [5 empty] | 1.564% | 1.664% | 53512605300 | 0% |  |  |  | 0% |  |  |  | 0% |  |  |  | 0%
D.1 | D.1 | Supervisory Services by WIKA |  |  |  |  | 0.07926% | 0.07926% | 0.08431% | 2711978693 | 0% |  |  |  | 0% |  |  |  | 0% |  |  |  | 0%
|  | D.1.1 | TEST AND COMMISSIONING
|  | 1 | FIELD TEST, COMMISSIONING & TRAINING |  |  |  | 0.07926% | 0.07926% | 0.08431% | 2711978692.5
D.2 | D.2 | Spare Part | [5 empty] | 1.485% | 1.579% | 50800626607 | 0% |  |  |  | 0% |  |  |  | 0% |  |  |  | 0%
|  | D.2.1 | SPARE PART FOR 1 YEAR OPERATION |  |  | 0% | 0.5049% | 0.5049% | 0.537% | 17274831420 | 0% |  |  |  | 0% |  |  |  | 0%
|  | 1 | System 2 |  |  | 0% | 0.4574% | 0.4574% | 0.4865% | 15649445542.5
|  |  |  | Hydraulic cylinder (Cover lifting system) | Calcine transport system
|  |  |  | Sealing for hydraulic cylinder | Calcine transport system
|  |  |  | Spare parts for container transport car | Calcine transport system
|  |  |  | Spare parts for container maintenance car | Calcine transport system
|  |  |  | Spare parts for charging crane | Calcine transport system
|  |  |  | Spare parts for furnace bin dedusting | Calcine transport system
|  |  |  | Pressure ring | Electrode column lower part
|  |  |  | Sealing parts | Electrode column lower part
|  |  |  | Expansion belows | Electrode column lower part
|  |  |  | Protection ring | Electrode column lower part
|  |  |  | Contact clamp | Electrode column lower part
|  |  |  | Clamping frame | Electrode column lower part
|  |  |  | Sealing cylinder | Electrode column lower part
|  |  |  | Insulting parts electrode column lower part | Electrode column lower part
|  |  |  | Sealing parts | Electrode column lower part
|  |  |  | Pressure pads | Electrode column upper part
|  |  |  | Clamping ring cylinder | Electrode column upper part
|  |  |  | Sealing for clamping ring cylinder | Electrode column upper part
|  |  |  | cup springs | Electrode column upper part
|  |  |  | Lifting cylinder | Electrode column upper part
|  |  |  | Sealing for lifting cylinder | Electrode column upper part
|  |  |  | Regulating cylinder | Electrode column upper part
|  |  |  | Sealing for regulating cylinder | Electrode column upper part
|  |  |  | Insulating parts | Electrode column upper part
|  |  |  | Flexible cables electrode column | High current supply system
|  |  |  | Insulating parts | High current supply system
|  |  |  | High pressure pump | Hydraulic system
|  |  |  | Filter | Hydraulic system
|  |  |  | Var. valves | Hydraulic system
|  |  |  | Var. minor parts | Hydraulic system
|  |  |  | Spare parts | Taphole drilling machine
|  |  |  | Metal tap block (face plate) | Copper cooler
|  |  |  | Metal taphole refractory | Copper cooler
|  |  |  | Slag tap block (slag insert) | Copper cooler
|  |  |  | Flexible hose for cooling water | Copper cooler
|  |  |  | RTD for copper cooler | Copper cooler
|  |  |  | Bearing | Pump
|  |  |  | O-Ring | Pump
|  |  |  | Packing | Pump
|  |  |  | Shaft Sleave | Pump
|  |  |  | Liquid Sealant | Pump
|  |  |  | Packing | Pump
|  |  |  | Bearing | Cooling Tower
|  |  |  | Oil Seal | Cooling Tower
|  |  |  | V-belt | Cooling Tower
|  | 2 | System 4 |  |  |  | 0.04751% | 0.04751% | 0.05053% | 1625385877.5
|  |  |  | Bearing | Water pump
|  |  |  | O-Ring | Water pump
|  |  |  | Gland Packing | Water pump
|  |  |  | Shaft Sleave | Water pump
|  |  |  | Liquid Sealant | Water pump
|  |  |  | Packing | Water pump
|  |  |  | Bearing | Clarifier
|  |  |  | Gasket | Clarifier
|  |  |  | Gasket | Sand Filter Tank
|  |  |  | Filter material (sand) | Sand Filter Tank
|  |  |  | Ion exchanger Resin | Softener
|  |  |  | Strainer Basket | Softener
|  |  |  | Bearing | Cooling tower
|  |  |  | Oil Seal | Cooling tower
|  |  |  | V-belt | Cooling tower
|  |  |  | Ball Bearing | Oil pump
|  |  |  | O-Ring | Oil pump
|  |  |  | Oil Seal | Oil pump
|  |  |  | Liquid Sealant | Oil pump
|  |  |  | Air filter Element | Air compressor
|  |  |  | Oil Filter Element | Air compressor
|  |  |  | O-Ring | Air compressor
|  |  |  | Packing | Air compressor
|  |  |  | Mechanical Seal | Air compressor
|  |  |  | Gasket | Air compressor
|  |  |  | Gasket | Air receiver tank
|  |  |  | Drain kit | Air receiver tank
|  |  |  | Dry separator | Air dryer
|  |  |  | Oil separator | Air dryer
|  |  |  | Air filter | Air dryer
|  |  |  | Filter material | Air dryer
|  |  |  | Gasket | Air dryer
|  |  |  | Valve | Oksigen compressor
|  |  |  | O-Ring | Oksigen compressor
|  |  |  | Packing | Oksigen compressor
|  |  |  | Gasket | Oksigen compressor
|  |  |  | Valve | Nitrogen compressor
|  |  |  | O-Ring | Nitrogen compressor
|  |  |  | Packing | Nitrogen compressor
|  |  |  | Gasket | Nitrogen compressor
|  | D.2.2 | SPARE PART FOR 1 YEAR OPERATION |  |  |  |  | 0.7308% | 0.7773% | 25004823112.5 | 0% |  |  |  | 0% |  |  |  | 0% |  |  | 0%
|  |  |  | System-1 Ore Production & Calcining System |  | 0.7308% |  | 0.7308% | 0.7773% | 25004823112.5
|  | D.2.3 | SPARE PART FOR 1 YEAR OPERATION |  |  | 0% | 0.249% | 0.249% | 0.2649% | 8520972075 | 0% |  |  |  | 0% |  |  |  | 0%
|  | 1 | System 3 |  |  | 0% | 0.1594% | 0.1594% | 0.1696% | 5454194130
|  |  |  | Stirrer shaft | Desulphurizing equipment
|  |  |  | Bearing for Stirrer drive | Desulphurizing equipment
|  |  |  | Wire mesh belt | Net conveyor
|  |  |  | Chain | Net conveyor
|  |  |  | Solenoid valve | Dryer burner
|  |  |  | Ultravision sensor | Dryer burner
|  |  |  | Ignition plug | Dryer burner
|  |  |  | belt | Dryer fan
|  |  |  | Bearing | Dryer fan
|  |  |  | Punching plate | Trommel
|  |  |  | Wire rope | Ladle handling crane
|  |  |  | Wheel | Ladle handling crane
|  |  |  | Brake shoes | Ladle handling crane
|  |  |  | Rubber bushing for coupling | Ladle handling crane
|  |  |  | Bake disc for c/t | Ladle handling crane
|  |  |  | Brake disc for lit | Ladle handling crane
|  |  |  | Safety chatch for hook | Ladle handling crane
|  |  |  | Bearing | Ladle handling crane
|  |  |  | Limit switch | Product storage crane
|  |  |  | Rope guide support arm | Product storage crane
|  |  |  | Wire rope | Product storage crane
|  |  |  | Coupling for gear | Product storage crane
|  |  |  | Bearing | Product storage crane
|  |  |  | Hoist brake, | Product storage crane
|  |  |  | Limit switch | Product storage crane
|  |  |  | Safety catch for hook | Product storage crane
|  |  |  | MFO burner | Ladle preheating quipment
|  |  |  | Oil and air hose | Ladle preheating quipment
|  | 2 | Electrical and Instrument |  |  | 0% | 0.08963% | 0.08963% | 0.09534% | 3066777945
|  |  |  | Carbon brush | High voltage wound-rotor induction. motor
|  |  |  | Fuse element | Starter Reactor
|  |  |  | LED lamp for signal lamp | Local control panel for VVVF motor
Over-current relay
|  |  |  | LED lamp for signal lamp | 6.6kV Cubicle
Auxiliary relay
Control switch
Power fuse for VT
Fuse element
Earth leakage relay
|  |  |  | Over-current relay | LV Cubicle
LED lamp for signal lamp
Auxiliary relay
Control switch
Fuse element each type
Magnetic contactor each type
|  |  |  | MCCB each type | Motor control center
LED lamp for signal lamp
Fuse element each type
Earth leakage protection module
Overload protection module
Connector Pin for draw-out MCC
cabel lug each size
Soft starter / Inverter below 75 kW (each type)
Push button switch
|  |  |  | HV bushing | Braking Resistor Unit
|  |  |  | Silicagel breather TR | Local control box (LCB)
|  |  |  | Silicagel breather OLTC | Furnace Transformer
Complete set of gaskets
Buchholz relay
Oil level indicator
Dial type thermometer
Pressure relief device
Oil flow indicator
Water flow indicator
Diverter switch components
Oil circulating pump
Transformer Oil
Rotation detector (each type)
Belt deviation switch (each type)
|  |  |  | Pull rope switch | Field control devices
Limit switch
Thermocouple (each type)
Battery pack
|  |  |  | Pressure Gauge (each type) | Field and panel instruments
Temp Gauge
Level, Temp, Position, Flow, Pressure Switch
D/P transmitter
P Transmitter (each range)
Flow Transmitter (each range)
Solenoid Valve
Load Cell
RTD (each type)
Sirene
Filter element
O-ring
|  |  |  | Diaphragm | Gas analyzer
Standard gas (CO)
Standard gas (N2)
Gas aspirator
Auxiliary relay
Timer
Bulb for signal lamp
Digital Input unit
Digital output unit
|  |  |  | Analog Input unit | PLC panel
Analog Output unit
PSU
Auxiliary relay (each type)

## PLEASE UPDATE INFO
Please Update Every Month For Information
Sheet | Remark
SumProgress : | Progress in This Month (M16)
SumCommercial : | Total Overall Progress May 31, 2018
Print A,B,C,D : | 2018-05-31
Custom Footer Print A, B, C, D | P3FH- PM-9000-PRG-1016B Monthly Report Commercial May 2018 - Attachment 3 - Progress Payment
Nb : Please Update Every Month for The Information, this information will hyper link to every sheet

## S Curve Realisasi
Attachment 1.1 Progress S-Curve EPC Engineering Procurement and Construction
S-CURVE OVERALL EPC - ENGINEERING PROCUREMENT AND CONSTRUCTION
PROYEK PEMBANGUNAN PABRIK FERONIKEL HALMAHERA TIMUR
2018-05-31
| Activity ID | Activity Name |  |  | TOTAL |  | 2017-02-15 | 2017-03-17 | 2017-04-16 | 2017-05-16 | 2017-06-15 | 2017-07-15 | 2017-08-14 | 2017-09-13 | 2017-10-13 | 2017-11-12 | 2017-12-12 | 2018-01-11 | 2018-02-10 | 2018-03-12 | 2018-04-11 | 2018-05-11 | 2018-06-10 | 2018-07-10 | 2018-08-09 | 2018-09-08 | 2018-10-08 | 2018-11-07 | 2018-12-07 | 2019-01-06 | 2019-02-05 | 2019-03-07 | 2019-04-06 | 2019-05-06 | 2019-06-05 | 2019-07-05
[5 empty] | IDR | BOBOT | M.1 | M.2 | M.3 | M.4 | M.5 | M.6 | M.7 | M.8 | M.9 | M.10 | M.11 | M.12 | M.13 | M.14 | M.15 | M.16 | M.17 | M.18 | M.19 | M.20 | M.21 | M.22 | M.23 | M.24 | M.25 | M.26 | M.27 | M.28 | M.29 | M.30
[7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| P3FH - 28 M. Milestone | [35 empty] | 0%
| MLST1000 | Letter of Award | [34 empty] | 0%
| MLST1110 | Contract Signing | [34 empty] | 0%
| MLST1120 | Effective Date Contract (EDC) | [34 empty] | 0%
| MLST1140 | Power Receiving (Supplied by Owner) | [34 empty] | 0%
| MLST1150 | Utililty Receiving (Supplied by Owner) | [34 empty] | 0%
| MLST1160 | Material Receiving (Supplied by Owner) | [34 empty] | 0%
| MLST1180 | Kiln Firing | [34 empty] | 0%
| MLST1121 | Taking Over / Warranty Period Start for System-1 | [34 empty] | 0%
| MLST1169 | ESF Burner On | [34 empty] | 0%
| MLST1170 | ESF Switch On | [34 empty] | 0%
| MLST1122 | Delivery Date / Warranty Period Start for System-2 Calcine Transfer, 3 & 4 | [34 empty] | 0%
| MLST1200 | Project Completion | [34 empty] | 0%
| MLST1123 | Delivery Date / Warranty Period Start for System-2 ESF | [34 empty] | 0%
| P3FH - 28 M.1.2 Milestone Submission Document | [35 empty] | 0%
| P3FH - 28 M.1.2.11.1 System - 1 Ore Preparation | [35 empty] | 0%
| DDEK1210 | A-21 As-Built Drawing | [34 empty] | 0%
| DDEK1220 | B-01 Drawing List | [34 empty] | 0%
| DDEK1230 | B-02 Detailed design calculation sheets | [34 empty] | 0%
| DDEK1240 | B-03 Work Schedule | [34 empty] | 0%
| DDEK1250 | B-04 Minutes of Meeting | [34 empty] | 0%
| DDEK1260 | B-05 Plans for factory test | [34 empty] | 0%
| DDEK1270 | B-06 Results of for factory test | [34 empty] | 0%
| DDEK1280 | B-07 Plans for field test | [34 empty] | 0%
| DDEK1290 | B-08 Results of field test | [34 empty] | 0%
| DDEK1300 | B-09 Manual and catalogues | [34 empty] | 0%
| DDEK1000 | A-01 Detail Specification of Equipment | [34 empty] | 0%
| DDEK1020 | A-03 General/Partial Arrangement Drawing | [34 empty] | 0%
| DDEK1150 | A-15 Foundation Load Plan and Anchoor Bolt | [34 empty] | 0%
| DDEK1010 | A-02 Process and Instrumentation Diagram | [34 empty] | 0%
| DDEK1160 | A-16 Foundation Drawing for Equipment and Building with Bill of Quantity | [34 empty] | 0%
| DDEK1170 | A-17 Road and Drainage Plan | [34 empty] | 0%
| DDEK1180 | A-18 Building Standard Drawing | [34 empty] | 0%
| DDEK1190 | A-19 Building Lighting Plan | [34 empty] | 0%
| DDEK1200 | A-20 Building (Structure) Drawing | [34 empty] | 0%
| DDEK1030 | A-04 Assembly Drawing | [34 empty] | 0%
| DDEK1040 | A-05 Detail Drawings Mechanical | [34 empty] | 0%
| DDEK1080 | A-08 Electric Data Sheets | [34 empty] | 0%
| DDEK1100 | A-10 Equipment Load List | [34 empty] | 0%
| DDEK1140 | A-14 Control System Architecture Drawing | [34 empty] | 0%
| DDEK1050 | A-05 Detail Drawings Electrical and Instrumentation | [34 empty] | 0%
| DDEK1070 | A-07 System Control Logic Diagram and Description | [34 empty] | 0%
| DDEK1090 | A-09 Electrical Wiring Diagram | [34 empty] | 0%
| DDEK1110 | A-11 Cable List and Cable Layout Plan | [34 empty] | 0%
| DDEK1130 | A-13 Instrument Hook Up Drawing | [34 empty] | 0%
| DDEK1120 | A-12 Instrument Connection Table | [34 empty] | 0%
| P3FH - 28 M.1.2.11.2 System - 2 Electric Smelting Furnace | [35 empty] | 0%
| DDEW1230 | A-21 As-Built Drawing | [34 empty] | 0%
| DDEW1680 | B-01 Drawing List | [34 empty] | 0%
| DDEW1690 | B-02 Detailed design calculation sheets | [34 empty] | 0%
| DDEW1700 | B-03 Work Schedule | [34 empty] | 0%
| DDEW1710 | B-04 Minutes of Meeting | [34 empty] | 0%
| DDEW1720 | B-05 Plans for factory test | [34 empty] | 0%
| DDEW1730 | B-06 Results of for factory test | [34 empty] | 0%
| DDEW1740 | B-07 Plans for field test | [34 empty] | 0%
| DDEW1750 | B-08 Results of field test | [34 empty] | 0%
| DDEW1760 | B-09 Manual and catalogues | [34 empty] | 0%
| DDEW1180 | A-16 Foundation Drawing for Equipment and Building with Bill of Quantity | [34 empty] | 0%
| DDEW1190 | A-17 Road and Drainage Plan | [34 empty] | 0%
| DDEW1200 | A-18 Building Standard Drawing | [34 empty] | 0%
| DDEW1210 | A-19 Building Lighting Plan | [34 empty] | 0%
| DDEW1220 | A-20 Building (Structure) Drawing | [34 empty] | 0%
| DDEW1080 | A-06 Lubrication List | [34 empty] | 0%
| DDEW1050 | A-03 General/Partial Arrangement Drawing | [34 empty] | 0%
| DDEW1060 | A-04 Assembly Drawing | [34 empty] | 0%
| DDEW1100 | A-08 Electric Data Sheets | [34 empty] | 0%
| DDEW1160 | A-14 Control System Architecture Drawing | [34 empty] | 0%
| DDEW1030 | A-01 Detail Specification of Equipment | [34 empty] | 0%
| DDEW1040 | A-02 Process and Instrumentation Diagram | [34 empty] | 0%
| DDEW1070 | A-05 Detail Drawings Mechanical, Electrical and Instrumentation | [34 empty] | 0%
| DDEW1090 | A-07 System Control Logic Diagram and Description | [34 empty] | 0%
| DDEW1170 | A-15 Foundation Load Plan | [34 empty] | 0%
| DDEW1110 | A-09 Electrical Wiring Diagram | [34 empty] | 0%
| DDEW1120 | A-10 Equipment Load List | [34 empty] | 0%
| DDEW1130 | A-11 Cable List and Cable Layout Plan | [34 empty] | 0%
| DDEW1150 | A-13 Instrument Hook Up Drawing | [34 empty] | 0%
| DDEW1140 | A-12 Instrument Connection Table | [34 empty] | 0%
| P3FH - 28 M.1.2.11.3 System - 3 Refining & Casting | [35 empty] | 0%
| DDEW1300 | A-06 Lubrication List | [34 empty] | 0%
| DDEW1450 | A-21 As-Built Drawing | [34 empty] | 0%
| DDEW1770 | B-01 Drawing List | [34 empty] | 0%
| DDEW1780 | B-02 Detailed design calculation sheets | [34 empty] | 0%
| DDEW1790 | B-03 Work Schedule | [34 empty] | 0%
| DDEW1800 | B-04 Minutes of Meeting | [34 empty] | 0%
| DDEW1810 | B-05 Plans for factory test | [34 empty] | 0%
| DDEW1820 | B-06 Results of for factory test | [34 empty] | 0%
| DDEW1830 | B-07 Plans for field test | [34 empty] | 0%
| DDEW1840 | B-08 Results of field test | [34 empty] | 0%
| DDEW1850 | B-09 Manual and catalogues | [34 empty] | 0%
| DDEW1240 | A-01 Detail Specification of Equipment | [34 empty] | 0%
| DDEW1250 | A-02 Process and Instrumentation Diagram | [34 empty] | 0%
| DDEW1260 | A-03 General/Partial Arrangement Drawing | [34 empty] | 0%
| DDEW1390 | A-15 Foundation Load Plan and Anchoor Bolt | [34 empty] | 0%
| DDEW1400 | A-16 Foundation Drawing for Equipment and Building with Bill of Quantity | [34 empty] | 0%
| DDEW1410 | A-17 Road and Drainage Plan | [34 empty] | 0%
| DDEW1420 | A-18 Building Standard Drawing | [34 empty] | 0%
| DDEW1430 | A-19 Building Lighting Plan | [34 empty] | 0%
| DDEW1440 | A-20 Building (Structure) Drawing | [34 empty] | 0%
| DDEW1270 | A-04 Assembly Drawing | [34 empty] | 0%
| DDEW1280 | A-05 Detail Drawings Mechanical | [34 empty] | 0%
| DDEW1320 | A-08 Electric Data Sheets | [34 empty] | 0%
| DDEW1340 | A-10 Equipment Load List | [34 empty] | 0%
| DDEW1380 | A-14 Control System Architecture Drawing | [34 empty] | 0%
| DDEW1290 | A-05 Detail Drawings Electrical and Instrumentation | [34 empty] | 0%
| DDEW1310 | A-07 System Control Logic Diagram and Description | [34 empty] | 0%
| DDEW1330 | A-09 Electrical Wiring Diagram | [34 empty] | 0%
| DDEW1350 | A-11 Cable List and Cable Layout Plan | [34 empty] | 0%
| DDEW1370 | A-13 Instrument Hook Up Drawing | [34 empty] | 0%
| DDEW1360 | A-12 Instrument Connection Table | [34 empty] | 0%
| P3FH - 28 M.1.2.11.4 System - 4 Utility | [35 empty] | 0%
| DDEW1520 | A-06 Lubrication List | [34 empty] | 0%
| DDEW1670 | A-21 As-Built Drawing | [34 empty] | 0%
| DDEW1860 | B-01 Drawing List | [34 empty] | 0%
| DDEW1870 | B-02 Detailed design calculation sheets | [34 empty] | 0%
| DDEW1880 | B-03 Work Schedule | [34 empty] | 0%
| DDEW1890 | B-04 Minutes of Meeting | [34 empty] | 0%
| DDEW1900 | B-05 Plans for factory test | [34 empty] | 0%
| DDEW1910 | B-06 Results of for factory test | [34 empty] | 0%
| DDEW1920 | B-07 Plans for field test | [34 empty] | 0%
| DDEW1930 | B-08 Results of field test | [34 empty] | 0%
| DDEW1940 | B-09 Manual and catalogues | [34 empty] | 0%
| DDEW1460 | A-01 Detail Specification of Equipment | [34 empty] | 0%
| DDEW1470 | A-02 Process and Instrumentation Diagram | [34 empty] | 0%
| DDEW1480 | A-03 General/Partial Arrangement Drawing | [34 empty] | 0%
| DDEW1610 | A-15 Foundation Load Plan and Anchoor Bolt | [34 empty] | 0%
| DDEW1620 | A-16 Foundation Drawing for Equipment and Building with Bill of Quantity | [34 empty] | 0%
| DDEW1630 | A-17 Road and Drainage Plan | [34 empty] | 0%
| DDEW1640 | A-18 Building Standard Drawing | [34 empty] | 0%
| DDEW1650 | A-19 Building Lighting Plan | [34 empty] | 0%
| DDEW1660 | A-20 Building (Structure) Drawing | [34 empty] | 0%
| DDEW1490 | A-04 Assembly Drawing | [34 empty] | 0%
| DDEW1500 | A-05 Detail Drawings Mechanical | [34 empty] | 0%
| DDEW1540 | A-08 Electric Data Sheets | [34 empty] | 0%
| DDEW1560 | A-10 Equipment Load List | [34 empty] | 0%
| DDEW1600 | A-14 Control System Architecture Drawing | [34 empty] | 0%
| DDEW1510 | A-05 Detail Drawings Electrical and Instrumentation | [34 empty] | 0%
| DDEW1530 | A-07 System Control Logic Diagram and Description | [34 empty] | 0%
| DDEW1550 | A-09 Electrical Wiring Diagram | [34 empty] | 0%
| DDEW1570 | A-11 Cable List and Cable Layout Plan | [34 empty] | 0%
| DDEW1590 | A-13 Instrument Hook Up Drawing | [34 empty] | 0%
| DDEW1580 | A-12 Instrument Connection Table | [34 empty] | 0%
0%
0%
0%
| P3FH - 28 M. Engineering & Project Management |  |  |  | 358782600487.5 | 10.49% | 0.3753% | 0.3962% | 0.289% | 0.6721% | 0.4108% | 1.364% | 0.9332% | 1.431% | 1.517% | 0.9001% | 0.3017% | 0.1538% | 0.1312% | 0.09447% | 0.278% | 0.08214% | 0.08214% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.074%
| P3FH - 28 M. Detail Engineering Design |  |  |  | 170694208965 | 4.989% | 0.1594% | 0.2774% | 0.143% | 0.3094% | 0.2493% | 0.4407% | 0.5626% | 0.7868% | 1.096% | 0.7181% | 0.1453% | 0.06095% | 0.03906% | 0.00078% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.596e-06%
| P3FH - 28 M. Project Management, Temporary Office, Onshore Engineering KHI |  |  |  | 188088391522.5 | 5.497% | 0.2159% | 0.1188% | 0.146% | 0.3627% | 0.1615% | 0.9231% | 0.3706% | 0.6446% | 0.421% | 0.1821% | 0.1564% | 0.09286% | 0.09212% | 0.09369% | 0.278% | 0.08214% | 0.08214% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.074%
0%
A2 |  | 0 |  | 100% | 55999831545 | 1.637% | 2017-02-15: 0.05456%; 2017-03-17: 0.05456%; 2017-04-16: 0.05456%; 2017-05-16: 0.05456%; 2017-06-15: 0.05456%; 2017-07-15: 0.05456%; 2017-08-14: 0.05456%; 2017-09-13: 0.05456%; 2017-10-13: 0.05456%; 2017-11-12: 0.05456%; 2017-12-12: 0.05456%; 2018-01-11: 0.05456%; 2018-02-10: 0.05456%; 2018-03-12: 0.05456%; 2018-04-11: 0.05456%; 2018-05-11: 0.05456%; 2018-06-10: 0.08214% | 0.6816%
0%
A5 | GENR1010 | Temporary Office for Contractor, Barak Pekerja, Temporary Warehouse, & Water for Construction |  | 100% | 65838481275 | 1.924% | 2017-02-15: 0.00641%; 2017-03-17: 0.04875%; 2017-04-16: 0.02758%; 2017-05-16: 0.06607%; 2017-06-15: 0.02758%; 2017-07-15: 0.5568%; 2017-08-14: 0.02758%; 2017-09-13: 0.3441%; 2017-10-13: 0.02758%; 2017-11-12: 0.02758%; 2017-12-12: 0.02792%; 2018-01-11: 0.03302%; 2018-02-10: 0.02758%; 2018-03-12: 0.03913%; 2018-04-11: 0.2229%; 2018-05-11: 0.02758% | 0.3862%
0%
A17 |  | 0 |  | 100% | 66250078702.5 | 1.936% | 2017-02-15: 0.1549%; 2017-03-17: 0.01549%; 2017-04-16: 0.0639%; 2017-05-16: 0.242%; 2017-06-15: 0.07939%; 2017-07-15: 0.3117%; 2017-08-14: 0.2885%; 2017-09-13: 0.2459%; 2017-10-13: 0.3389%; 2017-11-12: 0.09992%; 2017-12-12: 0.07393%; 2018-01-11: 0.00528%; 2018-02-10: 0.00998%; 2018-03-12: 0%; 2018-04-11: 0.00058% | 0.005877%
0%
0%
| P3FH - 28 M. Procurement (Including Transportation) |  |  |  | 2.499e+12 | 73.04% | 3.314% | 0.8266% | 2.515% | 0.1467% | 1.085% | 0.9903% | 2.239% | 4.002% | 1.74% | 3.767% | 6.01% | 2.89% | 5.955% | 6.751% | 4.15% | 2.001% | 5.434% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 19.22%
| P3FH - 28 M. Civil |  |  |  | 436644995640.0001 | 12.76% | 0.6161% | 0.6701% | 1.866% | 0% | 0.5677% | 0.6224% | 0.546% | 3.13% | 0.6334% | 0% | 0% | 0% | 0.413% | 0.1967% | 0.3482% | 0.2691% | 5.434% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -2.551%
| P3FH - 28 M.13.13.1.3 Batching Plant kap.60m3/h @1 unit | [5 empty] | 2018-06-10: 5.434% | -5.434%
| PRWC2130 | BATCHING PLANT - RFQ | [34 empty] | 0%
| PRWC2140 | BATCHING PLANT - Received of Bids | [34 empty] | 0%
| PRWC2150 | BATCHING PLANT - TBE | [34 empty] | 0%
| PRWC2160 | BATCHING PLANT - CBE | [34 empty] | 0%
| PRWC2170 | BATCHING PLANT - LOI | [34 empty] | 0%
| PRWC2180 | BATCHING PLANT - PO | [34 empty] | 0%
| PRWC2190 | BATCHING PLANT - Eq. Preparation | [34 empty] | 0%
| PRWC2200 | BATCHING PLANT - Delivery to Site | [34 empty] | 0%
| P3FH - 28 M.13.13.1.13.1.1 System 1 - Ore Preparation | [35 empty] | 0%
C46 | P3FH - 28 M.13.13.1.13.1.1.1 Piles | [35 empty] | 0%
| PRWC1120 | SYSTEM 1 - PILES - Received of Bids | [34 empty] | 0%
| PRWC1140 | SYSTEM 1 - PILES - CBE | [34 empty] | 0%
| PRWC1150 | SYSTEM 1 - PILES - LOI | [34 empty] | 0%
| PRWC1160 | SYSTEM 1 - PILES - PO | [34 empty] | 0%
|  |  |  | 20% | 285688987.5 | 0.00835% | 2017-02-15: 0.00835% | 0%
|  |  |  | 20% | 1271743672.5 | 0.03717% | 2017-03-17: 0.03717% | 0%
|  |  |  | 20% | 175861245 | 0.00514% | 2017-02-15: 0.00514% | 0%
|  |  |  | 20% | 369513900 | 0.0108% | 2017-02-15: 0.0108% | 0%
|  |  |  | 20% | 1628256157.5 | 0.04759% | 2017-02-15: 0.04759% | 0%
|  |  |  | 20% | 333588937.5 | 0.00975% | 2017-02-15: 0.00975% | 0%
|  |  |  | 20% | 1391493547.5 | 0.04067% | 2017-02-15: 0.04067% | 0%
0%
|  |  |  | 20% | 440679540 | 0.01288% | 2017-03-17: 0.01289% | -1e-05%
| PRWC1170 | SYSTEM 1 - PILES - Fabrication ( Ex Work ) | [34 empty] | 0%
|  |  |  | 60% | 856724820 | 0.02504% | 2017-02-15: 0.02504% | 0%
|  |  |  | 60% | 3815915302.5 | 0.1115% | 2017-04-16: 0.1115% | 0%
|  |  |  | 60% | 527241592.5 | 0.01541% | 2017-02-15: 0.01541% | 0%
|  |  |  | 60% | 1108199557.5 | 0.03239% | 2017-02-15: 0.03239% | 0%
|  |  |  | 60% | 4884768472.5 | 0.1428% | 2017-02-15: 0.1428% | 0%
|  |  |  | 60% | 1000766812.5 | 0.02925% | 2017-02-15: 0.02925% | 0%
|  |  |  | 60% | 4174480642.5 | 0.122% | 2017-02-15: 0.122% | 0%
0%
|  |  |  | 60% | 1323407190 | 0.03868% | 2017-04-16: 0.03868% | 0%
| PRWC1180 | SYSTEM 1 - PILES - Delivery to Site | [34 empty] | 0%
|  |  |  | 20% | 285688987.5 | 0.00835% | 2017-03-17: 0.00835% | 0%
|  |  |  | 20% | 1271743672.5 | 0.03717% | 2017-06-15: 0.03717% | 0%
|  |  |  | 20% | 175861245 | 0.00514% | 2017-03-17: 0.00513% | 1e-05%
|  |  |  | 20% | 369513900 | 0.0108% | 2017-03-17: 0.0108% | 0%
|  |  |  | 20% | 1628256157.5 | 0.04759% | 2017-03-17: 0.04759% | 0%
|  |  |  | 20% | 333588937.5 | 0.00975% | 2017-03-17: 0.00975% | 0%
|  |  |  | 20% | 1391493547.5 | 0.04067% | 2017-03-17: 0.04067% | 0%
0%
|  |  |  | 20% | 440679540 | 0.01288% | 2017-06-15: 0.01288% | 0%
| PRWC2300 | SYSTEM 1 - PILES - Delivery to Site (1100 & 1200) | [34 empty] | 0%
| PRWC2310 | SYSTEM 1 - PILES - Delivery to Site (1300, 1400, 1500, 1700, 1800) | [34 empty] | 0%
C47 | P3FH - 28 M.13.13.1.13.1.1.2 Reinforcement Bar | [35 empty] | 0%
| PRWC1200 | SYSTEM 1 - REBAR - Received of Bids | [34 empty] | 0%
| PRWC1220 | SYSTEM 1 - REBAR - CBE | [34 empty] | 0%
| PRWC1230 | SYSTEM 1 - REBAR - LOI | [34 empty] | 0%
| PRWC1240 | SYSTEM 1 - REBAR - PO | [34 empty] | 0%
|  |  |  | 20% | 2245481227.5 | 0.06563% | 2017-03-17: 0.06563% | 0%
|  |  |  | 20% | 623041492.5 | 0.01821% | 2017-03-17: 0.01821% | 0%
|  |  |  | 20% | 765714915 | 0.02238% | 2017-03-17: 0.02239% | -1e-05%
|  |  |  | 20% | 291163267.5 | 0.00851% | 2017-03-17: 0.00851% | 0%
|  |  |  | 20% | 2118546360 | 0.06192% | 2017-03-17: 0.06193% | -1e-05%
|  |  |  | 20% | 256949017.5 | 0.00751% | 2017-03-17: 0.00751% | 0%
|  |  |  | 20% | 460865947.5 | 0.01347% | 2017-03-17: 0.01347% | 0%
|  |  |  | 20% | 455049525 | 0.0133% | 2017-03-17: 0.0133% | 0%
|  |  |  | 20% | 391068877.5 | 0.01143% | 2017-03-17: 0.01143% | 0%
|  |  |  | 20% | 247369027.5 | 0.00723% | 2017-03-17: 0.00723% | 0%
|  |  |  | 20% | 203232645 | 0.00594% | 2017-03-17: 0.00594% | 0%
|  |  |  | 20% | 460181662.5 | 0.01345% | 2017-03-17: 0.01345% | 0%
| PRWC1250 | SYSTEM 1 - REBAR - Purchasing (Ex Work) | [34 empty] | 0%
|  |  |  | 60% | 6736785825 | 0.1969% | 2017-04-16: 0.1969% | 0%
|  |  |  | 60% | 1869124477.5 | 0.05463% | 2017-04-16: 0.05463% | 0%
|  |  |  | 60% | 2297486887.5 | 0.06715% | 2017-04-16: 0.06715% | 0%
|  |  |  | 60% | 873831945 | 0.02554% | 2017-04-16: 0.02554% | 0%
|  |  |  | 60% | 6355981222.5 | 0.1858% | 2017-04-16: 0.1858% | 0%
|  |  |  | 60% | 770504910 | 0.02252% | 2017-04-16: 0.02252% | 0%
|  |  |  | 60% | 1382255700 | 0.0404% | 2017-04-16: 0.0404% | 0%
|  |  |  | 60% | 1365148575 | 0.0399% | 2017-04-16: 0.0399% | 0%
|  |  |  | 60% | 1172864490 | 0.03428% | 2017-04-16: 0.03428% | 0%
|  |  |  | 60% | 741764940 | 0.02168% | 2017-04-16: 0.02168% | 0%
|  |  |  | 60% | 610040077.5 | 0.01783% | 2017-04-16: 0.01783% | 0%
|  |  |  | 60% | 1380544987.5 | 0.04035% | 2017-04-16: 0.04035% | 0%
| PRWC1260 | SYSTEM 1 - REBAR - Delivery to Site (25%) | [34 empty] | 0%
| PRWC2320 | SYSTEM 1 - REBAR - Delivery to Site (50%) | [34 empty] | 0%
| PRWC2330 | SYSTEM 1 - REBAR - Delivery to Site (75%) | [34 empty] | 0%
| PRWC2340 | SYSTEM 1 - REBAR - Delivery to Site (100%) | [34 empty] | 0%
|  |  |  | 20% | 2245481227.5 | 0.06563% | 2017-06-15: 0.06563% | 0%
|  |  |  | 20% | 623041492.5 | 0.01821% | 2017-06-15: 0.01821% | 0%
|  |  |  | 20% | 765714915 | 0.02238% | 2017-06-15: 0.02238% | 0%
|  |  |  | 20% | 291163267.5 | 0.00851% | 2017-06-15: 0.00851% | 0%
|  |  |  | 20% | 2118546360 | 0.06192% | 2017-06-15: 0.06192% | 0%
|  |  |  | 20% | 256949017.5 | 0.00751% | 2017-06-15: 0.00751% | 0%
|  |  |  | 20% | 460865947.5 | 0.01347% | 2017-06-15: 0.01347% | 0%
|  |  |  | 20% | 455049525 | 0.0133% | 2017-06-15: 0.0133% | 0%
|  |  |  | 20% | 391068877.5 | 0.01143% | 2017-06-15: 0.01143% | 0%
|  |  |  | 20% | 247369027.5 | 0.00723% | 2017-06-15: 0.00723% | 0%
|  |  |  | 20% | 203232645 | 0.00594% | 2017-06-15: 0.00594% | 0%
|  |  |  | 20% | 460523805 | 0.01346% | 2017-06-15: 0.01346% | 0%
| P3FH - 28 M.13.13.1.13.1.1.4 Special Formwork | [35 empty] | 0%
| PRWC2240 | SYSTEM 1 - SPECIAL FORMWORK - Received of Bids | [34 empty] | 0%
| PRWC2260 | SYSTEM 1 - SPECIAL FORMWORK - CBE | [34 empty] | 0%
| PRWC2270 | SYSTEM 1 - SPECIAL FORMWORK - LOI | [34 empty] | 0%
| PRWC2280 | SYSTEM 1 - SPECIAL FORMWORK - PO | [34 empty] | 0%
| PRWC2290 | SYSTEM 1 - SPECIAL FORMWORK - Delivery to Site (100%) | [34 empty] | 0%
| P3FH - 28 M.13.13.1.13.1.1.5 Concrete Material | [35 empty] | 0%
| PRWC2420 | SYSTEM 1 - CONCRETE MAT'L - Received of Bids | [34 empty] | 0%
| PRWC2430 | SYSTEM 1 - CONCRETE MAT'L - CBE | [34 empty] | 0%
| PRWC2440 | SYSTEM 1 - CONCRETE MAT'L - LOI | [34 empty] | 0%
| PRWC2450 | SYSTEM 1 - CONCRETE MAT'L - PO | [34 empty] | 0%
| PRWC2460 | SYSTEM 1 - CONCRETE MAT'L - Purchasing | [34 empty] | 0%
| PRWC2470 | SYSTEM 1 - CONCRETE MAT'L - Delivery to Site (25%) | [34 empty] | 0%
| PRWC2480 | SYSTEM 1 - CONCRETE MAT'L - Delivery to Site (50%) | [34 empty] | 0%
| PRWC2490 | SYSTEM 1 - CONCRETE MAT'L - Delivery to Site (75%) | [34 empty] | 0%
| PRWC2500 | SYSTEM 1 - CONCRETE MAT'L - Delivery to Site (100%) | [34 empty] | 0%
| P3FH - 28 M.13.13.1.13.1.1.6 Anchoor Bolt | [35 empty] | 0%
| PRWC2510 | SYSTEM 1 - CONCRETE MAT'L - Received of Bids | [34 empty] | 0%
| PRWC2520 | SYSTEM 1 - CONCRETE MAT'L - CBE | [34 empty] | 0%
| PRWC2530 | SYSTEM 1 - CONCRETE MAT'L - LOI | [34 empty] | 0%
| PRWC2540 | SYSTEM 1 - CONCRETE MAT'L - PO | [34 empty] | 0%
| PRWC2550 | SYSTEM 1 - CONCRETE MAT'L - Purchasing | [34 empty] | 0%
| PRWC2560 | SYSTEM 1 - CONCRETE MAT'L - Delivery to Site (25%) | [34 empty] | 0%
| PRWC2570 | SYSTEM 1 - CONCRETE MAT'L - Delivery to Site (50%) | [34 empty] | 0%
| PRWC2580 | SYSTEM 1 - CONCRETE MAT'L - Delivery to Site (75%) | [34 empty] | 0%
| PRWC2590 | SYSTEM 1 - CONCRETE MAT'L - Delivery to Site (100%) | [34 empty] | 0%
C48 | P3FH - 28 M.13.13.1.13.1.1.3 Steel Structure & Roof Siding | [35 empty] | 0%
| PRWC1280 | SYSTEM 1 - SS - Received of Bids | [34 empty] | 0%
| PRWC1300 | SYSTEM 1 - SS - CBE | [34 empty] | 0%
| PRWC1310 | SYSTEM 1 - SS - LOI | [34 empty] | 0%
| PRWC1320 | SYSTEM 1 - SS - PO | [34 empty] | 0%
|  | Raw Ore Storage |  | 20% | 3895634505 | 0.1139% | 2017-07-15: 0.05692% | 0.05694%
|  | Ore Drying Equipment & Ore Sizing Equipment |  | 20% | 1882468035 | 0.05502% | 2017-07-15: 0.02751% | 0.02751%
|  | Conditioned Ore Storage |  | 20% | 1576934782.5 | 0.04609% | 2017-07-15: 0.02304% | 0.02305%
|  | Ore Mixing Equipment & Dust Treatment Equipment |  | 20% | 2532880927.5 | 0.07403% | 2017-07-15: 0.03701% | 0.03701%
|  | Rotary Kiln & Exhaust Gas Treatment Equipment |  | 20% | 5990230890 | 0.1751% | 2017-07-15: 0.08754% | 0.08754%
|  | Coal Firing Equipment |  | 20% | 1306642207.5 | 0.03819% | 2017-07-15: 0.0191% | 0.0191%
|  | Fuel Coal Storage |  | 20% | 1413048525 | 0.0413% | 2017-07-15: 0.02065% | 0.02065%
|  | Reductant Coal Storage |  | 20% | 1501321290 | 0.04388% | 2017-07-15: 0.02194% | 0.02194%
|  | Belt Conveyor / Transfer Towe, Girder & Support. |  | 20% | 3428952135 | 0.1002% | 2017-07-15: 0.05011% | 0.05011%
| PRWC1330 | SYSTEM 1 - SS - Fabrication | [34 empty] | 0%
|  | Raw Ore Storage |  | 60% | 11686561372.5 | 0.3416% | 2017-09-13: 0.1423%; 2018-02-10: 0.04981%; 2018-04-11: 0.1036%; 2018-05-11: 0.05978% | -0.01395%
|  | Ore Drying Equipment & Ore Sizing Equipment |  | 60% | 5647061962.5 | 0.1651% | 2017-09-13: 0.06877% | 0.09628%
|  | Conditioned Ore Storage |  | 60% | 4730804347.5 | 0.1383% | 2017-09-13: 0.05761%; 2018-02-10: 0.03514%; 2018-03-12: 0.05104%; 2018-04-11: 0.02765%; 2018-05-11: 0.02673% | -0.0599%
|  | Ore Mixing Equipment & Dust Treatment Equipment |  | 60% | 7598984925 | 0.2221% | 2017-09-13: 0.09254% | 0.1296%
|  | Rotary Kiln & Exhaust Gas Treatment Equipment |  | 60% | 17970350527.5 | 0.5252% | 2017-09-13: 0.2188%; 2018-05-11: 0.04384% | 0.2625%
|  | Coal Firing Equipment |  | 60% | 3919584480 | 0.1146% | 2017-09-13: 0.04773% | 0.06683%
|  | Fuel Coal Storage |  | 60% | 4239145575 | 0.1239% | 2017-09-13: 0.05163%; 2018-02-10: 0.08534%; 2018-03-12: 0.0431%; 2018-04-11: 0.00578% | -0.06195%
|  | Reductant Coal Storage |  | 60% | 4503621727.5 | 0.1316% | 2017-09-13: 0.05485%; 2018-02-10: 0.09066%; 2018-03-12: 0.04579%; 2018-04-11: 0.00614% | -0.06581%
|  | Belt Conveyor / Transfer Towe, Girder & Support. |  | 60% | 10288224975 | 0.3007% | 2017-09-13: 0.1253%; 2018-05-11: 0.00495% | 0.1705%
| PRWC1340 | SYSTEM 1 - SS - 1st Shipment Delivery (1100,1810,1410) | [34 empty] | 0%
| PRWC1600 | SYSTEM 1 - SS - 2nd Shipment Delivery (1300) | [34 empty] | 0%
| PRWC1610 | SYSTEM 1 - SS - 3rd Shipment Delivery (1400,1700) | [34 empty] | 0%
| PRWC1620 | SYSTEM 1 - SS - 4th Shipment Delivery (1200,1500,1600,1820) | [34 empty] | 0%
|  | Raw Ore Storage |  | 20% | 3895634505 | 0.1139% | [30 empty] | 0.1139%
|  | Ore Drying Equipment & Ore Sizing Equipment |  | 20% | 1882468035 | 0.05502% | [30 empty] | 0.05502%
|  | Conditioned Ore Storage |  | 20% | 1576934782.5 | 0.04609% | [30 empty] | 0.04609%
|  | Ore Mixing Equipment & Dust Treatment Equipment |  | 20% | 2532880927.5 | 0.07403% | [30 empty] | 0.07403%
|  | Rotary Kiln & Exhaust Gas Treatment Equipment |  | 20% | 5990230890 | 0.1751% | [30 empty] | 0.1751%
|  | Coal Firing Equipment |  | 20% | 1306642207.5 | 0.03819% | [30 empty] | 0.03819%
|  | Fuel Coal Storage |  | 20% | 1413048525 | 0.0413% | [30 empty] | 0.0413%
|  | Reductant Coal Storage |  | 20% | 1501321290 | 0.04388% | [30 empty] | 0.04388%
|  | Belt Conveyor / Transfer Towe, Girder & Support. |  | 20% | 3428952135 | 0.1002% | [30 empty] | 0.1002%
| P3FH - 28 M.13.13.1.13.1.2 System 2 - Electric Smelting Furnace | [35 empty] | 0%
C85 | P3FH - 28 M.13.13.1.13.1.2.1 Piles | [35 empty] | 0%
| PRWC1370 | SYSTEM 2 - PILES - Received of Bids | [34 empty] | 0%
| PRWC1390 | SYSTEM 2 - PILES - CBE | [34 empty] | 0%
| PRWC1400 | SYSTEM 2 - PILES - LOI | [34 empty] | 0%
| PRWC1410 | SYSTEM 2 - PILES - PO | [34 empty] | 0%
|  |  |  | 20% | 2236585522.5 | 0.06537% | 2017-04-16: 0.06537% | 0%
|  |  |  | 20% | 483789495 | 0.01414% | 2017-04-16: 0.01414% | 0%
|  |  |  | 20% | 264134010 | 0.00772% | 2017-02-15: 0.00772% | 0%
| PRWC1420 | SYSTEM 2 - PILES - Fabrication (Ex Work) | [34 empty] | 0%
|  |  |  | 60% | 6709072282.5 | 0.1961% | 2017-04-16: 0.1961% | 0%
|  |  |  | 60% | 1451710627.5 | 0.04243% | 2017-04-16: 0.04243% | 0%
|  |  |  | 60% | 792059887.5 | 0.02315% | 2017-02-15: 0.02315% | 0%
| PRWC1430 | SYSTEM 2 - PILES - Delivery to Site | [34 empty] | 0%
|  |  |  | 20% | 2236585522.5 | 0.06537% | 2017-06-15: 0.02849% | 0.03688%
|  |  |  | 20% | 483789495 | 0.01414% | 2017-06-15: 0.01414% | 0%
|  |  |  | 20% | 264134010 | 0.00772% | 2017-03-17: 0.00771%; 2017-09-13: 0.03688% | -0.03687%
0%
C86 | P3FH - 28 M.13.13.1.13.1.2.2 Reinforcement Bar | [35 empty] | 0%
| PRWC1450 | SYSTEM 2 - REBAR - Received of Bids | [34 empty] | 0%
| PRWC1470 | SYSTEM 2 - REBAR - CBE | [34 empty] | 0%
| PRWC1480 | SYSTEM 2 - REBAR - LOI | [34 empty] | 0%
| PRWC1490 | SYSTEM 2 - REBAR - PO | [34 empty] | 0%
|  |  |  | 20% | 1297404360 | 0.03792% | 2017-03-17: 0.03792% | 0%
|  |  |  | 20% | 169702680 | 0.00496% | 2017-03-17: 0.00495% | 1e-05%
|  |  |  | 20% | 15054270 | 0.00044% | 2017-03-17: 0.00044% | 0%
|  |  |  | 20% | 24634260 | 0.00072% | 2017-03-17: 0.00071% | 1e-05%
|  |  |  | 20% | 4789995 | 0.00014% | 2017-03-17: 0.00014% | 0%
|  |  |  | 20% | 2394997.5 | 7e-05% | 2017-03-17: 7e-05% | 0%
|  |  |  | 20% | 244289745 | 0.00714% | 2017-03-17: 0.00715% | -1e-05%
|  |  |  | 20% | 2737140 | 8e-05% | 2017-03-17: 8e-05% | 0%
|  |  |  | 20% | 15054270 | 0.00044% | 2017-03-17: 0.00043% | 1e-05%
|  |  |  | 20% | 4789995 | 0.00014% | 2017-03-17: 0.00013% | 1e-05%
|  |  |  | 20% | 23949975 | 0.0007% | 2017-03-17: 0.00071% | -1e-05%
|  |  |  | 20% | 246342600 | 0.0072% | 2017-03-17: 0.0072% | 0%
|  |  |  | 20% | 7184992.5 | 0.00021% | 2017-09-13: 0.00021% | 0%
|  |  |  | 20% | 10264275 | 0.0003% | 2017-09-13: 0.0003% | 0%
|  |  |  | 20% | 3079282.5 | 9e-05% | 2017-09-13: 9e-05% | 0%
|  |  |  | 20% | 4105710 | 0.00012% | 2017-03-17: 0.00013% | -1e-05%
| PRWC1500 | SYSTEM 2 - REBAR - Purchasing (Ex Work) | [34 empty] | 0%
|  |  |  | 60% | 3891870937.5 | 0.1138% | 2017-04-16: 0.1138% | 0%
|  |  |  | 60% | 508765897.5 | 0.01487% | 2017-04-16: 0.01487% | 0%
|  |  |  | 60% | 45504952.5 | 0.00133% | 2017-04-16: 0.00133% | 0%
|  |  |  | 60% | 73560637.5 | 0.00215% | 2017-04-16: 0.00215% | 0%
|  |  |  | 60% | 14027842.5 | 0.00041% | 2017-04-16: 0.00041% | 0%
|  |  |  | 60% | 6842850 | 0.0002% | 2017-04-16: 0.0002% | 0%
|  |  |  | 60% | 733211377.5 | 0.02143% | 2017-04-16: 0.02143% | 0%
|  |  |  | 60% | 8553562.5 | 0.00025% | 2017-04-16: 0.00024% | 1e-05%
|  |  |  | 60% | 44820667.5 | 0.00131% | 2017-04-16: 0.00131% | 0%
|  |  |  | 60% | 14027842.5 | 0.00041% | 2017-04-16: 0.00041% | 0%
|  |  |  | 60% | 72192067.5 | 0.00211% | 2017-04-16: 0.00211% | 0%
|  |  |  | 60% | 738685657.5 | 0.02159% | 2017-04-16: 0.02159% | 0%
|  |  |  | 60% | 21897120 | 0.00064% | 2017-09-13: 0.00065% | -1e-05%
|  |  |  | 60% | 31134967.5 | 0.00091% | 2017-09-13: 0.00092% | -1e-05%
|  |  |  | 60% | 8895705 | 0.00026% | 2017-09-13: 0.00026% | 0%
|  |  |  | 60% | 13343557.5 | 0.00039% | 2017-04-16: 0.00039% | 0%
| PRWC1510 | SYSTEM 2 - REBAR - Delivery to Site (25%) | [34 empty] | 0%
| PRWC2350 | SYSTEM 2 - REBAR - Delivery to Site (50%) | [34 empty] | 0%
| PRWC2360 | SYSTEM 2 - REBAR - Delivery to Site (75%) | [34 empty] | 0%
| PRWC2370 | SYSTEM 2 - REBAR - Delivery to Site (100%) | [34 empty] | 0%
|  |  |  | 20% | 1297267503 | 0.03792% | 2017-06-15: 0.03792% | 0%
|  |  |  | 20% | 169634251.5 | 0.004958% | 2017-06-15: 0.004958% | 0%
|  |  |  | 20% | 15191127 | 0.000444% | 2017-06-15: 0.000444% | 0%
|  |  |  | 20% | 24565831.5 | 0.000718% | 2017-06-15: 0.000718% | 0%
|  |  |  | 20% | 4721566.5 | 0.000138% | 2017-06-15: 0.000138% | 0%
|  |  |  | 20% | 2258140.5 | 6.6e-05% | 2017-06-15: 6.6e-05% | 0%
|  |  |  | 20% | 244358173.5 | 0.007142% | 2017-06-15: 0.007142% | 0%
|  |  |  | 20% | 2805568.5 | 8.2e-05% | 2017-06-15: 8.2e-05% | 0%
|  |  |  | 20% | 14917413 | 0.000436% | 2017-06-15: 0.000436% | 0%
|  |  |  | 20% | 4653138 | 0.000136% | 2017-06-15: 0.000136% | 0%
|  |  |  | 20% | 24018403.5 | 0.000702% | 2017-06-15: 0.000702% | 0%
|  |  |  | 20% | 246274171.5 | 0.007198% | 2017-06-15: 0.007198% | 0%
|  |  |  | 20% | 7321849.5 | 0.000214% | 2017-08-14: 0.000214% | 0%
|  |  |  | 20% | 10332703.5 | 0.000302% | 2017-08-14: 0.000302% | 0%
|  |  |  | 20% | 3010854 | 8.8e-05% | 2017-08-14: 8.8e-05% | 0%
|  |  |  | 20% | 4447852.5 | 0.00013% | 2017-06-15: 0.00013% | 0%
| P3FH - 28 M.13.13.1.13.1.2.4 Common Formwork | [35 empty] | 0%
| PRWC2600 | SYSTEM 2 - COMMON FORMWORK - Received of Bids | [34 empty] | 0%
| PRWC2610 | SYSTEM 2 - COMMON FORMWORK - CBE | [34 empty] | 0%
| PRWC2620 | SYSTEM 2 - COMMON FORMWORK - LOI | [34 empty] | 0%
| PRWC2630 | SYSTEM 2 - COMMON FORMWORK - PO | [34 empty] | 0%
| PRWC2640 | SYSTEM 2 - COMMON FORMWORK - Purchasing | [34 empty] | 0%
| PRWC2650 | SYSTEM 2 - COMMON FORMWORK - Delivery to Site (25%) | [34 empty] | 0%
| PRWC2660 | SYSTEM 2 - COMMON FORMWORK - Delivery to Site (50%) | [34 empty] | 0%
| PRWC2670 | SYSTEM 2 - COMMON FORMWORK - Delivery to Site (75%) | [34 empty] | 0%
| PRWC2680 | SYSTEM 2 - COMMON FORMWORK - Delivery to Site (100%) | [34 empty] | 0%
| P3FH - 28 M.13.13.1.13.1.2.5 Concrete Material | [35 empty] | 0%
| PRWC2690 | SYSTEM 2 - CONCRETE MAT'L - Received of Bids | [34 empty] | 0%
| PRWC2700 | SYSTEM 2 - CONCRETE MAT'L - CBE | [34 empty] | 0%
| PRWC2710 | SYSTEM 2 - CONCRETE MAT'L - LOI | [34 empty] | 0%
| PRWC2720 | SYSTEM 2 - CONCRETE MAT'L - PO | [34 empty] | 0%
| PRWC2730 | SYSTEM 2 - CONCRETE MAT'L - Purchasing | [34 empty] | 0%
| PRWC2740 | SYSTEM 2 - CONCRETE MAT'L - Delivery to Site (25%) | [34 empty] | 0%
| PRWC2750 | SYSTEM 2 - CONCRETE MAT'L - Delivery to Site (50%) | [34 empty] | 0%
| PRWC2760 | SYSTEM 2 - CONCRETE MAT'L - Delivery to Site (75%) | [34 empty] | 0%
| PRWC2770 | SYSTEM 2 - CONCRETE MAT'L - Delivery to Site (100%) | [34 empty] | 0%
| P3FH - 28 M.13.13.1.13.1.2.6 Anchoor Bolt | [35 empty] | 0%
| PRWC2780 | SYSTEM 2 - REBAR - Received of Bids | [34 empty] | 0%
| PRWC2790 | SYSTEM 2 - REBAR - CBE | [34 empty] | 0%
| PRWC2800 | SYSTEM 2 - REBAR - LOI | [34 empty] | 0%
| PRWC2810 | SYSTEM 2 - REBAR - PO | [34 empty] | 0%
| PRWC2820 | SYSTEM 2 - REBAR - Purchasing | [34 empty] | 0%
| PRWC2830 | SYSTEM 2 - REBAR - Delivery to Site (25%) | [34 empty] | 0%
| PRWC2840 | SYSTEM 2 - REBAR - Delivery to Site (50%) | [34 empty] | 0%
| PRWC2850 | SYSTEM 2 - REBAR - Delivery to Site (75%) | [34 empty] | 0%
| PRWC2860 | SYSTEM 2 - REBAR - Delivery to Site (100%) | [34 empty] | 0%
C87 | P3FH - 28 M.13.13.1.13.1.2.3 Steel Structure & Roof Siding | [35 empty] | 0%
| PRWC1530 | SYSTEM 2 - SS - Received of Bids | [34 empty] | 0%
| PRWC1550 | SYSTEM 2 - SS - CBE | [34 empty] | 0%
| PRWC1560 | SYSTEM 2 - SS - LOI | [34 empty] | 0%
| PRWC1570 | SYSTEM 2 - SS - PO | [34 empty] | 0%
|  |  |  | 20% | 8464605450 | 0.2474% | 2017-07-15: 0.1237% | 0.1237%
|  |  |  | 20% | 447522390 | 0.01308% | 2017-07-15: 0.00654% | 0.00654%
|  |  |  | 20% | 26687115 | 0.00078% | 2017-07-15: 0.00039% | 0.00039%
|  |  |  | 20% | 36267105 | 0.00106% | 2017-07-15: 0.00053% | 0.00053%
|  |  |  | 20% | 48584235 | 0.00142% | 2017-07-15: 0.00071% | 0.00071%
|  |  |  | 20% | 129672007.5 | 0.00379% | 2017-07-15: 0.001895% | 0.001895%
|  |  |  | 20% | 198442650 | 0.0058% | 2017-07-15: 0.0029% | 0.0029%
|  |  |  | 20% | 71849925 | 0.0021% | 2017-07-15: 0.00105% | 0.00105%
|  |  |  | 20% | 22581405 | 0.00066% | 2017-07-15: 0.00033% | 0.00033%
| PRWC1580 | SYSTEM 2 - SS - Fabrication | [34 empty] | 0%
|  | ESF Building |  | 60% | 25393816350 | 0.7422% | 2017-10-13: 0.3093%; 2018-02-10: 0.0018%; 2018-03-12: 0.01539%; 2018-04-11: 0.1421%; 2018-05-11: 0.05771% | 0.216%
|  |  |  | 60% | 1342225027.5 | 0.03923% | 2017-10-13: 0.01635% | 0.02288%
|  |  |  | 60% | 80403487.5 | 0.00235% | 2017-10-13: 0.00098% | 0.00137%
|  |  |  | 60% | 109143457.5 | 0.00319% | 2017-10-13: 0.00133% | 0.00186%
|  |  |  | 60% | 145752705 | 0.00426% | 2017-10-13: 0.00178% | 0.00248%
|  |  |  | 60% | 388673880 | 0.01136% | 2017-10-13: 0.00473% | 0.00663%
|  |  |  | 60% | 594985807.5 | 0.01739% | 2017-10-13: 0.00725% | 0.01014%
|  |  |  | 60% | 215891917.5 | 0.00631% | 2017-10-13: 0.00263% | 0.00368%
|  |  |  | 60% | 67402072.5 | 0.00197% | 2017-10-13: 0.00082% | 0.00115%
| PRWC1590 | SYSTEM 2 - SS - Delivery to SIte (up to SS GL 1+11.0m & Main Aisle) | [34 empty] | 0%
| PRWC2210 | SYSTEM 2 - SS - Delivery to SIte (GL 1+19.8m s.d GL 1+27.3m include Roof & Siding) | [34 empty] | 0%
|  |  |  | 20% | 8464605450 | 0.2474% | [30 empty] | 0.2474%
|  |  |  | 20% | 447522390 | 0.01308% | [30 empty] | 0.01308%
|  |  |  | 20% | 26687115 | 0.00078% | [30 empty] | 0.00078%
|  |  |  | 20% | 36267105 | 0.00106% | [30 empty] | 0.00106%
|  |  |  | 20% | 48584235 | 0.00142% | [30 empty] | 0.00142%
|  |  |  | 20% | 129672007.5 | 0.00379% | [30 empty] | 0.00379%
|  |  |  | 20% | 198442650 | 0.0058% | [30 empty] | 0.0058%
|  |  |  | 20% | 71849925 | 0.0021% | [30 empty] | 0.0021%
|  |  |  | 20% | 22239262.5 | 0.00065% | [30 empty] | 0.00065%
| P3FH - 28 M.13.13.1.13.1.3 System 3 - Refinery | [35 empty] | 0%
C136 | P3FH - 28 M.13.13.1.13.1.3.1 Piles | [35 empty] | 0%
| PRWC1640 | SYSTEM 3 - PILES - Received of Bids | [34 empty] | 0%
| PRWC1660 | SYSTEM 3 - PILES - CBE | [34 empty] | 0%
| PRWC1670 | SYSTEM 3 - PILES - LOI | [34 empty] | 0%
| PRWC1680 | SYSTEM 3 - PILES - PO | [34 empty] | 0%
|  |  |  | 20% | 32161395 | 0.00094% | 2017-02-15: 0.00094% | 0%
|  |  |  | 20% | 157727692.5 | 0.00461% | 2017-03-17: 0.00462% | -1e-05%
| PRWC1690 | SYSTEM 3 - PILES - Fabrication | [34 empty] | 0%
|  |  |  | 60% | 96142042.5 | 0.00281% | 2017-02-15: 0.00281% | 0%
|  |  |  | 60% | 473867362.5 | 0.01385% | 2017-04-16: 0.01386% | -1e-05%
| PRWC1700 | SYSTEM 3 - PILES - Delivery to Site | [34 empty] | 0%
|  |  |  | 20% | 32161395 | 0.00094% | 2017-03-17: 0.00094% | 0%
|  |  |  | 20% | 158069835 | 0.00462% | 2017-06-15: 0.00199%; 2017-09-13: 0.00265% | -2e-05%
C137 | P3FH - 28 M.13.13.1.13.1.3.2 Reinforcement Bar | [35 empty] | 0%
| PRWC1720 | SYSTEM 3 - REBAR - Received of Bids | [34 empty] | 0%
| PRWC1740 | SYSTEM 3 - REBAR - CBE | [34 empty] | 0%
| PRWC1750 | SYSTEM 3 - REBAR - LOI | [34 empty] | 0%
| PRWC1760 | SYSTEM 3 - REBAR - PO | [34 empty] | 0%
|  |  |  | 20% | 45847095 | 0.00134% | 2017-03-17: 0.00134% | 0%
|  |  |  | 20% | 123855585 | 0.00362% | 2017-03-17: 0.00362% | 0%
|  |  |  | 20% | 25318545 | 0.00074% | 2017-03-17: 0.00074% | 0%
|  |  |  | 20% | 210075495 | 0.00614% | 2017-03-17: 0.00614% | 0%
|  |  |  | 20% | 141646995 | 0.00414% | 2017-03-17: 0.00414% | 0%
|  |  |  | 20% | 2737140 | 8e-05% | 2017-03-17: 8e-05% | 0%
|  |  |  | 20% | 3421425 | 0.0001% | 2017-03-17: 0.0001% | 0%
|  |  |  | 20% | 8553562.5 | 0.00025% | 2017-03-17: 0.00025% | 0%
|  |  |  | 20% | 1026427.5 | 3e-05% | 2017-03-17: 3e-05% | 0%
|  |  |  | 20% | 1026427.5 | 3e-05% | 2017-03-17: 3e-05% | 0%
|  |  |  | 20% | 2052855 | 6e-05% | 2017-03-17: 6e-05% | 0%
|  |  |  | 20% | 3763567.5 | 0.00011% | 2017-03-17: 0.00011% | 0%
| PRWC1770 | SYSTEM 3 - REBAR - Purchase | [34 empty] | 0%
|  |  |  | 60% | 137883427.5 | 0.00403% | 2017-04-16: 0.00403% | 0%
|  |  |  | 60% | 371224612.5 | 0.01085% | 2017-04-16: 0.01085% | 0%
|  |  |  | 60% | 75613492.5 | 0.00221% | 2017-04-16: 0.00221% | 0%
|  |  |  | 60% | 630568627.5 | 0.01843% | 2017-04-16: 0.01843% | 0%
|  |  |  | 60% | 425283127.5 | 0.01243% | 2017-04-16: 0.01243% | 0%
|  |  |  | 60% | 7869277.5 | 0.00023% | 2017-04-16: 0.00023% | 0%
|  |  |  | 60% | 9922132.5 | 0.00029% | 2017-04-16: 0.00029% | 0%
|  |  |  | 60% | 26002830 | 0.00076% | 2017-04-16: 0.00075% | 1e-05%
|  |  |  | 60% | 3421425 | 0.0001% | 2017-04-16: 0.0001% | 0%
|  |  |  | 60% | 3079282.5 | 9e-05% | 2017-04-16: 9e-05% | 0%
|  |  |  | 60% | 6158565 | 0.00018% | 2017-04-16: 0.00018% | 0%
|  |  |  | 60% | 11290702.5 | 0.00033% | 2017-04-16: 0.00033% | 0%
| PRWC1780 | SYSTEM 3 - REBAR - Delivery to Site (50%) | [34 empty] | 0%
| PRWC2380 | SYSTEM 3 - REBAR - Delivery to Site (100%) | [34 empty] | 0%
|  |  |  | 20% | 45847095 | 0.00134% | 2017-06-15: 0.00134% | 0%
|  |  |  | 20% | 123855585 | 0.00362% | 2017-06-15: 0.00362% | 0%
|  |  |  | 20% | 25318545 | 0.00074% | 2017-06-15: 0.00074% | 0%
|  |  |  | 20% | 210075495 | 0.00614% | 2017-06-15: 0.00614% | 0%
|  |  |  | 20% | 141646995 | 0.00414% | 2017-06-15: 0.00414% | 0%
|  |  |  | 20% | 2737140 | 8e-05% | 2017-06-15: 8e-05% | 0%
|  |  |  | 20% | 3421425 | 0.0001% | 2017-06-15: 0.0001% | 0%
|  |  |  | 20% | 8553562.5 | 0.00025% | 2017-06-15: 0.00025% | 0%
|  |  |  | 20% | 1026427.5 | 3e-05% | 2017-06-15: 3e-05% | 0%
|  |  |  | 20% | 1026427.5 | 3e-05% | 2017-06-15: 3e-05% | 0%
|  |  |  | 20% | 2052855 | 6e-05% | 2017-06-15: 6e-05% | 0%
|  |  |  | 20% | 3763567.5 | 0.00011% | 2017-06-15: 0.00011% | 0%
| P3FH - 28 M.13.13.1.13.1.3.4 Common Formwork | [35 empty] | 0%
| PRWC2870 | SYSTEM 3 - COMMON FORMWORK - Received of Bids | [34 empty] | 0%
| PRWC2880 | SYSTEM 3 - COMMON FORMWORK - CBE | [34 empty] | 0%
| PRWC2890 | SYSTEM 3 - COMMON FORMWORK - LOI | [34 empty] | 0%
| PRWC2900 | SYSTEM 3 - COMMON FORMWORK - PO | [34 empty] | 0%
| PRWC2910 | SYSTEM 3 - COMMON FORMWORK - Purchase | [34 empty] | 0%
| PRWC2920 | SYSTEM 3 - COMMON FORMWORK - Delivery to Site (50%) | [34 empty] | 0%
| PRWC2930 | SYSTEM 3 - COMMON FORMWORK - Delivery to Site (100%) | [34 empty] | 0%
| P3FH - 28 M.13.13.1.13.1.3.5 Concrete Material | [35 empty] | 0%
| PRWC2940 | SYSTEM 3 - REBAR - Received of Bids | [34 empty] | 0%
| PRWC2950 | SYSTEM 3 - REBAR - CBE | [34 empty] | 0%
| PRWC2960 | SYSTEM 3 - REBAR - LOI | [34 empty] | 0%
| PRWC2970 | SYSTEM 3 - REBAR - PO | [34 empty] | 0%
| PRWC2980 | SYSTEM 3 - REBAR - Purchase | [34 empty] | 0%
| PRWC2990 | SYSTEM 3 - REBAR - Delivery to Site (50%) | [34 empty] | 0%
| PRWC3000 | SYSTEM 3 - REBAR - Delivery to Site (100%) | [34 empty] | 0%
| P3FH - 28 M.13.13.1.13.1.3.6 Anchoor Bolt | [35 empty] | 0%
| PRWC3010 | SYSTEM 3 - REBAR - Received of Bids | [34 empty] | 0%
| PRWC3020 | SYSTEM 3 - REBAR - CBE | [34 empty] | 0%
| PRWC3030 | SYSTEM 3 - REBAR - LOI | [34 empty] | 0%
| PRWC3040 | SYSTEM 3 - REBAR - PO | [34 empty] | 0%
| PRWC3050 | SYSTEM 3 - REBAR - Purchase | [34 empty] | 0%
| PRWC3060 | SYSTEM 3 - REBAR - Delivery to Site (50%) | [34 empty] | 0%
| PRWC3070 | SYSTEM 3 - REBAR - Delivery to Site (100%) | [34 empty] | 0%
C138 | P3FH - 28 M.13.13.1.13.1.3.3 Steel Structure & Roof Siding | [35 empty] | 0%
| PRWC1800 | SYSTEM 3 - SS - Received of Bids | [34 empty] | 0%
| PRWC1820 | SYSTEM 3 - SS - CBE | [34 empty] | 0%
| PRWC1830 | SYSTEM 3 - SS - LOI | [34 empty] | 0%
| PRWC1840 | SYSTEM 3 - SS - PO | [34 empty] | 0%
|  |  |  | 20% | 280214707.5 | 0.00819% | 2017-07-15: 0.004095% | 0.004095%
|  |  |  | 20% | 1079459587.5 | 0.03155% | 2017-07-15: 0.01578% | 0.01578%
|  |  |  | 20% | 49952805 | 0.00146% | 2017-07-15: 0.00073% | 0.00073%
|  |  |  | 20% | 25318545 | 0.00074% | 2017-07-15: 0.00037% | 0.00037%
| PRWC1850 | SYSTEM 3 - SS - Fabrication | [34 empty] | 0%
|  |  |  | 60% | 840644122.5 | 0.02457% | 2018-02-10: 0.01024% | 0.01433%
|  |  |  | 60% | 3238720905 | 0.09466% | 2018-02-10: 0.03944% | 0.05522%
|  |  |  | 60% | 150200557.5 | 0.00439% | 2018-02-10: 0.00183% | 0.00256%
|  |  |  | 60% | 75613492.5 | 0.00221% | 2018-02-10: 0.00092% | 0.00129%
| PRWC1860 | SYSTEM 3 - SS - Delivery to Site | [34 empty] | 0%
|  |  |  | 20% | 280214707.5 | 0.00819% | [30 empty] | 0.00819%
|  |  |  | 20% | 1079459587.5 | 0.03155% | [30 empty] | 0.03155%
|  |  |  | 20% | 49952805 | 0.00146% | [30 empty] | 0.00146%
|  |  |  | 20% | 25318545 | 0.00074% | [30 empty] | 0.00074%
| P3FH - 28 M.13.13.1.13.1.4 System 4 - Utility Supply | [35 empty] | 0%
C189 | P3FH - 28 M.13.13.1.13.1.4.1 Piles | [35 empty] | 0%
| PRWC1880 | SYSTEM 4 - PILES - Received of Bids | [34 empty] | 0%
| PRWC1900 | SYSTEM 4 - PILES - CBE | [34 empty] | 0%
| PRWC1910 | SYSTEM 4 - PILES - LOI | [34 empty] | 0%
| PRWC1920 | SYSTEM 4 - PILES - PO | [34 empty] | 0%
|  |  |  | 20% | 609355792.5 | 0.01781% | 2017-02-15: 0.01781% | 0%
|  |  |  | 20% | 137541285 | 0.00402% | 2017-02-15: 0.00402% | 0%
|  |  |  | 20% | 267555435 | 0.00782% | 2017-03-17: 0.00782% | 0%
|  |  |  | 20% | 692496420 | 0.02024% | 2017-03-17: 0.02024% | 0%
|  |  |  | 20% | 176203387.5 | 0.00515% | 2017-03-17: 0.00515% | 0%
| PRWC1930 | SYSTEM 4 - PILES - Fabrication | [34 empty] | 0%
|  |  |  | 60% | 1828409520 | 0.05344% | 2017-02-15: 0.05344% | 0%
|  |  |  | 60% | 412281712.5 | 0.01205% | 2017-02-15: 0.01205% | 0%
|  |  |  | 60% | 803008447.5 | 0.02347% | 2017-04-16: 0.02347% | 0%
|  |  |  | 60% | 2076804975 | 0.0607% | 2017-04-16: 0.0607% | 0%
|  |  |  | 60% | 528952305 | 0.01546% | 2017-04-16: 0.01546% | 0%
| PRWC1940 | SYSTEM 4 - PILES - Delivery to Site | [34 empty] | 0%
|  |  |  | 20% | 609355792.5 | 0.01781% | 2017-03-17: 0.01782% | -1e-05%
|  |  |  | 20% | 137541285 | 0.00402% | 2017-03-17: 0.00401% | 1e-05%
|  |  |  | 20% | 267555435 | 0.00782% | 2017-06-15: 0.00782% | 0%
|  |  |  | 20% | 692496420 | 0.02024% | 2017-06-15: 0.02024% | 0%
|  |  |  | 20% | 176203387.5 | 0.00515% | 2017-06-15: 0.00515% | 0%
C169 | P3FH - 28 M.13.13.1.13.1.4.2 Reinforcement Bar | [35 empty] | 0%
| PRWC1960 | SYSTEM 4 - REBAR - Received of Bids | [34 empty] | 0%
| PRWC1980 | SYSTEM 4 - REBAR - CBE | [34 empty] | 0%
| PRWC1990 | SYSTEM 4 - REBAR - LOI | [34 empty] | 0%
| PRWC2000 | SYSTEM 4 - REBAR - PO | [34 empty] | 0%
|  |  |  | 20% | 173466247.5 | 0.00507% | 2017-03-17: 0.00508% | -1e-05%
|  |  |  | 20% | 13685700 | 0.0004% | 2017-03-17: 0.00039% | 1e-05%
|  |  |  | 20% | 17449267.5 | 0.00051% | 2017-03-17: 0.00051% | 0%
|  |  |  | 20% | 229235475 | 0.0067% | 2017-03-17: 0.00669% | 1e-05%
|  |  |  | 20% | 79719202.5 | 0.00233% | 2017-03-17: 0.00233% | 0%
|  |  |  | 20% | 8895705 | 0.00026% | 2017-03-17: 0.00026% | 0%
|  |  |  | 20% | 15738555 | 0.00046% | [30 empty] | 0.00046%
|  |  |  | 20% | 7184992.5 | 0.00021% | 2017-03-17: 0.00021% | 0%
|  |  |  | 20% | 110512027.5 | 0.00323% | 2017-03-17: 0.00322% | 1e-05%
|  |  |  | 20% | 26687115 | 0.00078% | 2017-03-17: 0.00078% | 0%
|  |  |  | 20% | 7184992.5 | 0.00021% | 2017-03-17: 0.00021% | 0%
|  |  |  | 20% | 29082112.5 | 0.00085% | 2017-03-17: 0.00086% | -1e-05%
|  |  |  | 20% | 6500707.5 | 0.00019% | 2017-03-17: 0.00019% | 0%
|  |  |  | 20% | 16422840 | 0.00048% | 2017-03-17: 0.00048% | 0%
|  |  |  | 20% | 43109955 | 0.00126% | 2017-03-17: 0.00126% | 0%
|  |  |  | 20% | 50294947.5 | 0.00147% | 2017-03-17: 0.00147% | 0%
|  |  |  | 20% | 50294947.5 | 0.00147% | 2017-03-17: 0.00148% | -1e-05%
|  |  |  | 20% | 18475695 | 0.00054% | 2017-03-17: 0.00054% | 0%
|  |  |  | 20% | 22923547.5 | 0.00067% | 2017-03-17: 0.00067% | 0%
|  |  |  | 20% | 30108540 | 0.00088% | 2017-03-17: 0.00088% | 0%
|  |  |  | 20% | 30108540 | 0.00088% | 2017-03-17: 0.00088% | 0%
|  |  |  | 20% | 80403487.5 | 0.00235% | 2017-03-17: 0.00235% | 0%
|  |  |  | 20% | 91009905 | 0.00266% | 2017-03-17: 0.00266% | 0%
|  |  |  | 20% | 118723447.5 | 0.00347% | 2017-03-17: 0.00347% | 0%
|  |  |  | 20% | 63638505 | 0.00186% | 2017-03-17: 0.00186% | 0%
|  |  |  | 20% | 70823497.5 | 0.00207% | 2017-03-17: 0.00207% | 0%
|  |  |  | 20% | 69797070 | 0.00204% | 2017-03-17: 0.00204% | 0%
|  |  |  | 20% | 2161314172.5 | 0.06317% | 2017-08-14: 0.06317% | 0%
|  |  |  | 20% | 465655942.5 | 0.01361% | 2017-08-14: 0.01361% | 0%
|  |  |  | 20% | 832090560 | 0.02432% | 2017-03-17: 0.02432% | 0%
|  |  |  | 20% | 350011777.5 | 0.01023% | 2017-03-17: 0.01023% | 0%
|  |  |  | 20% | 350011777.5 | 0.01023% | 2017-08-14: 0.01023% | 0%
|  |  |  | 20% | 72534210 | 0.00212% | 2017-08-14: 0.00212% | 0%
|  |  |  | 20% | 142331280 | 0.00416% | 2017-03-17: 0.00416% | 0%
|  |  |  | 20% | 142331280 | 0.00416% | 2017-03-17: 0.00416% | 0%
|  |  |  | 20% | 73902780 | 0.00216% | 2017-03-17: 0.00216% | 0%
|  |  |  | 20% | 60901365 | 0.00178% | 2017-03-17: 0.00179% | -1e-05%
|  |  |  | 20% | 7184992.5 | 0.00021% | 2017-08-14: 0.00021% | 0%
|  |  |  | 20% | 14369985 | 0.00042% | 2017-08-14: 0.00042% | 0%
|  |  |  | 20% | 14369985 | 0.00042% | 2017-03-17: 0.00042% | 0%
|  |  |  | 20% | 5816422.5 | 0.00017% | 2017-03-17: 0.00017% | 0%
|  |  |  | 20% | 18133552.5 | 0.00053% | 2017-03-17: 0.00053% | 0%
|  |  |  | 20% | 50979232.5 | 0.00149% | 2017-03-17: 0.00149% | 0%
|  |  |  | 20% | 82798485 | 0.00242% | 2017-03-17: 0.00241% | 1e-05%
|  |  |  | 20% | 79377060 | 0.00232% | 2017-08-14: 0.00232% | 0%
|  |  |  | 20% | 221366197.5 | 0.00647% | 2017-08-14: 0.00647% | 0%
|  |  |  | 20% | 368829615 | 0.01078% | 2017-08-14: 0.01078% | 0%
|  |  |  | 20% | 369513900 | 0.0108% | 2017-08-14: 0.01078% | 2e-05%
| PRWC2010 | SYSTEM 4 - REBAR - Purchase (Ex Work) | [34 empty] | 0%
|  |  |  | 60% | 520740885 | 0.01522% | 2017-04-16: 0.01522% | 0%
|  |  |  | 60% | 40714957.5 | 0.00119% | 2017-04-16: 0.00119% | 0%
|  |  |  | 60% | 52689945 | 0.00154% | 2017-04-16: 0.00153% | 1e-05%
|  |  |  | 60% | 687364282.5 | 0.02009% | 2017-04-16: 0.02009% | 0%
|  |  |  | 60% | 239499750 | 0.007% | 2017-04-16: 0.00699% | 1e-05%
|  |  |  | 60% | 27029257.5 | 0.00079% | 2017-04-16: 0.00079% | 0%
|  |  |  | 60% | 47215665 | 0.00138% | [30 empty] | 0.00138%
|  |  |  | 60% | 21212835 | 0.00062% | 2017-04-16: 0.00062% | 0%
|  |  |  | 60% | 331193940 | 0.00968% | 2017-04-16: 0.00968% | 0%
|  |  |  | 60% | 79719202.5 | 0.00233% | 2017-04-16: 0.00233% | 0%
|  |  |  | 60% | 21212835 | 0.00062% | 2017-04-16: 0.00062% | 0%
|  |  |  | 60% | 87588480 | 0.00256% | 2017-04-16: 0.00256% | 0%
|  |  |  | 60% | 19844265 | 0.00058% | 2017-04-16: 0.00058% | 0%
|  |  |  | 60% | 48926377.5 | 0.00143% | 2017-04-16: 0.00143% | 0%
|  |  |  | 60% | 128987722.5 | 0.00377% | 2017-04-16: 0.00377% | 0%
|  |  |  | 60% | 151226985 | 0.00442% | 2017-04-16: 0.00442% | 0%
|  |  |  | 60% | 151226985 | 0.00442% | 2017-04-16: 0.00442% | 0%
|  |  |  | 60% | 55427085 | 0.00162% | 2017-04-16: 0.00162% | 0%
|  |  |  | 60% | 69112785 | 0.00202% | 2017-04-16: 0.00202% | 0%
|  |  |  | 60% | 90325620 | 0.00264% | 2017-04-16: 0.00264% | 0%
|  |  |  | 60% | 90325620 | 0.00264% | 2017-04-16: 0.00264% | 0%
|  |  |  | 60% | 241552605 | 0.00706% | 2017-04-16: 0.00706% | 0%
|  |  |  | 60% | 273371857.5 | 0.00799% | 2017-04-16: 0.00799% | 0%
|  |  |  | 60% | 356512485 | 0.01042% | 2017-04-16: 0.01042% | 0%
|  |  |  | 60% | 191257657.5 | 0.00559% | 2017-04-16: 0.00559% | 0%
|  |  |  | 60% | 212128350 | 0.0062% | 2017-04-16: 0.0062% | 0%
|  |  |  | 60% | 209391210 | 0.00612% | 2017-04-16: 0.00612% | 0%
|  |  |  | 60% | 6484284660 | 0.1895% | 2017-09-13: 0.1895% | 0%
|  |  |  | 60% | 1397309970 | 0.04084% | 2017-09-13: 0.04083% | 1e-05%
|  |  |  | 60% | 2496613822.5 | 0.07297% | 2017-04-16: 0.07297% | 0%
|  |  |  | 60% | 1050377475 | 0.0307% | 2017-04-16: 0.0307% | 0%
|  |  |  | 60% | 1050377475 | 0.0307% | 2017-09-13: 0.0307% | 0%
|  |  |  | 60% | 217944772.5 | 0.00637% | 2017-09-13: 0.00637% | 0%
|  |  |  | 60% | 427335982.5 | 0.01249% | 2017-04-16: 0.01249% | 0%
|  |  |  | 60% | 427335982.5 | 0.01249% | 2017-04-16: 0.01249% | 0%
|  |  |  | 60% | 221366197.5 | 0.00647% | 2017-04-16: 0.00647% | 0%
|  |  |  | 60% | 183046237.5 | 0.00535% | 2017-04-16: 0.00535% | 0%
|  |  |  | 60% | 21212835 | 0.00062% | 2017-09-13: 0.00063% | -1e-05%
|  |  |  | 60% | 43109955 | 0.00126% | 2017-09-13: 0.00126% | 0%
|  |  |  | 60% | 43109955 | 0.00126% | 2017-04-16: 0.00126% | 0%
|  |  |  | 60% | 17107125 | 0.0005% | 2017-04-16: 0.0005% | 0%
|  |  |  | 60% | 54058515 | 0.00158% | 2017-04-16: 0.00158% | 0%
|  |  |  | 60% | 152595555 | 0.00446% | 2017-04-16: 0.00446% | 0%
|  |  |  | 60% | 248395455 | 0.00726% | 2017-04-16: 0.00726% | 0%
|  |  |  | 60% | 238473322.5 | 0.00697% | 2017-09-13: 0.00697% | 0%
|  |  |  | 60% | 663756450 | 0.0194% | 2017-09-13: 0.0194% | 0%
|  |  |  | 60% | 1106488845 | 0.03234% | 2017-09-13: 0.03234% | 0%
|  |  |  | 60% | 1105462417.5 | 0.03231% | 2017-09-13: 0.03234% | -3e-05%
| PRWC2390 | SYSTEM 4 - REBAR - Delivery to site (40%) | [34 empty] | 0%
| PRWC2400 | SYSTEM 4 - REBAR - Delivery to site (80%) | [34 empty] | 0%
| PRWC2410 | SYSTEM 4 - REBAR - Delivery to site (100%) | [34 empty] | 0%
|  |  |  | 20% | 173466247.5 | 0.00507% | 2017-06-15: 0.00507% | 0%
|  |  |  | 20% | 13685700 | 0.0004% | 2017-06-15: 0.0004% | 0%
|  |  |  | 20% | 17449267.5 | 0.00051% | 2017-06-15: 0.00051% | 0%
|  |  |  | 20% | 229235475 | 0.0067% | 2017-06-15: 0.0067% | 0%
|  |  |  | 20% | 79719202.5 | 0.00233% | 2017-06-15: 0.00233% | 0%
|  |  |  | 20% | 8895705 | 0.00026% | 2017-06-15: 0.00026% | 0%
|  |  |  | 20% | 15738555 | 0.00046% | [30 empty] | 0.00046%
|  |  |  | 20% | 7184992.5 | 0.00021% | 2017-06-15: 0.00021% | 0%
|  |  |  | 20% | 110512027.5 | 0.00323% | 2017-06-15: 0.00323% | 0%
|  |  |  | 20% | 26687115 | 0.00078% | 2017-06-15: 0.00078% | 0%
|  |  |  | 20% | 7184992.5 | 0.00021% | 2017-06-15: 0.00021% | 0%
|  |  |  | 20% | 29082112.5 | 0.00085% | 2017-06-15: 0.00085% | 0%
|  |  |  | 20% | 6500707.5 | 0.00019% | 2017-06-15: 0.00019% | 0%
|  |  |  | 20% | 16422840 | 0.00048% | 2017-06-15: 0.00048% | 0%
|  |  |  | 20% | 43109955 | 0.00126% | 2017-06-15: 0.00126% | 0%
|  |  |  | 20% | 50294947.5 | 0.00147% | 2017-06-15: 0.00147% | 0%
|  |  |  | 20% | 50294947.5 | 0.00147% | 2017-06-15: 0.00147% | 0%
|  |  |  | 20% | 18475695 | 0.00054% | 2017-06-15: 0.00054% | 0%
|  |  |  | 20% | 22923547.5 | 0.00067% | 2017-06-15: 0.00067% | 0%
|  |  |  | 20% | 30108540 | 0.00088% | 2017-06-15: 0.00088% | 0%
|  |  |  | 20% | 30108540 | 0.00088% | 2017-06-15: 0.00088% | 0%
|  |  |  | 20% | 80403487.5 | 0.00235% | 2017-06-15: 0.00235% | 0%
|  |  |  | 20% | 91009905 | 0.00266% | 2017-06-15: 0.00266% | 0%
|  |  |  | 20% | 118723447.5 | 0.00347% | 2017-06-15: 0.00347% | 0%
|  |  |  | 20% | 63638505 | 0.00186% | 2017-06-15: 0.00186% | 0%
|  |  |  | 20% | 70823497.5 | 0.00207% | 2017-06-15: 0.00207% | 0%
|  |  |  | 20% | 69797070 | 0.00204% | 2017-06-15: 0.00204% | 0%
|  |  |  | 20% | 2161314172.5 | 0.06317% | 2017-09-13: 0.06317% | 0%
|  |  |  | 20% | 465655942.5 | 0.01361% | 2017-09-13: 0.01361% | 0%
|  |  |  | 20% | 832090560 | 0.02432% | 2017-06-15: 0.02432% | 0%
|  |  |  | 20% | 350011777.5 | 0.01023% | 2017-06-15: 0.01023% | 0%
|  |  |  | 20% | 350011777.5 | 0.01023% | 2017-09-13: 0.01023% | 0%
|  |  |  | 20% | 72534210 | 0.00212% | 2017-09-13: 0.00212% | 0%
|  |  |  | 20% | 142331280 | 0.00416% | 2017-06-15: 0.00416% | 0%
|  |  |  | 20% | 142331280 | 0.00416% | 2017-06-15: 0.00416% | 0%
|  |  |  | 20% | 73902780 | 0.00216% | 2017-06-15: 0.00216% | 0%
|  |  |  | 20% | 60901365 | 0.00178% | 2017-06-15: 0.00178% | 0%
|  |  |  | 20% | 7184992.5 | 0.00021% | 2017-09-13: 0.00021% | 0%
|  |  |  | 20% | 14369985 | 0.00042% | 2017-09-13: 0.00042% | 0%
|  |  |  | 20% | 14369985 | 0.00042% | 2017-06-15: 0.00042% | 0%
|  |  |  | 20% | 5816422.5 | 0.00017% | 2017-06-15: 0.00017% | 0%
|  |  |  | 20% | 18133552.5 | 0.00053% | 2017-06-15: 0.00053% | 0%
|  |  |  | 20% | 50979232.5 | 0.00149% | 2017-06-15: 0.00149% | 0%
|  |  |  | 20% | 82798485 | 0.00242% | 2017-06-15: 0.00242% | 0%
|  |  |  | 20% | 79377060 | 0.00232% | 2017-09-13: 0.00232% | 0%
|  |  |  | 20% | 221366197.5 | 0.00647% | 2017-09-13: 0.00647% | 0%
|  |  |  | 20% | 368829615 | 0.01078% | 2017-09-13: 0.01078% | 0%
|  |  |  | 20% | 369513900 | 0.0108% | 2017-09-13: 0.01078% | 2e-05%
| P3FH - 28 M.13.13.1.13.1.4.4 Common Formwork | [35 empty] | 0%
| PRWC3090 | SYSTEM 4 - COMMON FORMWORK - Received of Bids | [34 empty] | 0%
| PRWC3110 | SYSTEM 4 - COMMON FORMWORK- CBE | [34 empty] | 0%
| PRWC3120 | SYSTEM 4 - COMMON FORMWORK - LOI | [34 empty] | 0%
| PRWC3130 | SYSTEM 4 - COMMON FORMWORK - PO | [34 empty] | 0%
| PRWC3140 | SYSTEM 4 - COMMON FORMWORK - Purchase | [34 empty] | 0%
| PRWC3150 | SYSTEM 4 - COMMON FORMWORK - Delivery to site (40%) | [34 empty] | 0%
| PRWC3160 | SYSTEM 4 - COMMON FORMWORK- Delivery to site (80%) | [34 empty] | 0%
| PRWC3170 | SYSTEM 4 - COMMON FORMWORK - Delivery to site (100%) | [34 empty] | 0%
| P3FH - 28 M.13.13.1.13.1.4.5 Concrete Material | [35 empty] | 0%
| PRWC3190 | SYSTEM 4 - CONCRETE MAT'L - Received of Bids | [34 empty] | 0%
| PRWC3210 | SYSTEM 4 - CONCRETE MAT'L - CBE | [34 empty] | 0%
| PRWC3220 | SYSTEM 4 - CONCRETE MAT'L - LOI | [34 empty] | 0%
| PRWC3230 | SYSTEM 4 - CONCRETE MAT'L - PO | [34 empty] | 0%
| PRWC3240 | SYSTEM 4 - CONCRETE MAT'L - Purchase | [34 empty] | 0%
| PRWC3250 | SYSTEM 4 - CONCRETE MAT'L - Delivery to site (40%) | [34 empty] | 0%
| PRWC3260 | SYSTEM 4 - CONCRETE MAT'L - Delivery to site (80%) | [34 empty] | 0%
| PRWC3270 | SYSTEM 4 - CONCRETE MAT'L - Delivery to site (100%) | [34 empty] | 0%
| P3FH - 28 M.13.13.1.13.1.4.6 Anchoor Bolt | [35 empty] | 0%
| PRWC3290 | SYSTEM 4 - ANCHOOR BOLT - Received of Bids | [34 empty] | 0%
| PRWC3310 | SYSTEM 4 - ANCHOOR BOLT - CBE | [34 empty] | 0%
| PRWC3320 | SYSTEM 4 - ANCHOOR BOLT - LOI | [34 empty] | 0%
| PRWC3330 | SYSTEM 4 - ANCHOOR BOLT - PO | [34 empty] | 0%
| PRWC3340 | SYSTEM 4 - ANCHOOR BOLT - Purchase | [34 empty] | 0%
| PRWC3350 | SYSTEM 4 - ANCHOOR BOLT - Delivery to site (40%) | [34 empty] | 0%
| PRWC3360 | SYSTEM 4 - ANCHOOR BOLT - Delivery to site (80%) | [34 empty] | 0%
| PRWC3370 | SYSTEM 4 - ANCHOOR BOLT - Delivery to site (100%) | [34 empty] | 0%
C172 | P3FH - 28 M.13.13.1.13.1.4.3 Steel Structure & Roof Siding | [35 empty] | 0%
| PRWC2040 | SYSTEM 4 - SS - Received of Bids | [34 empty] | 0%
| PRWC2060 | SYSTEM 4 - SS - CBE | [34 empty] | 0%
| PRWC2070 | SYSTEM 4 - SS - LOI | [34 empty] | 0%
| PRWC2080 | SYSTEM 4 - SS - PO | [34 empty] | 0%
|  |  |  | 20% | 84851340 | 0.00248% | 2017-07-15: 0.00124% | 0.00124%
|  |  |  | 20% | 27713542.5 | 0.00081% | 2017-07-15: 0.00041% | 0.0004%
|  |  |  | 20% | 61243507.5 | 0.00179% | 2017-07-15: 0.0009% | 0.00089%
|  |  |  | 20% | 26344972.5 | 0.00077% | 2017-07-15: 0.000385% | 0.000385%
|  |  |  | 20% | 1392177832.5 | 0.04069% | 2017-07-15: 0.02035% | 0.02035%
|  |  |  | 20% | 26687115 | 0.00078% | 2017-07-15: 0.00039% | 0.00039%
|  |  |  | 20% | 51663517.5 | 0.00151% | 2017-07-15: 0.000755% | 0.000755%
|  |  |  | 20% | 22239262.5 | 0.00065% | 2017-07-15: 0.000325% | 0.000325%
|  |  |  | 20% | 135146287.5 | 0.00395% | 2017-07-15: 0.001975% | 0.001975%
|  |  |  | 20% | 95115615 | 0.00278% | 2017-07-15: 0.00139% | 0.00139%
|  |  |  | 20% | 520056600 | 0.0152% | 2017-07-15: 0.0076% | 0.0076%
|  |  |  | 20% | 26344972.5 | 0.00077% | 2017-07-15: 0.000385% | 0.000385%
|  |  |  | 20% | 39346387.5 | 0.00115% | 2017-07-15: 0.000575% | 0.000575%
|  |  |  | 20% | 38662102.5 | 0.00113% | 2017-07-15: 0.000565% | 0.000565%
| PRWC2090 | SYSTEM 4 - SS - Fabrication (Ex Work) | [34 empty] | 0%
|  | Oxygen Plant Building |  | 60% | 254211877.5 | 0.00743% | 2017-10-13: 0.0031% | 0.00433%
|  | Pump Room for Water Intake (Wayanof river) |  | 60% | 82798485 | 0.00242% | 2017-10-13: 0.00102% | 0.0014%
|  | Pump Room for Water Intake (sea) |  | 60% | 183388380 | 0.00536% | 2017-10-13: 0.00224% | 0.00312%
|  | Pump Room for MFO/HSD transfer |  | 60% | 79377060 | 0.00232% | 2017-10-13: 0.00097% | 0.00135%
|  | Cable Rack Structure |  | 60% | 4176533497.5 | 0.1221% | 2017-10-13: 0.05086%; 2018-04-11: 0.01773%; 2018-05-11: 0.02991% | 0.02357%
|  |  |  | 60% | 79719202.5 | 0.00233% | 2017-10-13: 0.00097% | 0.00136%
|  |  |  | 60% | 154648410 | 0.00452% | 2017-10-13: 0.00188% | 0.00264%
|  |  |  | 60% | 66375645 | 0.00194% | 2017-10-13: 0.00081% | 0.00113%
|  |  |  | 60% | 405096720 | 0.01184% | 2017-10-13: 0.00494% | 0.0069%
|  |  |  | 60% | 285346845 | 0.00834% | 2017-10-13: 0.00348% | 0.00486%
|  |  |  | 60% | 1560511942.5 | 0.04561% | 2017-10-13: 0.019% | 0.02661%
|  |  |  | 60% | 79377060 | 0.00232% | 2017-10-13: 0.00097% | 0.00135%
|  |  |  | 60% | 118039162.5 | 0.00345% | 2017-10-13: 0.00144% | 0.00201%
|  |  |  | 60% | 117354877.5 | 0.00343% | 2017-10-13: 0.00143% | 0.002%
| PRWC2100 | SYSTEM 4 - SS - Delivery to Site (Head Tank) | [34 empty] | 0%
|  |  |  | 20% | 84851340 | 0.00248% | [30 empty] | 0.00248%
| PRWC2220 | SYSTEM 4 - SS - Delivery to Site (Pipe Rack Structure & Oxygen Plant) | [34 empty] | 0%
|  |  |  | 20% | 84851340 | 0.00248% | [30 empty] | 0.00248%
|  |  |  | 20% | 27713542.5 | 0.00081% | [30 empty] | 0.00081%
|  |  |  | 20% | 61243507.5 | 0.00179% | [30 empty] | 0.00179%
|  |  |  | 20% | 26344972.5 | 0.00077% | [30 empty] | 0.00077%
|  |  |  | 20% | 1392177832.5 | 0.04069% | [30 empty] | 0.04069%
|  |  |  | 20% | 26687115 | 0.00078% | [30 empty] | 0.00078%
|  |  |  | 20% | 51663517.5 | 0.00151% | [30 empty] | 0.00151%
|  |  |  | 20% | 22239262.5 | 0.00065% | [30 empty] | 0.00065%
|  |  |  | 20% | 135146287.5 | 0.00395% | [30 empty] | 0.00395%
|  |  |  | 20% | 95115615 | 0.00278% | [30 empty] | 0.00278%
|  |  |  | 20% | 26344972.5 | 0.00077% | [30 empty] | 0.00077%
|  |  |  | 20% | 39346387.5 | 0.00115% | [30 empty] | 0.00115%
|  |  |  | 20% | 473867362.5 | 0.01385% | [30 empty] | 0.01385%
| P3FH - 28 M.13.13.1.1 Non Process Building | [35 empty] | 0%
| P3FH - 28 M.13.13.1.1.2 Warehouse for Chemical, Mechanical, & Electrical | [35 empty] | 0%
C302 | P3FH - 28 M.13.13.1.1.2.14 Reinforcement Bar | [35 empty] | 0%
| PRWCNOPRCS1010 | WAREHOUSE - REBAR - Received of Bids | [34 empty] | 0%
| PRWCNOPRCS1030 | WAREHOUSE - REBAR - CBE | [34 empty] | 0%
| PRWCNOPRCS1040 | WAREHOUSE - REBAR - LOI | [34 empty] | 0%
| PRWCNOPRCS1050 | WAREHOUSE - REBAR - PO |  | 20% | 59190652.5 | 0.00173% | 2017-08-14: 0.00173% | 0%
| PRWCNOPRCS1060 | WAREHOUSE - REBAR - Purchase |  | 60% | 177229815 | 0.00518% | 2017-09-13: 0.00518% | 0%
| PRWCNOPRCS1070 | WAREHOUSE - REBAR - Delivery to Site |  | 20% | 58848510 | 0.00172% | 2017-09-13: 0.00172% | 0%
| P3FH - 28 M.13.13.1.1.2.1 Common Formwork | [35 empty] | 0%
| PRWCNOPRCS3860 | WAREHOUSE - COMMON FORMWORK - Received of Bids | [34 empty] | 0%
| PRWCNOPRCS3880 | WAREHOUSE - COMMON FORMWORK - CBE | [34 empty] | 0%
| PRWCNOPRCS3890 | WAREHOUSE - COMMON FORMWORK - LOI | [34 empty] | 0%
| PRWCNOPRCS3900 | WAREHOUSE - COMMON FORMWORK - PO | [34 empty] | 0%
| PRWCNOPRCS3910 | WAREHOUSE - COMMON FORMWORK - Purchase | [34 empty] | 0%
| PRWCNOPRCS3920 | WAREHOUSE - COMMON FORMWORK - Delivery to site | [34 empty] | 0%
| P3FH - 28 M.13.13.1.1.2.15 Concrete Material | [35 empty] | 0%
| PRWCNOPRCS2050 | WAREHOUSE - CONCRETE MAT'L - Received of Bids | [34 empty] | 0%
| PRWCNOPRCS2060 | WAREHOUSE - CONCRETE MAT'L - CBE | [34 empty] | 0%
| PRWCNOPRCS2080 | WAREHOUSE - CONCRETE MAT'L - LOI | [34 empty] | 0%
| PRWCNOPRCS2090 | WAREHOUSE - CONCRETE MAT'L - PO | [34 empty] | 0%
| PRWCNOPRCS2100 | WAREHOUSE - CONCRETE MAT'L - Purchase | [34 empty] | 0%
| PRWCNOPRCS2110 | WAREHOUSE - CONCRETE MAT'L - Delivery to site | [34 empty] | 0%
| P3FH - 28 M.13.13.1.1.2.2 Anchoor Bolt | [35 empty] | 0%
| PRWCNOPRCS3940 | WAREHOUSE - ANCHOOR BOLT - Received of Bids | [34 empty] | 0%
| PRWCNOPRCS3960 | WAREHOUSE - ANCHOOR BOLT - CBE | [34 empty] | 0%
| PRWCNOPRCS3970 | WAREHOUSE - ANCHOOR BOLT - LOI | [34 empty] | 0%
| PRWCNOPRCS3980 | WAREHOUSE - ANCHOOR BOLT - PO | [34 empty] | 0%
| PRWCNOPRCS3990 | WAREHOUSE - ANCHOOR BOLT - Purchase | [34 empty] | 0%
| PRWCNOPRCS4000 | WAREHOUSE - ANCHOOR BOLT - Delivery to site | [34 empty] | 0%
C303 | P3FH - 28 M.13.13.1.1.2.16 Steel Structure & Roofing Siding | [35 empty] | 0%
| PRWCNOPRCS3090 | WAREHOUSE - SS - Received of Bids | [34 empty] | 0%
| PRWCNOPRCS3110 | WAREHOUSE - SS - CBE | [34 empty] | 0%
| PRWCNOPRCS3120 | WAREHOUSE - SS - LOI | [34 empty] | 0%
| PRWCNOPRCS3130 | WAREHOUSE - SS - PO |  | 20% | 671625727.5 | 0.01963% | 2017-07-15: 0.009815% | 0.009815%
| PRWCNOPRCS3140 | WAREHOUSE - SS - Fabrication |  | 60% | 2015219325 | 0.0589% | 2017-10-13: 0.02453%; 2018-05-11: 0.00683% | 0.02754%
| PRWCNOPRCS3150 | WAREHOUSE - SS - Delivery to Site (Warehouse Chemical) | [34 empty] | 0%
| PRWCNOPRCS3560 | WAREHOUSE - SS - Delivery to Site (Warehouse Mechanical) | [34 empty] | 0%
| PRWCNOPRCS3570 | WAREHOUSE - SS - Delivery to Site (Warehouse Electrical) |  | 20% | 671625727.5 | 0.01963% | [30 empty] | 0.01963%
| P3FH - 28 M.13.13.1.1.7 Workshops | [35 empty] | 0%
C308 | P3FH - 28 M.13.13.1.1.7.1 Reinforcement Bar | [35 empty] | 0%
| PRWCNOPRCS1170 | WORKSHOP - REBAR - Received of Bids | [34 empty] | 0%
| PRWCNOPRCS1190 | WORKSHOP - REBAR - CBE | [34 empty] | 0%
| PRWCNOPRCS1200 | WORKSHOP - REBAR - LOI | [34 empty] | 0%
| PRWCNOPRCS1210 | WORKSHOP - REBAR - PO |  | 20% | 200495505 | 0.00586% | 2017-08-14: 0.00587% | -1e-05%
| PRWCNOPRCS1220 | WORKSHOP - REBAR - Purchase |  | 60% | 601828657.5 | 0.01759% | 2017-09-13: 0.01759% | 0%
| PRWCNOPRCS1230 | WORKSHOP - REBAR - Delivery to Site |  | 20% | 200837647.5 | 0.00587% | 2017-09-13: 0.00587% | 0%
| P3FH - 28 M.13.13.1.1.7.4 Common Formwork | [35 empty] | 0%
| PRWCNOPRCS4020 | WORKSHOP - COMMON FORMWORK - Received of Bids | [34 empty] | 0%
| PRWCNOPRCS4040 | WORKSHOP - COMMON FORMWORK - CBE | [34 empty] | 0%
| PRWCNOPRCS4050 | WORKSHOP - COMMON FORMWORK - LOI | [34 empty] | 0%
| PRWCNOPRCS4060 | WORKSHOP - COMMON FORMWORK - PO | [34 empty] | 0%
| PRWCNOPRCS4070 | WORKSHOP - COMMON FORMWORK - Purchase | [34 empty] | 0%
| PRWCNOPRCS4080 | WORKSHOP - COMMON FORMWORK - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.1.1.7.2 Concrete Material | [35 empty] | 0%
| PRWCNOPRCS2210 | WORKSHOP - CONCRETE MAT'L - Received of Bids | [34 empty] | 0%
| PRWCNOPRCS2230 | WORKSHOP - CONCRETE MAT'L - CBE | [34 empty] | 0%
| PRWCNOPRCS2240 | WORKSHOP - CONCRETE MAT'L - LOI | [34 empty] | 0%
| PRWCNOPRCS2250 | WORKSHOP - CONCRETE MAT'L - PO | [34 empty] | 0%
| PRWCNOPRCS2260 | WORKSHOP - CONCRETE MAT'L - Purchase | [34 empty] | 0%
| PRWCNOPRCS2270 | WORKSHOP - CONCRETE MAT'L - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.1.1.7.5 Anchoor Bolt | [35 empty] | 0%
| PRWCNOPRCS4100 | WORKSHOP - ANCHOOR BOLT - Received of Bids | [34 empty] | 0%
| PRWCNOPRCS4120 | WORKSHOP - ANCHOOR BOLT - CBE | [34 empty] | 0%
| PRWCNOPRCS4130 | WORKSHOP - ANCHOOR BOLT - LOI | [34 empty] | 0%
| PRWCNOPRCS4140 | WORKSHOP - ANCHOOR BOLT - PO | [34 empty] | 0%
| PRWCNOPRCS4150 | WORKSHOP - ANCHOOR BOLT - Purchase | [34 empty] | 0%
| PRWCNOPRCS4160 | WORKSHOP - ANCHOOR BOLT - Delivery | [34 empty] | 0%
C309 | P3FH - 28 M.13.13.1.1.7.3 Steel Structure & Roofing Siding | [35 empty] | 0%
| PRWCNOPRCS3250 | WORKSHOP - SS - Received of Bids | [34 empty] | 0%
| PRWCNOPRCS3270 | WORKSHOP - SS - CBE | [34 empty] | 0%
| PRWCNOPRCS3280 | WORKSHOP - SS - LOI | [34 empty] | 0%
| PRWCNOPRCS3290 | WORKSHOP - SS - PO |  | 20% | 1395599257.5 | 0.04079% | 2017-07-15: 0.02039% | 0.02039%
| PRWCNOPRCS3300 | WORKSHOP - SS - Fabrication |  | 60% | 4187139915 | 0.1224% | 2017-10-13: 0.05098%; 2018-02-10: 0.01687%; 2018-03-12: 0.02189%; 2018-04-11: 0.02333%; 2018-05-11: 0.0155% | -0.00619%
| PRWCNOPRCS3580 | WAREHOUSE - SS - Delivery to Site (Workshop for Heavy Equipment & Mech. Maintenance) | [34 empty] | 0%
| PRWCNOPRCS3590 | WAREHOUSE - SS - Delivery to Site (Workshop for Fabricant Machinary) | [34 empty] | 0%
| PRWCNOPRCS3600 | WAREHOUSE - SS - Delivery to Site (Workshop for Electrical Maintenance & Control Instrument) |  | 20% | 1395941400 | 0.0408% | [30 empty] | 0.0408%
| P3FH - 28 M.13.13.1.1.1 Administration Building, Laboratory, Fire Station, Weighbridge, Mosque, Gate House | [35 empty] | 0%
C299 | P3FH - 28 M.13.13.1.1.1.1 Reinforcement Bar | [35 empty] | 0%
| PRWCNOPRCS1410 | OFFICE, LABORATORY, MOSQUE, Etc - REBAR - Received of Bids | [34 empty] | 0%
| PRWCNOPRCS1430 | OFFICE, LABORATORY, MOSQUE, Etc - REBAR - CBE | [34 empty] | 0%
| PRWCNOPRCS1440 | OFFICE, LABORATORY, MOSQUE, Etc - REBAR - LOI | [34 empty] | 0%
| PRWCNOPRCS1450 | OFFICE, LABORATORY, MOSQUE, Etc - REBAR - PO |  | 20% | 3669820455 | 0.1073% | 2017-03-17: 0.0078%; 2017-08-14: 0.08319% | 0.01627%
| PRWCNOPRCS1460 | OFFICE, LABORATORY, MOSQUE, Etc - REBAR - Purchase |  | 60% | 8807090092.5 | 0.2574% | 2017-04-16: 0.0234%; 2017-09-13: 0.3327% | -0.09866%
| PRWCNOPRCS1470 | OFFICE, LABORATORY, MOSQUE, Etc - REBAR - Delivery to Site |  | 20% | 2201686987.5 | 0.06435% | 2017-06-15: 0.0078% | 0.05655%
C305 | P3FH - 28 M.13.13.1.1.1.4 Common Formwork | [35 empty] | 0%
| PRWCNOPRCS4180 | OFFICE, LABORATORY, MOSQUE, Etc - FORMWORK - Received of Bids | [34 empty] | 0%
| PRWCNOPRCS4200 | OFFICE, LABORATORY, MOSQUE, Etc - FORMWORK - CBE | [34 empty] | 0%
| PRWCNOPRCS4210 | OFFICE, LABORATORY, MOSQUE, Etc - FORMWORK - LOI | [34 empty] | 0%
| PRWCNOPRCS4220 | OFFICE, LABORATORY, MOSQUE, Etc - FORMWORK - PO |  | 20% | 53032087.5 | 0.00155% | 2017-02-15: 0.00155% | 0%
| PRWCNOPRCS4230 | OFFICE, LABORATORY, MOSQUE, Etc - FORMWORK - Purchase |  | 60% | 127619152.5 | 0.00373% | 2017-02-15: 0.00341% | 0.00032%
| PRWCNOPRCS4240 | OFFICE, LABORATORY, MOSQUE, Etc - FORMWORK - Reinforcement Bar |  | 20% | 31819252.5 | 0.00093% | 2017-03-17: 0.00124% | -0.00031%
| P3FH - 28 M.13.13.1.1.1.2 Concrete Material | [35 empty] | 0%
| PRWCNOPRCS2450 | OFFICE, LABORATORY, MOSQUE, Etc - CONCRETE MAT'L - Received of Bids | [34 empty] | 0%
| PRWCNOPRCS2470 | OFFICE, LABORATORY, MOSQUE, Etc - CONCRETE MAT'L - CBE | [34 empty] | 0%
| PRWCNOPRCS2480 | OFFICE, LABORATORY, MOSQUE, Etc - CONCRETE MAT'L - LOI | [34 empty] | 0%
| PRWCNOPRCS2490 | OFFICE, LABORATORY, MOSQUE, Etc - CONCRETE MAT'L - PO | [34 empty] | 0%
| PRWCNOPRCS2500 | OFFICE, LABORATORY, MOSQUE, Etc - CONCRETE MAT'L - Purchase | [34 empty] | 0%
| PRWCNOPRCS2510 | OFFICE, LABORATORY, MOSQUE, Etc - CONCRETE MAT'L - Reinforcement Bar | [34 empty] | 0%
C300 | P3FH - 28 M.13.13.1.1.1.3 Architectural Material | [35 empty] | 0%
| PRWCNOPRCS3490 | OFFICE, LABORATORY, MOSQUE, Etc - ARCHI MAT'L - Received of Bids | [34 empty] | 0%
| PRWCNOPRCS3510 | OFFICE, LABORATORY, MOSQUE, Etc - ARCHI MAT'L - CBE | [34 empty] | 0%
| PRWCNOPRCS3520 | OFFICE, LABORATORY, MOSQUE, Etc - ARCHI MAT'L - LOI | [34 empty] | 0%
| PRWCNOPRCS3530 | OFFICE, LABORATORY, MOSQUE, Etc - ARCHI MAT'L - PO |  | 20% | 4672982265 | 0.1366% | 2017-07-15: 0.05207% | 0.08451%
| PRWCNOPRCS3540 | OFFICE, LABORATORY, MOSQUE, Etc - ARCHI MAT'L - Fabrication |  | 60% | 11215089007.5 | 0.3278% | 2017-10-13: 0.1196%; 2018-02-10: 0.081%; 2018-03-12: 0.01951%; 2018-04-11: 0.02188%; 2018-05-11: 0.02384% | 0.06192%
| PRWCNOPRCS3550 | OFFICE, LABORATORY, MOSQUE, Etc - ARCHI MAT'L - Delivery to Site |  | 20% | 2803857787.5 | 0.08195% | [30 empty] | 0.08195%
| P3FH - 28 M.13.13.1.2 Road, Drainage, Parking Area & Retaining wall | [35 empty] | 0%
C12 | P3FH - 28 M.13.13.1.2.2 Reinforcement Bar | [35 empty] | 0%
50% | PRWCNOPRCS3620 | DRAINAGE, PARK, RETAINING WALL - REBAR - Received of Bids | [34 empty] | 0%
| PRWCNOPRCS3640 | DRAINAGE, PARK, RETAINING WALL - REBAR - CBE | [34 empty] | 0%
| PRWCNOPRCS3650 | DRAINAGE, PARK, RETAINING WALL - REBAR - LOI | [34 empty] | 0%
| PRWCNOPRCS3660 | DRAINAGE, PARK, RETAINING WALL - REBAR - PO |  |  | 3790254615 | 0.1108% | 2017-08-14: 0.2216%; 2017-09-13: 0.8862% | -0.997%
| PRWCNOPRCS3670 | DRAINAGE, PARK, RETAINING WALL - REBAR - Purchase |  |  | 11370763845 | 0.3323% | [30 empty] | 0.3323%
| PRWCNOPRCS3680 | DRAINAGE, PARK, RETAINING WALL - REBAR - Delivery to Site |  |  | 3790254615 | 0.1108% | [30 empty] | 0.1108%
C12 | P3FH - 28 M.13.13.1.2.3 Concrete Material | [35 empty] | 0%
35% | PRWCNOPRCS3700 | DRAINAGE, PARK, RETAINING WALL - CONCRETE MAT'L - Received of Bids | [34 empty] | 0%
| PRWCNOPRCS3720 | DRAINAGE, PARK, RETAINING WALL - CONCRETE MAT'L - CBE | [34 empty] | 0%
| PRWCNOPRCS3730 | DRAINAGE, PARK, RETAINING WALL - CONCRETE MAT'L - LOI | [34 empty] | 0%
| PRWCNOPRCS3740 | DRAINAGE, PARK, RETAINING WALL - CONCRETE MAT'L - PO |  |  | 2653315087.5 | 0.07755% | [30 empty] | 0.07755%
| PRWCNOPRCS3750 | DRAINAGE, PARK, RETAINING WALL - CONCRETE MAT'L - Purchase |  |  | 7959603120 | 0.2326% | [30 empty] | 0.2326%
| PRWCNOPRCS3760 | DRAINAGE, PARK, RETAINING WALL - CONCRETE MAT'L - Delivery to site |  |  | 2652972945 | 0.07754% | [30 empty] | 0.07754%
C12 | P3FH - 28 M.13.13.1.2.4 Common Formwork | [35 empty] | 0%
15% | PRWCNOPRCS4250 | DRAINAGE, PARK, RETAINING WALL - COMMON FORMWORK - Received of Bids | [34 empty] | 0%
| PRWCNOPRCS4260 | DRAINAGE, PARK, RETAINING WALL - COMMON FORMWORK- CBE | [34 empty] | 0%
| PRWCNOPRCS4270 | DRAINAGE, PARK, RETAINING WALL - COMMON FORMWORK - LOI | [34 empty] | 0%
| PRWCNOPRCS4280 | DRAINAGE, PARK, RETAINING WALL - COMMON FORMWORK - PO |  |  | 1136939527.5 | 0.03323% | [30 empty] | 0.03323%
| PRWCNOPRCS4290 | DRAINAGE, PARK, RETAINING WALL - COMMON FORMWORK - Purchase |  |  | 3411160725 | 0.0997% | [30 empty] | 0.0997%
| PRWCNOPRCS4300 | DRAINAGE, PARK, RETAINING WALL - COMMON FORMWORK - Delivery to site |  |  | 1137281670 | 0.03324% | [30 empty] | 0.03324%
C9 | P3FH - 28 M.13.13.1.2.1 Fence (Galvanized Wire Mesh) & SS Roof for Parking Area | [35 empty] | 0%
| PRWCNOPRCS3780 | FENCE & SS, Roof - Received of Bids | [34 empty] | 0%
| PRWCNOPRCS3800 | FENCE & SS, Roof - CBE | [34 empty] | 0%
| PRWCNOPRCS3810 | FENCE & SS, Roof - LOI | [34 empty] | 0%
| PRWCNOPRCS3820 | FENCE & SS, Roof - PO |  |  | 547428000 | 0.016% | 2017-08-14: 0.016% | 0%
| PRWCNOPRCS3830 | FENCE & SS, Roof - Fabrication |  |  | 1641941857.5 | 0.04799% | 2017-09-13: 0.04799% | 0%
| PRWCNOPRCS3840 | FENCE & SS, Roof - Delivery to Site |  |  | 547428000 | 0.016% | 2017-09-13: 0.016% | 0%
0%
C24 | [36 empty] | 0%
50% | [36 empty] | 0%
[5 empty] | 1658706840 | 0.04848% | 2017-08-14: 0.09696%; 2017-09-13: 0.3878% | -0.4363%
[5 empty] | 4975778377.5 | 0.1454% | [30 empty] | 0.1454%
[5 empty] | 1658364697.5 | 0.04847% | [30 empty] | 0.04847%
0%
35% | [36 empty] | 0%
[5 empty] | 1160889502.5 | 0.03393% | [30 empty] | 0.03393%
[5 empty] | 3483010650 | 0.1018% | [30 empty] | 0.1018%
[5 empty] | 1161231645 | 0.03394% | [30 empty] | 0.03394%
0%
15% | [36 empty] | 0%
[5 empty] | 497475195 | 0.01454% | [30 empty] | 0.01454%
[5 empty] | 1492767727.5 | 0.04363% | [30 empty] | 0.04363%
[5 empty] | 497475195 | 0.01454% | [30 empty] | 0.01454%
0%
0%
0%
C4 | Procurement Ground Improvement | [35 empty] | 0%
[5 empty] | 199811220 | 0.00584% | 2017-06-15: 0.00117%; 2017-09-13: 0.04673% | -0.04206%
[5 empty] | 599775802.5 | 0.01753% | 2017-06-15: 0.00351% | 0.01402%
[5 empty] | 199811220 | 0.00584% | 2017-06-15: 0.00117% | 0.00467%
0%
C4 | Procurement Ground Improvement | [35 empty] | 0%
[5 empty] | 139936282.5 | 0.00409% | 2017-06-15: 0.00082% | 0.00327%
[5 empty] | 419466705 | 0.01226% | 2017-06-15: 0.00245% | 0.00981%
[5 empty] | 139936282.5 | 0.00409% | 2017-06-15: 0.00082% | 0.00327%
0%
C4 | Procurement Ground Improvement | [35 empty] | 0%
[5 empty] | 59874937.5 | 0.00175% | 2017-06-15: 0.00035% | 0.0014%
[5 empty] | 179966955 | 0.00526% | 2017-06-15: 0.00105% | 0.00421%
[5 empty] | 59874937.5 | 0.00175% | 2017-06-15: 0.00035% | 0.0014%
0%
0%
| P3FH - 28 M. Mechanical |  |  |  | 1.7012e+12 | 49.72% | 2.698% | 0.1565% | 0.649% | 0.1467% | 0.504% | 0.3342% | 1.63% | 0.7539% | 0.9436% | 3.763% | 6.01% | 2.781% | 1.412% | 5.974% | 3.31% | 1.624% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 17.03%
| P3FH - 28 M.13.13.2.13.2.1 System 1 - Ore Preparation | [35 empty] | 0%
B4 | P3FH - 28 M.13.13.2.13.2.1.13.2.1.1 Ore Receiving Equipment | [35 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.1.13.2.1.1.1 Loading Hopper | [35 empty] | 0%
| PRKM1000 | LOADING HOPPER - PO & Manufacturing | [34 empty] | 0%
| PRKM1010 | LOADING HOPPER - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.1.13.2.1.1.2 Belt Conveyor N1102 A/B/C, N1103 | [35 empty] | 0%
| PRKM1020 | BELT CONVEYOR N1102A/B/C,N1103 - PO & Manufacturing | [34 empty] | 0%
| PRKM1030 | BELT CONVEYOR N1102A/B/C,N1103 - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.1.13.2.1.1.3 Belt Weigher | [35 empty] | 0%
| PRKM1040 | BELT WEIGHER - PO & Manufacturing | [34 empty] | 0%
| PRKM1050 | BELT WEIGHER - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.1.13.2.1.1.4 CDPS | [35 empty] | 0%
| PRKM1060 | CDPS - PO & Manufacturing |  | 90% | 9797250487.5 | 0.2863% | [30 empty] | 0.2863%
| PRKM1070 | CDPS - Delivery |  | 10% | 1088697435 | 0.03182% | [30 empty] | 0.03182%
F4 |  |  |  | 100% | 946708297.5 | 0% | [30 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.1.13.2.1.1.5 Shake Out Machine | [35 empty] | 0%
| PRKM1080 | SHAKE OUT MACHINE - PO & Manufacturing | [34 empty] | 0%
| PRKM1090 | SHAKE OUT MACHINE - Delivery | [34 empty] | 0%
0%
B5 | P3FH - 28 M.13.13.2.13.2.1.13.2.1.2 Ore Drying Equipment | [35 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.1 Shell & Accessories with Lifter | [35 empty] | 0%
| PRKM1100 | SHELL & ACESSORIES WIITH LIFTER - PO & Manufacturing | [34 empty] | 0%
| PRKM1110 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.2 Tire | [35 empty] | 0%
| PRKM1120 | TIRE - PO & Manufacturing | [34 empty] | 0%
| PRKM1130 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.3 Roller & Shaft | [35 empty] | 0%
| PRKM1140 | ROLLER&SHAFT - PO & Manufacturing | [34 empty] | 0%
| PRKM1150 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.4 Roller Bearing & Pinion Bearing | [35 empty] | 0%
| PRKM1160 | BEARING&PINION BEARING - PO & Manufacturing | [34 empty] | 0%
| PRKM1170 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.5 Roller Bearing Bed, Motor Bed & Pinion Bearing Bed | [35 empty] | 0%
| PRKM1180 | ROLLER BEARING BED,MOTOR BED&PINION BEARING - PO & Manufacturing | [34 empty] | 0%
| PRKM1190 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.6 Thruster | [35 empty] | 0%
| PRKM1200 | THRUSTER - PO & Manufacturing | [34 empty] | 0%
| PRKM1210 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.7 Girth Gear & Pinion | [35 empty] | 0%
| PRKM1220 | GIIRTH GEAR & PINION - PO & Manufacturing | [34 empty] | 0%
| PRKM1230 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.1 Gear Reducer | [35 empty] | 0%
| PRKM3350 | GEAR REDUCER - PO & Manufacturing | [34 empty] | 0%
| PRKM3360 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.8 Inlet Hood, Discharge Hood, Air Seal | [35 empty] | 0%
| PRKM1240 | INLET HOOD,DISCHARGE HOOD,AIR SEAL - PO & Manufacturing | [34 empty] | 0%
| PRKM1250 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.9 Chain Conveyor | [35 empty] | 0%
| PRKM1260 | CHAIN CONVEYOR - PO & Manufacturing | [34 empty] | 0%
| PRKM1270 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.10 Rotary Valve | [35 empty] | 0%
| PRKM1280 | ROTARY VALVE - PO & Manufacturing | [34 empty] | 0%
| PRKM1290 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.11 Process Fan | [35 empty] | 0%
| PRKM1300 | PROCESS FAN - PO & Manufacturing | [34 empty] | 0%
| PRKM1310 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.12 Stack For Dryer | [35 empty] | 0%
| PRKM1320 | STACK FOR DRYER - PO & Manufacturing | [34 empty] | 0%
| PRKM1330 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.13 Hot Air Generator (Shell) | [35 empty] | 0%
| PRKM1340 | HOT AIR GENERATOR (SHELL) - PO & Manufacturing | [34 empty] | 0%
| PRKM1350 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.14 Hot Air Generator (Burner, Pump Unit) | [35 empty] | 0%
| PRKM1360 | HOT AIR GENERATOR(BURNER,PUMP UNIT ) - PO & Manufacturing | [34 empty] | 0%
| PRKM1370 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.15 Valve Unit | [35 empty] | 0%
| PRKM1380 | VALVE UNIT - PO & Manufacturing | [34 empty] | 0%
| PRKM1390 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.16 General Fan | [35 empty] | 0%
| PRKM1400 | GENERAL FAN - PO & Manufacturing | [34 empty] | 0%
| PRKM1410 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.17 CDPS | [35 empty] | 0%
| PRKM1420 | CDPS - PO & Manufacturing | [34 empty] | 0%
| PRKM1430 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.18 Electrostatic Presipitator | [35 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.18.13.2.1.2.18.1 Casing | [35 empty] | 0%
| PRKM1440 | ELECTROSTATIC PRESIPITATOR,CASING - PO & Manufacturing | [34 empty] | 0%
| PRKM1450 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.18.13.2.1.2.18.2 Frame | [35 empty] | 0%
| PRKM1460 | ELECTROSTATIC PRESIPITATOR,FRAME - PO & Manufacturing | [34 empty] | 0%
| PRKM1470 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.18.13.2.1.2.18.3 Support Structure | [35 empty] | 0%
| PRKM1480 | ELECTROSTATIC PRESIPITATOR,SUIPPORT STRUCTURE - PO & Manufacturing | [34 empty] | 0%
| PRKM1490 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.18.13.2.1.2.18.4 Stair & Access | [35 empty] | 0%
| PRKM1500 | ELECTRIC PRESIPITATOR,STAIR&ACCESS - PO & Manufacturing | [34 empty] | 0%
| PRKM1510 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.18.13.2.1.2.18.5 Weather Enclosure | [35 empty] | 0%
| PRKM1520 | ELECTRIC PRESIPITATOR,WEATHER ENCLOSUR - PO & Manufacturing | [34 empty] | 0%
| PRKM1530 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.18.13.2.1.2.18.6 Rapping Hammer | [35 empty] | 0%
| PRKM1540 | ELECTRIC PRESIPITATOR,RAPPING HAMMER - PO & Manufacturing | [34 empty] | 0%
| PRKM1550 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.18.13.2.1.2.18.7 Collecting Plate | [35 empty] | 0%
| PRKM1560 | ELECTRIC PRESIPITATOR,C OLLECTING HAMMER - PO & Manufacturing | [34 empty] | 0%
| PRKM1570 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.18.13.2.1.2.18.8 Electrode | [35 empty] | 0%
| PRKM1580 | ELECTRIC PRESIPITATOR,ELCTRODE - PO & Manufacturing | [34 empty] | 0%
| PRKM1590 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.18.13.2.1.2.18.9 Electrical Component | [35 empty] | 0%
| PRKM1600 | ELECTRIC PRESIPITATOR,ELECTRICAL COMPONENT - PO & Manufacturing |  | 90% | 14241681562.5 | 0.4163% | [30 empty] | 0.4163%
| PRKM1610 | DELIVERY |  | 10% | 1582409062.5 | 0.04625% | [30 empty] | 0.04625%
F4 |  |  |  | 100% | 946708297.5 | 0% | [30 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.19 Dust Hopper | [35 empty] | 0%
| PRKM1620 | DUST HOPPER - PO & Manufacturing | [34 empty] | 0%
| PRKM1630 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.20 Pneumatic Conveyor | [35 empty] | 0%
| PRKM1640 | PNEUMATIC CONVEYOR - PO & Manufacturing | [34 empty] | 0%
| PRKM1650 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.2.13.2.1.2.21 Roots Blower | [35 empty] | 0%
| PRKM1660 | ROOT BLOWER - PO & Manufacturing | [34 empty] | 0%
| PRKM1670 | Delivery | [34 empty] | 0%
0%
B6 | P3FH - 28 M.13.13.2.13.2.1.13.2.1.3 Ore Sizing Equipment | [35 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.3.13.2.1.3.1 Impeller Breaker | [35 empty] | 0%
| PRKM1680 | IMPELLER BREAKER - PO & Manufacturing | [34 empty] | 0%
| PRKM1690 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.3.13.2.1.3.2 Belt Conveyor N1302, N1303, N1307, N1308, N1310 | [35 empty] | 0%
| PRKM1700 | BELT CONVEYOR N1302,N1303,N1307,N1308,N1310 - PO & Manufacturing | [34 empty] | 0%
| PRKM1710 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.3.13.2.1.3.3 Two Way Chute | [35 empty] | 0%
| PRKM1720 | TWO WAY CHUTE - PO & Manufacturing | [34 empty] | 0%
| PRKM1730 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.3.13.2.1.3.4 CDPS | [35 empty] | 0%
| PRKM1740 | CDPS - PO & Manufacturing |  | 90% | 7862434650 | 0.2298% | [30 empty] | 0.2298%
| PRKM1750 | Delivery |  | 10% | 873489802.5 | 0.02553% | [30 empty] | 0.02553%
F4 |  |  |  | 100% | 946708297.5 | 0% | [30 empty] | 0%
B7 | P3FH - 28 M.13.13.2.13.2.1.13.2.1.4 Ore Mixing Equipment | [35 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.4.13.2.1.4.1 Ore Bin & Loading Hopper | [35 empty] | 0%
| PRKM1760 | ORE BIN&LOADING HOPPER - PO & Manufacturing | [34 empty] | 0%
| PRKM1770 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.4.13.2.1.4.2 Belt Conveyor N1403, N1404, N1423 | [35 empty] | 0%
| PRKM1780 | BELT CONVEYOR N1403,N1404,N1423 - PO & Manufacturing |  | 90% | 8459131170 | 0.2472% | [30 empty] | 0.2472%
| PRKM1790 | Delivery |  | 10% | 939865447.5 | 0.02747% | [30 empty] | 0.02747%
F4 |  |  |  | 100% | 946708297.5 | 0% | [30 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.4.13.2.1.4.3 Grizzly Feeder | [35 empty] | 0%
| PRKM1800 | GRIZZLY FEEDER - PO & Manufacturing | [34 empty] | 0%
| PRKM1810 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.4.13.2.1.4.4 Weighing Feeder | [35 empty] | 0%
| PRKM1820 | WEIHHING FEEDER - PO & Manufacturing | [34 empty] | 0%
| PRKM1830 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.4.13.2.1.4.5 Two Way Chute | [35 empty] | 0%
| PRKM1840 | TWO WAY CHUTE - PO & Manufacturing | [34 empty] | 0%
| PRKM1850 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.4.13.2.1.4.6 CDPS | [35 empty] | 0%
| PRKM1860 | CDPS - PO & Manufacturing | [34 empty] | 0%
| PRKM1870 | Delivery | [34 empty] | 0%
0%
B8 | P3FH - 28 M.13.13.2.13.2.1.13.2.1.5 Dust Treatment Equipment | [35 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.5.13.2.1.5.1 Cyclone | [35 empty] | 0%
| PRKM1880 | CYCLONE - PO & Manufacturing | [34 empty] | 0%
| PRKM1890 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.5.13.2.1.5.2 Rotary Valve | [35 empty] | 0%
| PRKM1900 | ROTARY VALVE - PO & Manufacturing | [34 empty] | 0%
| PRKM1910 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.5.13.2.1.5.3 Ore Bin | [35 empty] | 0%
| PRKM1920 | ORE BIN - PO & Manufacturing | [34 empty] | 0%
| PRKM1930 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.5.13.2.1.5.4 Loop Feeder | [35 empty] | 0%
| PRKM1940 | LOOP FEEDER - PO & Manufacturing | [34 empty] | 0%
| PRKM1950 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.5.13.2.1.5.5 Bag Filter | [35 empty] | 0%
| PRKM1960 | BAG FILTER - PO & Manufacturing | [34 empty] | 0%
| PRKM1970 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.5.13.2.1.5.6 General Fan | [35 empty] | 0%
| PRKM1980 | GENERAL FAN - PO & Manufacturing | [34 empty] | 0%
| PRKM1990 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.5.13.2.1.5.7 Pug mill | [35 empty] | 0%
| PRKM2000 | PUG MILL - PO & Manufacturing | [34 empty] | 0%
| PRKM2010 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.5.13.2.1.5.8 Water Tank | [35 empty] | 0%
| PRKM2020 | WATER TANK - PO & Manufacturing | [34 empty] | 0%
| PRKM2030 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.5.13.2.1.5.9 Rod Mill | [35 empty] | 0%
| PRKM2040 | ROD MILL - PO & Manufacturing | [34 empty] | 0%
| PRKM2050 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.5.13.2.1.5.10 Screw Conveyor | [35 empty] | 0%
| PRKM2060 | SCREW CONVEYOR - PO & Manufacturing | [34 empty] | 0%
| PRKM2070 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.5.13.2.1.5.11 Chain Conveyor | [35 empty] | 0%
| PRKM2080 | CHAIN CONVEYOR - PO & Manufacturing | [34 empty] | 0%
| PRKM2090 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.5.13.2.1.5.12 Weighing Feeder | [35 empty] | 0%
| PRKM2100 | WEGHING FEEDER - PO & Manufacturing | [34 empty] | 0%
| PRKM2110 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.5.13.2.1.5.13 Feed bin | [35 empty] | 0%
| PRKM2120 | FEED BIN - PO & Manufacturing | [34 empty] | 0%
| PRKM2130 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.5.13.2.1.5.14 Briquetting Machine | [35 empty] | 0%
| PRKM2140 | BRIQUETTING MACHINE - PO & Manufacturing | [34 empty] | 0%
| PRKM2150 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.5.13.2.1.5.15 CDPS | [35 empty] | 0%
| PRKM2160 | CDPS - PO & Manufacturing |  | 90% | 1284402945 | 0.03754% | [30 empty] | 0.03754%
| PRKM2170 | Delivery |  | 10% | 142673422.5 | 0.00417% | [30 empty] | 0.00417%
F4 |  |  |  | 100% | 946708297.5 | 0% | [30 empty] | 0%
B9 | P3FH - 28 M.13.13.2.13.2.1.13.2.1.6 Rotary Kiln Equipment | [35 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.6.13.2.1.6.1 Shell & Accessories with Lifter | [35 empty] | 0%
| PRKM2180 | SHELL&ACCESOORIES WITH LIFTER - PO & Manufacturing | [34 empty] | 0%
| PRKM2190 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.6.13.2.1.6.2 Tire | [35 empty] | 0%
| PRKM2200 | TIRE - PO & Manufacturing | [34 empty] | 0%
| PRKM2210 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.6.13.2.1.6.3 Roller & Shaft | [35 empty] | 0%
| PRKM2220 | ROLLER&SHAFT - PO & Manufacturing | [34 empty] | 0%
| PRKM2230 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.6.13.2.1.6.4 Roller Bearing & Pinion Bearing | [35 empty] | 0%
| PRKM2240 | ROLLER&PINION BEARING - PO & Manufacturing | [34 empty] | 0%
| PRKM2250 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.6.13.2.1.6.5 Roller Bearing Bed, Motor Bed & Pinion Bearing Bed | [35 empty] | 0%
| PRKM2260 | ROLLER BEARING BED,MOTOR BED&PINION BEARING BED - PO & Manufacturing | [34 empty] | 0%
| PRKM2270 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.6.13.2.1.6.6 Thruster | [35 empty] | 0%
| PRKM2280 | THRUSTER - PO & Manufacturing | [34 empty] | 0%
| PRKM2290 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.6.13.2.1.6.7 Girth Gear & Pinion | [35 empty] | 0%
| PRKM2300 | GIRTH GEAR&PINION - PO & Manufacturing | [34 empty] | 0%
| PRKM2310 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.6.13.2.1.6.8 Gear Reducer | [35 empty] | 0%
| PRKM2320 | GEAR REDUCER - PO & Manufacturing |  | 90% | 11681771377.5 | 0.3414% | 2018-05-11: 0.3414% | 0%
| PRKM2330 | Delivery |  | 10% | 1298088645 | 0.03794% | 2018-05-11: 0.03794% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0% | [30 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.6.13.2.1.6.9 Kiln Buner | [35 empty] | 0%
| PRKM2340 | KILN BURNER - PO & Manufacturing | [34 empty] | 0%
| PRKM2350 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.6.13.2.1.6.10 Inlet Hood, Combustion Hood, Air seal, Scoop feeder cover | [35 empty] | 0%
| PRKM2360 | INLET HOOD,COMBUSTION HOD,AIR SEAL,SCOOP FEEDER COVER - PO & Manufacturing | [34 empty] | 0%
| PRKM2370 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.6.13.2.1.6.11 General Fan | [35 empty] | 0%
| PRKM2380 | GENERAL FAN - PO & Manufacturing | [34 empty] | 0%
| PRKM2390 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.6.13.2.1.6.12 Rotary Valve for Inlet Hood | [35 empty] | 0%
| PRKM2400 | ROTARY VALVE INLET HOOD - PO & Manufacturing | [34 empty] | 0%
| PRKM2410 | Delivery | [34 empty] | 0%
0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.7 Scoop Feeder | [35 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.7.13.2.1.7.1 Belt Conveyor N1651 | [35 empty] | 0%
| PRKM2420 | BELT CONVEYOR N1651 - PO & Manufacturing | [34 empty] | 0%
| PRKM2430 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.7.13.2.1.7.2 Belt Conveyor N1652, N1653 | [35 empty] | 0%
| PRKM2440 | BELT CONVEYOR N1652,N1653 - PO & Manufacturing | [34 empty] | 0%
| PRKM2450 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.7.13.2.1.7.3 Coal Bin for Scoop Feeder | [35 empty] | 0%
| PRKM2460 | COAL BIN FOR SCOOP FEEDER - PO & Manufacturing | [34 empty] | 0%
| PRKM2470 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.7.13.2.1.7.4 General Fan | [35 empty] | 0%
| PRKM2480 | GENERAL FAN - PO & Manufacturing | [34 empty] | 0%
| PRKM2490 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.7.13.2.1.7.5 Weighing Feeder | [35 empty] | 0%
| PRKM2500 | WEIGHING FEEDER - PO & Manufacturing | [34 empty] | 0%
| PRKM2510 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.7.13.2.1.7.6 CDPS | [35 empty] | 0%
| PRKM2520 | CDPS - PO & Manufacturing | [34 empty] | 0%
| PRKM2530 | Delivery | [34 empty] | 0%
0%
B10 | P3FH - 28 M.13.13.2.13.2.1.13.2.1.8 Exhaust Gas Treatment Equipment | [35 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.8.13.2.1.8.1 Multi-Cyclone | [35 empty] | 0%
| PRKM2540 | MULTI CYCLONE - PO & Manufacturing | [34 empty] | 0%
| PRKM2550 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.8.13.2.1.8.2 Electrostatic Presipitator | [35 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.8.13.2.1.8.2.13.2.1.8.2.1 Casing | [35 empty] | 0%
| PRKM2560 | ELECTROSTATIC PRESIPITATOR,CASING - PO & Manufacturing | [34 empty] | 0%
| PRKM2570 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.8.13.2.1.8.2.13.2.1.8.2.2 Frame | [35 empty] | 0%
| PRKM2580 | ELECTROSTATIC PRESIPITATOR,FRAME - PO & Manufacturing | [34 empty] | 0%
| PRKM2590 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.8.13.2.1.8.2.13.2.1.8.2.3 Support Structure | [35 empty] | 0%
| PRKM2600 | ELECTROSTATIC PRESIPITATOR,SUPPORT STRUCTURE - PO & Manufacturing | [34 empty] | 0%
| PRKM2610 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.8.13.2.1.8.2.13.2.1.8.2.4 Stair & Access | [35 empty] | 0%
| PRKM2620 | ELECTROSTATIC PRESIPITATOR,STAIR&ACCESS - PO & Manufacturing | [34 empty] | 0%
| PRKM2630 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.8.13.2.1.8.2.13.2.1.8.2.5 Weather Enclosure | [35 empty] | 0%
| PRKM2640 | ELECTROSTATICPRESIPITATOR,WEATHER ENCLOSURE - PO & Manufacturing | [34 empty] | 0%
| PRKM2650 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.8.13.2.1.8.2.13.2.1.8.2.6 Rapping Hammer | [35 empty] | 0%
| PRKM2660 | ELECTROSTATICPRESIPITATOR,RAPPING HAMMER - PO & Manufacturing | [34 empty] | 0%
| PRKM2670 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.8.13.2.1.8.2.13.2.1.8.2.7 Collecting Plate | [35 empty] | 0%
| PRKM2680 | ELECTROSTATICPRESIPITATOR,COLLECTING PLATE - PO & Manufacturing | [34 empty] | 0%
| PRKM2690 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.8.13.2.1.8.2.13.2.1.8.2.8 Electrode | [35 empty] | 0%
| PRKM2700 | ELECTROSTATICPRESIPITATOR,ELECTRODE - PO & Manufacturing | [34 empty] | 0%
| PRKM2710 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.8.13.2.1.8.2.13.2.1.8.2.9 Electrical Component | [35 empty] | 0%
| PRKM2720 | ELECTROSTATICPRESIPITATOR,ELECTRICAL COMPONENET - PO & Manufacturing |  | 90% | 11748831307.5 | 0.3434% | 2018-05-11: 0.3434% | 0%
| PRKM2730 | Delivery |  | 10% | 1305273637.5 | 0.03815% | 2018-05-11: 0.03815% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0% | [30 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.8.13.2.1.8.3 Process Fan | [35 empty] | 0%
| PRKM2740 | PROCESS FAN - PO & Manufacturing | [34 empty] | 0%
| PRKM2750 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.8.13.2.1.8.4 Stack | [35 empty] | 0%
| PRKM2760 | STACK - PO & Manufacturing | [34 empty] | 0%
| PRKM2770 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.8.13.2.1.8.5 Rotary Valve | [35 empty] | 0%
| PRKM2780 | ROTARY VALVE - PO & Manufacturing | [34 empty] | 0%
| PRKM2790 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.8.13.2.1.8.6 Chain Conveyor | [35 empty] | 0%
| PRKM2800 | CHAIN CONVEYOR - PO & Manufacturing | [34 empty] | 0%
| PRKM2810 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.8.13.2.1.8.7 Kiln Dust Bin | [35 empty] | 0%
| PRKM2820 | KILN DUST BIN - PO & Manufacturing | [34 empty] | 0%
| PRKM2830 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.8.13.2.1.8.8 Pneumatic Conveyor | [35 empty] | 0%
| PRKM2840 | PNEUMATIC CONVEYOR - PO & Manufacturing | [34 empty] | 0%
| PRKM2850 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.8.13.2.1.8.9 Roots Blower | [35 empty] | 0%
| PRKM2860 | ROOT BLOWER - PO & Manufacturing | [34 empty] | 0%
| PRKM2870 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.8.13.2.1.8.10 CDPS | [35 empty] | 0%
| PRKM2880 | CDPS - PO & Manufacturing | [34 empty] | 0%
| PRKM2890 | Delivery | [34 empty] | 0%
0%
B11 | P3FH - 28 M.13.13.2.13.2.1.13.2.1.9 Coal Firing Equipment | [35 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.9.13.2.1.9.1 Anchoor Frame | [35 empty] | 0%
| PRKM2900 | COAL FIRING EQUIPMENT - PO & Manufacturing | [34 empty] | 0%
| PRKM2910 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.9.13.2.1.9.2 Loading Hopper | [35 empty] | 0%
| PRKM2920 | LOADING HOOPER - PO & Manufacturing | [34 empty] | 0%
| PRKM2930 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.9.13.2.1.9.3 Raw Coal Bin | [35 empty] | 0%
| PRKM2940 | RAW COAL BIN - PO & Manufacturing | [34 empty] | 0%
| PRKM2950 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.9.13.2.1.9.4 Grizzly Feeder | [35 empty] | 0%
| PRKM2960 | GRIZZLY FEEDER - PO & Manufacturing | [34 empty] | 0%
| PRKM2970 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.9.13.2.1.9.5 Magnet Separator / Metal Detector | [35 empty] | 0%
| PRKM2980 | MAGNER SEPARATOR/METAL DETECTOR - PO & Manufacturing | [34 empty] | 0%
| PRKM2990 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.9.13.2.1.9.6 Belt Conveyor N1804 | [35 empty] | 0%
| PRKM3000 | BELT CONVEYOR N1804 - PO & Manufacturing | [34 empty] | 0%
| PRKM3010 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.9.13.2.1.9.7 Coal Grinding Mill | [35 empty] | 0%
| PRKM3020 | COAL GRINDING - PO & Manufacturing | [34 empty] | 0%
| PRKM3030 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.9.13.2.1.9.8 Bag Filter | [35 empty] | 0%
| PRKM3040 | BAG FILTER - PO & Manufacturing | [34 empty] | 0%
| PRKM3050 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.9.13.2.1.9.9 Hot Air Generator (Shell) | [35 empty] | 0%
| PRKM3060 | HOT AIR GENERATOR - PO & Manufacturing | [34 empty] | 0%
| PRKM3070 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.9.13.2.1.9.10 Valve Unit | [35 empty] | 0%
| PRKM3080 | VALVE UNIT - PO & Manufacturing | [34 empty] | 0%
| PRKM3090 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.9.13.2.1.9.11 Rotary Valve | [35 empty] | 0%
| PRKM3100 | ROTARY VALVE - PO & Manufacturing | [34 empty] | 0%
| PRKM3110 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.9.13.2.1.9.12 Screw Conveyor | [35 empty] | 0%
| PRKM3120 | SCREW CONVEYOR - PO & Manufacturing | [34 empty] | 0%
| PRKM3130 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.9.13.2.1.9.13 Pump Unit for HAG | [35 empty] | 0%
| PRKM3140 | PUMP UNIT FOR HAG - PO & Manufacturing | [34 empty] | 0%
| PRKM3150 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.9.13.2.1.9.14 Coal Weigher | [35 empty] | 0%
| PRKM3160 | COAL WEIGHER - PO & Manufacturing | [34 empty] | 0%
| PRKM3170 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.9.13.2.1.9.15 Pneumatic Conveyor | [35 empty] | 0%
| PRKM3180 | PNEUMATIC CONVEYOR - PO & Manufacturing | [34 empty] | 0%
| PRKM3190 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.9.13.2.1.9.16 Roots Blower | [35 empty] | 0%
| PRKM3200 | ROOTS BLOWER - PO & Manufacturing | [34 empty] | 0%
| PRKM3210 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.9.13.2.1.9.17 Pulverized Coal Bin | [35 empty] | 0%
| PRKM3220 | PULVERIZED COAL BIN - PO & Manufacturing | [34 empty] | 0%
| PRKM3230 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.9.13.2.1.9.18 General Fan | [35 empty] | 0%
| PRKM3240 | GENERAL FAN - PO & Manufacturing | [34 empty] | 0%
| PRKM3250 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.9.13.2.1.9.19 Process Fan | [35 empty] | 0%
| PRKM3260 | PROCESS FAN - PO & Manufacturing | [34 empty] | 0%
| PRKM3270 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.9.13.2.1.9.20 Limestone Hopper | [35 empty] | 0%
| PRKM3280 | LIMESTOEN HOPPER - PO & Manufacturing | [34 empty] | 0%
| PRKM3290 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.9.13.2.1.9.21 Hoist | [35 empty] | 0%
| PRKM3300 | HOIST - PO & Manufacturing | [34 empty] | 0%
| PRKM3310 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.13.2.1.9.13.2.1.9.22 CDPS | [35 empty] | 0%
| PRKM3320 | CDPS - PO & Manufacturing |  | 90% | 4956276255 | 0.1449% | 2018-05-11: 0.1449% | 0%
| PRKM3330 | Delivery |  | 10% | 550849425 | 0.0161% | 2018-05-11: 0.01411% | 0.00199%
F4 |  |  |  | 100% | 946708297.5 | 0% | [30 empty] | 0%
B12 | P3FH - 28 M.13.13.2.13.2.1.1 Surge Bin Equipment | [35 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.1.1 Surge Hopper | [35 empty] | 0%
| PRKM3430 | SURGE HOPPER - PO & Manufacturing |  | 90% | 2140101337.5 | 0.06255% | [30 empty] | 0.06255%
| PRKM3440 | SURGE HOPPER - Delivery |  | 10% | 237789037.5 | 0.00695% | [30 empty] | 0.00695%
F4 |  |  |  | 100% | 1893416595 | 0% | [30 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.1.2 Cyclone | [35 empty] | 0%
| PRKM3410 | MULTI CYCLONE - PO & Manufacturing | [34 empty] | 0%
| PRKM3420 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.1.3 Induced Fan | [35 empty] | 0%
| PRKM3390 | INDUCED FAN - PO & Manufacturing | [34 empty] | 0%
| PRKM3400 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.1.1.4 CDPS | [35 empty] | 0%
| PRKM3370 | CDPS - PO & Manufacturing | [34 empty] | 0%
| PRKM3380 | Delivery | [34 empty] | 0%
0%
B300 |  | Rotary Dryer | [34 empty] | 0%
B301 |  | Shell & Accessories with Lifter | [34 empty] | 0%
|  |  |  | 90% | 13594347952.5 | 0.3973% | 2017-12-12: 0.3973% | -1e-05%
|  |  |  | 10% | 1510559137.5 | 0.04415% | 2018-01-11: 0.04415% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.0084% | 2017-12-12: 0.0084% | 0%
|  | Tire | [34 empty] | 0%
|  |  |  | 90% | 2027536455 | 0.05926% | 2017-12-12: 0.05926% | 0%
|  |  |  | 10% | 225129765 | 0.00658% | 2018-04-11: 0.00658% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.0084% | 2017-12-12: 0.0084% | 0%
|  | Roller & Shaft | [34 empty] | 0%
|  |  |  | 90% | 2623548690 | 0.07668% | 2017-12-12: 0.07668% | 0%
|  |  |  | 10% | 291505410 | 0.00852% | 2018-04-11: 0.00852% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.0084% | 2017-12-12: 0.0084% | 0%
|  | Roller Bearing & Pinion Bearing | [34 empty] | 0%
|  |  |  | 90% | 1192708755 | 0.03486% | 2017-12-12: 0.03486% | 0%
|  |  |  | 10% | 132409147.5 | 0.00387% | 2018-04-11: 0.00387% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.0084% | 2017-12-12: 0.0084% | 0%
|  | Roller Bearing Bed, Motor Bed & Pinion Bearing Bed | [34 empty] | 0%
|  |  |  | 90% | 1311774345 | 0.03834% | 2017-11-12: 0.03834% | 0%
|  |  |  | 10% | 145752705 | 0.00426% | 2018-02-10: 0.00426% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.0084% | 2017-11-12: 0.0084% | 0%
|  | Thruster | [34 empty] | 0%
|  |  |  | 90% | 238815465 | 0.00698% | 2018-01-11: 0.00698% | 0%
|  |  |  | 10% | 26344972.5 | 0.00077% | 2018-04-11: 0.00077% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.0084% | 2018-01-11: 0.0084% | 0%
|  | Girth Gear & Pinion | [34 empty] | 0%
|  |  |  | 90% | 2504483100 | 0.0732% | 2017-12-12: 0.0732% | 0%
|  |  |  | 10% | 278161852.5 | 0.00813% | 2018-04-11: 0.00813% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.0084% | 2017-12-12: 0.0084% | 0%
B308 |  | Gear Reducer | [34 empty] | 0%
|  |  |  | 90% | 4173796357.5 | 0.122% | 2017-12-12: 0.122% | 0%
|  |  |  | 10% | 463603087.5 | 0.01355% | 2018-04-11: 0.01356% | -1e-05%
F4 |  |  |  | 100% | 946708297.5 | 0.0084% | 2017-12-12: 0.0084% | 0%
0%
|  | Rotary Kiln | [34 empty] | 0%
|  | Shell & Accessories with Nose Ring, Thermometer Case & Lifter | [34 empty] | 0%
|  |  |  | 90% | 49965806415 | 1.46% | 2017-12-12: 1.46% | 0%
|  |  |  | 10% | 5551604205 | 0.1623% | 2018-01-11: 0.1623% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.03028% | 2017-12-12: 0.03028% | 0%
|  | Tire | [34 empty] | 0%
|  |  |  | 90% | 13952229007.5 | 0.4078% | 2017-12-12: 0.4078% | 0%
|  |  |  | 10% | 1550247667.5 | 0.04531% | 2018-04-11: 0.04531% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.03028% | 2017-12-12: 0.03028% | 0%
|  | Roller & Shaft | [34 empty] | 0%
|  |  |  | 90% | 20988047377.5 | 0.6134% | 2017-12-12: 0.6134% | 0%
|  |  |  | 10% | 2332043280 | 0.06816% | 2018-04-11: 0.06816% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.03028% | 2017-12-12: 0.03028% | 0%
|  | Roller Bearing & Pinion Bearing | [34 empty] | 0%
|  |  |  | 90% | 7870646070 | 0.23% | 2017-12-12: 0.23% | 0%
|  |  |  | 10% | 874516230 | 0.02556% | 2018-04-11: 0.02556% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.03028% | 2017-12-12: 0.03028% | 0%
|  | Roller Bearing Bed, Motor Bed & Pinion Bearing Bed | [34 empty] | 0%
|  |  |  | 90% | 5485570702.5 | 0.1603% | 2017-11-12: 0.1603% | 0%
|  |  |  | 10% | 609355792.5 | 0.01781% | 2018-02-10: 0.01782% | -1e-05%
F4 |  |  |  | 100% | 946708297.5 | 0.03028% | 2017-11-12: 0.03028% | 0%
|  | Thruster | [34 empty] | 0%
|  |  |  | 90% | 1907786580 | 0.05576% | 2017-12-12: 0.05576% | 0%
|  |  |  | 10% | 212128350 | 0.0062% | 2018-04-11: 0.0062% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.03028% | 2017-12-12: 0.03028% | 0%
|  | Girth Gear & Pinion | [34 empty] | 0%
|  |  |  | 90% | 4770150735 | 0.1394% | 2017-12-12: 0.1394% | 0%
|  |  |  | 10% | 529978732.5 | 0.01549% | 2018-04-11: 0.01549% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.03028% | 2017-12-12: 0.03028% | 0%
|  | Gear Reducer | [34 empty] | 0%
|  |  |  | 90% | 9301486005 | 0.2719% | 2017-12-12: 0.2719% | -1e-05%
|  |  |  | 10% | 1033612492.5 | 0.03021% | 2018-04-11: 0.03021% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.03028% | 2017-12-12: 0.03028% | 0%
B319 |  | kiln burner | [34 empty] | 0%
|  |  |  | 90% | 5624822700 | 0.1644% | 2018-05-11: 0.1644% | -1e-05%
|  |  |  | 10% | 625094347.5 | 0.01827% | [30 empty] | 0.01827%
F4 |  |  |  | 100% | 946708297.5 | 0.03028% | [30 empty] | 0.03028%
0%
|  | Electrostatic Precipitator | [34 empty] | 0%
|  | Casing, Frame, Support Structure, Stair & Access, Weather Enclosure, Collecting Plate | [34 empty] | 0%
|  |  |  | 90% | 13086950625 | 0.3825% | 2017-12-12: 0.3825% | 0%
|  |  |  | 10% | 1454105625 | 0.0425% | 2018-01-11: 0.0425% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.02335% | 2017-12-12: 0.02335% | 0%
B323 |  | Rapping Hammer, Electrode, Electrical Components | [34 empty] | 0%
|  |  |  | 90% | 22283398882.5 | 0.6513% | 2017-11-12: 0.6513% | 0%
|  |  |  | 10% | 2475743130 | 0.07236% | 2018-01-11: 0.07236% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.02335% | 2017-11-12: 0.02335% | 0%
0%
B325 |  | Rod Mill | [34 empty] | 0%
|  |  |  | 90% | 25650081082.5 | 0.7497% | 2018-01-11: 0.7497% | 0%
|  |  |  | 10% | 2850047025 | 0.0833% | 2018-04-11: 0.0833% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.01953% | 2018-01-11: 0.01953% | 0%
|  | Briquetting Machine | [34 empty] | 0%
|  |  |  | 90% | 29587456972.5 | 0.8648% | 2018-01-11: 0.8648% | 0%
|  |  |  | 10% | 3287647282.5 | 0.09609% | 2018-04-11: 0.09608% | 1e-05%
F4 |  |  |  | 100% | 946708297.5 | 0.01024% | 2018-01-11: 0.01024% | 0%
|  | Load Cell | [34 empty] | 0%
|  |  |  | 90% | 2475058845 | 0.07234% | 2017-11-12: 0.07235% | -1e-05%
|  |  |  | 10% | 275082570 | 0.00804% | [30 empty] | 0.00804%
F4 |  |  |  | 100% | 946708297.5 | 0% | [30 empty] | 0%
|  | Impeller Breaker | [34 empty] | 0%
|  |  |  | 90% | 5062682572.5 | 0.148% | 2017-11-12: 0.148% | 0%
|  |  |  | 10% | 562482270 | 0.01644% | 2018-02-10: 0.01644% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.00229% | 2017-11-12: 0.00229% | 0%
|  | Hot Air Generator | [34 empty] | 0%
|  |  |  | 90% | 9899893237.5 | 0.2893% | 2018-01-11: 0.2893% | 0%
|  |  |  | 10% | 1099988137.5 | 0.03215% | 2018-04-11: 0.03215% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.01605% | 2018-01-11: 0.01605% | 0%
|  | Pneumatic Conveyor | [34 empty] | 0%
|  |  |  | 90% | 9224846085 | 0.2696% | 2017-11-12: 0.2696% | 0%
|  |  |  | 10% | 1025058930 | 0.02996% | 2018-02-10: 0.02995% | 1e-05%
F4 |  |  |  | 100% | 946708297.5 | 0.01606% | 2017-11-12: 0.01605% | 1e-05%
|  | Loop Feeder | [34 empty] | 0%
|  |  |  | 90% | 11587682190 | 0.3387% | 2017-11-12: 0.3387% | 0%
|  |  |  | 10% | 1287482227.5 | 0.03763% | 2018-02-10: 0.03763% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.0084% | 2017-11-12: 0.0084% | 0%
|  | Pug Mill | [34 empty] | 0%
|  |  |  | 90% | 3937375890 | 0.1151% | 2018-05-11: 0.1151% | 0%
|  |  |  | 10% | 437600257.5 | 0.01279% | [30 empty] | 0.01279%
F4 |  |  |  | 100% | 946708297.5 | 0.01605% | [30 empty] | 0.01605%
|  | Chain Conveyor | [34 empty] | 0%
|  |  |  | 90% | 9337753110 | 0.2729% | 2018-02-10: 0.2729% | 0%
|  |  |  | 10% | 1037376060 | 0.03032% | [30 empty] | 0.03032%
F4 |  |  |  | 100% | 946708297.5 | 0.01605% | [30 empty] | 0.01605%
|  | Magnet Separator / Metal Detector | [34 empty] | 0%
|  |  |  | 90% | 787269892.5 | 0.02301% | 2017-11-12: 0.02301% | 0%
|  |  |  | 10% | 87588480 | 0.00256% | 2018-02-10: 0.00256% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.01605% | 2017-11-12: 0.01605% | 0%
|  | Roots Blower | [34 empty] | 0%
|  |  |  | 90% | 6750129382.5 | 0.1973% | 2017-11-12: 0.1973% | 0%
|  |  |  | 10% | 749976360 | 0.02192% | 2018-02-10: 0.02192% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.01605% | 2017-11-12: 0.01605% | 0%
|  | General Fan | [34 empty] | 0%
|  |  |  | 90% | 4770150735 | 0.1394% | 2017-12-12: 0.1394% | 0%
|  |  |  | 10% | 529978732.5 | 0.01549% | 2018-04-11: 0.01549% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.00306% | 2017-12-12: 0.00306% | 0%
|  | Bag Filter | [34 empty] | 0%
|  |  |  | 90% | 13833163417.5 | 0.4043% | 2017-12-12: 0.4043% | 1e-05%
|  |  |  | 10% | 1536904110 | 0.04492% | 2018-04-11: 0.04492% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.01605% | 2017-12-12: 0.01605% | 0%
|  | Belt Weigher (Belt Scale) | [34 empty] | 0%
|  |  |  | 90% | 134804145 | 0.00394% | 2018-03-12: 0.00394% | 0%
|  |  |  | 10% | 15054270 | 0.00044% | [30 empty] | 0.00044%
F4 |  |  |  | 100% | 946708297.5 | 0.01605% | [30 empty] | 0.01605%
B339 |  | Coal Grinding Mill | [34 empty] | 0%
|  |  |  | 90% | 19361159790 | 0.5659% | 2017-11-12: 0.01811%; 2018-02-10: 0.5458% | 0.00201%
|  |  |  | 10% | 2151392040 | 0.06288% | 2017-12-12: 0.00201% | 0.06087%
F4 |  |  |  | 100% | 946708297.5 | 0.00774% | 2017-11-12: 0.00025% | 0.00749%
|  | Weighing Feeder | [34 empty] | 0%
|  |  |  | 90% | 4049940772.5 | 0.1184% | 2018-03-12: 0.1184% | 0%
|  |  |  | 10% | 449917387.5 | 0.01315% | [30 empty] | 0.01315%
F4 |  |  |  | 100% | 946708297.5 | 0.03028% | [30 empty] | 0.03028%
|  | Coal Weigher | [34 empty] | 0%
|  |  |  | 90% | 2295091890 | 0.06708% | 2018-03-12: 0.06708% | 0%
|  |  |  | 10% | 254896162.5 | 0.00745% | [30 empty] | 0.00745%
F4 |  |  |  | 100% | 946708297.5 | 0.01605% | [30 empty] | 0.01605%
|  | Process Fan | [34 empty] | 0%
|  |  |  | 90% | 13094819902.5 | 0.3827% | 2018-03-12: 0.3827% | 0%
|  |  |  | 10% | 1455132052.5 | 0.04253% | 2018-03-12: 0.04253% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.00306% | 2018-03-12: 0.00306% | 0%
|  | Screw Confeyor | [34 empty] | 0%
|  |  |  | 90% | 1350094305 | 0.03946% | 2018-01-11: 0.01315% | 0.02631%
|  |  |  | 10% | 149858415 | 0.00438% | 2018-04-11: 0.00146% | 0.00292%
F4 |  |  |  | 100% | 946708297.5 | 0.01605% | 2018-01-11: 0.00802% | 0.00803%
|  | Rotary Valve | [34 empty] | 0%
|  |  |  | 90% | 540243007.5 | 0.01579% | 2018-01-11: 0.01579% | 0%
|  |  |  | 10% | 59874937.5 | 0.00175% | 2018-04-11: 0.00176% | -1e-05%
F4 |  |  |  | 100% | 946708297.5 | 0.0084% | 2018-01-11: 0.0084% | 0%
|  | Grizzly Feeder (Vibrating Screen) | [34 empty] | 0%
|  |  |  | 90% | 1350094305 | 0.03946% | 2018-01-11: 0.03946% | 0%
|  |  |  | 10% | 149858415 | 0.00438% | 2018-03-12: 0.00438% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.01604% | 2018-03-12: 0.01604% | 0%
|  | Hoist | [34 empty] | 0%
|  |  |  | 90% | 1214948017.5 | 0.03551% | 2018-01-11: 0.03551% | 0%
|  |  |  | 10% | 135146287.5 | 0.00395% | 2018-03-12: 0.00395% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.03028% | 2018-03-12: 0.03028% | 0%
|  | Shake Out Machine | [34 empty] | 0%
|  |  |  | 90% | 10125023002.5 | 0.2959% | 2017-11-12: 0.2959% | 0%
|  |  |  | 10% | 1124964540 | 0.03288% | 2018-02-10: 0.03288% | 0%
F4 |  |  |  | 100% | 946708297.5 | 0.00509% | 2017-11-12: 0.00509% | 0%
|  | Refractory | [34 empty] | 0%
|  |  |  | 90% | 29587456972.5 | 0.8648% | [30 empty] | 0.8648%
|  |  |  | 10% | 3287647282.5 | 0.09609% | [30 empty] | 0.09609%
F4 |  |  |  | 100% | 946708297.5 | 0.2919% | [30 empty] | 0.2919%
|  | Other Small Equipment | [34 empty] | 0%
B350 |  | Other Mechanical Equipment (such as Pump, Double Flap Dumper, Steam, Heater) | [34 empty] | 0%
|  |  |  | 90% | 776321332.5 | 0.02269% | 2018-03-12: 0.02269% | 0%
|  |  |  | 10% | 86219910 | 0.00252% | 2018-03-12: 0.00253% | -1e-05%
F4 |  |  |  | 100% | 946708297.5 | 0.5456% | [30 empty] | 0.5456%
B351 |  | Auxillary Equipment (such as Damper, Ex-Joint, Polymer Liner, Small Parts of Rotary Klln & Rotary Dryer, etc.) | [34 empty] | 0%
|  |  |  | 90% | 39352546065 | 1.15% | 2017-11-12: 1.15% | -9e-05%
|  |  |  | 10% | 4372581150 | 0.1278% | 2018-03-12: 0.1277% | 0.00014%
F4 |  |  |  | 100% | 946708297.5 | 0.01605% | 2017-11-12: 0.01605% | 0%
B352 |  | Piping & Fitting | [34 empty] | 0%
|  |  |  | 90% | 15693734332.5 | 0.4587% | [30 empty] | 0.4587%
|  |  |  | 10% | 1743900322.5 | 0.05097% | [30 empty] | 0.05097%
F4 |  |  |  | 100% | 940549732.5 | 0.00439% | [30 empty] | 0.00439%
0%
| P3FH - 28 M.13.13.2.13.2.2 System 2 - Electric Smelting Furnace | [35 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.1 Hot Charge Equipment | [35 empty] | 0%
B18 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.1.13.2.2.1.1 Container (2111) | [35 empty] | 0%
| PRWM1000 | CONTAINER (2111) - RFQ | [34 empty] | 0%
| PRWM1001 | CONTAINER (2111) - Recieved of Bids | [34 empty] | 0%
| PRWM1002 | CONTAINER (2111) - CBE | [34 empty] | 0%
| PRWM1003 | CONTAINER (2111) - LOI | [34 empty] | 0%
| PRWM1004 | CONTAINER (2111) - PO |  | 20% | 862883385 | 0.02522% | 2017-07-15: 0.02522% | 0%
| PRWM1010 | CONTAINER (2111) - Fabrication by SIKO |  | 60% | 2588992297.5 | 0.07567% | 2018-05-11: 0.07567% | 0%
| PRWM1011 | CONTAINER (2111) - Packing by SIKO | [34 empty] | 0%
| PRWM1020 | CONTAINER (2111) - Delivery by WIKA |  | 20% | 863225527.5 | 0.02523% | [30 empty] | 0.02523%
F4 |  |  |  | 100% | 561455842.5 | 0.01641% | [30 empty] | 0.01641%
B19 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.1.13.2.2.1.2 Transfer Car (2112) | [35 empty] | 0%
| PRWM1021 | TRANSFER CAR (2112) - RFQ | [34 empty] | 0%
| PRWM1022 | TRANSFER CAR (2112) - Recieved of Bids | [34 empty] | 0%
| PRWM1023 | TRANSFER CAR (2112) - CBE | [34 empty] | 0%
| PRWM1024 | TRANSFER CAR (2112) - LOI | [34 empty] | 0%
| PRWM1025 | TRANSFER CAR (2112) - PO |  | 20% | 1114358122.5 | 0.03257% | 2017-07-15: 0.03257% | 0%
| PRWM1030 | TRANSFER CAR (2112) - Fabrication by SIKO |  | 60% | 3342732225 | 0.0977% | 2018-03-12: 0.09771% | -1e-05%
| PRWM1040 | TRANSFER CAR (2112) - Packing by SIKO | [34 empty] | 0%
| PRWM1050 | TRANSFER CAR (2112) - Delivery by WIKA |  | 20% | 1114358122.5 | 0.03257% | 2018-04-11: 0.03257% | 0%
F4 |  |  |  | 100% | 67744215 | 0.00198% | [30 empty] | 0.00198%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.1.13.2.2.1.3 Container Shaft with Rail (2113) | [35 empty] | 0%
| PRWM1051 | CONTAINER SHAFT WITH RAIL (2113) - RFQ | [34 empty] | 0%
| PRWM1052 | CONTAINER SHAFT WITH RAIL (2113) - Recieved of Bids | [34 empty] | 0%
| PRWM1053 | CONTAINER SHAFT WITH RAIL (2113) - CBE | [34 empty] | 0%
| PRWM1054 | CONTAINER SHAFT WITH RAIL (2113) - LOI | [34 empty] | 0%
| PRWM1055 | CONTAINER SHAFT WITH RAIL (2113) - PO | [34 empty] | 0%
| PRWM1060 | CONTAINER SHAFT WITH RAIL (2113) - Fabrication by SIKO | [34 empty] | 0%
| PRWM1070 | CONTAINER SHAFT WITH RAIL (2113) - Packing by SIKO | [34 empty] | 0%
| PRWM1080 | CONATINER SHAFT WITH RAIL (2113) - Delivery by WIKA | [34 empty] | 0%
B20 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.1.13.2.2.1.4 Hot Charge Crane (2114) | [35 empty] | 0%
| PRWM1081 | HOT CHARGE CRANE (2114) - RFQ | [34 empty] | 0%
| PRWM1082 | HOT CHARGE CRANE (2114) - Recieved of Bids | [34 empty] | 0%
| PRWM1083 | HOT CHARGE CRANE (2114) - CBE | [34 empty] | 0%
| PRWM1084 | HOT CHARGE CRANE (2114) - LOI | [34 empty] | 0%
| PRWM1085 | HOT CHARGE CRANE (2114) - PO |  | 25% | 5018546190 | 0.1467% | 2017-05-16: 0.1467%; 2017-08-14: -0.02934% | 0.02934%
| PRWM1100 | HOT CHARGE CRANE (2114) - Fabrication by Hyundai FOB Korea |  | 60% | 12044784570 | 0.352% | [30 empty] | 0.352%
| PRWM1110 | HOT CHARGE CRANE(2114) - Foreign Delivery by Hyundai |  | 15% | 3011196142.5 | 0.08801% | [30 empty] | 0.08801%
F4 |  |  |  | 100% | 5474280 | 0.00016% | [30 empty] | 0.00016%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.2 Furnace Charging System | [35 empty] | 0%
B17 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.2.13.2.2.2.1 Top Bin Cover (2121) | [35 empty] | 0%
| PRWM1111 | TOP BIN COVER (2121) - RFQ | [34 empty] | 0%
| PRWM1112 | TOP BIN COVER (2121) - Recieved of Bids | [34 empty] | 0%
| PRWM1113 | TOP BIN COVER (2121) - CBE | [34 empty] | 0%
| PRWM1114 | TOP BIN COVER (2121) - LOI | [34 empty] | 0%
| PRWM1115 | TOP BIN COVER (2121) - PO |  | 20% | 743475652.5 | 0.02173% | 2017-07-15: 0.02173% | 0%
| PRWM1120 | TOP BIN COVER (2121) - Fabrication by SIKO |  | 60% | 2230426957.5 | 0.06519% | 2018-03-12: 0.06519% | 0%
| PRWM1130 | TOP BIN COVER (2121) - Packing by SIKO | [34 empty] | 0%
| PRWM1140 | TOP BIN COVER (2121) - Delivery by WIKA |  | 20% | 743475652.5 | 0.02173% | 2018-04-11: 0.02173% | 0%
F4 |  |  |  | 100% | 132409147.5 | 0.00387% | [30 empty] | 0.00387%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.2.13.2.2.2.2 Dust Sucking Hood c/w Motorized Damper (2131) | [35 empty] | 0%
| PRWM1141 | DUST SUCKING HOOD C/W MOTORIZED DAMPER (2131) - RFQ | [34 empty] | 0%
| PRWM1142 | DUST SUCKING HOOD C/W MOTORIZED DAMPER (2131) - Recieved of Bids | [34 empty] | 0%
| PRWM1143 | DUST SUCKING HOOD C/W MOTORIZED DAMPER (2131) - CBE | [34 empty] | 0%
| PRWM1144 | DUST SUCKING HOOD C/W MOTORIZED DAMPER (2131) - LOI | [34 empty] | 0%
| PRWM1145 | DUST SUCKING HOOD C/W MOTORIZED DAMPER (2131) - PO | [34 empty] | 0%
| PRWM1150 | DUST SUCKING HOOD C/W MOTORIZED DAMPER (2131) - Fabrication by SIKO | [34 empty] | 0%
| PRWM1160 | DUST SUCKING HOOD C/W MOTORIZED DAMPER (2131) - Packing by SIKO | [34 empty] | 0%
| PRWM1170 | DUST SUCKING HOOD C/W MOTORIZED DAMPER (2131) - Delivery by WIKA | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.2.13.2.2.2.3 Bag Filter (2132) | [35 empty] | 0%
| PRWM1171 | BAG FILTER (2132) - RFQ | [34 empty] | 0%
| PRWM1172 | BAG FILTER (2132) - Recieved of Bids | [34 empty] | 0%
| PRWM1173 | BAG FILTER (2132) - CBE | [34 empty] | 0%
| PRWM1174 | BAG FILTER (2132) - LOI | [34 empty] | 0%
| PRWM1175 | BAG FILTER (2132) - PO | [34 empty] | 0%
| PRWM1180 | BAG FILTER (2132) - Fabrication by SIKO | [34 empty] | 0%
| PRWM1190 | BAG FILTER (2132) - Packing by SIKO | [34 empty] | 0%
| PRWM1200 | BAG FILTER (2132) - Delivery by WIKA | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.2.13.2.2.2.4 Fan (2133) | [35 empty] | 0%
| PRWM1201 | FAN (2133) - RFQ | [34 empty] | 0%
| PRWM1202 | FAN (2133) - Recieved of Bids | [34 empty] | 0%
| PRWM1203 | FAN (2133) - CBE | [34 empty] | 0%
| PRWM1204 | FAN (2133) - LOI | [34 empty] | 0%
| PRWM1205 | FAN (2133) - PO | [34 empty] | 0%
| PRWM1210 | FAN (2133) - Procurement by SIKO | [34 empty] | 0%
| PRWM1220 | FAN (2133) - Packing by SIKO | [34 empty] | 0%
| PRWM1230 | FAN (2133) - Foreign Delivery by WIKA | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.2.13.2.2.2.5 Screw Conveyor (2134) | [35 empty] | 0%
| PRWM1231 | SCREW CONVEYOR (2134) - RFQ | [34 empty] | 0%
| PRWM1232 | SCREW CONVEYOR (2134) - Recieved of Bids | [34 empty] | 0%
| PRWM1233 | SCREW CONVEYOR (2134) - CBE | [34 empty] | 0%
| PRWM1234 | SCREW CONVEYOR (2134) - LOI | [34 empty] | 0%
| PRWM1235 | SCREW CONVEYOR (2134) - PO | [34 empty] | 0%
| PRWM1240 | SCREW CONVEYOR (2134) - Fabrication by SIKO | [34 empty] | 0%
| PRWM1250 | SCREW CONVEYOR (2134) - Packing by SIKO | [34 empty] | 0%
| PRWM1260 | SCREW CONVEYOR (2134) - Delivery by WIKA | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.2.13.2.2.2.6 Air Compressor (2135) | [35 empty] | 0%
| PRWM1261 | AIR COMPRESSOR (2135) - RFQ | [34 empty] | 0%
| PRWM1262 | AIR COMPRESSOR (2135) - Recieved of Bids | [34 empty] | 0%
| PRWM1263 | AIR COMPRESSOR (2135) - CBE | [34 empty] | 0%
| PRWM1264 | AIR COMPRESSOR (2135) - LOI | [34 empty] | 0%
| PRWM1265 | AIR COMPRESSOR (2135) - PO | [34 empty] | 0%
| PRWM1270 | AIR COMPRESSOR (2135) - Procurement by WIKA | [34 empty] | 0%
| PRWM1280 | AIR COMPRESSOR (2135) - Packing by WIKA | [34 empty] | 0%
| PRWM1290 | AIR COMPRESSOR (2135) - Foreign Delivery by WIKA | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.2.13.2.2.2.7 Multi Cyclone (2136) | [35 empty] | 0%
| PRWM1291 | MULTI CYCLONE (2136) - RFQ | [34 empty] | 0%
| PRWM1292 | MULTI CYCLONE (2136) - Recieved of Bids | [34 empty] | 0%
| PRWM1293 | MULTI CYCLONE (2136) - CBE | [34 empty] | 0%
| PRWM1294 | MULTI CYCLONE (2136) - LOI | [34 empty] | 0%
| PRWM1295 | MULTI CYCLONE (2136) - PO | [34 empty] | 0%
| PRWM1300 | MULTI CYCLONE (2136) - Fabrication by SIKO | [34 empty] | 0%
| PRWM1310 | MULTI CYCLONE (2136) - Packing by SIKO | [34 empty] | 0%
| PRWM1320 | MULTI CYCLONE (2136) - Delivery by WIKA | [34 empty] | 0%
B25 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.2.13.2.2.2.8 Duct, Stack, and Support (2199) AUXILIARIES | [35 empty] | 0%
| PRWM1321 | DUST,STACK,SUPPORT (2199) - RFQ | [34 empty] | 0%
| PRWM1322 | DUST,STACK,SUPPORT (2199) - Recieved of Bids | [34 empty] | 0%
| PRWM1323 | DUST,STACK,SUPPORT (2199) - CBE | [34 empty] | 0%
| PRWM1324 | DUST,STACK,SUPPORT (2199) - LOI | [34 empty] | 0%
| PRWM1325 | DUST,STACK,SUPPORT (2199) - PO |  | 20% | 147463417.5 | 0.00431% | 2017-07-15: 0.00431% | 0%
| PRWM1330 | DUST,STACK,SUPPORT (2199) - Fabrication by SIKO |  | 60% | 442048110 | 0.01292% | [30 empty] | 0.01292%
| PRWM1340 | DUST,STACK,SUPPORT (2199) - Packing by SIKO | [34 empty] | 0%
| PRWM1350 | DUST,STACK,SUPPORT (2199) - Delivery by WIKA |  | 20% | 147121275 | 0.0043% | [30 empty] | 0.0043%
F4 |  |  |  | 100% | 1083223155 | 0.03166% | [30 empty] | 0.03166%
B23 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.2.13.2.2.2.9 Dust Collecting Equipment Platform (xxxx) | [35 empty] | 0%
| PRWM1351 | DUST COLLECTING EQUIPMENT PLATFORM - RFQ | [34 empty] | 0%
| PRWM1352 | DUST COLLECTING EQUIPMENT PLATFORM - Recieved of Bids | [34 empty] | 0%
| PRWM1353 | DUST COLLECTING EQUIPMENT PLATFORM - CBE | [34 empty] | 0%
| PRWM1354 | DUST COLLECTING EQUIPMENT PLATFORM - LOI | [34 empty] | 0%
| PRWM1355 | DUST COLLECTING EQUIPMENT PLATFORM - PO |  | 20% | 1103409562.5 | 0.03225% | 2017-07-15: 0.03225% | 0%
| PRWM1360 | DUST COLLECTING EQUIPMENT PLATFORM - Procurement Cycle |  | 60% | 3309886545 | 0.09674% | 2018-03-12: 0.09673% | 1e-05%
| PRWM1370 | DUST COLLECTING EQUIPMENT PLATFORM - Fabrication | [34 empty] | 0%
| PRWM1380 | DUST COLLECTING EQUIPMENT PLATFORM - Delivery |  | 20% | 1103067420 | 0.03224% | 2018-04-11: 0.03225% | -1e-05%
F4 |  |  |  | 100% | 243947602.5 | 0.00713% | [30 empty] | 0.00713%
B21 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.2.13.2.2.2.10 Furnace Top Bin (2137) | [35 empty] | 0%
| PRWM1381 | FURNACE TOP BIN (2137) - RFQ | [34 empty] | 0%
| PRWM1382 | FURNACE TOP BIN (2137) - Recieved of Bids | [34 empty] | 0%
| PRWM1383 | FURNACE TOP BIN (2137) - CBE | [34 empty] | 0%
| PRWM1384 | FURNACE TOP BIN (2137) - LOI | [34 empty] | 0%
| PRWM1385 | FURNACE TOP BIN (2137) - PO |  | 20% | 1776061717.5 | 0.05191% | 2017-07-15: 0.05191% | 0%
| PRWM1390 | FURNACE TOP BIN (2137) - Fabrication by SIKO |  | 60% | 5328527295 | 0.1557% | 2018-03-12: 0.1557% | 0%
| PRWM1400 | FURNACE TOP BIN (2137) - Packing by SIKO | [34 empty] | 0%
| PRWM1410 | FURNACE TOR BIN (2137) - Delivery by WIKA |  | 20% | 1776403860 | 0.05192% | 2018-04-11: 0.05192% | 0%
F4 |  |  |  | 100% | 918994755 | 0.02686% | [30 empty] | 0.02686%
B22 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.2.13.2.2.2.11 Charging Tubes (2138) | [35 empty] | 0%
| PRWM1411 | CHARGING TUBES (2138) - RFQ | [34 empty] | 0%
| PRWM1412 | CHARGING TUBES (2138) - Recieved of Bids | [34 empty] | 0%
| PRWM1413 | CHARGING TUBES (2138) - CBE | [34 empty] | 0%
| PRWM1414 | CHARGING TUBES (2138) - LOI | [34 empty] | 0%
| PRWM1415 | FURNACE TOP BIN (2137) - PO |  | 20% | 1638520432.5 | 0.04789% | 2017-07-15: 0.04788% | 1e-05%
| PRWM1420 | CHARGING TUBES (2138) - Fabrication by SIKO |  | 60% | 4915219155 | 0.1437% | 2018-03-12: 0.1437% | 0%
| PRWM1430 | CHARGING TUBES (2138) - Packing by SIKO | [34 empty] | 0%
| PRWM1440 | CHARGING TUBES (2138) - Delivery by WIKA |  | 20% | 1638178290 | 0.04788% | 2018-04-11: 0.04788% | 0%
F4 |  |  |  | 100% | 126934867.5 | 0.00371% | [30 empty] | 0.00371%
B35 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.2.13.2.2.2.12 Furnace Roof Equipment (2139) | [35 empty] | 0%
| PRWM1441 | FURNACE ROOF EQPT (2139) - RFQ | [34 empty] | 0%
| PRWM1442 | FURNACE ROOF EQPT (2139) - Recieved of Bids | [34 empty] | 0%
| PRWM1443 | FURNACE ROOF EQPT (2139) - CBE | [34 empty] | 0%
| PRWM1444 | FURNACE ROOF EQPT (2139) - LOI | [34 empty] | 0%
| PRWM1445 | FURNACE ROOF EQPT (2139) - PO |  | 25% | 1039428915 | 0.03038% | 2017-07-15: 0.03038% | 0%
| PRWM1460 | FURNACE ROOF EQPT (2139) - Fabrication |  | 60% | 2494560967.5 | 0.07291% | 2018-04-11: 0.0729% | 1e-05%
| PRWM1470 | FURNACE ROOF EQPT (2139) - Delivery by Chiyoda CIP Jakarta Port |  | 15% | 623383635 | 0.01822% | [30 empty] | 0.01822%
F4 |  |  |  | 100% | 6842850 | 0.0002% | [30 empty] | 0.0002%
B31 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.2.13.2.2.2.16 Electrode Suspension Device (2143) | [35 empty] | 0%
| PRWM1471 | ELECTRODE SUSPENSION DEVICE (2143) - RFQ | [34 empty] | 0%
| PRWM1472 | ELECTRODE SUSPENSION DEVICE (2143) - Recieved of Bids | [34 empty] | 0%
| PRWM1473 | ELECTRODE SUSPENSION DEVICE (2143) - CBE | [34 empty] | 0%
| PRWM1474 | ELECTRODE SUSPENSION DEVICE (2143) - LOI | [34 empty] | 0%
| PRWM1475 | ELECTRODE SUSPENSION DEVICE (2143) - PO |  | 25% | 2223926250 | 0.065% | 2017-04-16: 0.065% | 0%
| PRWM1580 | ELECTRODE SUSPENSION DEVICE (2143) - Fabrication by Chiyoda |  | 60% | 5337080857.5 | 0.156% | 2018-03-12: 0.156% | 0%
| PRWM1590 | ELECTRODE SUSPENSION DEVICE (2143) - Delivery by Chiyoda CIP Jakarta Port |  | 15% | 1334013607.5 | 0.03899% | [30 empty] | 0.03899%
F4 |  |  |  | 100% | 17107125 | 0.0005% | [30 empty] | 0.0005%
B26 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.2.13.2.2.2.17 Electrode Equipment (2144) | [35 empty] | 0%
| PRWM1591 | ELECTRODE EQPT (2144) - RFQ | [34 empty] | 0%
| PRWM1592 | ELECTRODE EQPT (2144) - Recieved of Bids | [34 empty] | 0%
| PRWM1593 | ELECTRODE EQPT (2144) - CBE | [34 empty] | 0%
| PRWM1594 | ELECTRODE EQPT (2144) - LOI | [34 empty] | 0%
| PRWM1595 | ELECTRODE EQPT (2144) - PO |  | 25% | 11106971977.5 | 0.3246% | 2017-04-16: 0.3246% | 0%
| PRWM1610 | ELECTRODE EQPT (2144) - Fabrication by Chiyoda |  | 60% | 26657006460 | 0.7791% | 2018-04-11: 0.7791% | 0%
| PRWM1620 | ELECTRODE EQPT (2144) - Delivery by Chiyoda CIP Jakarta Port |  | 15% | 6664251615 | 0.1948% | [30 empty] | 0.1948%
F4 |  |  |  | 100% | 789664890 | 0.02308% | [30 empty] | 0.02308%
B29 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.2.13.2.2.2.18 Water Cooling Equipment for Electrode & Trafo (2145) | [35 empty] | 0%
| PRWM1621 | WATER COOLING EQPT FOR ELECTRODE&TRAFO (2145) - RFQ | [34 empty] | 0%
| PRWM1622 | WATER COOLING EQPT FOR ELECTRODE&TRAFO (2145) - Recieved of Bids | [34 empty] | 0%
| PRWM1623 | WATER COOLING EQPT FOR ELECTRODE&TRAFO (2145) - CBE | [34 empty] | 0%
| PRWM1624 | WATER COOLING EQPT FOR ELECTRODE&TRAFO (2145) - LOI | [34 empty] | 0%
| PRWM1625 | WATER COOLING EQPT FOR ELECTRODE&TRAFO (2145) - PO |  | 25% | 422203845 | 0.01234% | 2017-04-16: 0.01234% | 0%
| PRWM1640 | WATER COOLING EQPT FOR ELECTRODE&TRAFO (2145) - Fabrication |  | 60% | 1013083942.5 | 0.02961% | [30 empty] | 0.02961%
| PRWM1650 | WATER COOLING EQPT FOR ELECTRODE&TRAFO (2145) - Delivery by Chiyoda CIP Jakarta Port |  | 15% | 253185450 | 0.0074% | [30 empty] | 0.0074%
F4 |  |  |  | 100% | 3421425 | 0.0001% | [30 empty] | 0.0001%
B28 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.2.13.2.2.2.19 Secondary Current Supply Equipment (2146) | [35 empty] | 0%
| PRWM1651 | SECONDARY CURRENT SUPPLY EQPT (2146) - RFQ | [34 empty] | 0%
| PRWM1652 | SECONDARY CURRENT SUPPLY EQPT (2146) - Recieved of Bids | [34 empty] | 0%
| PRWM1653 | SECONDARY CURRENT SUPPLY EQPT (2146) - CBE | [34 empty] | 0%
| PRWM1654 | SECONDARY CURRENT SUPPLY EQPT (2146) - LOI | [34 empty] | 0%
| PRWM1655 | SECONDARY CURRENT SUPPLY EQPT (2146) - PO |  | 25% | 5724386167.5 | 0.1673% | 2017-04-16: 0.1673% | 0%
| PRWM1670 | SECONDARY CURRENT SUPPLY EQPT (2146) - Fabrication |  | 60% | 13738389945 | 0.4015% | 2018-04-11: 0.4015% | 0%
| PRWM1680 | SECONDARY CURRENT SUPPLY EQPT (2146) - Delivery by Chiyoda CIP Jakarta Port |  | 15% | 3434768557.5 | 0.1004% | [30 empty] | 0.1004%
F4 |  |  |  | 100% | 124882012.5 | 0.00365% | [30 empty] | 0.00365%
B41 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.2.13.2.2.2.20 Hoist dor Paste Charge (2147) | [35 empty] | 0%
| PRWM1681 | HOIST FOR PASTE CHARGE (2147) - RFQ | [34 empty] | 0%
| PRWM1682 | HOIST FOR PASTE CHARGE (2147) - Recieved of Bids | [34 empty] | 0%
| PRWM1683 | HOIST FOR PASTE CHARGE (2147) - CBE | [34 empty] | 0%
| PRWM1684 | HOIST FOR PASTE CHARGE (2147) - LOI | [34 empty] | 0%
| PRWM1685 | HOIST FOR PASTE CHARGE (2147) - PO |  | 20% | 409544572.5 | 0.01495% | 2017-04-16: 0.01196%; 2017-08-14: 0.00299% | 0%
| PRWM1690 | HOIST FOR PASTE CHARGE (2147) - Fabrication by SIKO |  | 60% | 1228975860 | 0.03592% | 2018-04-11: 0.03592% | 0%
| PRWM1700 | HOIST FOR PASTE CHARGE (2147) - Packing by SIKO | [34 empty] | 0%
| PRWM1710 | HOIST FOR PASTE CHARGE (2147) - Delivery by WIKA |  | 20% | 409886715 | 0.009% | [30 empty] | 0.009%
F4 |  |  |  | 100% | 0 | 0% | [30 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.3 Electrical Smelting Furnace Equipment | [35 empty] | 0%
B27 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.3.13.2.2.3.1 Furnace Roof (Air Cooled Type) (2211) | [35 empty] | 0%
| PRWM1711 | FURNACE ROOF (AIR COOLED TYPE) (2211) - RFQ | [34 empty] | 0%
| PRWM1712 | FURNACE ROOF (AIR COOLED TYPE) (2211) - Recieved of Bids | [34 empty] | 0%
| PRWM1713 | FURNACE ROOF (AIR COOLED TYPE) (2211) - CBE | [34 empty] | 0%
| PRWM1714 | FURNACE ROOF (AIR COOLED TYPE) (2211) - LOI | [34 empty] | 0%
| PRWM1715 | FURNACE ROOF (AIR COOLED TYPE) (2211) - PO |  | 20% | 136857000 | 0.004% | 2017-10-13: 0.005% | -0.001%
| PRWM1730 | FURNACE ROOF (AIR COOLED TYPE) (2211) - Fabrication |  | 60% | 410913142.5 | 0.01201% | [30 empty] | 0.01201%
| PRWM1740 | FURNACE ROOF (AIR COOLED TYPE) (2211) - Delivery |  | 20% | 136857000 | 0.004% | [30 empty] | 0.004%
F4 |  |  |  | 100% | 14369985 | 0.00042% | [30 empty] | 0.00042%
B33 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.3.13.2.2.3.2 Furnace Shell (2221) | [35 empty] | 0%
| PRWM1741 | FURNACE SHELL (2221) - RFQ | [34 empty] | 0%
| PRWM1742 | FURNACE SHELL (2221) - Recieved of Bids | [34 empty] | 0%
| PRWM1743 | FURNACE SHELL (2221) - CBE | [34 empty] | 0%
| PRWM1744 | FURNACE SHELL (2221) - LOI | [34 empty] | 0%
| PRWM1745 | FURNACE SHELL (2221) - PO |  | 25% | 7904518177.5 | 0.1848% | 2017-09-13: 0.1848% | 1e-05%
| PRWM1760 | FURNACE SHELL (2221) - Fabrication |  | 60% | 18970433055 | 0.5545% | [30 empty] | 0.5545%
| PRWM1770 | FURNACE SHELL (2221) - Delivery |  | 15% | 4742437192.5 | 0.1848% | [30 empty] | 0.1848%
F4 |  |  |  | 100% | 23706027397.5 | 0.6929% | [30 empty] | 0.6929%
B30 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.3.13.2.2.3.3 Copper Coolers (2223) | [35 empty] | 0%
| PRWM1771 | COPPER COOLERS (2223) - RFQ | [34 empty] | 0%
| PRWM1772 | COPPER COOLERS (2223) - Recieved of Bids | [34 empty] | 0%
| PRWM1790 | COPPER COOLERS (2223) - Fabrication by HTV | [34 empty] | 0%
| PRWM1773 | COPPER COOLERS (2223) - CBE | [34 empty] | 0%
| PRWM1774 | COPPER COOLERS (2223) - LOI | [34 empty] | 0%
| PRWM1775 | COPPER COOLERS (2223) - PO |  | 25% | 2319041865 | 0.06778% | 2017-04-16: 0.06778% | 0%
| PRWM1791 | COPPER COOLERS (2223) - Inspection |  | 60% | 5565632047.5 | 0.1627% | [30 empty] | 0.1627%
| PRWM1800 | COPPER COOLERS (2223) - Delivery |  | 15% | 1391493547.5 | 0.04067% | [30 empty] | 0.04067%
F4 |  |  |  | 100% | 3483010650 | 0.1018% | [30 empty] | 0.1018%
B24 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.3.13.2.2.3.4 Furnace Refractory (2222) | [35 empty] | 0%
| PRWM1820 | FURNACE REFRACTORY (2222) - Fabrication by HTV | [34 empty] | 0%
| PRWM1801 | FURNACE REFRACTORY (2222) - RFQ | [34 empty] | 0%
| PRWM1802 | FURNACE REFRACTORY (2222) - Recieved of Bids | [34 empty] | 0%
| PRWM1803 | FURNACE REFRACTORY (2222) - CBE | [34 empty] | 0%
| PRWM1804 | FURNACE REFRACTORY (2222) - LOI | [34 empty] | 0%
| PRWM1805 | FURNACE REFRACTORY (2222) - PO | [34 empty] | 0%
| PRWM1821 | FURNACE REFRACTORY (2222) - Inspection | [34 empty] | 0%
| PRWM1830 | FURNACE REFRACTORY (2222) - Delivery | [34 empty] | 0%
0%
|  | Refractory Furnace Shell Lining | [34 empty] | 0%
|  | Sidewall | [34 empty] | 0%
|  | Hearth+Stadium | [34 empty] | 0%
|  | Roof Bricks, monolith+Bottom Monolithics | [34 empty] | 0%
|  | Miscelaneous and Insulation Boards | [34 empty] | 0%
|  | Hanger Ass't/ Isolation/ Sealing Components | [34 empty] | 0%
|  | Misc Set of Bits and Places | [34 empty] | 0%
|  |  |  | 25% | 35495915805 | 1.037% | 2017-02-15: 1.037% | 0%
|  |  |  | 15% | 21297686340 | 0.6225% | 2017-10-13: 0.6225% | 0%
|  |  |  | 15% | 21297686340 | 0.6225% | 2017-10-13: 0.1246%; 2017-12-12: 0.412%; 2018-01-11: 0.08584% | 1e-05%
|  |  |  | 15% | 21297686340 | 0.6225% | 2018-01-11: 0.3195%; 2018-03-12: 0.303% | 0%
|  |  |  | 15% | 21297686340 | 0.6225% | 2018-03-12: 0.6225% | 0%
|  |  |  | 15% | 21297002055 | 0.6225% | 2018-03-12: 0.00452% | 0.6179%
0%
|  | Copper Coolers | [34 empty] | 0%
|  | Sidewall Coopers (Upper+Mid) | [34 empty] | 0%
|  | Sidewall Coopers (Lower) | [34 empty] | 0%
|  |  |  | 25% | 46735639072.5 | 1.366% | 2017-02-15: 1.366% | 0%
|  |  |  | 12% | 22432915155 | 0.6557% | 2017-08-14: 0.6557% | 0%
|  |  |  | 12% | 22432915155 | 0.6557% | 2017-08-14: 0.4236%; 2018-03-12: 0.232% | 0%
|  |  |  | 12% | 22432915155 | 0.6557% | 2018-03-12: 0.6557% | 0%
|  |  |  | 12% | 22432915155 | 0.6557% | 2018-03-12: 0.6557% | 0%
|  |  |  | 12% | 22432915155 | 0.6557% | 2018-03-12: 0.6557% | 0%
|  |  |  | 15% | 28041999300 | 0.8196% | 2018-04-11: 0.3717% | 0.4479%
0%
|  | Offgas Stack Assembly | [34 empty] | 0%
|  | Offgas Refractory-Comb+Spray Chamber | [34 empty] | 0%
|  | Offgas Refractory-Emergency Duct+Stack | [34 empty] | 0%
|  | Offgas Refractory-Insulation Board | [34 empty] | 0%
|  |  |  | 25% | 8542271797.5 | 0.2497% | 2017-02-15: 0.2497% | 0%
|  |  |  | 20% | 6833612152.5 | 0.1997% | [30 empty] | 0.1997%
|  |  |  | 20% | 6833612152.5 | 0.1997% | [30 empty] | 0.1997%
|  |  |  | 20% | 6833612152.5 | 0.1997% | [30 empty] | 0.1997%
|  |  |  | 15% | 5125294650 | 0.1498% | [30 empty] | 0.1498%
0%
|  | Cooling Water System | [34 empty] | 0%
|  | Flexible Interconnecting Piping-Coolers | [34 empty] | 0%
|  |  |  | 25% | 528952305 | 0.01546% | 2017-02-15: 0.01546% | 0%
|  |  |  | 12% | 253869735 | 0.00742% | [30 empty] | 0.00742%
|  |  |  | 12% | 253869735 | 0.00742% | [30 empty] | 0.00742%
|  |  |  | 12% | 253869735 | 0.00742% | [30 empty] | 0.00742%
|  |  |  | 12% | 253869735 | 0.00742% | [30 empty] | 0.00742%
|  |  |  | 12% | 253869735 | 0.00742% | [30 empty] | 0.00742%
|  |  |  | 15% | 317508240 | 0.00928% | [30 empty] | 0.00928%
0%
|  | Tapping Lounder for Metal and Slag | [34 empty] | 0%
|  | Slag and Metal Side Launder Refractory | [34 empty] | 0%
|  |  |  | 25% | 564192982.5 | 0.01649% | 2017-02-15: 0.01649% | 0%
|  |  |  | 15% | 338378932.5 | 0.00989% | [30 empty] | 0.00989%
|  |  |  | 15% | 338378932.5 | 0.00989% | [30 empty] | 0.00989%
|  |  |  | 15% | 338378932.5 | 0.00989% | [30 empty] | 0.00989%
|  |  |  | 15% | 338378932.5 | 0.00989% | [30 empty] | 0.00989%
|  |  |  | 15% | 338378932.5 | 0.00989% | [30 empty] | 0.00989%
0%
|  | Tapping Fume System for Metal and Slag Taphole | [34 empty] | 0%
|  | Miscelaneous Lining Material for Tapping Fume System | [34 empty] | 0%
|  |  |  | 25% | 169018395 | 0.00494% | 2017-02-15: 0.00494% | 0%
|  |  |  | 20% | 135146287.5 | 0.00395% | [30 empty] | 0.00395%
|  |  |  | 20% | 135146287.5 | 0.00395% | [30 empty] | 0.00395%
|  |  |  | 20% | 135146287.5 | 0.00395% | [30 empty] | 0.00395%
|  |  |  | 15% | 101274180 | 0.00296% | [30 empty] | 0.00296%
0%
|  | Primary Offgas Dedusting System | [34 empty] | 0%
|  | Miscelaneous Lining Materials | [34 empty] | 0%
|  |  |  | 25% | 281583277.5 | 0.00823% | 2017-02-15: 0.00823% | 0%
|  |  |  | 20% | 225129765 | 0.00658% | [30 empty] | 0.00658%
|  |  |  | 20% | 225129765 | 0.00658% | [30 empty] | 0.00658%
|  |  |  | 20% | 225129765 | 0.00658% | [30 empty] | 0.00658%
|  |  |  | 15% | 169702680 | 0.00496% | [30 empty] | 0.00496%
0%
F4 |  |  |  | 100% | 67059930 | 0.00196% | [30 empty] | 0.00196%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.3.13.2.2.3.5 Water Cooled Copper Block for Metal Taphole (2224) | [35 empty] | 0%
| PRWM1831 | WATER COOLED COPPER BLOCK FOR METAL TAPHOLE (2224) - RFQ | [34 empty] | 0%
| PRWM1832 | WATER COOLED COPPER BLOCK FOR METAL TAPHOLE (2224) - Recieved of Bids | [34 empty] | 0%
| PRWM1850 | WATER COOLED COPPER BLOCK FOR METAL TAPHOLE (2224) - Fabrication by HTV | [34 empty] | 0%
| PRWM1833 | WATER COOLED COPPER BLOCK FOR METAL TAPHOLE (2224) - CBE | [34 empty] | 0%
| PRWM1834 | WATER COOLED COPPER BLOCK FOR METAL TAPHOLE (2224) - LOI | [34 empty] | 0%
| PRWM1835 | WATER COOLED COPPER BLOCK FOR METAL TAPHOLE (2224) - PO | [34 empty] | 0%
| PRWM1860 | WATER COOLED COPPER BLOCK FOR METAL TAPHOLE (2224) - Inspection | [34 empty] | 0%
| PRWM1870 | WATER COOLED COPPER BLOCK FOR METAL TAPHOLE (2224) - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.3.13.2.2.3.6 Water Cooled Copper Block for Slag Taphole (2225) | [35 empty] | 0%
| PRWM1871 | WATER COOLED COPPER BLOCK FOR SLAG TAPHOLE (2225) - RFQ | [34 empty] | 0%
| PRWM1872 | WATER COOLED COPPER BLOCK FOR SLAG TAPHOLE (2225) - Recieved of Bids | [34 empty] | 0%
| PRWM1880 | WATER COOLED COPPER BLOCK FOR SLAG TAPHOLE (2225) - Fabrication by HTV | [34 empty] | 0%
| PRWM1873 | WATER COOLED COPPER BLOCK FOR SLAG TAPHOLE (2225) - CBE | [34 empty] | 0%
| PRWM1874 | WATER COOLED COPPER BLOCK FOR SLAG TAPHOLE (2225) - LOI | [34 empty] | 0%
| PRWM1875 | WATER COOLED COPPER BLOCK FOR SLAG TAPHOLE (2225) - PO | [34 empty] | 0%
| PRWM1881 | WATER COOLED COPPER BLOCK FOR SLAG TAPHOLE (2225) - Inspection | [34 empty] | 0%
| PRWM1890 | WATER COOLED COPPER BLOCK FOR SLAG TAPHOLE (2225) - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.4 Tapping Equipment | [35 empty] | 0%
B32 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.4.13.2.2.4.1 Tapping Equipment for Metal & Slag (2232) | [35 empty] | 0%
| PRWM1891 | TAPPING EQPT FOR METAL & SLAG (2232) - RFQ | [34 empty] | 0%
| PRWM1892 | TAPPING EQPT FOR METAL & SLAG (2232) - Recieved of Bids | [34 empty] | 0%
| PRWM1893 | TAPPING EQPT FOR METAL & SLAG (2232) - CBE | [34 empty] | 0%
| PRWM1894 | TAPPING EQPT FOR METAL & SLAG (2232) - LOI | [34 empty] | 0%
| PRWM1895 | TAPPING EQPT FOR METAL & SLAG (2232) - PO |  | 25% | 5624822700 | 0.1644% | 2017-08-14: 0.1644% | 0%
| PRWM1910 | TAPPING EQPT FOR METAL & SLAG (2232) - Fabrication |  | 60% | 13499232337.5 | 0.3946% | 2018-04-11: 0.3946% | 0%
| PRWM1920 | TAPPING EQPT FOR METAL & SLAG (2232) - Delivery |  | 15% | 3374551477.5 | 0.09863% | [30 empty] | 0.09863%
F4 |  |  |  | 100% | 38662102.5 | 0.00113% | [30 empty] | 0.00113%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.4.13.2.2.4.2 Slag Stopper (2233) | [35 empty] | 0%
| PRWM1921 | SLAG STOPPER (2233) - RFQ | [34 empty] | 0%
| PRWM1922 | SLAG STOPPER (2233) - Recieved of Bids | [34 empty] | 0%
| PRWM1923 | SLAG STOPPER (2233) - CBE | [34 empty] | 0%
| PRWM1924 | SLAG STOPPER (2233) - LOI | [34 empty] | 0%
| PRWM1925 | SLAG STOPPER (2233) - PO | [34 empty] | 0%
| PRWM1930 | SLAG STOPPER (2233) - Procurement Cycle | [34 empty] | 0%
| PRWM1940 | SLAG STOPPER (2233) - Fabrication | [34 empty] | 0%
| PRWM1950 | SLAG STOPPER (2233) - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.4.13.2.2.4.3 Mud Kneader (2234) | [35 empty] | 0%
| PRWM1951 | MUD KNEADER (2234) - RFQ | [34 empty] | 0%
| PRWM1952 | MUD KNEADER (2234) - Recieved of Bids | [34 empty] | 0%
| PRWM1953 | MUD KNEADER (2234) - CBE | [34 empty] | 0%
| PRWM1954 | MUD KNEADER (2234) - LOI | [34 empty] | 0%
| PRWM1955 | MUD KNEADER (2234) - PO | [34 empty] | 0%
| PRWM1960 | MUD KNEADER (2234) - Fabrication by SIKO | [34 empty] | 0%
| PRWM1970 | MUD KNEADER (2234) - Packing by SIKO | [34 empty] | 0%
| PRWM1980 | MUD KNEADER (2234) - Delivery by WIKA | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.5 Cooling System | [35 empty] | 0%
B34 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.5.13.2.2.5.1 Furnace Roof Cooling Fan (2241) | [35 empty] | 0%
| PRWM1981 | FURNACE ROOF COOLING FAN (2241) - RFQ | [34 empty] | 0%
| PRWM1982 | FURNACE ROOF COOLING FAN (2241) - Recieved of Bids | [34 empty] | 0%
| PRWM1983 | FURNACE ROOF COOLING FAN (2241) - CBE | [34 empty] | 0%
| PRWM1984 | FURNACE ROOF COOLING FAN (2241) - LOI | [34 empty] | 0%
| PRWM1985 | FURNACE ROOF COOLING FAN (2241) - PO |  | 25% | 5002123350 | 0.1462% | 2018-04-11: 0.117% | 0.02924%
| PRWM1990 | FURNACE ROOF COOLING FAN (2241) - Procurement Cycle | [34 empty] | 0%
| PRWM2000 | FURNACE ROOF COOLING FAN (2241) - Fabrication |  | 60% | 12005096040 | 0.3509% | [30 empty] | 0.3509%
| PRWM2010 | FURNACE ROOF COOLING FAN (2241) - Foreign Delivery |  | 15% | 3001274010 | 0.08772% | [30 empty] | 0.08772%
F4 |  |  |  | 100% | 0 | 0% | [30 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.5.13.2.2.5.2 Furnace Bottom Cooling Fan (2242) | [35 empty] | 0%
| PRWM2011 | FURNCE BOTTOM COOLING FAN (2242) - RFQ | [34 empty] | 0%
| PRWM2012 | FURNCE BOTTOM COOLING FAN (2242) - Recieved of Bids | [34 empty] | 0%
| PRWM2013 | FURNCE BOTTOM COOLING FAN (2242) - CBE | [34 empty] | 0%
| PRWM2014 | FURNCE BOTTOM COOLING FAN (2242) - LOI | [34 empty] | 0%
| PRWM2015 | FURNCE BOTTOM COOLING FAN (2242) - PO | [34 empty] | 0%
| PRWM2020 | FURNCE BOTTOM COOLING FAN (2242) - Procurement Cycle | [34 empty] | 0%
| PRWM2030 | FURNCE BOTTOM COOLING FAN (2242) - Fabrication | [34 empty] | 0%
| PRWM2040 | FURNCE BOTTOM COOLING FAN (2242) - Delivery | [34 empty] | 0%
B36 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.5.13.2.2.5.3 Furnace Transformer(2243) | [35 empty] | 0%
| PRWM2041 | FURNCE LOWER SHELL COOLING SYSTEM (2243) - RFQ | [34 empty] | 0%
| PRWM2042 | FURNCE LOWER SHELL COOLING SYSTEM (2243) - Recieved of Bids | [34 empty] | 0%
| PRWM2043 | FURNCE LOWER SHELL COOLING SYSTEM (2243) - CBE | [34 empty] | 0%
| PRWM2044 | FURNCE LOWER SHELL COOLING SYSTEM (2243) - LOI | [34 empty] | 0%
| PRWM2045 | FURNCE LOWER SHELL COOLING SYSTEM (2243) - PO |  | 25% | 9488980095 | 0.2773% | 2017-06-15: 0.2773% | 0%
| PRWM2050 | FURNCE LOWER SHELL COOLING SYSTEM (2243) - Procurement Cycle |  | 60% | 22773689085 | 0.6656% | 2018-03-12: 0.6656% | 1e-05%
| PRWM2060 | FURNCE LOWER SHELL COOLING SYSTEM (2243) - Fabrication | [34 empty] | 0%
| PRWM2070 | FURNCE LOWER SHELL COOLING SYSTEM (2243) - Delivery |  | 15% | 5693251200 | 0.1664% | [30 empty] | 0.1664%
F4 |  |  |  | 100% | 1315537912.5 | 0.03845% | [30 empty] | 0.03845%
B37 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.6 Off Gas Furnace Treatment System | [35 empty] | 0%
|  | Bag House | [34 empty] | 0%
|  | Bag house and Bag house Compenents | [34 empty] | 0%
|  | Spray system | [34 empty] | 0%
|  | Expansion Joint | [34 empty] | 0%
|  | Damper | [34 empty] | 0%
|  | Bag Outlet Duct | [34 empty] | 0%
|  | Dust Handling Package | [34 empty] | 0%
|  | Main Fan Motor & VSD | [34 empty] | 0%
|  | Air Receiver | [34 empty] | 0%
|  | Explosion Vents | [34 empty] | 0%
|  | Air Compressor | [34 empty] | 0%
|  | Piping & Accessories | [34 empty] | 0%
|  | Electrical & Instrument | [34 empty] | 0%
|  | Misc Instrumentation (Bag House) | [34 empty] | 0%
|  |  |  | 25% | 18916199191.9688 | 0.4423% | 2017-09-13: 0.5511%; 2017-10-13: -0.1102% | 0.001424%
|  |  |  | 60% | 45398878060.725 | 1.327% | [30 empty] | 1.327%
|  |  |  | 15% | 11349719515.1812 | 0.4423% | [30 empty] | 0.4423%
0%
|  | Exhaust Gas Stack (for Emergency Use) | [34 empty] | 0%
|  | Emergency Duct-Steel | [34 empty] | 0%
|  | Emergency Stack-Steel | [34 empty] | 0%
|  |  |  | 25% | 2702314170.2812 | 0.07898% | 2018-03-12: 0.06318% | 0.0158%
|  |  |  | 60% | 6485554008.675 | 0.1896% | [30 empty] | 0.1896%
|  |  |  | 15% | 1621388502.1688 | 0.04739% | [30 empty] | 0.04739%
0%
|  | Control Damper For Exhaust Gas | [34 empty] | 0%
|  |  |  | 25% | 1080925668.1125 | 0.03159% | 2018-04-11: 0.02527% | 0.00632%
|  |  |  | 60% | 2594221603.47 | 0.07582% | [30 empty] | 0.07582%
|  |  |  | 15% | 648555400.8675 | 0.01896% | [30 empty] | 0.01896%
0%
|  | Tempering Purge Air Fan | [34 empty] | 0%
|  | Tempering Air Duct | [34 empty] | 0%
|  | Purge Air | [34 empty] | 0%
|  | Feed bin Duct | [34 empty] | 0%
|  | Secondary Duct | [34 empty] | 0%
|  | Common Duct | [34 empty] | 0%
|  |  |  | 25% | 5404628340.5625 | 0.158% | 2018-05-11: 0.1264% | 0.0316%
|  |  |  | 60% | 12971108017.35 | 0.3791% | [30 empty] | 0.3791%
|  |  |  | 15% | 3242777004.3375 | 0.09477% | [30 empty] | 0.09477%
0%
|  | Spray Chamber | [34 empty] | 0%
|  | Spray Chamber-Wall-Steel | [34 empty] | 0%
|  | Spray Chamber-Bottom-Steel | [34 empty] | 0%
|  | Combustion Chamber Steel | [34 empty] | 0%
|  | 20T & 50T Top Bin | [34 empty] | 0%
|  | Insulation & Jacketing | [34 empty] | 0%
|  |  |  | 25% | 10809256681.125 | 0.3159% | 2018-04-11: 0.2527% | 0.06319%
|  |  |  | 60% | 25942216034.7 | 0.7582% | [30 empty] | 0.7582%
|  |  |  | 15% | 6485554008.675 | 0.1895% | [30 empty] | 0.1895%
0%
|  | Smooke Hood | [34 empty] | 0%
|  | Smooke Hood Duct & Hood | [34 empty] | 0%
|  | Blowing Laedle Duct & Hood | [34 empty] | 0%
|  | Metal Tap Duct & Hood | [34 empty] | 0%
|  | Slag Tap Duct & Hood | [34 empty] | 0%
|  |  |  | 25% | 8106942510.8438 | 0.2369% | [30 empty] | 0.2369%
|  |  |  | 60% | 19456662026.025 | 0.5687% | [30 empty] | 0.5687%
|  |  |  | 15% | 4864165506.5062 | 0.1422% | [30 empty] | 0.1422%
0%
|  | Smoke Exhaust Fan | [34 empty] | 0%
|  | Fan Outlet Duct | [34 empty] | 0%
|  | Centrifugal Fan | [34 empty] | 0%
|  | Axial Fans | [34 empty] | 0%
|  |  |  | 25% | 1621388502.1688 | 0.04739% | 2018-05-11: 0.03791% | 0.00948%
|  |  |  | 60% | 3891332405.205 | 0.1137% | [30 empty] | 0.1137%
|  |  |  | 15% | 972833101.3012 | 0.02843% | [30 empty] | 0.02843%
0%
|  | Smoke Stack & Duct | [34 empty] | 0%
|  | Stack | [34 empty] | 0%
|  |  |  | 25% | 1080925668.1125 | 0.03159% | [30 empty] | 0.03159%
|  |  |  | 60% | 2594221603.47 | 0.07582% | [30 empty] | 0.07582%
|  |  |  | 15% | 648555400.8675 | 0.01896% | [30 empty] | 0.01896%
0%
|  | Ladle Hood | [34 empty] | 0%
|  | Structural Support | [34 empty] | 0%
|  | Foundations | [34 empty] | 0%
|  | Plate & Accessories | [34 empty] | 0%
|  |  |  | 25% | 4323702672.45 | 0.1264% | [30 empty] | 0.1264%
|  |  |  | 60% | 10376886413.88 | 0.3033% | [30 empty] | 0.3033%
|  |  |  | 15% | 2594221603.47 | 0.07582% | [30 empty] | 0.07582%
0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.6.13.2.2.6.1 Bag House (2401) | [35 empty] | 0%
| PRWM2071 | BAG HOUSE (2401) - RFQ | [34 empty] | 0%
| PRWM2072 | BAG HOUSE (2401) - Recieved of Bids | [34 empty] | 0%
| PRWM2073 | BAG HOUSE (2401) - CBE | [34 empty] | 0%
| PRWM2074 | BAG HOUSE (2401) - LOI | [34 empty] | 0%
| PRWM2075 | BAG HOUSE (2401) - PO | [34 empty] | 0%
| PRWM2090 | BAG HOUSE (2401) - Fabrication by HTV | [34 empty] | 0%
| PRWM2100 | BAG HOUSE (2401) - Foreign Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.6.13.2.2.6.2 Exhaust Gas Stack (2402) | [35 empty] | 0%
| PRWM2101 | EXHAUST GAS STACK (2402) - RFQ | [34 empty] | 0%
| PRWM2102 | EXHAUST GAS STACK (2402) - Recieved of Bids | [34 empty] | 0%
| PRWM2103 | EXHAUST GAS STACK (2402) - CBE | [34 empty] | 0%
| PRWM2104 | EXHAUST GAS STACK (2402) - LOI | [34 empty] | 0%
| PRWM2105 | EXHAUST GAS STACK (2402) - PO | [34 empty] | 0%
| PRWM2120 | EXHAUST GAS STACK (2402) - Fabrication by HTV | [34 empty] | 0%
| PRWM2130 | EXHAUST GAS STACK (2402) - Foreign Delivery | [34 empty] | 0%
F4 |  |  |  | 100% | 9948477472.5 | 0.2908% | [30 empty] | 0.2908%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.6.13.2.2.6.3 Control Damper for Exhaust Gas (2403) | [35 empty] | 0%
| PRWM2131 | CONTROL DAMPER FOR EXHAUST GAS (2403) - RFQ | [34 empty] | 0%
| PRWM2132 | CONTROL DAMPER FOR EXHAUST GAS (2403) - Recieved of Bids | [34 empty] | 0%
| PRWM2133 | CONTROL DAMPER FOR EXHAUST GAS (2403) - CBE | [34 empty] | 0%
| PRWM2134 | CONTROL DAMPER FOR EXHAUST GAS (2403) - LOI | [34 empty] | 0%
| PRWM2135 | CONTROL DAMPER FOR EXHAUST GAS (2403) - PO | [34 empty] | 0%
| PRWM2150 | CONTROL DAMPER FOR EXHAUST GAS (2403) - Fabrication by HTV | [34 empty] | 0%
| PRWM2160 | CONTROL DAMPER FOR EXHAUST GAS (2403) - Foreign Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.6.13.2.2.6.4 Tempering Purge Air Fan (2404) | [35 empty] | 0%
| PRWM2161 | TEMPERING PURGE AIR FAN (2404) - RFQ | [34 empty] | 0%
| PRWM2162 | TEMPERING PURGE AIR FAN (2404) - Recieved of Bids | [34 empty] | 0%
| PRWM2163 | TEMPERING PURGE AIR FAN (2404) - CBE | [34 empty] | 0%
| PRWM2164 | TEMPERING PURGE AIR FAN (2404) - LOI | [34 empty] | 0%
| PRWM2165 | TEMPERING PURGE AIR FAN (2404) - PO | [34 empty] | 0%
| PRWM2180 | TEMPERING PURGE AIR FAN (2404) - Fabrication by HTV | [34 empty] | 0%
| PRWM2190 | TEMPERING PURGE AIR FAN (2404) - Foreign Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.6.13.2.2.6.5 Spray Chamber (2405) | [35 empty] | 0%
| PRWM2191 | SPRAY CHAMBER (2405) - RFQ | [34 empty] | 0%
| PRWM2192 | SPRAY CHAMBER (2405) - Recieved of Bids | [34 empty] | 0%
| PRWM2193 | SPRAY CHAMBER (2405) - CBE | [34 empty] | 0%
| PRWM2194 | SPRAY CHAMBER (2405) - LOI | [34 empty] | 0%
| PRWM2195 | SPRAY CHAMBER (2405) - PO | [34 empty] | 0%
| PRWM2210 | SPRAY CHAMBER (2405) - Fabrication by HTV | [34 empty] | 0%
| PRWM2220 | SPRAY CHAMBER (2405) - Foreign Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.6.13.2.2.6.6 Smoke Hood (2411) | [35 empty] | 0%
| PRWM2221 | SMOKE HOOD (2411) - RFQ | [34 empty] | 0%
| PRWM2222 | SMOKE HOOD (2411) - Recieved of Bids | [34 empty] | 0%
| PRWM2223 | SMOKE HOOD (2411) - CBE | [34 empty] | 0%
| PRWM2224 | SMOKE HOOD (2411) - LOI | [34 empty] | 0%
| PRWM2225 | SMOKE HOOD (2411) - PO | [34 empty] | 0%
| PRWM2240 | SMOKE HOOD (2411) - Fabrication by HTV | [34 empty] | 0%
| PRWM2250 | SMOKE HOOD (2411) - Foreign Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.6.13.2.2.6.7 Smoke Exhaust Fan (2412) | [35 empty] | 0%
| PRWM2251 | SMOKE HOOD (2411) - RFQ | [34 empty] | 0%
| PRWM2252 | SMOKE HOOD (2411) - Recieved of Bids | [34 empty] | 0%
| PRWM2253 | SMOKE HOOD (2411) - CBE | [34 empty] | 0%
| PRWM2254 | SMOKE HOOD (2411) - LOI | [34 empty] | 0%
| PRWM2255 | SMOKE HOOD (2411) - PO | [34 empty] | 0%
| PRWM2270 | SMOKE EXHAUST FAN (2412) - Fabrication by HTV | [34 empty] | 0%
| PRWM2280 | SMOKE EXHAUST FAN (2412) - Foreign Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.6.13.2.2.6.8 Smoke Stack & Duct (2413) | [35 empty] | 0%
| PRWM2281 | SMOKE STACK & DUCT (2413) - RFQ | [34 empty] | 0%
| PRWM2282 | SMOKE STACK & DUCT (2413) - Recieved of Bids | [34 empty] | 0%
| PRWM2283 | SMOKE STACK & DUCT (2413) - CBE | [34 empty] | 0%
| PRWM2284 | SMOKE STACK & DUCT (2413) - LOI | [34 empty] | 0%
| PRWM2285 | SMOKE STACK & DUCT (2413) - PO | [34 empty] | 0%
| PRWM2300 | SMOKE STACK & DUCT (2413) - Fabrication by HTV | [34 empty] | 0%
| PRWM2310 | SMOKE STACK & DUCT (2413) - Local Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.6.13.2.2.6.9 Ladle Hood (2414) | [35 empty] | 0%
| PRWM2311 | LADLE HOOD (2414) - RFQ | [34 empty] | 0%
| PRWM2312 | LADLE HOOD (2414) - Recieved of Bids | [34 empty] | 0%
| PRWM2313 | LADLE HOOD (2414) - CBE | [34 empty] | 0%
| PRWM2314 | LADLE HOOD (2414) - LOI | [34 empty] | 0%
| PRWM2315 | LADLE HOOD (2414) - PO | [34 empty] | 0%
| PRWM2330 | LADLE HOOD (2414) - Fabrication by HTV | [34 empty] | 0%
| PRWM2340 | LADLE HOOD (2414) - Local Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.7 Other Auxiliary | [35 empty] | 0%
B38 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.7.13.2.2.7.1 Working Deck for Electrode (2701) | [35 empty] | 0%
| PRWM2341 | WORKING DECK FOR ELECTRODE (2701) - RFQ | [34 empty] | 0%
| PRWM2342 | WORKING DECK FOR ELECTRODE (2701) - Recieved of Bids | [34 empty] | 0%
| PRWM2343 | WORKING DECK FOR ELECTRODE (2701) - CBE | [34 empty] | 0%
| PRWM2344 | WORKING DECK FOR ELECTRODE (2701) - LOI | [34 empty] | 0%
| PRWM2345 | WORKING DECK FOR ELECTRODE (2701) - PO |  | 20% | 79034917.5 | 0.00231% | [30 empty] | 0.00231%
| PRWM2350 | WORKING DECK FOR ELECTRODE (2701) - Procurement Cycle | [34 empty] | 0%
| PRWM2360 | WORKING DECK FOR ELECTRODE (2701) - Fabrication |  | 60% | 237446895 | 0.00694% | [30 empty] | 0.00694%
| PRWM2370 | WORKING DECK FOR ELECTRODE (2701) - Local Delivery |  | 20% | 79034917.5 | 0.00231% | [30 empty] | 0.00231%
F4 |  |  |  | 100% | 56795655 | 0.00166% | [30 empty] | 0.00166%
B39 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.7.13.2.2.7.2 Tapping Deck (2702) | [35 empty] | 0%
| PRWM2371 | TAPPING DECK (2702) - RFQ | [34 empty] | 0%
| PRWM2372 | TAPPING DECK (2702) - Recieved of Bids | [34 empty] | 0%
| PRWM2373 | TAPPING DECK (2702) - CBE | [34 empty] | 0%
| PRWM2374 | TAPPING DECK (2702) - LOI | [34 empty] | 0%
| PRWM2375 | TAPPING DECK (2702) - PO |  | 20% | 291847552.5 | 0.00853% | 2017-10-13: 0.00853% | 0%
| PRWM2380 | TAPPING DECK (2702) - Procurement Cycle | [34 empty] | 0%
| PRWM2390 | TAPPING DECK (2702) - Fabrication |  | 60% | 875542657.5 | 0.02559% | [30 empty] | 0.02559%
| PRWM2400 | TAPPING DECK (2702) - Local Delivery |  | 20% | 291847552.5 | 0.00853% | [30 empty] | 0.00853%
F4 |  |  |  | 100% | 665809305 | 0.01946% | [30 empty] | 0.01946%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.7.13.2.2.7.3 Tapping Runner (2703) | [35 empty] | 0%
| PRWM2401 | TAPPING RUNNER (2703) - RFQ | [34 empty] | 0%
| PRWM2402 | TAPPING RUNNER (2703) - Recieved of Bids | [34 empty] | 0%
| PRWM2403 | TAPPING RUNNER (2703) - CBE | [34 empty] | 0%
| PRWM2404 | TAPPING RUNNER (2703) - LOI | [34 empty] | 0%
| PRWM2405 | TAPPING RUNNER (2703) - PO | [34 empty] | 0%
| PRWM2410 | TAPPING RUNNER (2703) - Procurement Cycle | [34 empty] | 0%
| PRWM2420 | TAPPING RUNNER (2703) - Fabrication | [34 empty] | 0%
| PRWM2430 | TAPPING RUNNER (2703) - Delivery | [34 empty] | 0%
0%
B40 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.7.13.2.2.7.4 Heat Prevention Board for Tapping Runner (2704) | [35 empty] | 0%
| PRWM2431 | HEAT PREVENTION BOARD TAPPING RUNNER (2704) - RFQ | [34 empty] | 0%
| PRWM2432 | HEAT PREVENTION BOARD TAPPING RUNNER (2704) - Recieved of Bids | [34 empty] | 0%
| PRWM2433 | HEAT PREVENTION BOARD TAPPING RUNNER (2704) - CBE | [34 empty] | 0%
| PRWM2434 | HEAT PREVENTION BOARD TAPPING RUNNER (2704) - LOI | [34 empty] | 0%
| PRWM2435 | HEAT PREVENTION BOARD TAPPING RUNNER (2704) - PO |  | 20% | 10264275 | 0.0003% | [30 empty] | 0.0003%
| PRWM2440 | HEAT PREVENTION BOARD TAPPING RUNNER (2704) - Procurement Cycle | [34 empty] | 0%
| PRWM2450 | HEAT PREVENTION BOARD TAPPING RUNNER (2704) - Fabrication |  | 60% | 30450682.5 | 0.00089% | [30 empty] | 0.00089%
| PRWM2460 | HEAT PREVENTION BOARD TAPPING RUNNER (2704) - Delivery |  | 20% | 10264275 | 0.0003% | [30 empty] | 0.0003%
F4 |  |  |  | 100% | 8211420 | 0.00024% | [30 empty] | 0.00024%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.8 Slag Granulation System | [35 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.8.13.2.2.8.1 Slag Handling Equipment | [35 empty] | 0%
B42 | P3FH - 28 M.13.13.2.13.2.2.13.2.2.8.13.2.2.8.1.13.2.2.8.1.1 Salg Granulation Launder (xxxx) | [35 empty] | 0%
| PRWM2461 | SLAG GRANULATION LAUNDER - RFQ | [34 empty] | 0%
| PRWM2462 | SLAG GRANULATION LAUNDER - Recieved of Bids | [34 empty] | 0%
| PRWM2463 | SLAG GRANULATION LAUNDER - CBE | [34 empty] | 0%
| PRWM2464 | SLAG GRANULATION LAUNDER - LOI | [34 empty] | 0%
| PRWM2465 | SLAG GRANULATION LAUNDER - PO |  | 25% | 732869235 | 0.02142% | 2017-11-12: 0.01714% | 0.00428%
| PRWM2480 | SLAG GRANULATION LAUNDER - Fabrication |  | 60% | 1758612450 | 0.0514% | 2018-05-11: 0.0514% | 0%
| PRWM2490 | SLAG GRANULATION LAUNDER - Foreign Delivery |  | 15% | 439310970 | 0.01284% | [30 empty] | 0.01284%
F4 |  |  |  | 100% | 0 | 0% | [30 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.8.13.2.2.8.2 Cooling Water Equipment | [35 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.8.13.2.2.8.2.13.2.2.8.2.1 Inject Water Pump (2803-1/2) | [35 empty] | 0%
| PRWM2491 | SLAG GRANULATION LAUNDER - RFQ | [34 empty] | 0%
| PRWM2492 | SLAG GRANULATION LAUNDER - Recieved of Bids | [34 empty] | 0%
| PRWM2493 | SLAG GRANULATION LAUNDER - CBE | [34 empty] | 0%
| PRWM2494 | SLAG GRANULATION LAUNDER - LOI | [34 empty] | 0%
| PRWM2495 | SLAG GRANULATION LAUNDER - PO | [34 empty] | 0%
| PRWM2510 | INJECT WATER PUMP(2803-1/2) - Fabrication | [34 empty] | 0%
| PRWM2520 | INJECT WATER PUMP(2803-1/2) - Foreign Delivery by | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.2.13.2.2.8.13.2.2.8.2.13.2.2.8.2.2 Portable Submerged Pump (2809) | [35 empty] | 0%
| PRWM2521 | SLAG GRANULATION LAUNDER - RFQ | [34 empty] | 0%
| PRWM2522 | SLAG GRANULATION LAUNDER - Recieved of Bids | [34 empty] | 0%
| PRWM2523 | SLAG GRANULATION LAUNDER - CBE | [34 empty] | 0%
| PRWM2524 | SLAG GRANULATION LAUNDER - LOI | [34 empty] | 0%
| PRWM2525 | SLAG GRANULATION LAUNDER - PO | [34 empty] | 0%
| PRWM2540 | PORTABLE SUBMERGED PUMP (2809) - Fabrication | [34 empty] | 0%
| PRWM2550 | PORTABLE SUBMERGED PUMP (2809) - Foreign Delivery by | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.3 System 3 - Refinery | [35 empty] | 0%
| A47230 | System 3 - RFQ | [34 empty] | 0%
| A47240 | System 3 - Received of Bids | [34 empty] | 0%
| A47250 | System 3 - CBE | [34 empty] | 0%
| A47260 | System 3 - LOI | [34 empty] | 0%
| A47270 | System 3 - PO System Package Vendor | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.3.13.2.3.1 Deshulphurizing Equipment | [35 empty] | 0%
B45 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.1.13.2.3.1.1 Stirrer Unit (3112 A/B) | [35 empty] | 0%
|  |  |  | 20% | 223419052.5 | 0.00653% | 2017-03-17: 0.00653% | 0%
| PRWM2560 | STIRRER UNIT(3112 A/B) - Fabrication by SIKO |  | 60% | 670599300 | 0.0196% | 2017-12-12: 0.0196% | 0%
| PRWM2570 | STIRRER UNIT(3112 A/B) - Packing by SIKO | [34 empty] | 0%
| PRWM2580 | STIRRER UNIT(3112 A/B) - Delivery by WIKA |  | 20% | 223761195 | 0.00654% | 2018-02-10: 0.00653% | 1e-05%
F4 |  |  |  | 100% | 56795655 | 0.00095% | 2017-12-12: 0.00095% | 0%
B46 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.1.13.2.3.1.2 Lifting Device (3115 A/B) | [35 empty] | 0%
|  |  |  | 20% | 182019810 | 0.00532% | 2017-03-17: 0.00532% | 0%
| PRWM2590 | LIFTING DEVICE (3115A/B) - Fabrication by SIKO |  | 60% | 546401572.5 | 0.01597% | 2017-12-12: 0.01596% | 1e-05%
| PRWM2600 | LIFTING DEVICE (3115A/B) - Packing by SIKO | [34 empty] | 0%
| PRWM2610 | LIFTING DEVICE (3115A/B) - Delivery by WIKA |  | 20% | 182019810 | 0.00532% | 2018-04-11: 0.00532% | 0%
F4 |  |  |  | 100% | 56795655 | 0.00077% | 2017-12-12: 0.00077% | 0%
B47 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.1.13.2.3.1.3 Shifting Device and Swinging Part (3118 A/B) | [35 empty] | 0%
|  |  |  | 20% | 255238305 | 0.00746% | 2017-03-17: 0.00746% | 0%
| PRWM2620 | SHIFTING DEVICE & SWINGING PART(3118 A/B) - Fabrication by SIKO |  | 60% | 765372772.5 | 0.02237% | 2017-11-12: 0.02238% | -1e-05%
| PRWM2630 | SHIFTING DEVICE & SWINGING PART(3118 A/B) - Packing by SIKO | [34 empty] | 0%
| PRWM2640 | SHIFTING DEVICE & SWINGING PART(3118 A/B) - Delivery by WIKA |  | 20% | 254896162.5 | 0.00745% | 2017-12-12: 0.00746% | -1e-05%
F4 |  |  |  | 100% | 56795655 | 0.00108% | 2017-11-12: 0.00108% | 0%
B48 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.1.13.2.3.1.4 Hoist (3134 A/B) | [35 empty] | 0%
|  |  |  | 20% | 81772057.5 | 0.00239% | 2017-03-17: 0.00239% | 0%
| PRWM2650 | HOIST(3134 A/B) - Fabrication by SIKO |  | 60% | 245658315 | 0.00718% | 2018-03-12: 0.00718% | 0%
| PRWM2660 | HOIST(3134 A/B) - Packing by SIKO | [34 empty] | 0%
| PRWM2670 | HOIST(3134 A/B) - Delivery by WIKA |  | 20% | 81772057.5 | 0.00239% | 2018-04-11: 0.00239% | 0%
F4 |  |  |  | 100% | 56795655 | 0.00035% | 2018-05-11: 0.00035% | 0%
| P3FH - 28 M.13.13.2.13.2.3.13.2.3.2 Shot Making Equipment | [35 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.1 Granulation Section | [35 empty] | 0%
B51 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.1.13.2.3.2.1.1 Ladle Tilting Machine (3511) | [35 empty] | 0%
|  |  |  | 20% | 1059957465 | 0.03098% | 2017-03-17: 0.03099% | -1e-05%
| PRWM2680 | LADLE TILTING MACHINE (3511) - Fabrication by SIKO |  | 60% | 3180214537.5 | 0.09295% | 2018-03-12: 0.09295% | 0%
| PRWM2690 | LADLE TILTING MACHINE (3511) - Packing by SIKO | [34 empty] | 0%
| PRWM2700 | LADLE TILTING MACHINE (3511) - Delivery by WIKA |  | 20% | 1060299607.5 | 0.03099% | 2018-04-11: 0.03099% | 0%
F4 |  |  |  | 100% | 56795655 | 0.00449% | 2018-04-11: 0.00449% | 0%
B50 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.1.13.2.3.2.1.2 Hydraulic Cylinder (3513) | [35 empty] | 0%
| Progress isi sebenarnya adalah Work Stage System 3 |  |  | 20% | 509108040 | 0.01488% | 2017-06-15: 0.01488% | 0%
| PRWM2710 | HYDRAULIC CYLINDER (3513) - Fabrication by WIKA |  | 60% | 1526981977.5 | 0.04463% | 2017-10-13: 0.04464% | -1e-05%
| PRWM2720 | HYDRAULIC CYLINDER (3513) - Packing by WIKA | [34 empty] | 0%
| PRWM2730 | HYDRAULIC CYLINDER (3513) - Delivery by WIKA |  | 20% | 509108040 | 0.01488% | 2017-11-12: 0.01488% | 0%
F4 |  |  |  | 100% | 56795655 | 0.00216% | 2017-10-13: 0.00216% | 0%
B49 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.1.13.2.3.2.1.3 Hydraulic Oil Pump Unit (3514) | [35 empty] | 0%
| Exhaust Gas Duct | Exhaust Gas Duct |  | 20% | 118381305 | 0.00346% | 2017-03-17: 0.00346% | 0%
| PRWM2740 | HYDRAULIC OIL PUMP UNIT (3513) - Fabrication by WIKA |  | 60% | 354801772.5 | 0.01037% | 2017-11-12: 0.01037% | 0%
| PRWM2750 | HYDRAULIC OIL PUMP UNIT (3513) - Packing by WIKA | [34 empty] | 0%
| PRWM2760 | HYDRAULIC OIL PUMP UNIT (3513) - Delivery by WIKA |  | 20% | 118381305 | 0.00346% | 2017-12-12: 0.00346% | 0%
F4 |  |  |  | 100% | 56795655 | 0.0005% | 2017-11-12: 0.0005% | 0%
B52 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.1.13.2.3.2.1.4 Runner (3515) | [35 empty] | 0%
|  |  |  | 20% | 104011320 | 0.00304% | 2017-03-17: 0.00304% | 0%
| PRWM2770 | RUNNER (3515) - Fabrication by SIKO |  | 60% | 312376102.5 | 0.00913% | 2017-11-12: 0.00913% | 0%
| PRWM2780 | RUNNER (3515) - Packing by SIKO | [34 empty] | 0%
| PRWM2790 | RUNNER (3515) - Delivery by WIKA |  | 20% | 104011320 | 0.00304% | 2017-12-12: 0.00305% | -1e-05%
F4 |  |  |  | 100% | 56795655 | 0.00044% | 2017-11-12: 0.00044% | 0%
B53 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.1.13.2.3.2.1.5 Spray Head (3522) | [35 empty] | 0%
|  |  |  | 20% | 19844265 | 0.00058% | 2017-03-17: 0.00058% | 0%
| PRWM2800 | SPRAY HEAD (3522) - Fabrication by SIKO |  | 60% | 59874937.5 | 0.00175% | 2017-11-12: 0.00176% | -1e-05%
| PRWM2810 | SPRAY HEAD (3522) - Packing by SIKO | [34 empty] | 0%
| PRWM2820 | SPRAY HEAD (3522) - Delivery by WIKA |  | 20% | 20186407.5 | 0.00059% | 2017-12-12: 0.00058% | 1e-05%
F4 |  |  |  | 100% | 56795655 | 8e-05% | 2017-11-12: 8e-05% | 0%
B54 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.1.13.2.3.2.1.6 Shot Making Tank (3531) | [35 empty] | 0%
|  |  |  | 20% | 599775802.5 | 0.01753% | 2017-06-15: 0.01753% | 0%
| PRWM2830 | SHOT MAKING TANK (3531) - Fabrication by SIKO |  | 60% | 1798985265 | 0.05258% | 2017-11-12: 0.05259% | -1e-05%
| PRWM2840 | SHOT MAKING TANK (3531) - Packing by SIKO | [34 empty] | 0%
| PRWM2850 | SHOT MAKING TANK (3531) - Delivery by WIKA |  | 20% | 599775802.5 | 0.01753% | 2017-12-12: 0.01752% | 1e-05%
F4 |  |  |  | 100% | 56795655 | 0.00254% | 2017-11-12: 0.00254% | 0%
B55 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.1.13.2.3.2.1.7 No.1 Net Conveyor (3532) | [35 empty] | 0%
|  |  |  | 20% | 449233102.5 | 0.01313% | 2017-03-17: 0.01313% | 0%
| PRWM2860 | NO.1 NET CONVEYOR (3532) - Fabrication by SIKO |  | 60% | 1347357165 | 0.03938% | 2017-10-13: 0.03938% | 0%
| PRWM2870 | NO.1 NET CONVEYOR (3532) - Packing by SIKO | [34 empty] | 0%
| PRWM2880 | NO.1 NET CONVEYOR (3532) - Delivery by WIKA |  | 20% | 448890960 | 0.01312% | 2017-11-12: 0.01312% | 0%
F4 |  |  |  | 100% | 56795655 | 0.0019% | 2017-10-13: 0.0019% | 0%
B56 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.1.13.2.3.2.1.8 Jet Water Pump (3533) | [35 empty] | 0%
|  |  |  | 20% | 62269935 | 0.00182% | 2017-07-15: 0.00182% | 0%
| PRWM2890 | JET WATER PUMP (3533) - Procurement Cycle by WIKA |  | 60% | 186467662.5 | 0.00545% | 2017-12-12: 0.00545% | 0%
| PRWM2900 | JET WATER PUMP (3533) - Fabrication by WIKA | [34 empty] | 0%
| PRWM2910 | JET WATER PUMP (3533) - Delivery by WIKA |  | 20% | 62269935 | 0.00182% | 2018-02-10: 0.00181% | 1e-05%
F4 |  |  |  | 100% | 56795655 | 0.00026% | 2017-12-12: 0.00026% | 0%
| P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.2 Drying Section | [35 empty] | 0%
B57 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.2.13.2.3.2.2.1 Surge Hopper (3541) | [35 empty] | 0%
|  |  |  | 20% | 93404902.5 | 0.00273% | 2017-06-15: 0.00273% | 0%
| PRWM2920 | SURGE HOPPER (3541) - Fabrication by SIKO |  | 60% | 279872565 | 0.00818% | 2017-10-13: 0.00819% | -1e-05%
| PRWM2930 | SURGE HOPPER (3541) - Packing by SIKO | [34 empty] | 0%
| PRWM2940 | SURGE HOPPER (3541) - Delivery by WIKA |  | 20% | 93404902.5 | 0.00273% | 2017-11-12: 0.00273% | 0%
F4 |  |  |  | 100% | 56795655 | 0.0004% | 2017-10-13: 0.0004% | 0%
B58 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.2.13.2.3.2.2.2 No.2 Net Conveyor (3542) | [35 empty] | 0%
|  |  |  | 20% | 528952305 | 0.01546% | 2017-03-17: 0.01546% | 0%
| PRWM2950 | NO.2 NET CONVEYOR (3542) - Fabrication by SIKO |  | 60% | 1586514772.5 | 0.04637% | 2017-10-13: 0.04637% | 0%
| PRWM2960 | NO.2 NET CONVEYOR (3542) - Packing by SIKO | [34 empty] | 0%
| PRWM2970 | NO.2 NET CONVEYOR (3542) - Delivery by WIKA |  | 20% | 528610162.5 | 0.01545% | 2017-11-12: 0.01545% | 0%
F4 |  |  |  | 100% | 56795655 | 0.00224% | 2017-10-13: 0.00224% | 0%
B59 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.2.13.2.3.2.2.3 Hot Stove (3543) | [35 empty] | 0%
|  |  |  | 20% | 46189237.5 | 0.00135% | 2017-03-17: 0.00135% | 0%
| PRWM2980 | HOT STOVE (3543) - Fabrication by SIKO |  | 60% | 138225570 | 0.00404% | 2017-11-12: 0.00404% | 0%
| PRWM2990 | HOT STOVE (3543) - Packing by SIKO | [34 empty] | 0%
| PRWM3000 | HOT STOVE (3543) - Delivery by WIKA |  | 20% | 46189237.5 | 0.00135% | 2017-12-12: 0.00134% | 1e-05%
F4 |  |  |  | 100% | 56795655 | 0.0002% | 2017-11-12: 0.00019% | 1e-05%
B60 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.2.13.2.3.2.2.4 Burner Dilution Fan (3544) | [35 empty] | 0%
|  |  |  | 20% | 33187822.5 | 0.00097% | 2017-07-15: 0.00097% | 0%
| PRWM3010 | BURNER DILUTION FAN (3544) - Procurement by SIKO |  | 60% | 99905610 | 0.00292% | 2017-12-12: 0.00291% | 1e-05%
| PRWM3020 | BURNER DILUTION FAN (3544) - Packing by SIKO | [34 empty] | 0%
| PRWM3030 | BURNER DILUTION FAN (3544) - Delivery by SIKO |  | 20% | 33187822.5 | 0.00097% | 2018-02-10: 0.00097% | 0%
F4 |  |  |  | 100% | 56795655 | 0.00014% | 2017-12-12: 0.00014% | 0%
B61 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.2.13.2.3.2.2.5 Hot Gas Circulation Fan (3545) | [35 empty] | 0%
|  |  |  | 20% | 68086357.5 | 0.00199% | 2017-07-15: 0.00199% | 0%
| PRWM3040 | HOT GAS CIRCULATION FAN (3545) - Procurement by SIKO |  | 60% | 204601215 | 0.00598% | 2017-12-12: 0.00598% | 0%
| PRWM3050 | HOT GAS CIRCULATION FAN (3545) - Packing by SIKO | [34 empty] | 0%
| PRWM3060 | HOT GAS CIRCULATION FAN (3545) - Delivery by SIKO |  | 20% | 68428500 | 0.002% | 2018-02-10: 0.00199% | 1e-05%
F4 |  |  |  | 100% | 56795655 | 0.00029% | 2017-12-12: 0.00029% | 0%
B62 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.2.13.2.3.2.2.6 Ducting (3546) | [35 empty] | 0%
|  |  |  | 20% | 116328450 | 0.0034% | 2017-03-17: 0.0034% | 0%
| PRWM3070 | DUCTING (3546) - Fabrication by SIKO |  | 60% | 349327492.5 | 0.01021% | 2017-10-13: 0.0102% | 1e-05%
| PRWM3080 | DUCTING (3546) - Packing by SIKO | [34 empty] | 0%
| PRWM3090 | DUCTING (3546) - Delivery by WIKA |  | 20% | 116328450 | 0.0034% | 2017-11-12: 0.00341% | -1e-05%
F4 |  |  |  | 100% | 56795655 | 0.00049% | 2017-10-13: 0.00049% | 0%
B63 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.2.13.2.3.2.2.7 Trommel (3551) | [35 empty] | 0%
|  |  |  | 20% | 151226985 | 0.00442% | 2017-03-17: 0.00442% | 0%
| PRWM3100 | TROMMEL (3551) - Fabrication by SIKO |  | 60% | 454023097.5 | 0.01327% | 2017-11-12: 0.01328% | -1e-05%
| PRWM3110 | TROMMEL (3551) - Packing by SIKO | [34 empty] | 0%
| PRWM3120 | TROMMEL (3551) - Delivery by SIKO |  | 20% | 151569127.5 | 0.00443% | 2017-12-12: 0.00443% | 0%
F4 |  |  |  | 100% | 56795655 | 0.00064% | 2017-11-12: 0.00064% | 0%
B64 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.2.13.2.3.2.2.8 Sound proof Box (3552) | [35 empty] | 0%
|  |  |  | 20% | 111538455 | 0.00326% | 2017-06-15: 0.00326% | 0%
| PRWM3130 | SOUND PROOF BOX (3552) - Fabrication by SIKO |  | 60% | 334957507.5 | 0.00979% | 2017-10-13: 0.00979% | 0%
| PRWM3140 | SOUND PROOF BOX (3552) - Packing by SIKO | [34 empty] | 0%
| PRWM3150 | SOUND PROOF BOX (3552) - Delivery by WIKA |  | 20% | 111538455 | 0.00326% | 2017-11-12: 0.00326% | 0%
F4 |  |  |  | 100% | 56795655 | 0.00047% | 2017-10-13: 0.00047% | 0%
| P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.3 Product Hadling Section | [35 empty] | 0%
B65 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.3.13.2.3.2.3.1 Container (3561) | [35 empty] | 0%
|  |  |  | 20% | 381146745 | 0.01114% | 2017-06-15: 0.01114% | 0%
| PRWM3160 | CONTAINER (3561) - Fabrication by SIKO |  | 60% | 1143098092.5 | 0.03341% | 2017-10-13: 0.03341% | 0%
| PRWM3170 | CONTAINER (3561) - Packing by SIKO | [34 empty] | 0%
| PRWM3180 | CONTAINER (3561) - Delivery by WIKA |  | 20% | 381146745 | 0.01114% | 2017-11-12: 0.01114% | 0%
F4 |  |  |  | 100% | 56795655 | 0.00162% | 2017-10-13: 0.00162% | 0%
B66 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.3.13.2.3.2.3.2 Container Car (3562) | [35 empty] | 0%
|  |  |  | 20% | 259344015 | 0.00758% | 2017-03-17: 0.00758% | 0%
| PRWM3190 | CONTAINER CAR (3562) - Fabrication by SIKO |  | 60% | 778032045 | 0.02274% | 2017-10-13: 0.02274% | 0%
| PRWM3200 | CONTAINER CAR (3562) - Packing by SIKO | [34 empty] | 0%
| PRWM3210 | CONTAINER CAR (3562) - Delivery by WIKA |  | 20% | 259344015 | 0.00758% | 2017-11-12: 0.00758% | 0%
F4 |  |  |  | 100% | 56795655 | 0.0011% | 2017-10-13: 0.0011% | 0%
| P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.4 Water Circulation Section | [35 empty] | 0%
B67 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.4.13.2.3.2.4.1 Shot Cooling Pump (3571) | [35 empty] | 0%
|  |  |  | 20% | 135830572.5 | 0.00397% | 2017-07-15: 0.00397% | 0%
| PRWM3220 | SHOT COOLING PUMP (3571) - Procurement by SIKO |  | 60% | 407833860 | 0.01192% | 2017-12-12: 0.01192% | 0%
| PRWM3230 | SHOT COOLING PUMP (3571) - Packing by SIKO | [34 empty] | 0%
| PRWM3240 | SHOT COOLING PUMP (3571) - Foreign Delivery by WIKA |  | 20% | 136172715 | 0.00398% | 2018-02-10: 0.00398% | 0%
F4 |  |  |  | 100% | 56795655 | 0.00058% | 2017-12-12: 0.00058% | 0%
B68 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.4.13.2.3.2.4.2 Cooling Tower (3572) | [35 empty] | 0%
|  |  |  | 20% | 338378932.5 | 0.00989% | 2017-07-15: 0.00989% | 0%
| PRWM3250 | COOLING TOWER (3572) - Procurement by SIKO |  | 60% | 1015478940 | 0.02968% | 2018-01-11: 0.02968% | 0%
| PRWM3260 | COOLING TOWER (3572) - Packing by SIKO | [34 empty] | 0%
| PRWM3270 | COOLING TOWER (3572) - Foreign Delivery by WIKA |  | 20% | 338378932.5 | 0.00989% | 2018-03-12: 0.00989% | 0%
F4 |  |  |  | 100% | 56795655 | 0.00144% | 2018-01-11: 0.00144% | 0%
B69 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.2.13.2.3.2.4.13.2.3.2.4.3 Cooling Tower Feed Pump (3573) | [35 empty] | 0%
|  |  |  | 20% | 135830572.5 | 0.00397% | 2017-07-15: 0.00398% | -1e-05%
| PRWM3280 | COOLING TOWER FEED PUMP (3573) - Procurement by SIKO |  | 60% | 407833860 | 0.01192% | 2017-12-12: 0.01192% | 0%
| PRWM3290 | COOLING TOWER FEED PUMP (3573) - Packing by SIKO | [34 empty] | 0%
| PRWM3300 | COOLING TOWER FEED PUMP (3573) - Foreign Delivery by WIKA |  | 20% | 136172715 | 0.00398% | 2018-02-10: 0.00398% | 0%
F4 |  |  |  | 100% | 56795655 | 0.00058% | 2017-12-12: 0.00058% | 0%
| P3FH - 28 M.13.13.2.13.2.3.13.2.3.3 Crane, Ladles, Ladle Preheating & Ladle Heating Equipment | [35 empty] | 0%
B70 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.3.13.2.3.3.1 Ladle Handling Crane (3611 A/B) | [35 empty] | 0%
|  |  |  | 20% | 5322026587.5 | 0.1555% | 2017-06-15: 0.1556% | -1e-05%
| PRWM3310 | LADLE HANDLING CRANE (3611 A/B) - Fabrication by SIKO |  | 60% | 15966421905 | 0.4667% | 2017-12-12: 0.2333% | 0.2333%
| PRWM3320 | LADLE HANDLING CRANE (3611 A/B) - Packing by SIKO | [34 empty] | 0%
| PRWM3330 | LADLE HANDLING CRANE (3611 A/B) - Delivery by WIKA |  | 20% | 5322368730 | 0.1556% | 2018-02-10: 0.3889% | -0.2333%
F4 |  |  |  | 100% | 56795655 | 0.02257% | 2017-12-12: 0.01128% | 0.01129%
B71 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.3.13.2.3.3.2 Ladle (3641) | [35 empty] | 0%
|  |  |  | 20% | 1079801730 | 0.03156% | 2017-03-17: 0.03156% | 0%
| PRWM3340 | LADLE (3641) - Fabrication by SIKO |  | 60% | 3239747332.5 | 0.09469% | 2018-03-12: 0.09469% | 0%
| PRWM3350 | LADLE (3641) - Packing by SIKO | [34 empty] | 0%
| PRWM3360 | LADLE (3641) - Delivery by WIKA |  | 20% | 1079801730 | 0.03156% | 2018-05-11: 0.03156% | 0%
F4 |  |  |  | 100% | 56795655 | 0.00458% | 2018-05-11: 0.00458% | 0%
B72 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.3.13.2.3.3.3 Slag Pot (3643) | [35 empty] | 0%
|  |  |  | 20% | 210417637.5 | 0.00615% | 2017-06-15: 0.00615%; 2017-07-15: -0.00615%; 2018-02-10: 0.00615% | 0%
| PRWM3370 | SLAG PLOT(3643) - Fabrication by SIKO |  | 60% | 630910770 | 0.01844% | 2018-04-11: 0.01844% | 0%
| PRWM3380 | SLAG PLOT(3643) - Packing by SIKO | [34 empty] | 0%
| PRWM3390 | SLAG PLOT(3643) - Delivery by WIKA |  | 20% | 210417637.5 | 0.00615% | 2018-05-11: 0.00615% | 0%
F4 |  |  |  | 100% | 56795655 | 0.00089% | 2018-05-11: 0.0009% | -1e-05%
B73 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.3.13.2.3.3.4 Hanger (3644) | [35 empty] | 0%
|  |  |  | 20% | 177571957.5 | 0.00519% | 2017-03-17: 0.00519% | 0%
| PRWM3400 | HANGER (3644) - Fabrication by SIKO |  | 60% | 533058015 | 0.01558% | [30 empty] | 0.01558%
| PRWM3410 | HANGER (3644) - Packing by SIKO | [34 empty] | 0%
| PRWM3420 | HANGER (3644) - Delivery by WIKA |  | 20% | 177914100 | 0.0052% | [30 empty] | 0.0052%
F4 |  |  |  | 100% | 56795655 | 0.00075% | [30 empty] | 0.00075%
B74 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.3.13.2.3.3.5 Service Tank (3601) | [35 empty] | 0%
|  |  |  | 20% | 40372815 | 0.00118% | 2017-03-17: 0.00118% | 0%
| PRWM3430 | SERVICE TANK (3601) - Fabrication by SIKO |  | 60% | 120776302.5 | 0.00353% | 2017-11-12: 0.00354% | -1e-05%
| PRWM3440 | SERVICE TANK (3601) - Packing by SIKO | [34 empty] | 0%
| PRWM3450 | SERVICE TANK (3601) - Delivery by WIKA |  | 20% | 40372815 | 0.00118% | 2017-12-12: 0.00118% | 0%
F4 |  |  |  | 100% | 56795655 | 0.00017% | 2017-11-12: 0.00017% | 0%
B75 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.3.13.2.3.3.6 Pump Unit (3602) | [35 empty] | 0%
|  |  |  | 20% | 36951390 | 0.00108% | 2017-07-15: 0.00108% | 0%
| PRWM3460 | PUMP UNIT(3602) - Procurement by SIKO |  | 60% | 110512027.5 | 0.00323% | 2018-03-12: 0.00323% | 0%
| PRWM3470 | PUMP UNIT(3602) - Packing by SIKO | [34 empty] | 0%
| PRWM3480 | PUMP UNIT(3602) - Delivery by WIKA |  | 20% | 36951390 | 0.00108% | 2018-04-11: 0.00108% | 0%
F4 |  |  |  | 100% | 56795655 | 0.00016% | 2018-05-11: 0.00016% | 0%
B76 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.3.13.2.3.3.7 Valve Unit (3603) | [35 empty] | 0%
|  |  |  | 20% | 110512027.5 | 0.00323% | 2017-07-15: 0.00323% | 0%
| PRWM3490 | VALVE UNIT(3603) - Fabrication by SIKO |  | 60% | 331878225 | 0.0097% | 2018-03-12: 0.0097% | 0%
| PRWM3500 | VALVE UNIT(3603) - Packing by SIKO | [34 empty] | 0%
| PRWM3510 | VALVE UNIT(3603) - Delivery by WIKA |  | 20% | 110854170 | 0.00324% | 2018-04-11: 0.00323% | 1e-05%
F4 |  |  |  | 100% | 56795655 | 0.00047% | 2018-05-11: 0.00047% | 0%
B77 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.3.13.2.3.3.8 Burner (3604) | [35 empty] | 0%
|  |  |  | 20% | 50294947.5 | 0.00147% | 2017-07-15: 0.00147% | 0%
| PRWM3520 | BURNER (3604) - Procurement by SIKO |  | 60% | 150884842.5 | 0.00441% | 2018-03-12: 0.00441% | 0%
| PRWM3530 | BURNER (3604) - Packing by SIKO | [34 empty] | 0%
| PRWM3540 | BURNER (3604) - Delivery by WIKA |  | 20% | 50294947.5 | 0.00147% | 2018-04-11: 0.00147% | 0%
F4 |  |  |  | 100% | 56795655 | 0.00021% | 2018-05-11: 0.00021% | 0%
B78 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.3.13.2.3.3.9 Ladle Preheating Unit (3606A) | [35 empty] | 0%
|  |  |  | 20% | 50294947.5 | 0.00147% | 2017-07-15: 0.00147% | 0%
| PRWM3550 | LADLE PREHEATING UNIT(3606A) - Fabrication by SIKO |  | 60% | 150884842.5 | 0.00441% | 2018-03-12: 0.00441% | 0%
| PRWM3560 | LADLE PREHEATING UNIT(3606A) - Packing by SIKO | [34 empty] | 0%
| PRWM3570 | LADLE PREHEATING UNIT(3606A) - Delivery by WIKA |  | 20% | 50294947.5 | 0.00147% | 2018-04-11: 0.00147% | 0%
F4 |  |  |  | 100% | 56795655 | 0.00022% | 2018-05-11: 0.00021% | 1e-05%
B79 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.3.13.2.3.3.10 Ladle Heating Unit (3606B) | [35 empty] | 0%
|  |  |  | 20% | 460523805 | 0.01346% | 2017-03-17: 0.01346% | 0%
| PRWM3580 | LADLE HEATING UNIT(3606B) - Fabrication by SIKO |  | 60% | 1381913557.5 | 0.04039% | 2017-11-12: 0.04039% | 0%
| PRWM3590 | CRANE LADLELADLE HEATING UNIT(3606B) - Packing by SIKO | [34 empty] | 0%
| PRWM3600 | LADLE HEATING UNIT(3606B) - Delivery by WIKA |  | 20% | 460523805 | 0.01346% | 2017-12-12: 0.01346% | 0%
F4 |  |  |  | 100% | 56795655 | 0.00195% | 2017-11-12: 0.00195% | 0%
B80 | P3FH - 28 M.13.13.2.13.2.3.13.2.3.3.13.2.3.3.11 Casting Storage Crane (3661) | [35 empty] | 0%
|  |  |  | 20% | 526899450 | 0.0154% | 2017-06-15: 0.0154% | 0%
| PRWM3610 | CASTING STORAGE CRANE (3661) - Fabrication by SIKO |  | 60% | 1580698350 | 0.0462% | 2017-12-12: 0.04621% | -1e-05%
| PRWM3620 | CASTING STORAGE CRANE (3661) - Packing by SIKO | [34 empty] | 0%
| PRWM3630 | CASTING STORAGE CRANE (3661) - Delivery by WIKA |  | 20% | 526899450 | 0.0154% | 2018-02-10: 0.0154% | 0%
F4 |  |  |  | 100% | 62269935 | 0.00224% | 2017-12-12: 0.00223% | 1e-05%
| P3FH - 28 M.13.13.2.13.2.4 System 4 - Utility Supply | [35 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.4.13.2.4.1 Raw Water Intake System | [35 empty] | 0%
B83 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.1.13.2.4.1.1 Raw Water Intake Pump (4102-1) | [35 empty] | 0%
| PRWM3639 | RAW WATER INTAKE PUMP (4102-1) - RFQ | [34 empty] | 0%
| PRWM3640 | RAW WATER INTAKE PUMP (4102-1) - Received of Bids | [34 empty] | 0%
| PRWM3641 | RAW WATER INTAKE PUMP (4102-1) - CBE | [34 empty] | 0%
| PRWM3642 | RAW WATER INTAKE PUMP (4102-1) - LOI | [34 empty] | 0%
| PRWM3643 | RAW WATER INTAKE PUMP (4102-1) - PO |  | 20% | 33872107.5 | 0.00099% | 2017-08-14: 0.00099% | 0%
| PRWM3644 | RAW WATER INTAKE PUMP (4102-1) - Fabrication |  | 60% | 101274180 | 0.00296% | 2018-05-11: 0.00296% | 0%
| PRWM3660 | RAW WATER INTAKE PUMP (4102-1) - Foreign Delivery |  | 20% | 33872107.5 | 0.00099% | [30 empty] | 0.00099%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B84 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.1.13.2.4.1.2 Raw Water Intake Pump (4102-2) | [35 empty] | 0%
| PRWM3669 | RAW WATER INTAKE PUIMP (4102-2) - RFQ | [34 empty] | 0%
| PRWM3670 | RAW WATER INTAKE PUIMP (4102-2) - Received of Bids | [34 empty] | 0%
| PRWM3671 | RAW WATER INTAKE PUIMP (4102-2) - CBE | [34 empty] | 0%
| PRWM3672 | RAW WATER INTAKE PUIMP (4102-2) - LOI | [34 empty] | 0%
| PRWM3673 | RAW WATER INTAKE PUIMP (4102-2) - PO |  | 20% | 84851340 | 0.00248% | 2017-08-14: 0.00248% | 0%
| PRWM3680 | RAW WATER INTAKE PUIMP (4102-2) - Fabrication |  | 60% | 254554020 | 0.00744% | 2018-05-11: 0.00744% | 0%
| PRWM3690 | RAW WATER INTAKE PUIMP (4102-2) - Foreign Delivery |  | 20% | 84851340 | 0.00248% | [30 empty] | 0.00248%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B85 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.1.13.2.4.1.3 Clarifier (4103) | [35 empty] | 0%
| PRWM3699 | CLARIFIER (4103) - RFQ | [34 empty] | 0%
| PRWM3700 | CLARIFIER (4103) - Received of Bids | [34 empty] | 0%
| PRWM3701 | CLARIFIER (4103) - CBE | [34 empty] | 0%
| PRWM3702 | CLARIFIER (4103) - LOI | [34 empty] | 0%
| PRWM3703 | CLARIFIER (4103) - PO |  | 20% | 249421882.5 | 0.00729% | 2017-08-14: 0.0073% | -1e-05%
| PRWM3710 | CLARIFIER (4103) - Fabrication |  | 60% | 748607790 | 0.02188% | 2018-03-12: 0.02188% | 0%
| PRWM3720 | CLARIFIER (4103) - Local Delivery |  | 20% | 249421882.5 | 0.00729% | 2018-03-12: 0.00729% | 0%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | 2018-04-11: 0.00208% | 3e-05%
B86 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.1.13.2.4.1.4 Water Transfer Pump (4104-1) | [35 empty] | 0%
| PRWM3729 | WATER TRANSFER PUMP (4104-1) - RFQ | [34 empty] | 0%
| PRWM3730 | WATER TRANSFER PUMP (4104-1) - Received of Bids | [34 empty] | 0%
| PRWM3731 | WATER TRANSFER PUMP (4104-1) - CBE | [34 empty] | 0%
| PRWM3732 | WATER TRANSFER PUMP (4104-1) - LOI | [34 empty] | 0%
| PRWM3733 | WATER TRANSFER PUMP (4104-1) - PO |  | 20% | 29424255 | 0.00086% | 2017-07-15: 0.00086% | 0%
| PRWM3740 | WATER TRANSFER PUMP (4104-1) - Fabrication |  | 60% | 87930622.5 | 0.00257% | 2018-05-11: 0.00258% | -1e-05%
| PRWM3750 | WATER TRANSFER PUMP (4104-1) - Foreign Delivery |  | 20% | 29424255 | 0.00086% | [30 empty] | 0.00086%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B87 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.1.13.2.4.1.5 Water Transfer Pump (4104-2) | [35 empty] | 0%
| PRWM3759 | WATER TRANSFER PUMP (4104-2) - RFQ | [34 empty] | 0%
| PRWM3760 | WATER TRANSFER PUMP (4104-2) - Received of Bids | [34 empty] | 0%
| PRWM3761 | WATER TRANSFER PUMP (4104-2) - CBE | [34 empty] | 0%
| PRWM3762 | WATER TRANSFER PUMP (4104-2) - LOI | [34 empty] | 0%
| PRWM3763 | WATER TRANSFER PUMP (4104-2) - PO |  | 20% | 207338355 | 0.00606% | 2017-07-15: 0.00606% | 0%
| PRWM3770 | WATER TRANSFER PUMP (4104-2) - Fabrication |  | 60% | 622357207.5 | 0.01819% | 2018-05-11: 0.01819% | 0%
| PRWM3780 | WATER TRANSFER PUMP (4104-2) - Foreign Delivery |  | 20% | 207338355 | 0.00606% | [30 empty] | 0.00606%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B88 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.1.13.2.4.1.6 No.1 Dosing Tank (4105-1) | [35 empty] | 0%
| PRWM3789 | N0.1 DOSING TANK (4105-1) - RFQ | [34 empty] | 0%
| PRWM3790 | N0.1 DOSING TANK (4105-1) - Received of Bids | [34 empty] | 0%
| PRWM3791 | N0.1 DOSING TANK (4105-1) - CBE | [34 empty] | 0%
| PRWM3792 | N0.1 DOSING TANK (4105-1) - LOI | [34 empty] | 0%
| PRWM3793 | N0.1 DOSING TANK (4105-1) - PO |  | 20% | 14027842.5 | 0.00041% | 2017-07-15: 0.00041% | 0%
| PRWM3800 | N0.1 DOSING TANK (4105-1) - Fabrication |  | 60% | 42767812.5 | 0.00125% | [30 empty] | 0.00125%
| PRWM3810 | N0.1 DOSING TANK (4105-1) - Local Delivery |  | 20% | 14027842.5 | 0.00041% | [30 empty] | 0.00041%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B89 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.1.13.2.4.1.7 Dosing Pump for No.1 Dosing Tank (4106-1) | [35 empty] | 0%
| PRWM3819 | DOSING PUMP FOR NO.1 DOSING TANK (4106-1) - RFQ | [34 empty] | 0%
| PRWM3820 | DOSING PUMP FOR NO.1 DOSING TANK (4106-1) - Received of Bids | [34 empty] | 0%
| PRWM3821 | DOSING PUMP FOR NO.1 DOSING TANK (4106-1) - CBE | [34 empty] | 0%
| PRWM3822 | DOSING PUMP FOR NO.1 DOSING TANK (4106-1) - LOI | [34 empty] | 0%
| PRWM3823 | DOSING PUMP FOR NO.1 DOSING TANK (4106-1) - PO |  | 20% | 16422840 | 0.00048% | 2017-07-15: 0.00048% | 0%
| PRWM3830 | DOSING PUMP FOR NO.1 DOSING TANK (4106-1) - Fabrication |  | 60% | 48926377.5 | 0.00143% | 2018-05-11: 1.43e-05 | 0%
| PRWM3840 | DOSING PUMP FOR NO.1 DOSING TANK (4106-1) - Foreign Delivery |  | 20% | 16422840 | 0.00048% | [30 empty] | 0.00048%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B90 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.1.13.2.4.1.8 No.2 Dosing Tank (4105-2) | [35 empty] | 0%
| PRWM3849 | NO.2 DOSING TANK (4105-2) - RFQ | [34 empty] | 0%
| PRWM3850 | NO.2 DOSING TANK (4105-2) - Received of Bids | [34 empty] | 0%
| PRWM3851 | NO.2 DOSING TANK (4105-2) - CBE | [34 empty] | 0%
| PRWM3852 | NO.2 DOSING TANK (4105-2) - LOI | [34 empty] | 0%
| PRWM3853 | NO.2 DOSING TANK (4105-2) - PO |  | 20% | 11290702.5 | 0.00033% | 2017-07-15: 0.00033% | 0%
| PRWM3860 | NO.2 DOSING TANK (4105-2) - Fabrication |  | 60% | 33872107.5 | 0.00099% | [30 empty] | 0.00099%
| PRWM3870 | NO.2 DOSING TANK (4105-2) - Local Delivery |  | 20% | 11290702.5 | 0.00033% | [30 empty] | 0.00033%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B91 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.1.13.2.4.1.9 Dosing Pump for No.2 Dosing Tank (4106-2) | [35 empty] | 0%
| PRWM3879 | DOSING PUMP FOR NO.2 DOSING TANK (4106-2) - RFQ | [34 empty] | 0%
| PRWM3880 | DOSING PUMP FOR NO.2 DOSING TANK (4106-2) - Received of Bids | [34 empty] | 0%
| PRWM3881 | DOSING PUMP FOR NO.2 DOSING TANK (4106-2) - CBE | [34 empty] | 0%
| PRWM3882 | DOSING PUMP FOR NO.2 DOSING TANK (4106-2) - LOI | [34 empty] | 0%
| PRWM3883 | DOSING PUMP FOR NO.2 DOSING TANK (4106-2) - PO |  | 20% | 16422840 | 0.00048% | 2017-07-15: 0.00048% | 0%
| PRWM3890 | DOSING PUMP FOR NO.2 DOSING TANK (4106-2) - Fabrication |  | 60% | 48926377.5 | 0.00143% | 2018-05-11: 1.43e-05 | 0%
| PRWM3900 | DOSING PUMP FOR NO.2 DOSING TANK (4106-2) - Foreign Delivery |  | 20% | 16422840 | 0.00048% | [30 empty] | 0.00048%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B92 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.1.13.2.4.1.10 Receiving Water Pump (4111-1) | [35 empty] | 0%
| PRWM3909 | RECEIVING WATER PUMP (4111-1) - RFQ | [34 empty] | 0%
| PRWM3910 | RECEIVING WATER PUMP (4111-1) - Received of Bids | [34 empty] | 0%
| PRWM3911 | RECEIVING WATER PUMP (4111-1) - CBE | [34 empty] | 0%
| PRWM3912 | RECEIVING WATER PUMP (4111-1) - LOI | [34 empty] | 0%
| PRWM3913 | RECEIVING WATER PUMP (4111-1) - PO |  | 20% | 17449267.5 | 0.00051% | 2017-07-15: 0.00051% | 0%
| PRWM3920 | RECEIVING WATER PUMP (4111-1) - Fabrication |  | 60% | 52005660 | 0.00152% | 2018-04-11: 0.00152% | 0%
| PRWM3930 | RECEIVING WATER PUMP (4111-1) - Foreign Delivery |  | 20% | 17449267.5 | 0.00051% | 2018-04-11: 0.00051% | 0%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B93 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.1.13.2.4.1.11 Receiving Water Pump (4111-2) | [35 empty] | 0%
| PRWM3939 | RECEIVING WATER PUMP (4111-2) - RFQ | [34 empty] | 0%
| PRWM3940 | RECEIVING WATER PUMP (4111-2) - Received of Bids | [34 empty] | 0%
| PRWM3941 | RECEIVING WATER PUMP (4111-2) - CBE | [34 empty] | 0%
| PRWM3942 | RECEIVING WATER PUMP (4111-2) - LOI | [34 empty] | 0%
| PRWM3943 | RECEIVING WATER PUMP (4111-2) - PO |  | 20% | 73218495 | 0.00214% | 2017-07-15: 0.00214% | 0%
| PRWM3950 | RECEIVING WATER PUMP (4111-2) - Fabrication |  | 60% | 220339770 | 0.00644% | 2018-04-11: 0.00644% | 0%
| PRWM3960 | RECEIVING WATER PUMP (4111-2) - Foreign Delivery |  | 20% | 73218495 | 0.00214% | 2018-04-11: 0.00213% | 1e-05%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B94 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.1.13.2.4.1.12 Sand Filter (4112) | [35 empty] | 0%
| PRWM3969 | SAND FILTER (4112) - RFQ | [34 empty] | 0%
| PRWM3970 | SAND FILTER (4112) - Received of Bids | [34 empty] | 0%
| PRWM3971 | SAND FILTER (4112) - CBE | [34 empty] | 0%
| PRWM3972 | SAND FILTER (4112) - LOI | [34 empty] | 0%
| PRWM3973 | SAND FILTER (4112) - PO |  | 20% | 341116072.5 | 0.00997% | 2017-07-15: 0.00997% | 0%
| PRWM3980 | SAND FILTER (4112) - Fabrication |  | 60% | 1023690360 | 0.02992% | 2018-03-12: 0.02992% | 0%
| PRWM3990 | SAND FILTER (4112) - Local Delivery |  | 20% | 341116072.5 | 0.00997% | [30 empty] | 0.00997%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B96 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.1.13.2.4.1.13 Filtered Water Pump (4114-1) | [35 empty] | 0%
| PRWM3999 | FILTERED WATER PUMP (4114-1) - RFQ | [34 empty] | 0%
| PRWM4000 | FILTERED WATER PUMP (4114-1) - Received of Bids | [34 empty] | 0%
| PRWM4001 | FILTERED WATER PUMP (4114-1) - CBE | [34 empty] | 0%
| PRWM4002 | FILTERED WATER PUMP (4114-1) - LOI | [34 empty] | 0%
| PRWM4003 | FILTERED WATER PUMP (4114-1) - PO |  | 20% | 23607832.5 | 0.00069% | 2017-07-15: 0.00069% | 0%
| PRWM4010 | FILTERED WATER PUMP (4114-1) - Fabrication |  | 60% | 70481355 | 0.00206% | 2018-04-11: 0.00206% | 0%
| PRWM4020 | FILTERED WATER PUMP (4114-1) - Foreign Delivery by SIKO |  | 20% | 23607832.5 | 0.00069% | 2018-04-11: 0.00069% | 0%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B97 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.1.13.2.4.1.14 Filtered Water Pump (4114-2) | [35 empty] | 0%
| PRWM4029 | FILTERED WATER PUMP(4114-2) - RFQ | [34 empty] | 0%
| PRWM4030 | FILTERED WATER PUMP(4114-2) - Received of Bids | [34 empty] | 0%
| PRWM4031 | FILTERED WATER PUMP(4114-2) - CBE | [34 empty] | 0%
| PRWM4032 | FILTERED WATER PUMP(4114-2) - LOI | [34 empty] | 0%
| PRWM4033 | FILTERED WATER PUMP(4114-2) - PO |  | 20% | 89641335 | 0.00262% | 2017-07-15: 0.00261% | 1e-05%
| PRWM4040 | FILTERED WATER PUMP(4114-2) - Fabrication |  | 60% | 268239720 | 0.00784% | 2018-04-11: 0.00784% | 0%
| PRWM4050 | FILTERED WATER PUMP(4114-2) - Foreign Delivery |  | 20% | 89641335 | 0.00262% | 2018-04-11: 0.00262% | 0%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B98 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.1.13.2.4.1.15 Softener (4115) | [35 empty] | 0%
| PRWM4059 | SOFTENER (4115) - RFQ | [34 empty] | 0%
| PRWM4060 | SOFTENER (4115) - Received of Bids | [34 empty] | 0%
| PRWM4061 | SOFTENER (4115) - CBE | [34 empty] | 0%
| PRWM4062 | SOFTENER (4115) - LOI | [34 empty] | 0%
| PRWM4063 | SOFTENER (4115) - PO |  | 20% | 493027342.5 | 0.01441% | 2017-07-15: 0.01441% | 0%
| PRWM4070 | SOFTENER (4115) - Fabrication |  | 60% | 1478397742.5 | 0.04321% | 2018-03-12: 0.04321% | 0%
| PRWM4080 | SOFTENER (4115) - Local Delivery |  | 20% | 493027342.5 | 0.01441% | [30 empty] | 0.01441%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B99 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.1.13.2.4.1.16 NaCl Tank (4116) | [35 empty] | 0%
| PRWM4089 | NaCl TANK (4116) - RFQ | [34 empty] | 0%
| PRWM4090 | NaCl TANK (4116) - Received of Bids | [34 empty] | 0%
| PRWM4091 | NaCl TANK (4116) - CBE | [34 empty] | 0%
| PRWM4092 | NaCl TANK (4116) - LOI | [34 empty] | 0%
| PRWM4093 | NaCl TANK (4116) - PO |  | 20% | 19502122.5 | 0.00057% | 2017-07-15: 0.00057% | 0%
| PRWM4100 | NaCl TANK (4116) - Fabrication |  | 60% | 58848510 | 0.00172% | 2018-05-11: 0.00172% | 0%
| PRWM4110 | NaCl TANK (4116) - Local Delivery |  | 20% | 19502122.5 | 0.00057% | [30 empty] | 0.00057%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
| P3FH - 28 M.13.13.2.13.2.4.13.2.4.2 Water Circulation NSW | [35 empty] | 0%
B100 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.2.13.2.4.2.1 NSW - Circulation Pump (4201-1) | [35 empty] | 0%
| PRWM4119 | NSW CIRCULATION PUMP (4201-1) - RFQ | [34 empty] | 0%
| PRWM4120 | NSW CIRCULATION PUMP (4201-1) - Received of Bids | [34 empty] | 0%
| PRWM4121 | NSW CIRCULATION PUMP (4201-1) - CBE | [34 empty] | 0%
| PRWM4122 | NSW CIRCULATION PUMP (4201-1) - LOI | [34 empty] | 0%
| PRWM4123 | NSW CIRCULATION PUMP (4201-1) - PO |  | 20% | 51663517.5 | 0.00151% | 2017-10-13: 0.00151% | 0%
| PRWM4130 | NSW CIRCULATION PUMP (4201-1) - Fabrication |  | 60% | 154990552.5 | 0.00453% | [30 empty] | 0.00453%
| PRWM4140 | NSW CIRCULATION PUMP (4201-1) - Foreign Delivery |  | 20% | 51663517.5 | 0.00151% | [30 empty] | 0.00151%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B101 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.2.13.2.4.2.2 NSW - Circulation Pump (4201-2) | [35 empty] | 0%
| PRWM4149 | NSW CIRCULATION PUMP (4201-2) - RFQ | [34 empty] | 0%
| PRWM4150 | NSW CIRCULATION PUMP (4201-2) - Received of Bids | [34 empty] | 0%
| PRWM4151 | NSW CIRCULATION PUMP (4201-2) - CBE | [34 empty] | 0%
| PRWM4152 | NSW CIRCULATION PUMP (4201-2) - LOI | [34 empty] | 0%
| PRWM4153 | NSW CIRCULATION PUMP (4201-2) - PO |  | 20% | 229577617.5 | 0.00671% | [30 empty] | 0.00671%
| PRWM4160 | NSW CIRCULATION PUMP (4201-2) - Fabrication |  | 60% | 689417137.5 | 0.02015% | 2017-10-13: 0.00671% | 0.01344%
| PRWM4170 | NSW CIRCULATION PUMP (4201-2) - Foreign Delivery |  | 20% | 229577617.5 | 0.00671% | [30 empty] | 0.00671%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B102 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.2.13.2.4.2.3 NSW - Head Tank (4202) | [35 empty] | 0%
| PRWM4179 | NSW HEAD TANK & STEEL STRUCTURE (4202) - RFQ | [34 empty] | 0%
| PRWM4180 | NSW HEAD TANK & STEEL STRUCTURE (4202) - Received of Bids | [34 empty] | 0%
| PRWM4181 | NSW HEAD TANK & STEEL STRUCTURE (4202) - CBE | [34 empty] | 0%
| PRWM4182 | NSW HEAD TANK & STEEL STRUCTURE (4202) - LOI | [34 empty] | 0%
| PRWM4183 | NSW HEAD TANK & STEEL STRUCTURE (4202) - PO |  | 20% | 345563925 | 0.0101% | 2017-08-14: 0.0101% | 0%
| PRWM4190 | NSW HEAD TANK & STEEL STRUCTURE (4202) - Fabrication |  | 60% | 1037033917.5 | 0.03031% | 2018-03-12: 0.03031% | 0%
| PRWM4200 | NSW HEAD TANK & STEEL STRUCTURE (4202) - Foreign Delivery |  | 20% | 345563925 | 0.0101% | 2018-03-12: 0.0101% | 0%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | 2018-04-11: 0.00207% | 4e-05%
B103 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.2.13.2.4.2.4 NSW - Return Water Pump (4204-1) | [35 empty] | 0%
| PRWM4209 | NSW RETURN WATER PUMP (4204-1) - RFQ | [34 empty] | 0%
| PRWM4210 | NSW RETURN WATER PUMP (4204-1) - Received of Bids | [34 empty] | 0%
| PRWM4211 | NSW RETURN WATER PUMP (4204-1) - CBE | [34 empty] | 0%
| PRWM4212 | NSW RETURN WATER PUMP (4204-1) - LOI | [34 empty] | 0%
| PRWM4213 | NSW RETURN WATER PUMP (4204-1) - PO |  | 25% | 24292117.5 | 0.00056% | [30 empty] | 0.00056%
| PRWM4220 | NSW RETURN WATER PUMP (4204-1) - Fabrication |  | 60% | 57822082.5 | 0.00169% | 2017-10-13: 0.00056% | 0.00113%
| PRWM4230 | NSW RETURN WATER PUMP (4204-1) - Foreign Delivery |  | 15% | 14369985 | 0.00057% | [30 empty] | 0.00057%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B104 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.2.13.2.4.2.5 NSW - Return Water Pump (4204-2) | [35 empty] | 0%
| PRWM4239 | NSW RETURN WATER PUMP(4204-2) - RFQ | [34 empty] | 0%
| PRWM4240 | NSW RETURN WATER PUMP(4204-2) - Received of Bids | [34 empty] | 0%
| PRWM4241 | NSW RETURN WATER PUMP(4204-2) - CBE | [34 empty] | 0%
| PRWM4242 | NSW RETURN WATER PUMP(4204-2) - LOI | [34 empty] | 0%
| PRWM4243 | NSW RETURN WATER PUMP(4204-2) - PO |  | 20% | 105379890 | 0.00308% | 2017-10-13: 0.00307% | 1e-05%
| PRWM4250 | NSW RETURN WATER PUMP(4204-2) - Fabrication |  | 60% | 315455385 | 0.00922% | [30 empty] | 0.00922%
| PRWM4260 | NSW RETURN WATER PUMP(4204-2) - Foreign Delivery |  | 20% | 105379890 | 0.00308% | [30 empty] | 0.00308%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B105 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.2.13.2.4.2.6 NSW - Cooling Tower (4205) | [35 empty] | 0%
| PRWM4269 | NSW COOLING TOWER (4205) - RFQ | [34 empty] | 0%
| PRWM4270 | NSW COOLING TOWER (4205) - Received of Bids | [34 empty] | 0%
| PRWM4271 | NSW COOLING TOWER (4205) - CBE | [34 empty] | 0%
| PRWM4272 | NSW COOLING TOWER (4205) - LOI | [34 empty] | 0%
| PRWM4273 | NSW COOLING TOWER (4205) - PO |  | 20% | 103327035 | 0.00302% | 2017-09-13: 0.00302% | 0%
| PRWM4280 | NSW COOLING TOWER (4205) - Fabrication |  | 60% | 309981105 | 0.00906% | 2018-03-12: 0.00906% | 0%
| PRWM4290 | NSW COOLING TOWER (4205) - Foreign Delivery |  | 20% | 103327035 | 0.00302% | 2018-03-12: 0.00302% | 0%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | 2018-04-11: 0.00207% | 4e-05%
| P3FH - 28 M.13.13.2.13.2.4.13.2.4.3 Water Circulation SW | [35 empty] | 0%
B106 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.3.13.2.4.3.1 SW - Circulation Pump (4211-1) | [35 empty] | 0%
| PRWM4299 | SW CIRCULATION PUMP (4211-1) - RFQ | [34 empty] | 0%
| PRWM4300 | SW CIRCULATION PUMP (4211-1) - Received of Bids | [34 empty] | 0%
| PRWM4301 | SW CIRCULATION PUMP (4211-1) - CBE | [34 empty] | 0%
| PRWM4302 | SW CIRCULATION PUMP (4211-1) - LOI | [34 empty] | 0%
| PRWM4303 | SW CIRCULATION PUMP (4211-1) - PO |  | 20% | 50294947.5 | 0.00147% | 2017-10-13: 1.48e-05 | -1e-05%
| PRWM4310 | SW CIRCULATION PUMP (4211-1) - Fabrication |  | 60% | 151226985 | 0.00442% | [30 empty] | 0.00442%
| PRWM4320 | SW CIRCULATION PUMP (4211-1) - Foreign Delivery |  | 20% | 50294947.5 | 0.00147% | [30 empty] | 0.00147%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B107 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.3.13.2.4.3.2 SW - Circulation Pump (4211-2) | [35 empty] | 0%
| PRWM4329 | SW CIRCULATION PUMP (4211-2) - RFQ | [34 empty] | 0%
| PRWM4330 | SW CIRCULATION PUMP (4211-2) - Received of Bids | [34 empty] | 0%
| PRWM4331 | SW CIRCULATION PUMP (4211-2) - CBE | [34 empty] | 0%
| PRWM4332 | SW CIRCULATION PUMP (4211-2) - LOI | [34 empty] | 0%
| PRWM4333 | SW CIRCULATION PUMP (4211-2) - PO |  | 20% | 219655485 | 0.00642% | 2017-10-13: 0.00642% | 0%
| PRWM4340 | SW CIRCULATION PUMP (4211-2) - Fabrication |  | 60% | 659308597.5 | 0.01927% | [30 empty] | 0.01927%
| PRWM4350 | SW CIRCULATION PUMP (4211-2) - Foreign Delivery |  | 20% | 219655485 | 0.00642% | [30 empty] | 0.00642%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B108 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.3.13.2.4.3.3 SW - Head Tank (4212) | [35 empty] | 0%
| PRWM4359 | SW HEAD TANK & STEEL STRUCTURE (4212) - RFQ | [34 empty] | 0%
| PRWM4360 | SW HEAD TANK & STEEL STRUCTURE (4212) - Received of Bids | [34 empty] | 0%
| PRWM4361 | SW HEAD TANK & STEEL STRUCTURE (4212) - CBE | [34 empty] | 0%
| PRWM4362 | SW HEAD TANK & STEEL STRUCTURE (4212) - LOI | [34 empty] | 0%
| PRWM4363 | SW HEAD TANK & STEEL STRUCTURE (4212) - PO |  | 20% | 406465290 | 0.01188% | 2017-08-14: 0.01188% | 0%
| PRWM4370 | SW HEAD TANK & STEEL STRUCTURE (4212) - Fabrication |  | 60% | 1220080155 | 0.03566% | 2018-03-12: 0.03566% | 0%
| PRWM4380 | SW HEAD TANK & STEEL STRUCTURE (4212) - Delivery |  | 20% | 406465290 | 0.01188% | 2018-03-12: 0.01188% | 0%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | 2018-04-11: 0.00208% | 3e-05%
B109 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.3.13.2.4.3.4 SW - Return Water Pump (4214-1) | [35 empty] | 0%
| PRWM4389 | SW RETURN WATER PUMP (4214-1) - RFQ | [34 empty] | 0%
| PRWM4390 | SW RETURN WATER PUMP (4214-1) - Received of Bids | [34 empty] | 0%
| PRWM4391 | SW RETURN WATER PUMP (4214-1) - CBE | [34 empty] | 0%
| PRWM4392 | SW RETURN WATER PUMP (4214-1) - LOI | [34 empty] | 0%
| PRWM4393 | SW RETURN WATER PUMP (4214-1) - PO |  | 20% | 57479940 | 0.00168% | 2017-10-13: 0.00168% | 0%
| PRWM4400 | SW RETURN WATER PUMP (4214-1) - Fabrication |  | 60% | 173124105 | 0.00506% | [30 empty] | 0.00506%
| PRWM4410 | SW RETURN WATER PUMP (4214-1) - Foreign Delivery |  | 20% | 57479940 | 0.00168% | [30 empty] | 0.00168%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B110 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.3.13.2.4.3.5 SW - Return Water Pump (4214-2) | [35 empty] | 0%
| PRWM4219 | SW RETURN WATER PUMP (4214-2) - RFQ | [34 empty] | 0%
| PRWM4420 | SW RETURN WATER PUMP (4214-2) - Received of Bids | [34 empty] | 0%
| PRWM4421 | SW RETURN WATER PUMP (4214-2) - CBE | [34 empty] | 0%
| PRWM4422 | SW RETURN WATER PUMP (4214-2) - LOI | [34 empty] | 0%
| PRWM4423 | SW RETURN WATER PUMP (4214-2) - PO |  | 20% | 151569127.5 | 0.00443% | 2017-10-13: 0.00443% | 0%
| PRWM4430 | SW RETURN WATER PUMP (4214-2) - Fabrication |  | 60% | 455049525 | 0.0133% | [30 empty] | 0.0133%
| PRWM4440 | SW RETURN WATER PUMP (4214-2) - Foreign Delivery |  | 20% | 151569127.5 | 0.00443% | [30 empty] | 0.00443%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B111 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.3.13.2.4.3.6 SW - Cooling Tower (4215) | [35 empty] | 0%
| PRWM4449 | SW COOLING TOWER (4215) - RFQ | [34 empty] | 0%
| PRWM4450 | SW COOLING TOWER (4215) - Received of Bids | [34 empty] | 0%
| PRWM4451 | SW COOLING TOWER (4215) - CBE | [34 empty] | 0%
| PRWM4452 | SW COOLING TOWER (4215) - LOI | [34 empty] | 0%
| PRWM4453 | SW COOLING TOWER (4215) - PO |  | 20% | 216576202.5 | 0.00633% | 2017-09-13: 0.00633% | 0%
| PRWM4460 | SW COOLING TOWER (4215) - Fabrication |  | 60% | 649386465 | 0.01898% | 2018-03-12: 0.01898% | 0%
| PRWM4470 | SW COOLING TOWER (4215) - Foreign Delivery |  | 20% | 216576202.5 | 0.00633% | 2018-03-12: 0.00633% | 0%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | 2018-04-11: 0.00208% | 3e-05%
B112 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.3.13.2.4.3.7 SW - Inline Filter (4216) | [35 empty] | 0%
| PRWM4479 | SW INLINE FILTER (4216) - RFQ | [34 empty] | 0%
| PRWM4480 | SW INLINE FILTER (4216) - Received of Bids | [34 empty] | 0%
| PRWM4481 | SW INLINE FILTER (4216) - CBE | [34 empty] | 0%
| PRWM4482 | SW INLINE FILTER (4216) - LOI | [34 empty] | 0%
| PRWM4483 | SW INLINE FILTER (4216) - PO |  | 20% | 13685700 | 0.0004% | 2017-07-15: 0.0004% | 0%
| PRWM4490 | SW INLINE FILTER (4216) - Fabrication |  | 60% | 41741385 | 0.00122% | 2018-05-11: 0.00121% | 1e-05%
| PRWM4500 | SW INLINE FILTER (4216) - Foreign Delivery |  | 20% | 13685700 | 0.0004% | [30 empty] | 0.0004%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
| P3FH - 28 M.13.13.2.13.2.4.13.2.4.4 Water Circulation SW (Copper Cooler) | [35 empty] | 0%
B113 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.4.13.2.4.4.1 SW - Circulation Pump (4221-1) | [35 empty] | 0%
| PRWM4509 | SW CIRCULATION PUMP (4221-1) - RFQ | [34 empty] | 0%
| PRWM4510 | SW CIRCULATION PUMP (4221-1) - Received of Bids | [34 empty] | 0%
| PRWM4511 | SW CIRCULATION PUMP (4221-1) - CBE | [34 empty] | 0%
| PRWM4512 | SW CIRCULATION PUMP (4221-1) - LOI | [34 empty] | 0%
| PRWM4513 | SW CIRCULATION PUMP (4221-1) - PO |  | 20% | 50294947.5 | 0.00147% | 2017-10-13: 0.00148% | -1e-05%
| PRWM4520 | SW CIRCULATION PUMP (4221-1) - Fabrication |  | 60% | 151226985 | 0.00442% | [30 empty] | 0.00442%
| PRWM4530 | SW CIRCULATION PUMP (4221-1) - Foreign Delivery |  | 20% | 50294947.5 | 0.00147% | [30 empty] | 0.00147%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B114 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.4.13.2.4.4.2 SW - Circulation Pump (4221-2) | [35 empty] | 0%
| PRWM4539 | SW CIRCULATION PUMP (4221-2) - RFQ | [34 empty] | 0%
| PRWM4540 | SW CIRCULATION PUMP (4221-2) - Received of Bids | [34 empty] | 0%
| PRWM4541 | SW CIRCULATION PUMP (4221-2) - CBE | [34 empty] | 0%
| PRWM4542 | SW CIRCULATION PUMP (4221-2) - LOI | [34 empty] | 0%
| PRWM4543 | SW CIRCULATION PUMP (4221-2) - PO |  | 20% | 265844722.5 | 0.00777% | 2017-10-13: 0.00777% | 0%
| PRWM4550 | SW CIRCULATION PUMP (4221-2) - Fabrication |  | 60% | 797192025 | 0.0233% | [30 empty] | 0.0233%
| PRWM4560 | SW CIRCULATION PUMP (4221-2) - Foreign Delivery |  | 20% | 265844722.5 | 0.00777% | [30 empty] | 0.00777%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B115 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.4.13.2.4.4.3 SW - Head Tank (4222) | [35 empty] | 0%
| PRWM4569 | SW HEAD TANK (4222) - RFQ | [34 empty] | 0%
| PRWM4570 | SW HEAD TANK (4222) - Received of Bids | [34 empty] | 0%
| PRWM4571 | SW HEAD TANK (4222) - CBE | [34 empty] | 0%
| PRWM4572 | SW HEAD TANK (4222) - LOI | [34 empty] | 0%
| PRWM4573 | SW HEAD TANK (4222) - PO |  | 20% | 345563925 | 0.0101% | 2017-08-14: 0.0101% | 0%
| PRWM4580 | SW HEAD TANK (4222) - Fabrication |  | 60% | 1037033917.5 | 0.03031% | 2018-03-12: 0.03031% | 0%
| PRWM4590 | SW HEAD TANK (4222) - Delivery |  | 20% | 345563925 | 0.0101% | 2018-03-12: 0.0101% | 0%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | 2018-04-11: 0.00208% | 3e-05%
B116 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.4.13.2.4.4.4 SW - Return Water Pump (4224-1) | [35 empty] | 0%
| PRWM4599 | SW RETURN WATER PUMP (4224-1) - RFQ | [34 empty] | 0%
| PRWM4600 | SW RETURN WATER PUMP (4224-1) - Received of Bids | [34 empty] | 0%
| PRWM4601 | SW RETURN WATER PUMP (4224-1) - CBE | [34 empty] | 0%
| PRWM4602 | SW RETURN WATER PUMP (4224-1) - LOI | [34 empty] | 0%
| PRWM4603 | SW RETURN WATER PUMP (4224-1) - PO |  | 20% | 39004245 | 0.00114% | 2017-10-13: 0.00114% | 0%
| PRWM4610 | SW RETURN WATER PUMP (4224-1) - Fabrication |  | 60% | 116670592.5 | 0.00341% | [30 empty] | 0.00341%
| PRWM4620 | SW RETURN WATER PUMP (4224-1) - Foreign Delivery |  | 20% | 39004245 | 0.00114% | [30 empty] | 0.00114%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B117 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.4.13.2.4.4.5 SW - Return Water Pump (4224-2) | [35 empty] | 0%
| PRWM4629 | SW RETURN WATER PUMP (4224-2) - RFQ | [34 empty] | 0%
| PRWM4630 | SW RETURN WATER PUMP (4224-2) - Received of Bids | [34 empty] | 0%
| PRWM4631 | SW RETURN WATER PUMP (4224-2) - CBE | [34 empty] | 0%
| PRWM4632 | SW RETURN WATER PUMP (4224-2) - LOI | [34 empty] | 0%
| PRWM4633 | SW RETURN WATER PUMP (4224-2) - PO |  | 20% | 188862660 | 0.00552% | 2017-10-13: 0.00553% | -1e-05%
| PRWM4640 | SW RETURN WATER PUMP (4224-2) - Fabrication |  | 60% | 567272265 | 0.01658% | [30 empty] | 0.01658%
| PRWM4650 | SW RETURN WATER PUMP (4224-2) - Foreign Delivery |  | 20% | 188862660 | 0.00552% | [30 empty] | 0.00552%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B118 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.4.13.2.4.4.6 SW - Cooling Tower (4225) | [35 empty] | 0%
| PRWM4659 | SW COOLING TOWER (4225) - RFQ | [34 empty] | 0%
| PRWM4660 | SW COOLING TOWER (4225) - Received of Bids | [34 empty] | 0%
| PRWM4661 | SW COOLING TOWER (4225) - CBE | [34 empty] | 0%
| PRWM4662 | SW COOLING TOWER (4225) - LOI | [34 empty] | 0%
| PRWM4663 | SW COOLING TOWER (4225) - PO |  | 20% | 295268977.5 | 0.00863% | 2017-09-13: 0.00863% | 0%
| PRWM4670 | SW COOLING TOWER (4225) - Fabrication |  | 60% | 885464790 | 0.02588% | 2018-03-12: 0.02588% | 0%
| PRWM4680 | SW COOLING TOWER (4225) - Foreign Delivery |  | 20% | 295268977.5 | 0.00863% | 2018-03-12: 0.00863% | 0%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | 2018-04-11: 0.00208% | 3e-05%
B119 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.4.13.2.4.4.7 SW - Inline Filter (4226) | [35 empty] | 0%
| PRWM4679 | SW INLINE FILTER (4226) - RFQ | [34 empty] | 0%
| PRWM4690 | SW INLINE FILTER (4226) - Received of Bids | [34 empty] | 0%
| PRWM4691 | SW INLINE FILTER (4226) - CBE | [34 empty] | 0%
| PRWM4692 | SW INLINE FILTER (4226) - LOI | [34 empty] | 0%
| PRWM4693 | SW INLINE FILTER (4226) - PO |  | 20% | 11632845 | 0.00034% | 2017-10-13: 0.00034% | 0%
| PRWM4700 | SW INLINE FILTER (4226) - Fabrication |  | 60% | 35582820 | 0.00104% | 2018-05-11: 0.00103% | 1e-05%
| PRWM4710 | SW INLINE FILTER (4226) - Foreign Delivery |  | 20% | 11632845 | 0.00034% | [30 empty] | 0.00034%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
| P3FH - 28 M.13.13.2.13.2.4.13.2.4.5 Compressed Air | [35 empty] | 0%
B120 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.5.13.2.4.5.1 Air Receiver Tank (4702) | [35 empty] | 0%
| PRWM4719 | AIR RECEIVER TANK (4702) - RFQ | [34 empty] | 0%
| PRWM4720 | AIR RECEIVER TANK (4702) - Received of Bids | [34 empty] | 0%
| PRWM4721 | AIR RECEIVER TANK (4702) - CBE | [34 empty] | 0%
| PRWM4722 | AIR RECEIVER TANK (4702) - LOI | [34 empty] | 0%
| PRWM4723 | AIR RECEIVER TANK (4702) - PO |  | 20% | 808482727.5 | 0.02363% | 2017-07-15: 0.00093%; 2017-10-13: 0.02269% | 1e-05%
| PRWM4730 | AIR RECEIVER TANK (4702) - Fabrication |  | 60% | 2425106040 | 0.07088% | [30 empty] | 0.07088%
| PRWM4740 | AIR RECEIVER TANK (4702) - Local Delivery |  | 20% | 808482727.5 | 0.02363% | [30 empty] | 0.02363%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B122 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.5.13.2.4.5.2 Air Receiver Tank (4703-1/2/3/4/5) | [35 empty] | 0%
| PRWM4749 | AIR RECEIVER TANK(4703-1/2/3/4/5) - RFQ | [34 empty] | 0%
| PRWM4750 | AIR RECEIVER TANK(4703-1/2/3/4/5) - Received of Bids | [34 empty] | 0%
| PRWM4751 | AIR RECEIVER TANK(4703-1/2/3/4/5) - CBE | [34 empty] | 0%
| PRWM4752 | AIR RECEIVER TANK(4703-1/2/3/4/5) - LOI | [34 empty] | 0%
| PRWM4753 | AIR RECEIVER TANK(4703-1/2/3/4/5) - PO |  | 20% | 95457757.5 | 0.00279% | 2017-07-15: 0.0028% | -1e-05%
| PRWM4760 | AIR RECEIVER TANK(4703-1/2/3/4/5) - Fabrication |  | 60% | 286031130 | 0.00836% | [30 empty] | 0.00836%
| PRWM4770 | AIR RECEIVER TANK(4703-1/2/3/4/5) - Local Delivery |  | 20% | 95457757.5 | 0.00279% | [30 empty] | 0.00279%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B123 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.5.13.2.4.5.3 Air Receiver Tank (4703-6) | [35 empty] | 0%
| PRWM4779 | AIR RECEIVER TANK (4703-6) - RFQ | [34 empty] | 0%
| PRWM4780 | AIR RECEIVER TANK (4703-6) - Received of Bids | [34 empty] | 0%
| PRWM4781 | AIR RECEIVER TANK (4703-6) - CBE | [34 empty] | 0%
| PRWM4782 | AIR RECEIVER TANK (4703-6) - LOI | [34 empty] | 0%
| PRWM4783 | AIR RECEIVER TANK (4703-6) - PO |  | 20% | 8895705 | 0.00026% | 2017-07-15: 0.00026% | 0%
| PRWM4790 | AIR RECEIVER TANK (4703-6) - Fabrication |  | 60% | 26344972.5 | 0.00077% | [30 empty] | 0.00077%
| PRWM4800 | AIR RECEIVER TANK (4703-6) - Local Delivery |  | 20% | 8895705 | 0.00026% | [30 empty] | 0.00026%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B124 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.5.13.2.4.5.4 Air Dryer for Gas Treatment Instrument (4704-2) | [35 empty] | 0%
| PRWM4809 | AIR DRYER FOR GAS TREATMENT INSTRUMENT (4704-2) - RFQ | [34 empty] | 0%
| PRWM4810 | AIR DRYER FOR GAS TREATMENT INSTRUMENT (4704-2) - Received of Bids | [34 empty] | 0%
| PRWM4811 | AIR DRYER FOR GAS TREATMENT INSTRUMENT (4704-2) - CBE | [34 empty] | 0%
| PRWM4812 | AIR DRYER FOR GAS TREATMENT INSTRUMENT (4704-2) - LOI | [34 empty] | 0%
| PRWM4813 | AIR DRYER FOR GAS TREATMENT INSTRUMENT (4704-2) - PO |  | 20% | 2737140 | 8e-05% | 2017-07-15: 8e-05% | 0%
| PRWM4820 | AIR DRYER FOR GAS TREATMENT INSTRUMENT (4704-2) - Fabrication |  | 60% | 8895705 | 0.00026% | [30 empty] | 0.00026%
| PRWM4830 | AIR DRYER FOR GAS TREATMENT INSTRUMENT (4704-2) - Foreign Delivery |  | 20% | 2737140 | 8e-05% | [30 empty] | 8e-05%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B125 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.5.13.2.4.5.5 Air Dryer for Instrument for Kiln (4704-3) | [35 empty] | 0%
| PRWM4839 | AIR DRYER FOR INSTRUMENT FOR KILN (4704-3) - RFQ | [34 empty] | 0%
| PRWM4840 | AIR DRYER FOR INSTRUMENT FOR KILN (4704-3) - Received of Bids | [34 empty] | 0%
| PRWM4841 | AIR DRYER FOR INSTRUMENT FOR KILN (4704-3) - CBE | [34 empty] | 0%
| PRWM4842 | AIR DRYER FOR INSTRUMENT FOR KILN (4704-3) - LOI | [34 empty] | 0%
| PRWM4843 | AIR DRYER FOR INSTRUMENT FOR KILN (4704-3) - PO |  | 20% | 2737140 | 8e-05% | 2017-07-15: 8e-05% | 0%
| PRWM4850 | AIR DRYER FOR INSTRUMENT FOR KILN (4704-3) - Fabrication |  | 60% | 8895705 | 0.00026% | [30 empty] | 0.00026%
| PRWM4860 | AIR DRYER FOR INSTRUMENT FOR KILN (4704-3) - Foreign Delivery |  | 20% | 2737140 | 8e-05% | [30 empty] | 8e-05%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B126 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.5.13.2.4.5.6 Air Dryer for De-S System and Other (4704-4) | [35 empty] | 0%
| PRWM4869 | AIR DRYER FOR DE-S SYSTEM AND OTHER (4704-4) - RFQ | [34 empty] | 0%
| PRWM4870 | AIR DRYER FOR DE-S SYSTEM AND OTHER (4704-4) - Receieved of Bids | [34 empty] | 0%
| PRWM4871 | AIR DRYER FOR DE-S SYSTEM AND OTHER (4704-4) - CBE | [34 empty] | 0%
| PRWM4872 | AIR DRYER FOR DE-S SYSTEM AND OTHER (4704-4) - LOI | [34 empty] | 0%
| PRWM4873 | AIR DRYER FOR DE-S SYSTEM AND OTHER (4704-4) - PO |  | 20% | 2737140 | 8e-05% | 2017-07-15: 8e-05% | 0%
| PRWM4880 | AIR DRYER FOR DE-S SYSTEM AND OTHER (4704-4) - Fabrication |  | 60% | 8895705 | 0.00026% | [30 empty] | 0.00026%
| PRWM4890 | AIR DRYER FOR DE-S SYSTEM AND OTHER (4704-4) - Foreign Delivery |  | 20% | 2737140 | 8e-05% | [30 empty] | 8e-05%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B128 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.5.13.2.4.5.7 Air Compressor for - Type ESF & Refinary (4705) | [35 empty] | 0%
| PRWM4899 | AIR COMPRESSOR FOR-TYPE ESF & REFINARY (4705) - RFQ | [34 empty] | 0%
| PRWM4900 | AIR COMPRESSOR FOR-TYPE ESF & REFINARY (4705) - Received of Bids | [34 empty] | 0%
| PRWM4901 | AIR COMPRESSOR FOR-TYPE ESF & REFINARY (4705) - CBE | [34 empty] | 0%
| PRWM4902 | AIR COMPRESSOR FOR-TYPE ESF & REFINARY (4705) - LOI | [34 empty] | 0%
| PRWM4903 | AIR COMPRESSOR FOR-TYPE ESF & REFINARY (4705) - PO |  | 20% | 502949475 | 0.0147% | 2017-07-15: 0.0147% | 0%
| PRWM4910 | AIR COMPRESSOR FOR-TYPE ESF & REFINARY (4705) - Fabrication |  | 60% | 1509532710 | 0.04412% | [30 empty] | 0.04412%
| PRWM4920 | AIR COMPRESSOR FOR-TYPE ESF & REFINARY (4705) - Foreign Delivery |  | 20% | 502949475 | 0.0147% | [30 empty] | 0.0147%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B129 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.5.13.2.4.5.8 Air Receiver Tank (4706) | [35 empty] | 0%
| PRWM4929 | AIR RECEIVER TANK (4706) - RFQ | [34 empty] | 0%
| PRWM4930 | AIR RECEIVER TANK (4706) - Received of Bids | [34 empty] | 0%
| PRWM4931 | AIR RECEIVER TANK (4706) - CBE | [34 empty] | 0%
| PRWM4932 | AIR RECEIVER TANK (4706) - LOI | [34 empty] | 0%
| PRWM4933 | AIR RECEIVER TANK (4706) - PO |  | 20% | 20870692.5 | 0.00061% | 2017-07-15: 0.00061% | 0%
| PRWM4940 | AIR RECEIVER TANK (4706) - Fabrication |  | 60% | 61927792.5 | 0.00181% | [30 empty] | 0.00181%
| PRWM4950 | AIR RECEIVER TANK (4706) - Local Delivery |  | 20% | 20870692.5 | 0.00061% | [30 empty] | 0.00061%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B127 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.5.13.2.4.5.9 Air Compressor for - Type Mud Gun (4707-1/2) | [35 empty] | 0%
| PRWM4959 | AIR COMPRESSOR FOR -TYPE MUD GUN (4707-1/2) - RFQ | [34 empty] | 0%
| PRWM4960 | AIR COMPRESSOR FOR -TYPE MUD GUN (4707-1/2) - Received of Bids | [34 empty] | 0%
| PRWM4961 | AIR COMPRESSOR FOR -TYPE MUD GUN (4707-1/2) - CBE | [34 empty] | 0%
| PRWM4962 | AIR COMPRESSOR FOR -TYPE MUD GUN (4707-1/2) - LOI | [34 empty] | 0%
| PRWM4963 | AIR COMPRESSOR FOR -TYPE MUD GUN (4707-1/2) - PO |  | 20% | 94773472.5 | 0.00277% | 2017-07-15: 0.00277% | 0%
| PRWM4970 | AIR COMPRESSOR FOR -TYPE MUD GUN (4707-1/2) - Fabrication |  | 60% | 284662560 | 0.00832% | [30 empty] | 0.00832%
| PRWM4980 | AIR COMPRESSOR FOR -TYPE MUD GUN (4707-1/2) - Local Delivery |  | 20% | 94773472.5 | 0.00277% | [30 empty] | 0.00277%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B130 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.5.13.2.4.5.10 Air Receiver Tank (4708-1/2) | [35 empty] | 0%
| PRWM4989 | AIR RECEIVER TANK (4708-1/2) - RFQ | [34 empty] | 0%
| PRWM4990 | AIR RECEIVER TANK (4708-1/2) - Received of Bids | [34 empty] | 0%
| PRWM4991 | AIR RECEIVER TANK (4708-1/2) - CBE | [34 empty] | 0%
| PRWM4992 | AIR RECEIVER TANK (4708-1/2) - LOI | [34 empty] | 0%
| PRWM4993 | AIR RECEIVER TANK (4708-1/2) - PO |  | 20% | 13685700 | 0.0004% | 2017-07-15: 0.0004% | 0%
| PRWM5000 | AIR RECEIVER TANK (4708-1/2) - Fabrication |  | 60% | 41741385 | 0.00122% | [30 empty] | 0.00122%
| PRWM5010 | AIR RECEIVER TANK (4708-1/2) - Local Delivery |  | 20% | 13685700 | 0.0004% | [30 empty] | 0.0004%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B131 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.5.13.2.4.5.11 Air Receiver Tank (4709-1) | [35 empty] | 0%
| PRWM5019 | AIR RECEIVER TANK (4709-1) - RFQ | [34 empty] | 0%
| PRWM5020 | AIR RECEIVER TANK (4709-1) - Received of Bids | [34 empty] | 0%
| PRWM5021 | AIR RECEIVER TANK (4709-1) - CBE | [34 empty] | 0%
| PRWM5022 | AIR RECEIVER TANK (4709-1) - LOI | [34 empty] | 0%
| PRWM5023 | AIR RECEIVER TANK (4709-1) - PO |  | 20% | 6842850 | 0.0002% | 2017-07-15: 0.0002% | 0%
| PRWM5030 | AIR RECEIVER TANK (4709-1) - Fabrication |  | 60% | 20870692.5 | 0.00061% | [30 empty] | 0.00061%
| PRWM5040 | AIR RECEIVER TANK (4709-1) - Local Delivery |  | 20% | 6842850 | 0.0002% | [30 empty] | 0.0002%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B132 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.5.13.2.4.5.12 Air Dryer for ESF and Instrument Air (4711-1) | [35 empty] | 0%
| PRWM5049 | AIR DRYER FOR ESF AND INSTRUMENT AIR (4711-1) - RFQ | [34 empty] | 0%
| PRWM5050 | AIR DRYER FOR ESF AND INSTRUMENT AIR (4711-1) - Received of Bids | [34 empty] | 0%
| PRWM5051 | AIR DRYER FOR ESF AND INSTRUMENT AIR (4711-1) - CBE | [34 empty] | 0%
| PRWM5052 | AIR DRYER FOR ESF AND INSTRUMENT AIR (4711-1) - LOI | [34 empty] | 0%
| PRWM5053 | AIR DRYER FOR ESF AND INSTRUMENT AIR (4711-1) - PO |  | 20% | 49610662.5 | 0.00145% | 2017-07-15: 0.00145% | 0%
| PRWM5060 | AIR DRYER FOR ESF AND INSTRUMENT AIR (4711-1) - Fabrication |  | 60% | 149516272.5 | 0.00437% | [30 empty] | 0.00437%
| PRWM5070 | AIR DRYER FOR ESF AND INSTRUMENT AIR (4711-1) - Foreign Delivery |  | 20% | 49610662.5 | 0.00145% | [30 empty] | 0.00145%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
| P3FH - 28 M.13.13.2.13.2.4.13.2.4.6 Fuel Oil System | [35 empty] | 0%
B133 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.6.13.2.4.6.1 Feed Pump for MFO Fuel (4302-1) | [35 empty] | 0%
| PRWM5079 | FEED PUMP FOR MFO FUEL (4302-1) - RFQ | [34 empty] | 0%
| PRWM5080 | FEED PUMP FOR MFO FUEL (4302-1) - Received of Bids | [34 empty] | 0%
| PRWM5081 | FEED PUMP FOR MFO FUEL (4302-1) - CBE | [34 empty] | 0%
| PRWM5082 | FEED PUMP FOR MFO FUEL (4302-1) - LOI | [34 empty] | 0%
| PRWM5083 | FEED PUMP FOR MFO FUEL (4302-1) - PO |  | 20% | 38319960 | 0.00112% | 2017-11-12: 0.00112% | 0%
| PRWM5090 | FEED PUMP FOR MFO FUEL (4302-1) - Fabrication |  | 60% | 115302022.5 | 0.00337% | 2018-03-12: 0.00337% | 0%
| PRWM5100 | FEED PUMP FOR MFO FUEL (4302-1) - Foreign Delivery |  | 20% | 38319960 | 0.00112% | 2018-04-11: 0.00112% | 0%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B134 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.6.13.2.4.6.2 Feed Pump for MFO Fuel (4302-2) | [35 empty] | 0%
| PRWM5109 | FEED PUMP FOR MFO FUEL (4302-2) - RFQ | [34 empty] | 0%
| PRWM5110 | FEED PUMP FOR MFO FUEL (4302-2) - Received of Bids | [34 empty] | 0%
| PRWM5111 | FEED PUMP FOR MFO FUEL (4302-2) - CBE | [34 empty] | 0%
| PRWM5112 | FEED PUMP FOR MFO FUEL (4302-2) - LOI | [34 empty] | 0%
| PRWM5113 | FEED PUMP FOR MFO FUEL (4302-2) - PO |  | 20% | 76297777.5 | 0.00223% | 2017-11-12: 0.00223% | 0%
| PRWM5120 | FEED PUMP FOR MFO FUEL (4302-2) - Fabrication |  | 60% | 229235475 | 0.0067% | 2018-03-12: 0.0067% | 0%
| PRWM5130 | FEED PUMP FOR MFO FUEL (4302-2) - Foreign Delivery |  | 20% | 76297777.5 | 0.00223% | 2018-04-11: 0.00223% | 0%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B135 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.6.13.2.4.6.3 Feed Pump for HSD Fuel (4401-1) | [35 empty] | 0%
| PRWM5139 | FEED PUMP FOR HSD FUEL (4401-1) - RFQ | [34 empty] | 0%
| PRWM5140 | FEED PUMP FOR HSD FUEL (4401-1) - Received of Bids | [34 empty] | 0%
| PRWM5141 | FEED PUMP FOR HSD FUEL (4401-1) - CBE | [34 empty] | 0%
| PRWM5142 | FEED PUMP FOR HSD FUEL (4401-1) - LOI | [34 empty] | 0%
| PRWM5143 | FEED PUMP FOR HSD FUEL (4401-1) - PO |  | 20% | 38319960 | 0.00112% | 2017-10-13: 0.00112% | 0%
| PRWM5150 | FEED PUMP FOR HSD FUEL (4401-1) - Fabrication |  | 60% | 115302022.5 | 0.00337% | [30 empty] | 0.00337%
| PRWM5160 | FEED PUMP FOR HSD FUEL (4401-1) - Foreign Delivery |  | 20% | 38319960 | 0.00112% | [30 empty] | 0.00112%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B136 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.6.13.2.4.6.4 Feed Pump for HSD Fuel (4401-2) | [35 empty] | 0%
| PRWM5169 | FEED PUMP FOR HSD FUEL (4401-2) - RFQ | [34 empty] | 0%
| PRWM5170 | FEED PUMP FOR HSD FUEL (4401-2) - Received of Bids | [34 empty] | 0%
| PRWM5171 | FEED PUMP FOR HSD FUEL (4401-2) - CBE | [34 empty] | 0%
| PRWM5172 | FEED PUMP FOR HSD FUEL (4401-2) - LOI | [34 empty] | 0%
| PRWM5173 | FEED PUMP FOR HSD FUEL (4401-2) - PO |  | 20% | 76297777.5 | 0.00223% | 2017-10-13: 0.00222% | 1e-05%
| PRWM5180 | FEED PUMP FOR HSD FUEL (4401-2) - Fabrication |  | 60% | 229235475 | 0.0067% | [30 empty] | 0.0067%
| PRWM5190 | FEED PUMP FOR HSD FUEL (4401-2) - Foreign Delivery |  | 20% | 76297777.5 | 0.00223% | [30 empty] | 0.00223%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
| P3FH - 28 M.13.13.2.13.2.4.13.2.4.7 Sea Water Intake System | [35 empty] | 0%
B138 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.7.13.2.4.7.1 Sea Water Intake Pump (4901-1/2/3) | [35 empty] | 0%
| PRWM5199 | SEA WATER INTAKE PUMP(4901-1/2/3) - RFQ | [34 empty] | 0%
| PRWM5200 | SEA WATER INTAKE PUMP(4901-1/2/3) - Received of Bids | [34 empty] | 0%
| PRWM5201 | SEA WATER INTAKE PUMP(4901-1/2/3) - CBE | [34 empty] | 0%
| PRWM5202 | SEA WATER INTAKE PUMP(4901-1/2/3) - LOI | [34 empty] | 0%
| PRWM5203 | SEA WATER INTAKE PUMP(4901-1/2/3) - PO |  | 20% | 1236160852.5 | 0.03613% | 2017-08-14: 0.03613% | 0%
| PRWM5210 | SEA WATER INTAKE PUMP(4901-1/2/3) - Fabrication |  | 60% | 3708824700 | 0.1084% | [30 empty] | 0.1084%
| PRWM5220 | SEA WATER INTAKE PUMP(4901-1/2/3) - Foreign Delivery |  | 20% | 1236160852.5 | 0.03613% | [30 empty] | 0.03613%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B137 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.7.13.2.4.7.2 Sea Water Intake Pump (4901-4) | [35 empty] | 0%
| PRWM5229 | SEA WATER INTAKE PUMP(4901-4) - RFQ | [34 empty] | 0%
| PRWM5230 | SEA WATER INTAKE PUMP(4901-4) - Received of Bids | [34 empty] | 0%
| PRWM5231 | SEA WATER INTAKE PUMP(4901-4) - CBE | [34 empty] | 0%
| PRWM5232 | SEA WATER INTAKE PUMP(4901-4) - LOI | [34 empty] | 0%
| PRWM5233 | SEA WATER INTAKE PUMP(4901-4) - PO |  | 20% | 576167970 | 0.01684% | 2018-04-11: 0.01684% | 0%
| PRWM5240 | SEA WATER INTAKE PUMP(4901-4) - Fabrication |  | 60% | 1728846052.5 | 0.05053% | 2018-05-11: 0.05052% | 1e-05%
| PRWM5250 | SEA WATER INTAKE PUMP(4901-4) - Foreign Delivery |  | 20% | 576167970 | 0.01684% | [30 empty] | 0.01684%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
| P3FH - 28 M.13.13.2.13.2.4.13.2.4.8 Fire Water System | [35 empty] | 0%
B139 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.8.13.2.4.8.1 Fire Water Tank (4801) | [35 empty] | 0%
| PRWM5259 | FIRE WATER TANK (4801) - RFQ | [34 empty] | 0%
| PRWM5260 | FIRE WATER TANK (4801) - Received of Bids | [34 empty] | 0%
| PRWM5261 | FIRE WATER TANK (4801) - CBE | [34 empty] | 0%
| PRWM5262 | FIRE WATER TANK (4801) - LOI | [34 empty] | 0%
| PRWM5263 | FIRE WATER TANK (4801) - PO |  | 20% | 316481812.5 | 0.00925% | 2017-08-14: 0.00925% | 0%
| PRWM5270 | FIRE WATER TANK (4801) - Fabrication |  | 60% | 948761152.5 | 0.02773% | 2018-03-12: 0.02773% | 0%
| PRWM5280 | FIRE WATER TANK (4801) - Delivery |  | 20% | 316481812.5 | 0.00925% | 2018-03-12: 0.00925% | 0%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | 2018-04-11: 0.00207% | 4e-05%
B140 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.8.13.2.4.8.2 Fire Water Pump (4802-A/B) | [35 empty] | 0%
| PRWM5289 | FIRE WATER PUMP (4802-A/B) - RFQ | [34 empty] | 0%
| PRWM5290 | FIRE WATER PUMP (4802-A/B) - Received of Bids | [34 empty] | 0%
| PRWM5291 | FIRE WATER PUMP (4802-A/B) - CBE | [34 empty] | 0%
| PRWM5292 | FIRE WATER PUMP (4802-A/B) - LOI | [34 empty] | 0%
| PRWM5293 | FIRE WATER PUMP (4802-A/B) - PO |  | 20% | 329483227.5 | 0.00963% | 2017-08-14: 0.00963% | 0%
| PRWM5300 | FIRE WATER PUMP (4802-A/B) - Fabrication |  | 60% | 987765397.5 | 0.02887% | 2018-04-11: 0.02887% | 0%
| PRWM5310 | FIRE WATER PUMP (4802-A/B) - Foreign Delivery |  | 20% | 329483227.5 | 0.00963% | [30 empty] | 0.00963%
F4 |  |  |  | 100% | 72192067.5 | 0.00211% | [30 empty] | 0.00211%
B141 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.8.13.2.4.8.3 Jockey Pump (4803) | [35 empty] | 0%
| PRWM5319 | JOCKEY PUMP(4803) - RFQ | [34 empty] | 0%
| PRWM5320 | JOCKEY PUMP(4803) - Received of Bids | [34 empty] | 0%
| PRWM5321 | JOCKEY PUMP(4803) - CBE | [34 empty] | 0%
| PRWM5322 | JOCKEY PUMP(4803) - LOI | [34 empty] | 0%
| PRWM5323 | JOCKEY PUMP(4803) - PO |  | 20% | 80745630 | 0.00236% | 2017-08-14: 0.00236% | 0%
| PRWM5330 | JOCKEY PUMP(4803) - Fabrication |  | 60% | 242579032.5 | 0.00709% | 2018-04-11: 0.00709% | 0%
| PRWM5340 | JOCKEY PUMP(4803) - Foreign Delivery |  | 20% | 80745630 | 0.00236% | [30 empty] | 0.00236%
F4 |  |  |  | 100% | 0 | 0% | [30 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.4.13.2.4.9 Oxygen Plant | [35 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.4.13.2.4.9.13.2.4.9.1 Nitrogen Buffer Vessel | [35 empty] | 0%
| PRWM5349 | NITROGEN BUFFER VESSEL - RFQ | [34 empty] | 0%
| PRWM5350 | NITROGEN BUFFER VESSEL - Received of Bids | [34 empty] | 0%
| PRWM5351 | NITROGEN BUFFER VESSEL - CBE | [34 empty] | 0%
| PRWM5352 | NITROGEN BUFFER VESSEL - LOI | [34 empty] | 0%
| PRWM5353 | NITROGEN BUFFER VESSEL - PO | [34 empty] | 0%
| PRWM5360 | NITROGEN BUFFER VESSEL - Fabrication | [34 empty] | 0%
| PRWM5370 | NITROGEN BUFFER VESSEL - Foreign Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.4.13.2.4.9.13.2.4.9.2 Oxygen Buffer Vessel | [35 empty] | 0%
| PRWM6229 | OXYGEN BUFFER VESSEL - RFQ | [34 empty] | 0%
| PRWM6230 | OXYGEN BUFFER VESSEL - Received of Bids | [34 empty] | 0%
| PRWM6240 | OXYGEN BUFFER VESSEL - CBE | [34 empty] | 0%
| PRWM6250 | OXYGEN BUFFER VESSEL - LOI | [34 empty] | 0%
| PRWM6260 | OXYGEN BUFFER VESSEL - PO | [34 empty] | 0%
| PRWM6270 | OXYGEN BUFFER VESSEL - Fabrication | [34 empty] | 0%
| PRWM6280 | OXYGEN BUFFER VESSEL - Foreign Delivery | [34 empty] | 0%
B142 | P3FH - 28 M.13.13.2.13.2.4.13.2.4.9.13.2.4.9.3 Oxygent Plant | [35 empty] | 0%
| PRWM5409 | COMPRESSOR - RFQ | [34 empty] | 0%
| PRWM5410 | COMPRESSOR - Received of Bids | [34 empty] | 0%
| PRWM5411 | COMPRESSOR - CBE | [34 empty] | 0%
| PRWM5412 | COMPRESSOR - LOI | [34 empty] | 0%
| PRWM5413 | COMPRESSOR - PO |  | 25% | 10681688850 | 0.3122% | 2017-08-14: 0.3122%; 2018-01-11: -0.06243% | 0.06243%
| PRWM5420 | COMPRESSOR - Fabrication |  | 60% | 25635711097.5 | 0.7493% | [30 empty] | 0.7493%
| PRWM5430 | COMPRESSOR - Foreign Delivery |  | 15% | 6409013310 | 0.1873% | [30 empty] | 0.1873%
F4 |  |  |  | 100% | 139936282.5 | 0.00409% | [30 empty] | 0.00409%
| P3FH - 28 M.13.13.2.13.2.4.13.2.4.9.13.2.4.9.4 Nitrogen Compressor | [35 empty] | 0%
| PRWM5439 | NITROGEN COMPRESSOR - RFQ | [34 empty] | 0%
| PRWM5440 | NITROGEN COMPRESSOR - Received of Bids | [34 empty] | 0%
| PRWM5441 | NITROGEN COMPRESSOR - CBE | [34 empty] | 0%
| PRWM5442 | NITROGEN COMPRESSOR - LOI | [34 empty] | 0%
| PRWM5443 | NITROGEN COMPRESSOR - PO | [34 empty] | 0%
| PRWM5450 | NITROGEN COMPRESSOR - Fabrication | [34 empty] | 0%
| PRWM5460 | NITROGEN COMPRESSOR - Foreign Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.4.13.2.4.9.13.2.4.9.5 Oxygen Compressor | [35 empty] | 0%
| PRWM5469 | OXYGEN COMPRESSOR - RFQ | [34 empty] | 0%
| PRWM5470 | OXYGEN COMPRESSOR - Received of Bids | [34 empty] | 0%
| PRWM5471 | OXYGEN COMPRESSOR - CBE | [34 empty] | 0%
| PRWM5472 | OXYGEN COMPRESSOR - LOI | [34 empty] | 0%
| PRWM5473 | OXYGEN COMPRESSOR - PO | [34 empty] | 0%
| PRWM5480 | OXYGEN COMPRESSOR - Fabrication | [34 empty] | 0%
| PRWM5490 | OXYGEN COMPRESSOR - Foreign Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.4.13.2.4.9.13.2.4.9.6 Turbine | [35 empty] | 0%
| PRWM5449 | TURBINE - RFQ | [34 empty] | 0%
| PRWM5500 | TURBINE - Received of Bids | [34 empty] | 0%
| PRWM5501 | TURBINE - CBE | [34 empty] | 0%
| PRWM5502 | TURBINE - LOI | [34 empty] | 0%
| PRWM5503 | TURBINE - PO | [34 empty] | 0%
| PRWM5510 | TURBINE - Fabrication | [34 empty] | 0%
| PRWM5520 | TURBINE - Foreign Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.4.13.2.4.9.13.2.4.9.7 Heat Exchanger | [35 empty] | 0%
| PRWM5529 | HEAT EXCHANGER - RFQ | [34 empty] | 0%
| PRWM5530 | HEAT EXCHANGER - Received of Bids | [34 empty] | 0%
| PRWM5531 | HEAT EXCHANGER - CBE | [34 empty] | 0%
| PRWM5532 | HEAT EXCHANGER - LOI | [34 empty] | 0%
| PRWM5533 | HEAT EXCHANGER - PO | [34 empty] | 0%
| PRWM5540 | HEAT EXCHANGER - Fabrication | [34 empty] | 0%
| PRWM5550 | HEAT EXCHANGER - Foreign Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.4.13.2.4.9.13.2.4.9.8 Precooling Unit | [35 empty] | 0%
| PRWM5559 | PRECOOLING UNIT - RFQ | [34 empty] | 0%
| PRWM5560 | PRECOOLING UNIT - Received of Bids | [34 empty] | 0%
| PRWM5561 | PRECOOLING UNIT - CBE | [34 empty] | 0%
| PRWM5562 | PRECOOLING UNIT - LOI | [34 empty] | 0%
| PRWM5563 | PRECOOLING UNIT - PO | [34 empty] | 0%
| PRWM5570 | PRECOOLING UNIT - Fabrication | [34 empty] | 0%
| PRWM5580 | PRECOOLING UNIT - Foreign Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.4.13.2.4.9.13.2.4.9.9 Purification Unit Vessel | [35 empty] | 0%
| PRWM5589 | PURIFICATION UNIT VESSEL - RFQ | [34 empty] | 0%
| PRWM5590 | PURIFICATION UNIT VESSEL - Received of Bids | [34 empty] | 0%
| PRWM5591 | PURIFICATION UNIT VESSEL - CBE | [34 empty] | 0%
| PRWM5592 | PURIFICATION UNIT VESSEL - LOI | [34 empty] | 0%
| PRWM5593 | PURIFICATION UNIT VESSEL - PO | [34 empty] | 0%
| PRWM5600 | PURIFICATION UNIT VESSEL - Fabrication | [34 empty] | 0%
| PRWM5610 | PURIFICATION UNIT VESSEL - Foreign Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.4.13.2.4.9.13.2.4.9.10 Air Filter | [35 empty] | 0%
| PRWM5619 | AIR FILTER - RFQ | [34 empty] | 0%
| PRWM5620 | AIR FILTER - Received of Bids | [34 empty] | 0%
| PRWM5621 | AIR FILTER - CBE | [34 empty] | 0%
| PRWM5622 | AIR FILTER - LOI | [34 empty] | 0%
| PRWM5623 | AIR FILTER - PO | [34 empty] | 0%
| PRWM5630 | AIR FILTER - Fabrication | [34 empty] | 0%
| PRWM5640 | AIR FILTER - Foreign Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.4.13.2.4.9.13.2.4.9.11 Electric Heater | [35 empty] | 0%
| PRWM5649 | ELECTRIC HEATER - RFQ | [34 empty] | 0%
| PRWM5650 | ELECTRIC HEATER - Received of Bids | [34 empty] | 0%
| PRWM5651 | ELECTRIC HEATER - CBE | [34 empty] | 0%
| PRWM5652 | ELECTRIC HEATER - LOI | [34 empty] | 0%
| PRWM5653 | ELECTRIC HEATER - PO | [34 empty] | 0%
| PRWM5660 | ELECTRIC HEATER - Fabrication | [34 empty] | 0%
| PRWM5670 | ELECTRIC HEATER - Foreign Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.4.13.2.4.9.13.2.4.9.12 Moisture Separator | [35 empty] | 0%
| PRWM5679 | MOISTURE SEPERATOR - RFQ | [34 empty] | 0%
| PRWM5680 | MOISTURE SEPERATOR - Received of Bids | [34 empty] | 0%
| PRWM5681 | MOISTURE SEPERATOR - CBE | [34 empty] | 0%
| PRWM5682 | MOISTURE SEPERATOR - LOI | [34 empty] | 0%
| PRWM5683 | MOISTURE SEPERATOR - PO | [34 empty] | 0%
| PRWM5690 | MOISTURE SEPERATOR - Fabrication | [34 empty] | 0%
| PRWM5700 | MOISTURE SEPERATOR - Foreign Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.4.13.2.4.9.13.2.4.9.13 Cold Box | [35 empty] | 0%
| PRWM5709 | COLD BOX - RFQ | [34 empty] | 0%
| PRWM5710 | COLD BOX - Received of Bids | [34 empty] | 0%
| PRWM5711 | COLD BOX - CBE | [34 empty] | 0%
| PRWM5712 | COLD BOX - LOI | [34 empty] | 0%
| PRWM5713 | COLD BOX - PO | [34 empty] | 0%
| PRWM5720 | COLD BOX - Fabrication | [34 empty] | 0%
| PRWM5730 | COLD BOX - Foreign Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.4.13.2.4.9.13.2.4.9.14 Pump | [35 empty] | 0%
| PRWM5739 | PUMP - RFQ | [34 empty] | 0%
| PRWM5740 | PUMP - Received of Bids | [34 empty] | 0%
| PRWM5741 | PUMP - CBE | [34 empty] | 0%
| PRWM5742 | PUMP - LOI | [34 empty] | 0%
| PRWM5743 | PUMP - PO | [34 empty] | 0%
| PRWM5750 | PUMP - Fabrication | [34 empty] | 0%
| PRWM5760 | PUMP - Foreign Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.13.2.4.1 Emergency Diesel Generator (EDG) | [35 empty] | 0%
| PRWE2721 | EMERGENCY DIESEL GENERATOR (EDG) - RFQ | [34 empty] | 0%
| PRWE2722 | EMERGENCY DIESEL GENERATOR (EDG) - Received of Bids | [34 empty] | 0%
| PRWE2723 | EMERGENCY DIESEL GENERATOR (EDG) - CBE | [34 empty] | 0%
| PRWE2724 | EMERGENCY DIESEL GENERATOR (EDG) - LOI | [34 empty] | 0%
| PRWE2730 | EMERGENCY DIESEL GENERATOR (EDG) - PO | [34 empty] | 0%
| PRWE2740 | EMERGENCY DIESEL GENERATOR (EDG) - Fabrication | [34 empty] | 0%
| PRWE2750 | EMERGENCY DIESEL GENERATOR (EDG) - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.2.1 Non Process Building | [35 empty] | 0%
| PRWM-NONPROS-1240 | AC, VENTILATION FAN, SUPPLY FAN - RFQ | [34 empty] | 0%
| PRWM-NONPROS-1250 | AC, VENTILATION FAN, SUPPLY FAN - Received of Bids | [34 empty] | 0%
| PRWM-NONPROS-1260 | AC, VENTILATION FAN, SUPPLY FAN - TBE & CBE | [34 empty] | 0%
| PRWM-NONPROS-1270 | AC, VENTILATION FAN, SUPPLY FAN - PO | [34 empty] | 0%
| PRWM-NONPROS-1280 | AC, VENTILATION FAN, SUPPLY FAN - Purchase & Packaging | [34 empty] | 0%
| PRWM-NONPROS-1290 | AC, VENTILATION FAN, SUPPLY FAN - Delivery to Site | [34 empty] | 0%
0%
| P3FH - 28 M. Piping |  |  |  | 54064673565 | 1.58% | 0% | 0% | 0% | 0% | 0% | 0.02646% | 0% | 0.1187% | 0% | 0% | 0% | 0% | 0.03047% | 0% | 0.03085% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.374%
F4 |  | Sistem 1 |  |  | 592590810 | 0.01732% | [30 empty] | 0.01732%
| P3FH - 28 M.13.13.3.13.3.1 System 2 - Electric Smelting Furnace | [35 empty] | 0%
B240 | P3FH - 28 M.13.13.3.13.3.1.13.3.1.1 Copper Cooler Water Piping (2245) | [35 empty] | 0%
| PRWM5770 | Procurement Cycle |  | 20% | 4825919962.5 | 0.1411% | [30 empty] | 0.1411%
| PRWM5780 | Fabrication |  | 60% | 14478102030 | 0.4232% | [30 empty] | 0.4232%
| PRWM5790 | Delivery |  | 15% | 4826262105 | 0.1411% | [30 empty] | 0.1411%
F4 |  |  |  | 100% | 979211835 | 0.02862% | [30 empty] | 0.02862%
B243 | P3FH - 28 M.13.13.3.13.3.2 System 3 - Refinery (Pipe & Support) | [35 empty] | 0%
| PRWM5800 | SYSTEM 3 - (PIPE & SUPPORT Incl. Acc) - Fabrication by SIKO |  | 80% | 607645080 | 0.01776% | [30 empty] | 0.01776%
| PRWM5810 | SYSTEM 3 - (PIPE & SUPPORT Incl. Acc) - Packing | [34 empty] | 0%
| PRWM5820 | SYSTEM 3 - (PIPE & SUPPORT Incl. Acc) - Delivery |  | 15% | 151911270 | 0.00444% | [30 empty] | 0.00444%
F4 |  |  |  | 100% | 35924962.5 | 0.00105% | [30 empty] | 0.00105%
| P3FH - 28 M.13.13.3.13.3.3 System 4 - Utility Supply | [35 empty] | 0%
| P3FH - 28 M.13.13.3.13.3.3.13.3.3.1 Raw Water Intake System | [35 empty] | 0%
B249 | P3FH - 28 M.13.13.3.13.3.3.13.3.3.1.13.3.3.1.1 Pipe, Support (4107) include Acc. & painting | [35 empty] | 0%
| PRWM5830 | PIPE&SUPPORT(4107) - Received of Bids | [34 empty] | 0%
| PRWM5831 | PIPE&SUPPORT(4107) - CBE | [34 empty] | 0%
| PRWM5832 | PIPE&SUPPORT(4107) - LOI | [34 empty] | 0%
| PRWM5833 | PIPE&SUPPORT(4107) - PO |  | 20% | 905651197.5 | 0.02647% | 2017-07-15: 0.0002646 | 1e-05%
| PRWM5840 | PIPE&SUPPORT(4107) - Fabrication |  | 60% | 2716953592.5 | 0.07941% | 2018-02-10: 0.00556%; 2018-04-11: 0.00562% | 0.06823%
| PRWM5850 | PIPE&SUPPORT(4107) - Delivery |  | 15% | 905651197.5 | 0.02647% | [30 empty] | 0.02647%
F4 |  |  |  | 100% | 455733810 | 0.01332% | [30 empty] | 0.01332%
B251 | P3FH - 28 M.13.13.3.13.3.3.13.3.3.1.13.3.3.1.2 Piping (4108) include Acc. & painting | [35 empty] | 0%
| PRWM5860 | PIPING(4108) - Received of Bids | [34 empty] | 0%
| PRWM5861 | PIPING(4108) - CBE | [34 empty] | 0%
| PRWM5862 | PIPING(4108) - LOI | [34 empty] | 0%
| PRWM5863 | PIPING(4108) - PO |  | 20% | 181335525 | 0.0053% | 2017-09-13: 0.0053% | 0%
| PRWM5870 | PIPING(4108) - Fabrication |  | 60% | 543664432.5 | 0.01589% | 2018-02-10: 0.00111%; 2018-04-11: 0.00113% | 0.01365%
| PRWM5880 | PIPING(4108) - Delivery |  | 15% | 181335525 | 0.0053% | [30 empty] | 0.0053%
F4 |  |  |  | 100% | 455733810 | 0.01332% | [30 empty] | 0.01332%
B252 | P3FH - 28 M.13.13.3.13.3.3.13.3.3.1.13.3.3.1.3 Piping (4119) include Acc. & painting | [35 empty] | 0%
| PRWM5890 | PIPING(4119) - Received of Bids | [34 empty] | 0%
| PRWM5891 | PIPING(4119) - CBE | [34 empty] | 0%
| PRWM5892 | PIPING(4119) - LOI | [34 empty] | 0%
| PRWM5893 | PIPING(4119) - PO |  | 20% | 238473322.5 | 0.00697% | 2017-09-13: 0.00697% | 0%
| PRWM5900 | PIPING(4119) - Fabrication |  | 60% | 715762110 | 0.02092% | 2018-02-10: 0.00147%; 2018-04-11: 0.00148% | 0.01797%
| PRWM5910 | PIPING(4119) - Delivery |  | 15% | 238473322.5 | 0.00697% | [30 empty] | 0.00697%
F4 |  |  |  | 100% | 455733810 | 0.01332% | [30 empty] | 0.01332%
| P3FH - 28 M.13.13.3.13.3.3.13.3.3.2 Circulation Water NSW | [35 empty] | 0%
| P3FH - 28 M.13.13.3.13.3.3.13.3.3.2.13.3.3.2.1 Piping & Support NSW (4209) | [35 empty] | 0%
| PRWM5920 | PIPING & SUPPORT NSW(4209) - Received of Bids | [34 empty] | 0%
| PRWM5921 | PIPING & SUPPORT NSW(4209) - CBE | [34 empty] | 0%
| PRWM5922 | PIPING & SUPPORT NSW(4209) - LOI | [34 empty] | 0%
| PRWM5923 | PIPING & SUPPORT NSW(4209) - PO | [34 empty] | 0%
| PRWM5930 | PIPING & SUPPORT NSW(4209) - Fabrication | [34 empty] | 0%
| PRWM5940 | PIPING & SUPPORT NSW(4209) - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.3.13.3.3.13.3.3.3 Circulation Water SW | [35 empty] | 0%
| P3FH - 28 M.13.13.3.13.3.3.13.3.3.3.13.3.3.3.1 Piping & Support SW (4219) | [35 empty] | 0%
| PRWM5950 | PIPING & SUPPORT SW(4219) - Received of Bids | [34 empty] | 0%
| PRWM5951 | PIPING & SUPPORT SW(4219) - CBE | [34 empty] | 0%
| PRWM5952 | PIPING & SUPPORT SW(4219) - LOI | [34 empty] | 0%
| PRWM5953 | PIPING & SUPPORT SW(4219) - PO | [34 empty] | 0%
| PRWM5960 | PIPING & SUPPORT SW(4219) - Fabrication | [34 empty] | 0%
| PRWM5970 | PIPING & SUPPORT SW(4219) - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.3.13.3.3.13.3.3.4 Circulation Water SW (Copper Cooler) | [35 empty] | 0%
| P3FH - 28 M.13.13.3.13.3.3.13.3.3.4.13.3.3.4.1 Piping & Support SW Copper Cooler (4229) | [35 empty] | 0%
| PRWM5980 | PIPING & SUPPORT SW COPPER COOLER (4229) - Received of Bids | [34 empty] | 0%
| PRWM5981 | PIPING & SUPPORT SW COPPER COOLER (4229) - CBE | [34 empty] | 0%
| PRWM5982 | PIPING & SUPPORT SW COPPER COOLER (4229) - LOI | [34 empty] | 0%
| PRWM5983 | PIPING & SUPPORT SW COPPER COOLER (4229) - PO | [34 empty] | 0%
| PRWM5990 | PIPING & SUPPORT SW COPPER COOLER (4229) - Fabrication | [34 empty] | 0%
| PRWM6000 | PIPING & SUPPORT SW COPPER COOLER (4229) - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.3.13.3.3.13.3.3.5 Compressed Air and Distribution System | [35 empty] | 0%
B248 | P3FH - 28 M.13.13.3.13.3.3.13.3.3.5.13.3.3.5.1 Piping & Support Compressed Air (4719) | [35 empty] | 0%
| PRWM6010 | PIPING & SUPPORT COMPRESSED AIR (4719) - Received of Bids | [34 empty] | 0%
| PRWM6011 | PIPING & SUPPORT COMPRESSED AIR (4719) - CBE | [34 empty] | 0%
| PRWM6012 | PIPING & SUPPORT COMPRESSED AIR (4719) - LOI | [34 empty] | 0%
| PRWM6013 | PIPING & SUPPORT COMPRESSED AIR (4719) - PO |  | 20% | 189204802.5 | 0.00553% | 2017-09-13: 0.00553% | 0%
| PRWM6020 | PIPING & SUPPORT COMPRESSED AIR (4719) - Fabrication |  | 60% | 567272265 | 0.01658% | 2018-02-10: 0.00116%; 2018-04-11: 0.00118% | 0.01424%
| PRWM6030 | PIPING & SUPPORT COMPRESSED AIR (4719) - Delivery |  | 15% | 188862660 | 0.00552% | [30 empty] | 0.00552%
F4 |  |  |  | 100% | 455733810 | 0.01332% | [30 empty] | 0.01332%
| P3FH - 28 M.13.13.3.13.3.3.13.3.3.6 Fuel Oil System | [35 empty] | 0%
B247 | P3FH - 28 M.13.13.3.13.3.3.13.3.3.6.13.3.3.6.1 Piping & Support for MFO Fuel (4319) | [35 empty] | 0%
| PRWM6040 | PIPING & SUPPORT FOR MFO FUEL(4319) - Received of Bids | [34 empty] | 0%
| PRWM6041 | PIPING & SUPPORT FOR MFO FUEL(4319) - CBE | [34 empty] | 0%
| PRWM6042 | PIPING & SUPPORT FOR MFO FUEL(4319) - LOI | [34 empty] | 0%
| PRWM6043 | PIPING & SUPPORT FOR MFO FUEL(4319) - PO |  | 20% | 314771100 | 0.0092% | 2017-09-13: 0.00919% | 1e-05%
| PRWM6050 | PIPING & SUPPORT FOR MFO FUEL(4319) - Fabrication |  | 60% | 943971157.5 | 0.02759% | 2018-02-10: 0.00193%; 2018-04-11: 0.00196% | 0.0237%
| PRWM6060 | PIPING & SUPPORT FOR MFO FUEL(4319) - Delivery |  | 15% | 314771100 | 0.0092% | [30 empty] | 0.0092%
F4 |  |  |  | 100% | 455733810 | 0.01332% | [30 empty] | 0.01332%
| P3FH - 28 M.13.13.3.13.3.3.13.3.3.6.13.3.3.6.2 Piping & Support for HSD Fuel (4419) | [35 empty] | 0%
| PRWM6070 | PIPING & SUPPORT FOR HSD FUEL(4419) - Received of Bids | [34 empty] | 0%
| PRWM6071 | PIPING & SUPPORT FOR HSD FUEL(4419) - CBE | [34 empty] | 0%
| PRWM6072 | PIPING & SUPPORT FOR HSD FUEL(4419) - LOI | [34 empty] | 0%
| PRWM6073 | PIPING & SUPPORT FOR HSD FUEL(4419) - PO | [34 empty] | 0%
| PRWM6080 | PIPING & SUPPORT FOR HSD FUEL(4419) - Fabrication | [34 empty] | 0%
| PRWM6090 | PIPING & SUPPORT FOR HSD FUEL(4419) - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.3.13.3.3.13.3.3.7 Sea Water Intake System | [35 empty] | 0%
B250 | P3FH - 28 M.13.13.3.13.3.3.13.3.3.7.13.3.3.7.1 Piping & Support for Sea Water Intake (4909) | [35 empty] | 0%
| PRWM6100 | PIPING & SUPPORT FOR SEA WATER INTAKE (4909) - Received of Bids | [34 empty] | 0%
| PRWM6101 | PIPING & SUPPORT FOR SEA WATER INTAKE (4909) - CBE | [34 empty] | 0%
| PRWM6102 | PIPING & SUPPORT FOR SEA WATER INTAKE (4909) - LOI | [34 empty] | 0%
| PRWM6103 | PIPING & SUPPORT FOR SEA WATER INTAKE (4909) - PO |  | 20% | 3137446725 | 0.0917% | 2017-09-13: 0.09169% | 1e-05%
| PRWM6110 | PIPING & SUPPORT FOR SEA WATER INTAKE (4909) - Fabrication |  | 60% | 9411998032.5 | 0.2751% | 2018-02-10: 0.01924%; 2018-04-11: 0.01948% | 0.2364%
| PRWM6120 | PIPING & SUPPORT FOR SEA WATER INTAKE (4909) - Delivery |  | 15% | 3137104582.5 | 0.09169% | [30 empty] | 0.09169%
F4 |  |  |  | 100% | 455733810 | 0.01332% | [30 empty] | 0.01332%
| P3FH - 28 M.13.13.3.13.3.3.13.3.3.8 Steam Supply System | [35 empty] | 0%
| P3FH - 28 M.13.13.3.13.3.3.13.3.3.8.13.3.3.8.1 Pipe & Support for Steam | [35 empty] | 0%
| PRWM6130 | PIPE & SUPPORT FOR STEAM - Received of Bids | [34 empty] | 0%
| PRWM6131 | PIPE & SUPPORT FOR STEAM - CBE | [34 empty] | 0%
| PRWM6132 | PIPE & SUPPORT FOR STEAM - LOI | [34 empty] | 0%
| PRWM6133 | PIPE & SUPPORT FOR STEAM - PO | [34 empty] | 0%
| PRWM6140 | PIPE & SUPPORT FOR STEAM - Fabrication | [34 empty] | 0%
| PRWM6150 | PIPE & SUPPORT FOR STEAM - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.3.13.3.3.13.3.3.9 O2 & N2 | [35 empty] | 0%
| P3FH - 28 M.13.13.3.13.3.3.13.3.3.9.13.3.3.9.1 Pipe & Support for O2 | [35 empty] | 0%
| PRWM6160 | PIPE & SUPPORT FOR 02 - Received of Bids | [34 empty] | 0%
| PRWM6161 | PIPE & SUPPORT FOR 02 - CBE | [34 empty] | 0%
| PRWM6162 | PIPE & SUPPORT FOR 02 - LOI | [34 empty] | 0%
| PRWM6163 | PIPE & SUPPORT FOR 02 - PO | [34 empty] | 0%
| PRWM6170 | PIPE & SUPPORT FOR 02 - Fabrication | [34 empty] | 0%
| PRWM6180 | PIPE & SUPPORT FOR 02 - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.3.13.3.3.13.3.3.9.13.3.3.9.2 Pipe & Support for N2 | [35 empty] | 0%
| PRWM6190 | PIPE & SUPPORT FOR N2 - Received of Bids | [34 empty] | 0%
| PRWM6191 | PIPE & SUPPORT FOR N2 - CBE | [34 empty] | 0%
| PRWM6192 | PIPE & SUPPORT FOR N2 - LOI | [34 empty] | 0%
| PRWM6193 | PIPE & SUPPORT FOR N2 - PO | [34 empty] | 0%
| PRWM6200 | PIPE & SUPPORT FOR N2 - Fabrication | [34 empty] | 0%
| PRWM6210 | PIPE & SUPPORT FOR N2 - Delivery | [34 empty] | 0%
0%
| P3FH - 28 M. Electrical |  |  |  | 245323357492.4998 | 7.17% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1258% | 0% | 0% | 0.07264% | 4.099% | 0.5697% | 0.316% | 0.061% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.926%
| P3FH - 28 M.13.13.4.13.4.1 System 1 - Ore Preparation | [35 empty] | 0%
| P3FH - 28 M.13.13.4.13.4.1.13.4.1.1 Supply by KHI | [35 empty] | 0%
| P3FH - 28 M.13.13.4.13.4.1.13.4.1.1.13.4.1.1.2 Switchgear | [35 empty] | 0%
| PRKE1030 | SWITCHGEAR - Procurement Cycle | [34 empty] | 0%
| PRKE1040 | Fabrication | [34 empty] | 0%
| PRKE1050 | Delivery | [34 empty] | 0%
B146 | P3FH - 28 M.13.13.4.13.4.1.13.4.1.1.13.4.1.1.1 Construction Material (Cable, Rack, steel material and so on) | [35 empty] | 0%
| PRKE1000 | CONSTRUCTION MATERIAL (CABLE,RACK,STEEL MAT. Etc ) - Procurement Cycle |  | 25% | 44780978970 | 1.309% | 2017-10-13: 0.00626%; 2018-01-11: 0.01297%; 2018-02-10: 1.29% | 0%
| PRKE1010 | Fabrication |  | 60% | 107474144242.5 | 3.141% | 2018-02-10: 2.786%; 2018-03-12: 0.3547% | 0%
| PRKE1020 | Delivery 1st Priority (All Electric & Control Room, Main Substation, & Main Cable Route) | [34 empty] | 0%
| PRKE1180 | Delivery 2nd Priority (Cable Building) | [34 empty] | 0%
| PRKE1190 | Delivery 3rd Priority (Grounding, Lighting Building) |  | 15% | 26868450525 | 0.7853% | 2018-03-12: 0.07788%; 2018-04-11: 0.2757% | 0.4317%
F4 |  |  |  | 100% | 207338355 | 0.00606% | [30 empty] | 0.00606%
| P3FH - 28 M.13.13.4.13.4.1.13.4.1.1.13.4.1.1.3 Transformer | [35 empty] | 0%
| PRKE1060 | TRANSFORMER - Procurement Cycle | [34 empty] | 0%
| PRKE1070 | Fabrication | [34 empty] | 0%
| PRKE1080 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.4.13.4.1.13.4.1.1.13.4.1.1.31 Neutral Grounding Resistor | [35 empty] | 0%
| PRKE1200 | NEUTRAL GROUNDING RESISTOR - Procurement Cycle | [34 empty] | 0%
| PRKE1210 | NEUTRAL GROUNDING RESISTOR - Fabrication | [34 empty] | 0%
| PRKE1220 | NEUTRAL GROUNDING RESISTOR - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.4.13.4.1.13.4.1.1.13.4.1.1.311 DC Battery & Charger | [35 empty] | 0%
| PRKE1230 | DC BATTERY & CHARGER - Procurement Cycle | [34 empty] | 0%
| PRKE1240 | DC BATTERY & CHARGER - Fabrication | [34 empty] | 0%
| PRKE1250 | DC BATTERY & CHARGER - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.4.13.4.1.13.4.1.1.13.4.1.1.4 Panel | [35 empty] | 0%
| PRKE1090 | PANEL - Procurement Cycle | [34 empty] | 0%
| PRKE1100 | PANEL - Fabrication | [34 empty] | 0%
| PRKE1110 | PANEL - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.4.13.4.1.13.4.1.1.13.4.1.1.5 Motor | [35 empty] | 0%
| PRKE1120 | MOTOR - Procurement Cycle | [34 empty] | 0%
| PRKE1130 | MOTOR - Fabrication | [34 empty] | 0%
| PRKE1140 | MOTOR - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.4.13.4.1.13.4.1.1.13.4.1.1.6 MV VVVF Motor and Drive | [35 empty] | 0%
| PRKE1150 | MV VVVF MOTOR & DRIVE - Procurement Cycle | [34 empty] | 0%
| PRKE1160 | MV VVVF MOTOR & DRIVE - Fabrication | [34 empty] | 0%
| PRKE1170 | MV VVVF MOTOR & DRIVE - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.4.13.4.1.13.4.1.1.13.4.1.2.4 Lighting and Small Power Panel | [35 empty] | 0%
| PRWE1090 | LIGHTING AND SMALL POWER PANEL - Procurement Cycle | [34 empty] | 0%
| PRWE1100 | LIGHTING AND SMALL POWER PANEL - Fabrication | [34 empty] | 0%
| PRWE1110 | LIGHTING AND SMALL POWER PANEL - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.4.13.4.1.1 Supply by WIKA | [35 empty] | 0%
| P3FH - 28 M.13.13.4.13.4.1.1.13.4.1.2.9 Grounding & lightning Protection for Building | [35 empty] | 0%
| PRWE1240 | GROUNDING & LIGHTING PROTECTION - Procurement Cycle | [34 empty] | 0%
| PRWE1250 | GROUNDING & LIGHTING PROTECTION - Fabrication | [34 empty] | 0%
| PRWE1260 | GROUNDING & LIGHTING PROTECTION - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.4.13.4.1.1.13.4.1.2.5 Indoor and Outdoor Lighting | [35 empty] | 0%
| PRWE1120 | INOOR & OUTDOOR LIGHTING - Procurement Cycle | [34 empty] | 0%
| PRWE1130 | INOOR & OUTDOOR LIGHTING - Fabrication | [34 empty] | 0%
| PRWE1140 | INOOR & OUTDOOR LIGHTING - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.4.13.4.1.1.13.4.1.2.8 Bulk Material | [35 empty] | 0%
| PRWE1210 | BULK MATERIAL - Procurement Cycle | [34 empty] | 0%
| PRWE1220 | BULK MATERIAL - Fabrication | [34 empty] | 0%
| PRWE1230 | BULK MATERIAL - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.4.13.4.2 System 2 - Electric Smelting Furnace | [35 empty] | 0%
| P3FH - 28 M.13.13.4.13.4.2.13.4.2.1 MV Switchgear for Furnace | [35 empty] | 0%
| PRWE1261 | MV SWITCHGEAR FOR FURNACE - RFQ | [34 empty] | 0%
| PRWE1262 | MV SWITCHGEAR FOR FURNACE - Received Bids | [34 empty] | 0%
| PRWE1263 | MV SWITCHGEAR FOR FURNACE - CBE | [34 empty] | 0%
| PRWE1264 | MV SWITCHGEAR FOR FURNACE - LOI | [34 empty] | 0%
| PRWE1265 | MV SWITCHGEAR FOR FURNACE - PO | [34 empty] | 0%
| PRWE1280 | MV SWITCHGEAR FOR FURNACE - Fabrication | [34 empty] | 0%
| PRWE1290 | MV SWITCHGEAR FOR FURNACE - Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.4.13.4.2.13.4.2.2 Furnace Transformer (2145) | [35 empty] | 0%
| PRWE1291 | FURNACE TRANSFORMER (2145) - RFQ | [34 empty] | 0%
| PRWE1292 | FURNACE TRANSFORMER (2145) - Received Bids | [34 empty] | 0%
| PRWE1293 | FURNACE TRANSFORMER (2145) - CBE | [34 empty] | 0%
| PRWE1294 | FURNACE TRANSFORMER (2145) - LOI | [34 empty] | 0%
| PRWE1295 | FURNACE TRANSFORMER (2145) - PO | [34 empty] | 0%
| PRWE1310 | FURNACE TRANSFORMER (2145) - Fabrication | [34 empty] | 0%
| PRWE1320 | FURNACE TRANSFORMER (2145) - Delivery | [34 empty] | 0%
B149 | P3FH - 28 M.13.13.4.13.4.2.13.4.2.3 MV Switchgear 6.6 kV | [35 empty] | 0%
| PRWE1321 | MV SWITCHGEAR 6.6 KV - RFQ | [34 empty] | 0%
| PRWE1322 | MV SWITCHGEAR 6.6 KV - Received Bids | [34 empty] | 0%
| PRWE1323 | MV SWITCHGEAR 6.6 KV - CBE | [34 empty] | 0%
| PRWE1324 | MV SWITCHGEAR 6.6 KV - LOI | [34 empty] | 0%
| PRWE1325 | MV SWITCHGEAR 6.6 KV - PO |  | 25% | 662045737.5 | 0.01935% | 2017-10-13: 0.01548% | 0.00387%
| PRWE1340 | MV SWITCHGEAR 6.6 KV - Fabrication |  | 60% | 1589251912.5 | 0.04645% | [30 empty] | 0.04645%
| PRWE1350 | MV SWITCHGEAR 6.6 KV - Delivery |  | 15% | 397227442.5 | 0.01161% | [30 empty] | 0.01161%
F4 |  |  |  | 100% | 23265690 | 0.00068% | [30 empty] | 0.00068%
B150 | P3FH - 28 M.13.13.4.13.4.2.13.4.2.4 Power Transformer 6.6 / 0.4 kV | [35 empty] | 0%
| PRWE1351 | POWER TRANSFORMER 6.6/0.4 KV - RFQ | [34 empty] | 0%
| PRWE1352 | POWER TRANSFORMER 6.6/0.4 KV - Received Bids | [34 empty] | 0%
| PRWE1353 | POWER TRANSFORMER 6.6/0.4 KV - CBE | [34 empty] | 0%
| PRWE1354 | POWER TRANSFORMER 6.6/0.4 KV - LOI | [34 empty] | 0%
| PRWE1355 | POWER TRANSFORMER 6.6/0.4 KV - PO |  | 25% | 83824912.5 | 0.00245% | 2017-10-13: 0.00196% | 0.00049%
| PRWE1370 | POWER TRANSFORMER 6.6/0.4 KV - Fabrication |  | 60% | 200837647.5 | 0.00587% | 2018-03-12: 0.00587% | 0%
| PRWE1380 | POWER TRANSFORMER 6.6/0.4 KV - Delivery |  | 15% | 50294947.5 | 0.00147% | [30 empty] | 0.00147%
F4 |  |  |  | 100% | 23265690 | 0.00068% | [30 empty] | 0.00068%
B151 | P3FH - 28 M.13.13.4.13.4.2.13.4.2.5 LV Switchgear 400 V | [35 empty] | 0%
| PRWE1381 | LV SWITCHGEAR - RFQ | [34 empty] | 0%
| PRWE1382 | LV SWITCHGEAR - Received Bids | [34 empty] | 0%
| PRWE1383 | LV SWITCHGEAR - CBE | [34 empty] | 0%
| PRWE1384 | LV SWITCHGEAR - LOI | [34 empty] | 0%
| PRWE1385 | LV SWITCHGEAR - PO |  | 25% | 861172672.5 | 0.02013% | 2018-01-11: 0.02013% | 0%
| PRWE1400 | LV SWITCHGEAR - Fabrication |  | 60% | 2066540700 | 0.0604% | [30 empty] | 0.0604%
| PRWE1410 | LV SWITCHGEAR - Delivery |  | 15% | 516293032.5 | 0.02013% | [30 empty] | 0.02013%
F4 |  |  |  | 100% | 23607832.5 | 0.00069% | [30 empty] | 0.00069%
B158 | P3FH - 28 M.13.13.4.13.4.2.13.4.2.6 Motor Control Centre | [35 empty] | 0%
| PRWE1411 | MCC - RFQ | [34 empty] | 0%
| PRWE1412 | MCC - Received Bids | [34 empty] | 0%
| PRWE1413 | MCC - CBE | [34 empty] | 0%
| PRWE1414 | MCC - LOI | [34 empty] | 0%
| PRWE1415 | MCC - PO |  | 25% | 99221325 | 0.0029% | [30 empty] | 0.0029%
| PRWE1430 | MCC - Fabrication |  | 60% | 238473322.5 | 0.00697% | [30 empty] | 0.00697%
| PRWE1440 | MCC - Delivery |  | 15% | 59532795 | 0.00174% | [30 empty] | 0.00174%
F4 |  |  |  | 100% | 23607832.5 | 0.00069% | [30 empty] | 0.00069%
B152 | P3FH - 28 M.13.13.4.13.4.2.13.4.2.7 Capacitor Bank Panel | [35 empty] | 0%
| PRWE1441 | CAPACITOR BANK PANEL - RFQ | [34 empty] | 0%
| PRWE1442 | CAPACITOR BANK PANEL - Received Bids | [34 empty] | 0%
| PRWE1443 | CAPACITOR BANK PANEL - CBE | [34 empty] | 0%
| PRWE1444 | CAPACITOR BANK PANEL - LOI | [34 empty] | 0%
| PRWE1445 | CAPACITOR BANK PANEL - PO |  | 25% | 371224612.5 | 0.01085% | 2017-10-13: 0.00868% | 0.00217%
| PRWE1460 | CAPACITOR BANK PANEL - Fabrication |  | 60% | 890939070 | 0.02604% | 2018-05-11: 0.02604% | 0%
| PRWE1470 | CAPACITOR BANK PANEL - Delivery |  | 15% | 222734767.5 | 0.00651% | [30 empty] | 0.00651%
F4 |  |  |  | 100% | 23607832.5 | 0.00069% | [30 empty] | 0.00069%
B153 | P3FH - 28 M.13.13.4.13.4.2.13.4.2.8 Panel Lighting and Small Power | [35 empty] | 0%
| PRWE1471 | PANEL LIGHTING AND SMALL POWER - RFQ | [34 empty] | 0%
| PRWE1472 | PANEL LIGHTING AND SMALL POWER - Received Bids | [34 empty] | 0%
| PRWE1473 | PANEL LIGHTING AND SMALL POWER - CBE | [34 empty] | 0%
| PRWE1474 | PANEL LIGHTING AND SMALL POWER - LOI | [34 empty] | 0%
| PRWE1475 | PANEL LIGHTING AND SMALL POWER - PO |  | 25% | 5816422.5 | 0.00017% | [30 empty] | 0.00017%
| PRWE1490 | PANEL LIGHTING AND SMALL POWER - Fabrication |  | 60% | 13685700 | 0.0004% | [30 empty] | 0.0004%
| PRWE1500 | PANEL LIGHTING AND SMALL POWER - Delivery |  | 15% | 3421425 | 0.0001% | [30 empty] | 0.0001%
F4 |  |  |  | 100% | 23607832.5 | 0.00069% | [30 empty] | 0.00069%
B154 | P3FH - 28 M.13.13.4.13.4.2.13.4.2.9 Indoor and Outdoor Lighting | [35 empty] | 0%
| PRWE1501 | INDOOR & OUTDOOR LIGHTING - RFQ | [34 empty] | 0%
| PRWE1502 | INDOOR & OUTDOOR LIGHTING - Received Bids | [34 empty] | 0%
| PRWE1503 | INDOOR & OUTDOOR LIGHTING - CBE | [34 empty] | 0%
| PRWE1504 | INDOOR & OUTDOOR LIGHTING - LOI | [34 empty] | 0%
| PRWE1505 | INDOOR & OUTDOOR LIGHTING - PO |  | 25% | 182361952.5 | 0.00533% | [30 empty] | 0.00533%
| PRWE1520 | INDOOR & OUTDOOR LIGHTING - Fabrication |  | 60% | 437258115 | 0.01278% | [30 empty] | 0.01278%
| PRWE1530 | INDOOR & OUTDOOR LIGHTING - Delivery |  | 15% | 109143457.5 | 0.00319% | [30 empty] | 0.00319%
F4 |  |  |  | 100% | 23607832.5 | 0.00069% | [30 empty] | 0.00069%
| P3FH - 28 M.13.13.4.13.4.2.13.4.2.10 AC UPS | [35 empty] | 0%
| PRWE1531 | AC UPS - RFQ | [34 empty] | 0%
| PRWE1532 | AC UPS - Received Bids | [34 empty] | 0%
| PRWE1533 | AC UPS - CBE | [34 empty] | 0%
| PRWE1534 | AC UPS - LOI | [34 empty] | 0%
| PRWE1535 | AC UPS - PO | [34 empty] | 0%
| PRWE1550 | AC UPS - Fabrication | [34 empty] | 0%
| PRWE1560 | AC UPS - Delivery | [34 empty] | 0%
B155 | P3FH - 28 M.13.13.4.13.4.2.13.4.2.11 DC UPS | [35 empty] | 0%
| PRWE1561 | DC UPS - RFQ | [34 empty] | 0%
| PRWE1562 | DC UPS - Received Bids | [34 empty] | 0%
| PRWE1563 | DC UPS - CBE | [34 empty] | 0%
| PRWE1564 | DC UPS - LOI | [34 empty] | 0%
| PRWE1565 | DC UPS - PO |  | 25% | 412281712.5 | 0.01205% | 2018-03-12: 0.00965% | 0.0024%
| PRWE1580 | DC UPS - Fabrication |  | 60% | 989818252.5 | 0.02893% | [30 empty] | 0.02893%
| PRWE1590 | DC UPS - Delivery |  | 15% | 247369027.5 | 0.00723% | [30 empty] | 0.00723%
F4 |  |  |  | 100% | 23607832.5 | 0.00069% | [30 empty] | 0.00069%
| P3FH - 28 M.13.13.4.13.4.2.13.4.2.171 DC Battery & Charger | [35 empty] | 0%
| PRWE2751 | DC BATTERY & CHARGER - RFQ | [34 empty] | 0%
| PRWE2752 | DC BATTERY & CHARGER - Received Bids | [34 empty] | 0%
| PRWE2753 | DC BATTERY & CHARGER - CBE | [34 empty] | 0%
| PRWE2754 | DC BATTERY & CHARGER - LOI | [34 empty] | 0%
| PRWE2755 | DC BATTERY & CHARGER - PO | [34 empty] | 0%
| PRWE2770 | DC BATTERY & CHARGER - Fabrication | [34 empty] | 0%
| PRWE2780 | DC BATTERY & CHARGER - Delivery | [34 empty] | 0%
B156 | P3FH - 28 M.13.13.4.13.4.2.13.4.2.12 MV Power Cable | [35 empty] | 0%
| PRWE1591 | MV POWER CABLE - RFQ | [34 empty] | 0%
| PRWE1592 | MV POWER CABLE - Received Bids | [34 empty] | 0%
| PRWE1593 | MV POWER CABLE - CBE | [34 empty] | 0%
| PRWE1594 | MV POWER CABLE - LOI | [34 empty] | 0%
| PRWE1595 | MV POWER CABLE - PO |  | 25% | 42083527.5 | 0.00123% | [30 empty] | 0.00123%
| PRWE1610 | MV POWER CABLE - Fabrication |  | 60% | 100589895 | 0.00294% | [30 empty] | 0.00294%
| PRWE1620 | MV POWER CABLE - Delivery |  | 15% | 24976402.5 | 0.00073% | [30 empty] | 0.00073%
F4 |  |  |  | 100% | 23607832.5 | 0.00069% | [30 empty] | 0.00069%
B157 | P3FH - 28 M.13.13.4.13.4.2.13.4.2.13 LV Power Cable | [35 empty] | 0%
| PRWE1621 | LV POWER CABLE - RFQ | [34 empty] | 0%
| PRWE1622 | LV POWER CABLE - Received Bids | [34 empty] | 0%
| PRWE1623 | LV POWER CABLE - CBE | [34 empty] | 0%
| PRWE1624 | LV POWER CABLE - LOI | [34 empty] | 0%
| PRWE1625 | LV POWER CABLE - PO |  | 25% | 764346345 | 0.02234% | [30 empty] | 0.02234%
| PRWE1640 | LV POWER CABLE - Fabrication |  | 60% | 1834225942.5 | 0.05361% | [30 empty] | 0.05361%
| PRWE1650 | LV POWER CABLE - Delivery |  | 15% | 458470950 | 0.0134% | [30 empty] | 0.0134%
F4 |  |  |  | 100% | 23607832.5 | 0.00069% | [30 empty] | 0.00069%
| P3FH - 28 M.13.13.4.13.4.2.13.4.2.14 Local Control Panel | [35 empty] | 0%
| PRWE1651 | LOCAL CONTROL PANEL - RFQ | [34 empty] | 0%
| PRWE1652 | LOCAL CONTROL PANEL - Received Bids | [34 empty] | 0%
| PRWE1653 | LOCAL CONTROL PANEL - CBE | [34 empty] | 0%
| PRWE1654 | LOCAL CONTROL PANEL - LOI | [34 empty] | 0%
| PRWE1655 | LOCAL CONTROL PANEL - PO | [34 empty] | 0%
| PRWE1670 | LOCAL CONTROL PANEL - Fabrication | [34 empty] | 0%
| PRWE1680 | LOCAL CONTROL PANEL - Delivery | [34 empty] | 0%
B159 | P3FH - 28 M.13.13.4.13.4.2.13.4.2.15 Cable Ladder & Cable Tray | [35 empty] | 0%
| PRWE1681 | CABLE LADDER & CABLE TRAY - RFQ | [34 empty] | 0%
| PRWE1682 | CABLE LADDER & CABLE TRAY - Received Bids | [34 empty] | 0%
| PRWE1683 | CABLE LADDER & CABLE TRAY - CBE | [34 empty] | 0%
| PRWE1684 | CABLE LADDER & CABLE TRAY - LOI | [34 empty] | 0%
| PRWE1685 | CABLE LADDER & CABLE TRAY - PO |  | 25% | 313060387.5 | 0.00915% | [30 empty] | 0.00915%
| PRWE1700 | CABLE LADDER & CABLE TRAY - Fabrication |  | 60% | 751344930 | 0.02196% | [30 empty] | 0.02196%
| PRWE1710 | CABLE LADDER & CABLE TRAY - Delivery |  | 15% | 187836232.5 | 0.00549% | [30 empty] | 0.00549%
F4 |  |  |  | 100% | 23607832.5 | 0.00069% | [30 empty] | 0.00069%
B160 | P3FH - 28 M.13.13.4.13.4.2.13.4.2.16 Bulk Material | [35 empty] | 0%
| PRWE1711 | BULK MATERIAL - RFQ | [34 empty] | 0%
| PRWE1712 | BULK MATERIAL - Received Bids | [34 empty] | 0%
| PRWE1713 | BULK MATERIAL - CBE | [34 empty] | 0%
| PRWE1714 | BULK MATERIAL - LOI | [34 empty] | 0%
| PRWE1715 | BULK MATERIAL - PO |  | 25% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
| PRWE1730 | BULK MATERIAL - Fabrication |  | 60% | 455733810 | 0.01332% | [30 empty] | 0.01332%
| PRWE1740 | BULK MATERIAL - Delivery |  | 15% | 113933452.5 | 0.00333% | [30 empty] | 0.00333%
F4 |  |  |  | 100% | 23607832.5 | 0.00069% | [30 empty] | 0.00069%
B161 | P3FH - 28 M.13.13.4.13.4.2.13.4.2.17 Grounding & Lightning Protection | [35 empty] | 0%
| PRWE1741 | GROUNDING & LIGHTNING PROTECTION - RFQ | [34 empty] | 0%
| PRWE1742 | GROUNDING & LIGHTNING PROTECTION - Received Bids | [34 empty] | 0%
| PRWE1743 | GROUNDING & LIGHTNING PROTECTION - CBE | [34 empty] | 0%
| PRWE1744 | GROUNDING & LIGHTNING PROTECTION - LOI | [34 empty] | 0%
| PRWE1745 | GROUNDING & LIGHTNING PROTECTION - PO |  | 25% | 102984892.5 | 0.00301% | [30 empty] | 0.00301%
| PRWE1760 | GROUNDING & LIGHTNING PROTECTION - Fabrication |  | 60% | 247369027.5 | 0.00723% | [30 empty] | 0.00723%
| PRWE1770 | GROUNDING & LIGHTNING PROTECTION - Delivery |  | 15% | 61927792.5 | 0.00181% | [30 empty] | 0.00181%
F4 |  |  |  | 100% | 23607832.5 | 0.00069% | [30 empty] | 0.00069%
| P3FH - 28 M.13.13.4.13.4.3 System 3 - Refinery | [35 empty] | 0%
B164 | P3FH - 28 M.13.13.4.13.4.3.13.4.3.1 MV Switchgear 6.6 kV | [35 empty] | 0%
| PRWE1779 | MV SWITCHGEAR 6.6 KV - RFQ | [34 empty] | 0%
| PRWE1780 | MV SWITCHGEAR 6.6 KV - Received Bids | [34 empty] | 0%
| PRWE1781 | MV SWITCHGEAR 6.6 KV - CBE | [34 empty] | 0%
| PRWE1782 | MV SWITCHGEAR 6.6 KV - LOI | [34 empty] | 0%
| PRWE1783 | MV SWITCHGEAR 6.6 KV - PO |  | 20% | 326403945 | 0.00954% | 2017-10-13: 0.00954% | 0%
| PRWE1790 | MV SWITCHGEAR 6.6 KV - Fabrication |  | 60% | 978869692.5 | 0.02861% | [30 empty] | 0.02861%
| PRWE1800 | MV SWITCHGEAR 6.6 KV - Delivery |  | 20% | 326403945 | 0.00954% | [30 empty] | 0.00954%
F4 |  |  |  | 100% | 10948560 | 0.00032% | [30 empty] | 0.00032%
B165 | P3FH - 28 M.13.13.4.13.4.3.13.4.3.2 Power Transformer 6.6 / 0.4 kV | [35 empty] | 0%
| PRWE1809 | POWER TRANSFORMER - RFQ | [34 empty] | 0%
| PRWE1810 | POWER TRANSFORMER - Received Bids | [34 empty] | 0%
| PRWE1811 | POWER TRANSFORMER - CBE | [34 empty] | 0%
| PRWE1812 | POWER TRANSFORMER - LOI | [34 empty] | 0%
| PRWE1813 | POWER TRANSFORMER - PO |  | 20% | 35240677.5 | 0.00103% | 2017-10-13: 0.00103% | 0%
| PRWE1820 | POWER TRANSFORMER - Fabrication |  | 60% | 105722032.5 | 0.00309% | 2018-03-12: 0.00309% | 0%
| PRWE1830 | POWER TRANSFORMER - Delivery |  | 20% | 35240677.5 | 0.00103% | [30 empty] | 0.00103%
F4 |  |  |  | 100% | 10948560 | 0.00032% | [30 empty] | 0.00032%
B166 | P3FH - 28 M.13.13.4.13.4.3.13.4.3.3 LV Switchgear 400V | [35 empty] | 0%
| PRWE1839 | LV SWITCHGEAR - RFQ | [34 empty] | 0%
| PRWE1840 | LV SWITCHGEAR - Received of Bids | [34 empty] | 0%
| PRWE1841 | LV SWITCHGEAR - CBE | [34 empty] | 0%
| PRWE1842 | LV SWITCHGEAR - LOI | [34 empty] | 0%
| PRWE1843 | LV SWITCHGEAR - PO |  | 20% | 435205260 | 0.01272% | 2017-10-13: 0.01272% | 0%
| PRWE1850 | LV SWITCHGEAR - Fabrication |  | 60% | 1304931495 | 0.03814% | [30 empty] | 0.03814%
| PRWE1860 | LV SWITCHGEAR - Delivery |  | 20% | 435205260 | 0.01272% | [30 empty] | 0.01272%
F4 |  |  |  | 100% | 10948560 | 0.00032% | [30 empty] | 0.00032%
B173 | P3FH - 28 M.13.13.4.13.4.3.13.4.3.4 Motor Control Centre | [35 empty] | 0%
| PRWE1869 | MOTOR CONTROL CENTRE - RFQ | [34 empty] | 0%
| PRWE1870 | MOTOR CONTROL CENTRE - Recceived of Bids | [34 empty] | 0%
| PRWE1871 | MOTOR CONTROL CENTRE - CBE | [34 empty] | 0%
| PRWE1872 | MOTOR CONTROL CENTRE - LOI | [34 empty] | 0%
| PRWE1873 | MOTOR CONTROL CENTRE - PO |  | 20% | 19502122.5 | 0.00057% | 2018-02-10: 0.00057% | 0%
| PRWE1880 | MOTOR CONTROL CENTRE - Fabrication |  | 60% | 58506367.5 | 0.00171% | 2018-02-10: 0.00171% | 0%
| PRWE1890 | MOTOR CONTROL CENTRE - Delivery |  | 20% | 19502122.5 | 0.00057% | 2018-02-10: 0.00057% | 0%
F4 |  |  |  | 100% | 10948560 | 0.00032% | [30 empty] | 0.00032%
B167 | P3FH - 28 M.13.13.4.13.4.3.13.4.3.5 Capacitor Bank Panel | [35 empty] | 0%
| PRWE1899 | CAPASITOR BANK PANEL - RFQ | [34 empty] | 0%
| PRWE1900 | CAPASITOR BANK PANEL - Received of Bids | [34 empty] | 0%
| PRWE1901 | CAPASITOR BANK PANEL - CBE | [34 empty] | 0%
| PRWE1902 | CAPASITOR BANK PANEL - LOI | [34 empty] | 0%
| PRWE1903 | CAPASITOR BANK PANEL - PO |  | 20% | 148489845 | 0.00434% | 2017-10-13: 0.00434% | 0%
| PRWE1910 | CAPASITOR BANK PANEL - Fabrication |  | 60% | 445469535 | 0.01302% | 2018-05-11: 0.01302% | 0%
| PRWE1920 | CAPASITOR BANK PANEL - Delivery |  | 20% | 148489845 | 0.00434% | [30 empty] | 0.00434%
F4 |  |  |  | 100% | 10948560 | 0.00032% | [30 empty] | 0.00032%
B168 | P3FH - 28 M.13.13.4.13.4.3.13.4.3.6 Panel for Lighting and Small Power | [35 empty] | 0%
| PRWE1929 | PANEL FOR LIGHTING & SMALL POWER - RFQ | [34 empty] | 0%
| PRWE1930 | PANEL FOR LIGHTING & SMALL POWER - Received of Bids | [34 empty] | 0%
| PRWE1931 | PANEL FOR LIGHTING & SMALL POWER - CBE | [34 empty] | 0%
| PRWE1932 | PANEL FOR LIGHTING & SMALL POWER - LOI | [34 empty] | 0%
| PRWE1933 | PANEL FOR LIGHTING & SMALL POWER - PO |  | 20% | 1368570 | 4e-05% | [30 empty] | 4e-05%
| PRWE1940 | PANEL FOR LIGHTING & SMALL POWER - Fabrication |  | 60% | 4105710 | 0.00012% | [30 empty] | 0.00012%
| PRWE1950 | PANEL FOR LIGHTING & SMALL POWER- Delivery |  | 20% | 1368570 | 4e-05% | [30 empty] | 4e-05%
F4 |  |  |  | 100% | 10948560 | 0.00032% | [30 empty] | 0.00032%
B169 | P3FH - 28 M.13.13.4.13.4.3.13.4.4.7 Indoor and Outdoor Lighting | [35 empty] | 0%
| PRWE25898 | INDOOR & OUTDOOR LIGHTING - RFQ | [34 empty] | 0%
| PRWE25899 | INDOOR & OUTDOOR LIGHTING - Received of Bids | [34 empty] | 0%
| PRWE25900 | INDOOR & OUTDOOR LIGHTING - CBE | [34 empty] | 0%
| PRWE25901 | INDOOR & OUTDOOR LIGHTING - LOI | [34 empty] | 0%
| PRWE25902 | INDOOR & OUTDOOR LIGHTING - PO |  | 20% | 13343557.5 | 0.00039% | 2018-04-11: 0.00039% | 0%
| PRWE25909 | INDOOR & OUTDOOR LIGHTING - Fabrication |  | 60% | 40714957.5 | 0.00119% | [30 empty] | 0.00119%
| PRWE25919 | INDOOR & OUTDOOR LIGHTING - Delivery |  | 20% | 13343557.5 | 0.00039% | [30 empty] | 0.00039%
F4 |  |  |  | 100% | 11290702.5 | 0.00033% | [30 empty] | 0.00033%
| P3FH - 28 M.13.13.4.13.4.3.13.4.3.9 AC UPS | [35 empty] | 0%
| PRWE2019 | AC UPS - RFQ | [34 empty] | 0%
| PRWE2020 | AC UPS - Received of Bids | [34 empty] | 0%
| PRWE2021 | AC UPS - CBE | [34 empty] | 0%
| PRWE2022 | AC UPS - LOI | [34 empty] | 0%
| PRWE2023 | AC UPS - PO | [34 empty] | 0%
| PRWE2030 | AC UPS - Fabrication | [34 empty] | 0%
| PRWE2040 | AC UPS - Delivery | [34 empty] | 0%
B170 | P3FH - 28 M.13.13.4.13.4.3.13.4.3.10 DC UPS | [35 empty] | 0%
| PRWE2049 | DC UPS - RFQ | [34 empty] | 0%
| PRWE2050 | DC UPS - Received of Bids | [34 empty] | 0%
| PRWE2051 | DC UPS - CBE | [34 empty] | 0%
| PRWE2052 | DC UPS - LOI | [34 empty] | 0%
| PRWE2053 | DC UPS - PO |  | 20% | 229235475 | 0.0067% | 2018-01-11: 0.00669% | 1e-05%
| PRWE2060 | DC UPS - Fabrication |  | 60% | 687022140 | 0.02008% | [30 empty] | 0.02008%
| PRWE2070 | DC UPS - Delivery |  | 20% | 229235475 | 0.0067% | [30 empty] | 0.0067%
F4 |  |  |  | 100% | 11290702.5 | 0.00033% | [30 empty] | 0.00033%
B171 | P3FH - 28 M.13.13.4.13.4.3.13.4.3.11 MV Power Cable | [35 empty] | 0%
| PRWE2079 | MV POWER CABLE - RFQ | [34 empty] | 0%
| PRWE2080 | MV POWER CABLE - Received of Bids | [34 empty] | 0%
| PRWE2081 | MV POWER CABLE - CBE | [34 empty] | 0%
| PRWE2082 | MV POWER CABLE - LOI | [34 empty] | 0%
| PRWE2083 | MV POWER CABLE - PO |  | 20% | 41057100 | 0.0012% | [30 empty] | 0.0012%
| PRWE2090 | MV POWER CABLE - Fabrication |  | 60% | 122487015 | 0.00358% | [30 empty] | 0.00358%
| PRWE2100 | MV POWER CABLE - Delivery |  | 20% | 41057100 | 0.0012% | [30 empty] | 0.0012%
F4 |  |  |  | 100% | 11290702.5 | 0.00033% | [30 empty] | 0.00033%
B172 | P3FH - 28 M.13.13.4.13.4.3.13.4.3.12 LV Power Cable | [35 empty] | 0%
| PRWE2109 | LV POWER CABLE - RFQ | [34 empty] | 0%
| PRWE2110 | LV POWER CABLE - Received of Bids | [34 empty] | 0%
| PRWE2111 | LV POWER CABLE - CBE | [34 empty] | 0%
| PRWE2112 | LV POWER CABLE - LOI | [34 empty] | 0%
| PRWE2113 | LV POWER CABLE - PO |  | 20% | 48926377.5 | 0.00143% | 2018-02-10: 0.00143% | 0%
| PRWE2120 | LV POWER CABLE - Fabrication |  | 60% | 146779132.5 | 0.00429% | 2018-02-10: 0.00429% | 0%
| PRWE2130 | LV POWER CABLE - Delivery |  | 20% | 48926377.5 | 0.00143% | 2018-02-10: 0.00143% | 0%
F4 |  |  |  | 100% | 11290702.5 | 0.00033% | [30 empty] | 0.00033%
| P3FH - 28 M.13.13.4.13.4.3.13.4.3.13 Local Control Panel | [35 empty] | 0%
| PRWE2139 | LOCAL CONTROL PANEL - RFQ | [34 empty] | 0%
| PRWE2140 | LOCAL CONTROL PANEL - Received of Bids | [34 empty] | 0%
| PRWE2141 | LOCAL CONTROL PANEL - CBE | [34 empty] | 0%
| PRWE2142 | LOCAL CONTROL PANEL - LOI | [34 empty] | 0%
| PRWE2143 | LOCAL CONTROL PANEL - PO | [34 empty] | 0%
| PRWE2150 | LOCAL CONTROL PANEL - Fabrication | [34 empty] | 0%
| PRWE2160 | LOCAL CONTROL PANEL - Delivery | [34 empty] | 0%
B174 | P3FH - 28 M.13.13.4.13.4.3.13.4.3.14 Cable Ladder & Cable Tray | [35 empty] | 0%
| PRWE2169 | CABLE LADDER & CABLE TRAY - RFQ | [34 empty] | 0%
| PRWE2170 | CABLE LADDER & CABLE TRAY - Received of Bids | [34 empty] | 0%
| PRWE2171 | CABLE LADDER & CABLE TRAY - CBE | [34 empty] | 0%
| PRWE2172 | CABLE LADDER & CABLE TRAY - LOI | [34 empty] | 0%
| PRWE2173 | CABLE LADDER & CABLE TRAY - PO |  | 20% | 138225570 | 0.00404% | 2018-04-11: 0.00404% | 0%
| PRWE2180 | CABLE LADDER & CABLE TRAY - Fabrication |  | 60% | 415360995 | 0.01214% | 2018-04-11: 0.01214% | 0%
| PRWE2190 | CABLE LADDER & CABLE TRAY - Delivery |  | 20% | 138225570 | 0.00404% | [30 empty] | 0.00404%
F4 |  |  |  | 100% | 11290702.5 | 0.00033% | [30 empty] | 0.00033%
B175 | P3FH - 28 M.13.13.4.13.4.3.13.4.3.15 Bulk Material | [35 empty] | 0%
| PRWE2199 | BULK MATERIAL - RFQ | [34 empty] | 0%
| PRWE2200 | BULK MATERIAL - Received of Bids | [34 empty] | 0%
| PRWE2201 | BULK MATERIAL - CBE | [34 empty] | 0%
| PRWE2202 | BULK MATERIAL - LOI | [34 empty] | 0%
| PRWE2203 | BULK MATERIAL - PO |  | 20% | 80745630 | 0.00236% | [30 empty] | 0.00236%
| PRWE2210 | BULK MATERIAL - Fabrication |  | 60% | 242236890 | 0.00708% | [30 empty] | 0.00708%
| PRWE2220 | BULK MATERIAL - Delivery |  | 20% | 80745630 | 0.00236% | [30 empty] | 0.00236%
F4 |  |  |  | 100% | 11290702.5 | 0.00033% | [30 empty] | 0.00033%
B176 | P3FH - 28 M.13.13.4.13.4.3.13.4.3.16 Grounding & Lightning Protection | [35 empty] | 0%
| PRWE2229 | GROUNDING & LIGHTNING - RFQ | [34 empty] | 0%
| PRWE2230 | GROUNDING & LIGHTNING - Received of Bids | [34 empty] | 0%
| PRWE2231 | GROUNDING & LIGHTNING - CBE | [34 empty] | 0%
| PRWE2232 | GROUNDING & LIGHTNING - LOI | [34 empty] | 0%
| PRWE2233 | GROUNDING & LIGHTNING - PO |  | 20% | 59532795 | 0.00174% | [30 empty] | 0.00174%
| PRWE2240 | GROUNDING & LIGHTNING - Fabrication |  | 60% | 178598385 | 0.00522% | [30 empty] | 0.00522%
| PRWE2250 | GROUNDING & LIGHTNING - Delivery |  | 20% | 59532795 | 0.00174% | [30 empty] | 0.00174%
F4 |  |  |  | 100% | 11290702.5 | 0.00033% | [30 empty] | 0.00033%
| P3FH - 28 M.13.13.4.13.4.4 System 4 - Utility Supply | [35 empty] | 0%
B179 | P3FH - 28 M.13.13.4.13.4.4.13.4.1.2.2 Generator Unit Control Panel (GCP) | [35 empty] | 0%
| PRWE1021 | GENERATOR UNIT CONTROL PANEL (GCP) - RFQ | [34 empty] | 0%
| PRWE1022 | GENERATOR UNIT CONTROL PANEL (GCP) - Received of Bids | [34 empty] | 0%
| PRWE1023 | GENERATOR UNIT CONTROL PANEL (GCP) - CBE | [34 empty] | 0%
| PRWE1024 | GENERATOR UNIT CONTROL PANEL (GCP) - LOI | [34 empty] | 0%
| PRWE1030 | GENERATOR UNIT CONTROL PANEL (GCP) - PO |  | 25% | 1285429372.5 | 0.03757% | 2017-10-13: 0.03005% | 0.00752%
| PRWE1040 | GENERATOR UNIT CONTROL PANEL GCP) - Fabrication |  | 60% | 3084756780 | 0.09016% | 2018-03-12: 0.09016% | 0%
| PRWE1050 | GENERATOR UNIT CONTROL PANEL (GCP) - Delivery |  | 15% | 770847052.5 | 0.02253% | [30 empty] | 0.02253%
F4 |  |  |  | 100% | 53032087.5 | 0.00155% | [30 empty] | 0.00155%
B180 | P3FH - 28 M.13.13.4.13.4.4.13.4.4.1 MV Switchgear 6.6 kV | [35 empty] | 0%
| PRWE2259 | MV SWITCHGEAR 6.6 KV - RFQ | [34 empty] | 0%
| PRWE2260 | MV SWITCHGEAR 6.6 KV - Received of Bids | [34 empty] | 0%
| PRWE2261 | MV SWITCHGEAR 6.6 KV - CBE | [34 empty] | 0%
| PRWE2262 | MV SWITCHGEAR 6.6 KV - LOI | [34 empty] | 0%
| PRWE2263 | MV SWITCHGEAR 6.6 KV - PO |  | 25% | 1185181620 | 0.03464% | 2017-10-13: 0.02772% | 0.00692%
| PRWE2270 | MV SWITCHGEAR 6.6 KV - Fabrication |  | 60% | 2844572745 | 0.08314% | [30 empty] | 0.08314%
| PRWE2280 | MV SWITCHGEAR 6.6 KV - Delivery |  | 15% | 711314257.5 | 0.02079% | [30 empty] | 0.02079%
F4 |  |  |  | 100% | 53032087.5 | 0.00155% | [30 empty] | 0.00155%
B181 | P3FH - 28 M.13.13.4.13.4.4.13.4.4.2 Power Transformer 6.6 / 0.4 kV | [35 empty] | 0%
| PRWE2289 | POWER TRANSFORMER 6.6 / 0.4 KV - RFQ | [34 empty] | 0%
| PRWE2290 | POWER TRANSFORMER 6.6 / 0.4 KV - Received of Bids | [34 empty] | 0%
| PRWE2291 | POWER TRANSFORMER 6.6 / 0.4 KV - CBE | [34 empty] | 0%
| PRWE2292 | POWER TRANSFORMER 6.6 / 0.4 KV - LOI | [34 empty] | 0%
| PRWE2293 | POWER TRANSFORMER 6.6 / 0.4 KV - PO |  | 25% | 154990552.5 | 0.00453% | 2017-10-13: 0.00363% | 0.0009%
| PRWE2300 | POWER TRANSFORMER 6.6 / 0.4 KV - Fabrication |  | 60% | 372251040 | 0.01088% | 2018-03-12: 0.01088% | 0%
| PRWE2310 | POWER TRANSFORMER 6.6 / 0.4 KV - Delivery |  | 15% | 93062760 | 0.00272% | [30 empty] | 0.00272%
F4 |  |  |  | 100% | 53032087.5 | 0.00155% | [30 empty] | 0.00155%
B182 | P3FH - 28 M.13.13.4.13.4.4.13.4.4.3 LV Switchgear 400V | [35 empty] | 0%
| PRWE2319 | LV SWITCHGEAR 400 V - RFQ | [34 empty] | 0%
| PRWE2320 | LV SWITCHGEAR 400 V - Received of Bids | [34 empty] | 0%
| PRWE2321 | LV SWITCHGEAR 400 V - CBE | [34 empty] | 0%
| PRWE2322 | LV SWITCHGEAR 400 V - LOI | [34 empty] | 0%
| PRWE2323 | LV SWITCHGEAR 400 V - PO |  | 25% | 1404837105 | 0.03285% | 2018-01-11: 0.03285% | 0%
| PRWE2330 | LV SWITCHGEAR 400 V - Fabrication |  | 60% | 3371472195 | 0.09854% | [30 empty] | 0.09854%
| PRWE2340 | LV SWITCHGEAR 400 V - Delivery |  | 15% | 843039120 | 0.03285% | [30 empty] | 0.03285%
F4 |  |  |  | 100% | 53032087.5 | 0.00155% | [30 empty] | 0.00155%
B190 | P3FH - 28 M.13.13.4.13.4.4.13.4.4.4 Motor Control Centre | [35 empty] | 0%
| PRWE2349 | MOTOR CONTROL CENTER - RFQ | [34 empty] | 0%
| PRWE2350 | MOTOR CONTROL CENTER - Received of Bids | [34 empty] | 0%
| PRWE2351 | MOTOR CONTROL CENTER - CBE | [34 empty] | 0%
| PRWE2352 | MOTOR CONTROL CENTER - LOI | [34 empty] | 0%
| PRWE2353 | MOTOR CONTROL CENTER - PO |  | 25% | 102300607.5 | 0.00299% | [30 empty] | 0.00299%
| PRWE2360 | MOTOR CONTROL CENTER - Fabrication |  | 60% | 245658315 | 0.00718% | [30 empty] | 0.00718%
| PRWE2370 | MOTOR CONTROL CENTER - Delivery |  | 15% | 61585650 | 0.0018% | [30 empty] | 0.0018%
F4 |  |  |  | 100% | 53032087.5 | 0.00155% | [30 empty] | 0.00155%
B183 | P3FH - 28 M.13.13.4.13.4.4.13.4.4.5 Capacitor Bank Panel | [35 empty] | 0%
| PRWE2379 | CAPACITOR BANK PANEL - RFQ | [34 empty] | 0%
| PRWE2380 | CAPACITOR BANK PANEL - Received of Bids | [34 empty] | 0%
| PRWE2381 | CAPACITOR BANK PANEL - CBE | [34 empty] | 0%
| PRWE2382 | CAPACITOR BANK PANEL - LOI | [34 empty] | 0%
| PRWE2383 | CAPACITOR BANK PANEL - PO |  | 25% | 185783377.5 | 0.00543% | 2017-10-13: 0.00434% | 0.00109%
| PRWE2390 | CAPACITOR BANK PANEL - Fabrication |  | 60% | 445469535 | 0.01302% | 2018-05-11: 0.01302% | 0%
| PRWE2400 | CAPACITOR BANK PANEL - Delivery |  | 15% | 111196312.5 | 0.00325% | [30 empty] | 0.00325%
F4 |  |  |  | 100% | 53032087.5 | 0.00155% | [30 empty] | 0.00155%
B185 | P3FH - 28 M.13.13.4.13.4.4.13.4.4.6 Panel for Lighting and Small Power | [35 empty] | 0%
| PRWE2409 | PANEL FOR LIGHTING & SMALL POWER - RFQ | [34 empty] | 0%
| PRWE2410 | PANEL FOR LIGHTING & SMALL POWER - Received of Bids | [34 empty] | 0%
| PRWE2411 | PANEL FOR LIGHTING & SMALL POWER - CBE | [34 empty] | 0%
| PRWE2412 | PANEL FOR LIGHTING & SMALL POWER - LOI | [34 empty] | 0%
| PRWE2413 | PANEL FOR LIGHTING & SMALL POWER - PO |  | 25% | 49610662.5 | 0.00145% | [30 empty] | 0.00145%
| PRWE2420 | PANEL FOR LIGHTING & SMALL POWER - Fabrication |  | 60% | 118723447.5 | 0.00347% | [30 empty] | 0.00347%
| PRWE2430 | PANEL FOR LIGHTING & SMALL POWER - Delivery |  | 15% | 29766397.5 | 0.00087% | [30 empty] | 0.00087%
F4 |  |  |  | 100% | 53032087.5 | 0.00155% | [30 empty] | 0.00155%
B186 | P3FH - 28 M.13.13.4.13.4.4.13.4.4.7 Indoor and Outdoor Lighting | [35 empty] | 0%
| PRWE2439 | INDOOR & OUTDOOR LIGHTING - RFQ | [34 empty] | 0%
| PRWE2440 | INDOOR & OUTDOOR LIGHTING - Received of Bids | [34 empty] | 0%
| PRWE2441 | INDOOR & OUTDOOR LIGHTING - CBE | [34 empty] | 0%
| PRWE2442 | INDOOR & OUTDOOR LIGHTING - LOI | [34 empty] | 0%
| PRWE2443 | INDOOR & OUTDOOR LIGHTING - PO |  | 25% | 1014794655 | 0.02966% | 2018-04-11: 0.02373% | 0.00593%
| PRWE2450 | INDOOR & OUTDOOR LIGHTING - Fabrication |  | 60% | 2435712457.5 | 0.07119% | [30 empty] | 0.07119%
| PRWE2460 | INDOOR & OUTDOOR LIGHTING - Delivery |  | 15% | 609013650 | 0.0178% | [30 empty] | 0.0178%
F4 |  |  |  | 100% | 53032087.5 | 0.00155% | [30 empty] | 0.00155%
| P3FH - 28 M.13.13.4.13.4.4.13.4.4.8 AC UPS | [35 empty] | 0%
| PRWE2469 | AC UPS - RFQ | [34 empty] | 0%
| PRWE2470 | AC UPS - Received of Bids | [34 empty] | 0%
| PRWE2471 | AC UPS - CBE | [34 empty] | 0%
| PRWE2472 | AC UPS - LOI | [34 empty] | 0%
| PRWE2473 | AC UPS - PO | [34 empty] | 0%
| PRWE2480 | AC UPS - Fabrication | [34 empty] | 0%
| PRWE2490 | AC UPS - Delivery | [34 empty] | 0%
B187 | P3FH - 28 M.13.13.4.13.4.4.13.4.4.9 DC UPS | [35 empty] | 0%
| PRWE2499 | DC UPS - RFQ | [34 empty] | 0%
| PRWE2500 | DC UPS - Received of Bids | [34 empty] | 0%
| PRWE2501 | DC UPS - CBE | [34 empty] | 0%
| PRWE2502 | DC UPS - LOI | [34 empty] | 0%
| PRWE2503 | DC UPS - PO |  | 25% | 746554935 | 0.02182% | 2018-03-12: 0.01746% | 0.00436%
| PRWE2510 | DC UPS - Fabrication |  | 60% | 1791800272.5 | 0.05237% | [30 empty] | 0.05237%
| PRWE2520 | DC UPS - Delivery |  | 15% | 448206675 | 0.0131% | [30 empty] | 0.0131%
F4 |  |  |  | 100% | 53032087.5 | 0.00155% | [30 empty] | 0.00155%
B188 | P3FH - 28 M.13.13.4.13.4.4.13.4.4.10 MV Power Cable | [35 empty] | 0%
| PRWE2529 | MV POWER CABLE - RFQ | [34 empty] | 0%
| PRWE2530 | MV POWER CABLE - Received of Bids | [34 empty] | 0%
| PRWE2531 | MV POWER CABLE - CBE | [34 empty] | 0%
| PRWE2532 | MV POWER CABLE - LOI | [34 empty] | 0%
| PRWE2533 | MV POWER CABLE - PO |  | 25% | 1245740842.5 | 0.03641% | [30 empty] | 0.03641%
| PRWE2540 | MV POWER CABLE - Fabrication |  | 60% | 2989641165 | 0.08738% | [30 empty] | 0.08738%
| PRWE2550 | MV POWER CABLE - Delivery |  | 15% | 747581362.5 | 0.02185% | [30 empty] | 0.02185%
F4 |  |  |  | 100% | 53032087.5 | 0.00155% | [30 empty] | 0.00155%
B189 | P3FH - 28 M.13.13.4.13.4.4.13.4.4.11 LV Power Cable | [35 empty] | 0%
| PRWE2559 | LV POWER CABLE - RFQ | [34 empty] | 0%
| PRWE2560 | LV POWER CABLE - Received of Bids | [34 empty] | 0%
| PRWE2561 | LV POWER CABLE - CBE | [34 empty] | 0%
| PRWE2562 | LV POWER CABLE - LOI | [34 empty] | 0%
| PRWE2563 | LV POWER CABLE - PO |  | 25% | 845091975 | 0.0247% | [30 empty] | 0.0247%
| PRWE2570 | LV POWER CABLE - Fabrication |  | 60% | 2028220740 | 0.05928% | [30 empty] | 0.05928%
| PRWE2580 | LV POWER CABLE - Delivery |  | 15% | 507055185 | 0.01482% | [30 empty] | 0.01482%
F4 |  |  |  | 100% | 53032087.5 | 0.00155% | [30 empty] | 0.00155%
B184 | P3FH - 28 M.13.13.4.13.4.4.13.4.4.12 Local Control Panel | [35 empty] | 0%
| PRWE25889 | LOCAL CONTROL PANEL - RFQ | [34 empty] | 0%
| PRWE2590 | LOCAL CONTROL PANEL - Received of Bids | [34 empty] | 0%
| PRWE2591 | LOCAL CONTROL PANEL - CBE | [34 empty] | 0%
| PRWE2592 | LOCAL CONTROL PANEL - LOI | [34 empty] | 0%
| PRWE2593 | LOCAL CONTROL PANEL - PO |  | 25% | 2737140 | 8e-05% | [30 empty] | 8e-05%
| PRWE2600 | LOCAL CONTROL PANEL - Fabrication |  | 60% | 6158565 | 0.00018% | [30 empty] | 0.00018%
| PRWE2610 | LOCAL CONTROL PANEL - Delivery |  | 15% | 1368570 | 4e-05% | [30 empty] | 4e-05%
F4 |  |  |  | 100% | 53032087.5 | 0.00155% | [30 empty] | 0.00155%
B191 | P3FH - 28 M.13.13.4.13.4.4.13.4.4.13 Cable Ladder & Cable Tray | [35 empty] | 0%
| PRWE2519 | CABLE LADDER & CABLE TRAY - RFQ | [34 empty] | 0%
| PRWE2620 | CABLE LADDER & CABLE TRAY - Received of Bids | [34 empty] | 0%
| PRWE2621 | CABLE LADDER & CABLE TRAY - CBE | [34 empty] | 0%
| PRWE2622 | CABLE LADDER & CABLE TRAY - LOI | [34 empty] | 0%
| PRWE2623 | CABLE LADDER & CABLE TRAY - PO |  | 25% | 381488887.5 | 0.01115% | 2018-05-11: 0.00892% | 0.00223%
| PRWE2630 | CABLE LADDER & CABLE TRAY - Fabrication |  | 60% | 915915472.5 | 0.02677% | [30 empty] | 0.02677%
| PRWE2640 | CABLE LADDER & CABLE TRAY - Delivery |  | 15% | 228893332.5 | 0.00669% | [30 empty] | 0.00669%
F4 |  |  |  | 100% | 53032087.5 | 0.00155% | [30 empty] | 0.00155%
B192 | P3FH - 28 M.13.13.4.13.4.4.13.4.4.14 Bulk Material | [35 empty] | 0%
| PRWE2649 | BULK MATERIAL - RFQ | [34 empty] | 0%
| PRWE2650 | BULK MATERIAL - Received of Bids | [34 empty] | 0%
| PRWE2651 | BULK MATERIAL - CBE | [34 empty] | 0%
| PRWE2652 | BULK MATERIAL - LOI | [34 empty] | 0%
| PRWE2653 | BULK MATERIAL - PO |  | 25% | 957999000 | 0.028% | [30 empty] | 0.028%
| PRWE2660 | BULK MATERIAL - Fabrication |  | 60% | 2298855457.5 | 0.06719% | [30 empty] | 0.06719%
| PRWE2670 | BULK MATERIAL - Delivery |  | 15% | 574457257.5 | 0.01679% | [30 empty] | 0.01679%
F4 |  |  |  | 100% | 53032087.5 | 0.00155% | [30 empty] | 0.00155%
B193 | P3FH - 28 M.13.13.4.13.4.4.13.4.4.15 Grounding & Lightning Protection | [35 empty] | 0%
| PRWE2679 | GROUNDING & LIGHTNING PROTECTION - RFQ | [34 empty] | 0%
| PRWE2680 | GROUNDING & LIGHTNING PROTECTION - Received of Bids | [34 empty] | 0%
| PRWE2681 | GROUNDING & LIGHTNING PROTECTION - CBE | [34 empty] | 0%
| PRWE2682 | GROUNDING & LIGHTNING PROTECTION - LOI | [34 empty] | 0%
| PRWE2683 | GROUNDING & LIGHTNING PROTECTION - PO |  | 25% | 563166555 | 0.01646% | 2018-02-10: 0.01316% | 0.0033%
| PRWE2690 | GROUNDING & LIGHTNING PROTECTION - Fabrication |  | 60% | 1351120732.5 | 0.03949% | [30 empty] | 0.03949%
| PRWE2700 | GROUNDING & LIGHTNING PROTECTION - Delivery |  | 15% | 337694647.5 | 0.00987% | [30 empty] | 0.00987%
F4 |  |  |  | 100% | 53032087.5 | 0.00155% | [30 empty] | 0.00155%
| P3FH - 28 M.13.13.4.1 Non Process Building | [35 empty] | 0%
| P3FH - 28 M.13.13.4.1.14 Electrical Equipment (Cable, Rack, Conduit, Steel, lighting, lightning, etc.) | [35 empty] | 0%
| PRWE-NONPROS-1000 | Electrical Equipment (Cable, Rack, Conduit, Steel, lighting, lightning, etc.) - RFQ | [34 empty] | 0%
| PRWE-NONPROS-1010 | Electrical Equipment (Cable, Rack, Conduit, Steel, lighting, lightning, etc.) - Received of Bids | [34 empty] | 0%
| PRWE-NONPROS-1020 | Electrical Equipment (Cable, Rack, Conduit, Steel, lighting, lightning, etc.) - TBE & CBE | [34 empty] | 0%
| PRWE-NONPROS-1030 | Electrical Equipment (Cable, Rack, Conduit, Steel, lighting, lightning, etc.) - PO | [34 empty] | 0%
| PRWE-NONPROS-1040 | Electrical Equipment (Cable, Rack, Conduit, Steel, lighting, lightning, etc.) - Purchase & Packaging | [34 empty] | 0%
| PRWE-NONPROS-1050 | Electrical Equipment (Cable, Rack, Conduit, Steel, lighting, lightning, etc.) - Delivery to Site | [34 empty] | 0%
F4 |  |  |  | 100% | 0 | 0% | [30 empty] | 0%
| P3FH - 28 M.13.13.4.2 Road, Drainage, Parking Area & Retaining Wall | [35 empty] | 0%
| P3FH - 28 M.13.13.4.2.14 Electrical Equipment (Cable, Rack, Conduit, Steel, lighting, lightning, etc.) | [35 empty] | 0%
| PRWE-INFRAS-1000 | Electrical Equipment (Cable, Rack, Conduit, Steel, lighting, lightning, etc.) - RFQ | [34 empty] | 0%
| PRWE-INFRAS-1010 | Electrical Equipment (Cable, Rack, Conduit, Steel, lighting, lightning, etc.) - Received of Bids | [34 empty] | 0%
| PRWE-INFRAS-1020 | Electrical Equipment (Cable, Rack, Conduit, Steel, lighting, lightning, etc.) - TBE & CBE | [34 empty] | 0%
| PRWE-INFRAS-1030 | Electrical Equipment (Cable, Rack, Conduit, Steel, lighting, lightning, etc.) - PO | [34 empty] | 0%
| PRWE-INFRAS-1040 | Electrical Equipment (Cable, Rack, Conduit, Steel, lighting, lightning, etc.) - Purchase & Packaging | [34 empty] | 0%
| PRWE-INFRAS-1050 | Electrical Equipment (Cable, Rack, Conduit, Steel, lighting, lightning, etc.) - Delivery to Site | [34 empty] | 0%
F4 |  |  |  | 100% | 0 | 0% | [30 empty] | 0%
0%
| P3FH - 28 M. Instrumentation |  |  |  | 61695135600 | 1.803% | 0% | 0% | 0% | 0% | 0.01307% | 0.0072% | 0.06359% | 0% | 0.03735% | 0.00405% | 0% | 0.0369% | 0% | 0.0108% | 0.1453% | 0.0467% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.438%
| P3FH - 28 M.13.13.51.13.5.1 System 1 - Ore Preparation | [35 empty] | 0%
| P3FH - 28 M.13.13.51.13.5.1.13.5.1.1 Field Instrument | [35 empty] | 0%
| A2160 | PO | [34 empty] | 0%
| A2170 | Manufacturing | [34 empty] | 0%
| A2180 | Delivery | [34 empty] | 0%
F4 |  |  |  |  | 191941942.5 | 0.00561% | [30 empty] | 0.00561%
| P3FH - 28 M.13.13.51.13.5.1.13.5.1.2 PLC & DCS | [35 empty] | 0%
| A2190 | PO | [34 empty] | 0%
| A2200 | Manufacturing | [34 empty] | 0%
| A2210 | Delivery | [34 empty] | 0%
| P3FH - 28 M.13.13.51.13.5.2 System 2 - Electric Smelting Furnace | [35 empty] | 0%
B203 | P3FH - 28 M.13.13.51.13.5.2.13.5.2.1 PLC & DCS | [35 empty] | 0%
| A2220 | PO |  | 25% | 2326911142.5 | 0.06801% | 2017-08-14: 0.05441% | 0.0136%
| A2230 | Manufacturing |  | 60% | 5584107742.5 | 0.1632% | [30 empty] | 0.1632%
| A2240 | Delivery |  | 15% | 1395941400 | 0.0408% | [30 empty] | 0.0408%
F4 |  |  |  | 100% | 48071021.25 | 0.001405% | [30 empty] | 0.001405%
B200 | P3FH - 28 M.13.13.51.13.5.2.13.5.2.11 Field Devices | [35 empty] | 0%
| A2460 | PO |  | 25% | 3221271637.5 | 0.09415% | [30 empty] | 0.09415%
| A2470 | Manufacturing |  | 60% | 7730709787.5 | 0.2259% | [30 empty] | 0.2259%
| A2480 | Delivery |  | 15% | 1932762982.5 | 0.05649% | [30 empty] | 0.05649%
F4 |  |  |  | 100% | 48071021.25 | 0.001405% | [30 empty] | 0.001405%
B208 | P3FH - 28 M.13.13.51.13.5.2.13.5.2.111 Instrument & Control Cables | [35 empty] | 0%
| A2490 | PO |  | 25% | 1313485057.5 | 0.03839% | [30 empty] | 0.03839%
| A2500 | Manufacturing |  | 60% | 3152500995 | 0.09214% | [30 empty] | 0.09214%
| A2510 | Delivery |  | 15% | 788296320 | 0.02304% | [30 empty] | 0.02304%
F4 |  |  |  | 100% | 48071021.25 | 0.001405% | [30 empty] | 0.001405%
B201 | P3FH - 28 M.13.13.51.13.5.2.13.5.2.1111 Bulk Material | [35 empty] | 0%
| A2520 | PO |  | 25% | 3355733640 | 0.09808% | 2017-10-13: 0.01089%; 2018-01-11: 0.00253%; 2018-05-11: 0.0076% | 0.07706%
| A2530 | Manufacturing |  | 60% | 8054034450 | 0.2354% | [30 empty] | 0.2354%
| A2540 | Delivery |  | 15% | 2013508612.5 | 0.05885% | [30 empty] | 0.05885%
F4 |  |  |  | 100% | 48071021.25 | 0.001405% | [30 empty] | 0.001405%
| P3FH - 28 M.13.13.51.13.5.3 System 3 - Refinery | [35 empty] | 0%
B215 | P3FH - 28 M.13.13.51.13.5.3.2 PLC & DCS | [35 empty] | 0%
| A2550 | PLC & DCS - RFQ | [34 empty] | 0%
| A2551 | PLC & DCS - Received of Bids | [34 empty] | 0%
| A2552 | PLC & DCS - TBE | [34 empty] | 0%
| A2553 | PLC & DCS - CBE | [34 empty] | 0%
| A2554 | PLC & DCS - LOI | [34 empty] | 0%
| A2555 | PLC & DCS - PO |  | 20% | 447522390 | 0.01308% | 2017-06-15: 0.01307% | 1e-05%
| A2560 | PLC & DCS - Manufacturing |  | 60% | 1342225027.5 | 0.03923% | [30 empty] | 0.03923%
| A2570 | PLC & DCS - Delivery |  | 20% | 447522390 | 0.01308% | [30 empty] | 0.01308%
F4 |  |  |  | 100% | 48071021.25 | 0.001405% | [30 empty] | 0.001405%
B212 | P3FH - 28 M.13.13.51.13.5.3.1 Field Control Devices | [35 empty] | 0%
| A2250 | FIELD CONTROL DEVICES - RFQ | [34 empty] | 0%
| A2251 | FIELD CONTROL DEVICES - Received of Bids | [34 empty] | 0%
| A2252 | FIELD CONTROL DEVICES - TBE | [34 empty] | 0%
| A2253 | FIELD CONTROL DEVICES - CBE | [34 empty] | 0%
| A2254 | FIELD CONTROL DEVICES - LOI | [34 empty] | 0%
| A2255 | FIELD CONTROL DEVICES - PO |  | 20% | 232314757.5 | 0.00679% | 2017-07-15: 0.00679% | 0%
| A2260 | FIELD CONTROL DEVICES - Manufacturing |  | 60% | 696602130 | 0.02036% | [30 empty] | 0.02036%
| A2270 | FIELD CONTROL DEVICES - Delivery |  | 20% | 232314757.5 | 0.00679% | [30 empty] | 0.00679%
F4 |  |  |  | 100% | 48071021.25 | 0.001405% | [30 empty] | 0.001405%
B220 | P3FH - 28 M.13.13.51.13.5.3.3 Instrument & Control Cables | [35 empty] | 0%
| A2580 | INSTRUMENT & CONTROL CABLES - RFQ | [34 empty] | 0%
| A2581 | INSTRUMENT & CONTROL CABLES - Received of Bids | [34 empty] | 0%
| A2582 | INSTRUMENT & CONTROL CABLES - TBE | [34 empty] | 0%
| A2583 | INSTRUMENT & CONTROL CABLES - CBE | [34 empty] | 0%
| A2584 | INSTRUMENT & CONTROL CABLES - LOI | [34 empty] | 0%
| A2585 | INSTRUMENT & CONTROL CABLES - PO |  | 20% | 138567712.5 | 0.00405% | 2017-11-12: 0.00405% | 0%
| A2590 | INSTRUMENT & CONTROL CABLES - Manufacturing |  | 60% | 416387422.5 | 0.01217% | [30 empty] | 0.01217%
| A2600 | INSTRUMENT & CONTROL CABLES - Delivery |  | 20% | 138567712.5 | 0.00405% | [30 empty] | 0.00405%
F4 |  |  |  | 100% | 48071021.25 | 0.001405% | [30 empty] | 0.001405%
B213 | P3FH - 28 M.13.13.51.13.5.3.4 Bulk Materials | [35 empty] | 0%
| A2611 | BULK MATERIAL - RFQ | [34 empty] | 0%
| A2612 | BULK MATERIAL - Receieved Bids | [34 empty] | 0%
| A2613 | BULK MATERIAL - TBE | [34 empty] | 0%
| A2614 | BULK MATERIAL - CBE | [34 empty] | 0%
| A2615 | BULK MATERIAL - LOI | [34 empty] | 0%
| A2616 | BULK MATERIAL - PO |  | 20% | 1031901780 | 0.03016% | 2017-07-15: 0.00041%; 2017-10-13: 0.01557%; 2018-01-11: 0.00338%; 2018-03-12: 0.0108% | 0%
| A2620 | BULK MATERIAL - Manufacturing |  | 60% | 3095363197.5 | 0.09047% | 2018-04-11: 0.03241%; 2018-05-11: 0.01013% | 0.04793%
| A2630 | BULK MATERIAL - Delivery |  | 20% | 1031901780 | 0.03016% | [30 empty] | 0.03016%
F4 |  |  |  | 100% | 48071021.25 | 0.001405% | [30 empty] | 0.001405%
| P3FH - 28 M.13.13.51.13.5.4 System 4 - Utility Supply | [35 empty] | 0%
B227 | P3FH - 28 M.13.13.51.13.5.4.1 PLC & DCS | [35 empty] | 0%
| A2280 | PLC & DCS - RFQ & Received of Bids | [34 empty] | 0%
| A2281 | PLC & DCS - TBE & CBE | [34 empty] | 0%
| A2282 | PLC & DCS - LOI | [34 empty] | 0%
| A2283 | PLC & DCS - PO |  | 20% | 314086815 | 0.00918% | 2017-08-14: 0.00918% | 0%
| A2290 | PLC & DCS - Manufacturing |  | 60% | 942260445 | 0.02754% | 2018-04-11: 0.02754% | 0%
| A2300 | PLC & DCS - Delivery |  | 20% | 314086815 | 0.00918% | [30 empty] | 0.00918%
F4 |  |  |  | 100% | 48071021.25 | 0.001405% | [30 empty] | 0.001405%
B224 | P3FH - 28 M.13.13.51.13.5.4.2 Field Devices | [35 empty] | 0%
| A2310 | FIELD DEVICE - RFQ & Recieved of Bids | [34 empty] | 0%
| A2311 | FIELD DEVICE - TBE & CBE | [34 empty] | 0%
| A2312 | FIELD DEVICE - LOI | [34 empty] | 0%
| A2313 | FIELD DEVICE - PO |  | 20% | 310323247.5 | 0.00907% | [30 empty] | 0.00907%
| A2320 | FIELD DEVICE - Manufacturing |  | 60% | 930969742.5 | 0.02721% | [30 empty] | 0.02721%
| A2330 | FIELD DEVICE - Delivery |  | 20% | 310323247.5 | 0.00907% | [30 empty] | 0.00907%
F4 |  |  |  | 100% | 48071021.25 | 0.001405% | [30 empty] | 0.001405%
B232 | P3FH - 28 M.13.13.51.13.5.4.3 Instrument & Control Cables | [35 empty] | 0%
| A2340 | INSTRUMENT & CONTROL CABLES - RFQ & Received of Bids | [34 empty] | 0%
| A2341 | INSTRUMENT & CONTROL CABLES - TBE & CBE | [34 empty] | 0%
| A2342 | INSTRUMENT & CONTROL CABLES - LOI | [34 empty] | 0%
| A2343 | INSTRUMENT & CONTROL CABLES - PO |  | 20% | 59874937.5 | 0.00175% | [30 empty] | 0.00175%
| A2350 | INSTRUMENT & CONTROL CABLES - Manufacturing |  | 60% | 179624812.5 | 0.00525% | [30 empty] | 0.00525%
| A2360 | INSTRUMENT & CONTROL CABLES - Delivery |  | 20% | 59874937.5 | 0.00175% | [30 empty] | 0.00175%
F4 |  |  |  | 100% | 48071021.25 | 0.001405% | [30 empty] | 0.001405%
B225 | P3FH - 28 M.13.13.51.13.5.4.4 Bulk Material | [35 empty] | 0%
| A2370 | BULK MATERIAL - Received of Bids | [34 empty] | 0%
| A2371 | BULK MATERIAL - CBE | [34 empty] | 0%
| A2372 | BULK MATERIAL - LOI | [34 empty] | 0%
| A2373 | BULK MATERIAL - PO |  | 20% | 1477029172.5 | 0.04317% | 2017-10-13: 0.01089%; 2018-01-11: 0.03099% | 0.00129%
| A2380 | BULK MATERIAL - Manufacturing |  | 60% | 4430403232.5 | 0.1295% | 2018-04-11: 0.08539%; 2018-05-11: 0.02897% | 0.01513%
| A2390 | BULK MATERIAL - Delivery |  | 20% | 1477029172.5 | 0.04317% | [30 empty] | 0.04317%
F4 |  |  |  | 100% | 48071021.25 | 0.001405% | [30 empty] | 0.001405%
| P3FH - 28 M.13.13.51.1 Non Process Building | [35 empty] | 0%
| P3FH - 28 M.13.13.51.1.14 CCTV, etc | [35 empty] | 0%
| A2400 | CCTV - RFQ | [34 empty] | 0%
| A2410 | CCTV - Received of Bids | [34 empty] | 0%
| A2420 | CCTV - TBE & CBE | [34 empty] | 0%
| A2430 | CCTV - PO |  | 20% | 0 | 0% | [30 empty] | 0%
| A2450 | CCTV - Purchase & Packaging |  | 60% | 0 | 0% | [30 empty] | 0%
| A24600 | CCTV - Delivery to Site |  | 20% | 0 | 0% | [30 empty] | 0%
0%
0%
| P3FH - 28 M. Construction |  |  |  | 506591581912.5008 | 14.81% | 0.05642% | 0.05641% | 0.0343% | 0.07988% | 0.09425% | 0.4493% | 0.3213% | 0.1703% | 0.2546% | 0.1211% | 0.1923% | 0.1584% | 0.1249% | 0.2988% | 0.2666% | 0.58% | 0.1272% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.42%
| P3FH - 28 M. Civil Work |  |  |  | 115503886575 | 3.376% | 0.02212% | 0.02211% | 0% | 0.04558% | 0.05995% | 0.1063% | 0.2832% | 0.1324% | 0.06216% | 0.105% | 0.1762% | 0.1423% | 0.1088% | 0.1343% | 0.1736% | 0.1318% | 0.1272% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.543%
C361 | GENR1000 | Soil Investigation & Topography Survey |  | 100% | 1513296277.5 | 0.04423% | 2017-02-15: 0.02212%; 2017-03-17: 0.02211%; 2018-06-10: 0.1272% | -0.1272%
C355 |  |  |  | 100% | 1926604417.5 | 0.05631% | 2017-06-15: 0.0079%; 2017-07-15: 0.00337%; 2017-09-13: 0.00396%; 2017-10-13: 0.00168%; 2017-12-12: 0.01126%; 2018-02-10: 0.01407%; 2018-03-12: 0.00563%; 2018-05-11: 0.00479% | 0.00365%
C364 |  |  |  | 100% | 799244880 | 0.02336% | 2018-03-12: 0.00036%; 2018-04-11: 0.00074%; 2018-05-11: 0.00012% | 0.02214%
| P3FH - 28 M.14.1.1 Batching Plant | [35 empty] | 0%
| GENR1020 | Foundation | [34 empty] | 0%
| GENR1030 | Erection & Installation M/E/I | [34 empty] | 0%
| GENR1040 | Test & Commissioning | [34 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1 System 1 - Ore Preparation | [35 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.1 Ore Receiving Equipment | [35 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.1.3 Ore Receiving Yard (Piling) | [35 empty] | 0%
C419 | CONC1000 | ORE RECEIVING EQ. - Piling | [34 empty] | 0%
| RAW ORE STORAGE PILING | Tranport Material to site |  | 10% | 160122690 | 0.00468% | 2017-07-15: 0.00468% | 0%
| RAW ORE STORAGE PILING | Install and Final Inspection |  | 90% | 1441446352.5 | 0.04213% | 2017-07-15: 0.04213% | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.1.1 Ore Receiving Yard (RC Construction) | [35 empty] | 0%
| CONC2730 | Foundation (Wall & Foundation) | [34 empty] | 0%
C420 | RAW ORE STORAGE REBAR | Tranport Material to site |  | 10% | 275424712.5 | 0.00805% | 2017-10-13: 0.00805% | 0%
| RAW ORE STORAGE REBAR | Install and Final Inspection |  | 90% | 2479164555 | 0.07246% | 2017-10-13: 0.00621%; 2017-11-12: 0.01119%; 2017-12-12: 0.01807%; 2018-01-11: 0.00983%; 2018-02-10: 0.00484%; 2018-03-12: 0.00945%; 2018-04-11: 0.00451%; 2018-05-11: 0.00812% | 0.00024%
0%
C421 | RAW ORE STORAGE CONCRETE | Tranport Material to site |  | 10% | 66717787.5 | 0.00195% | 2017-10-13: 0.00195% | 0%
| RAW ORE STORAGE CONCRETE | Install and Final Inspection |  | 90% | 600460087.5 | 0.01755% | 2017-10-13: 0.00149%; 2017-11-12: 0.00195%; 2017-12-12: 0.00383%; 2018-01-11: 0.00246%; 2018-02-10: 0.00122%; 2018-03-12: 0.00219%; 2018-04-11: 0.00185%; 2018-05-11: 0.00244% | 0.00012%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.1.2 Ore Receiving Yard (Steel Structure) | [35 empty] | 0%
C422 | CONC1010 | Ore Storage Yard (SS) | [34 empty] | 0%
| CONC1020 | Ore Storage Yard (Roof & Siding) | [34 empty] | 0%
| RAW ORE STORAGE STEEL STRUCTURE & ROOF SIDING | Transport material to site |  | 10% | 380120317.5 | 0.01111% | [30 empty] | 0.01111%
| RAW ORE STORAGE STEEL STRUCTURE & ROOF SIDING | Check elevation & orientation |  | 20% | 759898492.5 | 0.02221% | [30 empty] | 0.02221%
| RAW ORE STORAGE STEEL STRUCTURE & ROOF SIDING | Pre-assembly on the ground |  | 10% | 380120317.5 | 0.01111% | [30 empty] | 0.01111%
| RAW ORE STORAGE STEEL STRUCTURE & ROOF SIDING | Installation |  | 40% | 1519454842.5 | 0.04441% | [30 empty] | 0.04441%
| RAW ORE STORAGE STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 20% | 759898492.5 | 0.02221% | [30 empty] | 0.02221%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.2 Ore Drying Equipment & Gas Treatment | [35 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.2.2 Drying Building (Piling) | [35 empty] | 0%
C424 | CONC1030 | ORE DRYING & GAS TREATMENT - Piling | [34 empty] | 0%
| ORE DRYING EQUIPMENT & ORE SIZING EQUPMENT PILES | Tranport Material to site |  | 10% | 83140627.5 | 0.00243% | 2017-06-15: 0.00209%; 2017-07-15: 0.00034% | 0%
| ORE DRYING EQUIPMENT & ORE SIZING EQUPMENT PILES | Install and Final Inspection |  | 90% | 748949932.5 | 0.02189% | 2017-06-15: 0.01885%; 2017-07-15: 0.00304%; 2018-03-12: 0.00019% | -0.00019%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.2.1 Drying Building (RC Foundation) | [35 empty] | 0%
| CONC1040 | Drying Building (RC/Mech Foundation) | [34 empty] | 0%
C425 | ORE DRYING EQUIPMENT & ORE SIZING EQUPMENT REBAR | Tranport Material to site |  | 10% | 73218495 | 0.00214% | 2017-08-14: 0.00214% | 0%
| ORE DRYING EQUIPMENT & ORE SIZING EQUPMENT REBAR | Install and Final Inspection |  | 90% | 657597885 | 0.01922% | 2017-08-14: 0.00085%; 2017-10-13: 3.82e-05; 2017-11-12: 2.44e-05; 2017-12-12: 0.00229%; 2018-01-11: 0.00426%; 2018-02-10: 0.00142%; 2018-03-12: 0.00053%; 2018-04-11: 8e-05%; 2018-05-11: 9e-05% | 0.00344%
0%
C426 | ORE DRYING EQUIPMENT & ORE SIZING EQUPMENT CONCRETE | Tranport Material to site |  | 10% | 25318545 | 0.00074% | 2017-10-13: 0.00074% | 0%
| ORE DRYING EQUIPMENT & ORE SIZING EQUPMENT CONCRETE | Install and Final Inspection |  | 90% | 226840477.5 | 0.00663% | 2017-10-13: 2.8e-06; 2017-11-12: 7.1e-06; 2017-12-12: 0.00111%; 2018-01-11: 0.00167%; 2018-02-10: 0.00012%; 2018-04-11: 0.0003%; 2018-05-11: 0.0004% | 0.00204%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.2.14.2.1.2.3 Drying Building (SS) | [35 empty] | 0%
| CONC1120 | DRYING BUILDING(SS) - Duct Support Tower | [34 empty] | 0%
| CONC1130 | DRYING BUILDING(SS) - Exhaust Fan Duct Support | [34 empty] | 0%
| CONC1050 | DRYING BUILDING(SS) - Truss Walkway , Stair | [34 empty] | 0%
| CONC1140 | DRYING BUILDING(SS) - Fuel Oil Pump Roof | [34 empty] | 0%
| CONC1060 | DRYING BUILDING(SS) - Walkway from EP to Stack | [34 empty] | 0%
| CONC1070 | DRYING BUILDING(SS) - Drive Device Roof | [34 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.2.14.2.1.2.3.14.2.1.2.3.4 Dryer Inlet Side | [35 empty] | 0%
| CONC1080 | DRYER INLET SIDE - SS GL+5m, 8.75m, 9m, 11.33m | [34 empty] | 0%
| CONC1090 | DRYER INLET SIDE - SS GL+19m | [34 empty] | 0%
| CONC1100 | DRYER INLET SIDE - GL+23.1m, 27.6m, Roof, Siding | [34 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.2.14.2.1.2.3.14.2.1.2.3.5 Dryer Outlet Side | [35 empty] | 0%
C427 | CONC1110 | DRYER OUTLET SIDE - SS GL +3.5m, 8m | [34 empty] | 0%
| ORE DRYING EQUIPMENT & ORE SIZING EQUPMENT STEEL STRUCTURE & ROOF SIDING | Transport material to site |  | 10% | 191257657.5 | 0.00559% | [30 empty] | 0.00559%
| ORE DRYING EQUIPMENT & ORE SIZING EQUPMENT STEEL STRUCTURE & ROOF SIDING | Check elevation & orientation |  | 20% | 382515315 | 0.01118% | [30 empty] | 0.01118%
| ORE DRYING EQUIPMENT & ORE SIZING EQUPMENT STEEL STRUCTURE & ROOF SIDING | Pre-assembly on the ground |  | 10% | 191257657.5 | 0.00559% | [30 empty] | 0.00559%
| ORE DRYING EQUIPMENT & ORE SIZING EQUPMENT STEEL STRUCTURE & ROOF SIDING | Installation |  | 40% | 765714915 | 0.02238% | [30 empty] | 0.02238%
| ORE DRYING EQUIPMENT & ORE SIZING EQUPMENT STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 20% | 382515315 | 0.01118% | [30 empty] | 0.01118%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.3 Dryer EP Dust Bin Room | [35 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.3.1 Dust Bin Room (Piling) | [35 empty] | 0%
| CONC1150 | DRYER EP DUST BIN ROOM - Piling | [34 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.3.2 Dust Bin Room (RC Foundation) | [35 empty] | 0%
| CONC1160 | DRYER EP DUST BIN ROOM - RC Foundation | [34 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.3.14.2.1.3.3 Dust Bin Room (SS) | [35 empty] | 0%
| CONC1170 | DUST BIN ROOM (SS) - GL+4.3m | [34 empty] | 0%
| CONC1180 | DUST BIN ROOM (SS) - GL+7.3m | [34 empty] | 0%
| CONC1190 | DUST BIN ROOM (SS) - Roof & Siding | [34 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.4 Pulverized Coal Feeding for Dryer | [35 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.4.1 PULVERIZED COAL FEEDING FOR DRYER (RC Foundation) | [35 empty] | 0%
| CONC1200 | Pulverized Coal Feeding for Dryer (RC Foundation) | [34 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.4.14.2.1.4.2 PULVERIZED COAL FEEDING FOR DRYER (SS) | [35 empty] | 0%
| CONC1210 | PV COAL FEEDING (SS) - GL+4.0m, +8.8m | [34 empty] | 0%
| CONC1220 | PV COAL FEEDING (SS) - GL+13m | [34 empty] | 0%
| CONC1230 | PV COAL FEEDING (SS) - Roof & Siding | [34 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.5 Conditioned Ore Storage & Transport Conditioned Ore | [35 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.5.3 CONDITIONED ORE STORAGE &TRANSPORT (SS) | [35 empty] | 0%
| CONC1250 | CONDITIONED ORE STORAGE & TRANSPORT (Steel Structure) | [34 empty] | 0%
C432 | CONC1260 | Roof & Siding | [34 empty] | 0%
| CONDITIONED ORE STORAGE STEEL STRUCTURE & ROOF SIDING | Transport material to site |  | 10% | 159780547.5 | 0.00467% | [30 empty] | 0.00467%
| CONDITIONED ORE STORAGE STEEL STRUCTURE & ROOF SIDING | Check elevation & orientation |  | 20% | 319561095 | 0.00934% | 2018-05-11: 0.00654% | 0.0028%
| CONDITIONED ORE STORAGE STEEL STRUCTURE & ROOF SIDING | Pre-assembly on the ground |  | 10% | 159780547.5 | 0.00467% | [30 empty] | 0.00467%
| CONDITIONED ORE STORAGE STEEL STRUCTURE & ROOF SIDING | Installation |  | 40% | 638780047.5 | 0.01867% | [30 empty] | 0.01867%
| CONDITIONED ORE STORAGE STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 20% | 319561095 | 0.00934% | [30 empty] | 0.00934%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.5.1 CONDITIONED ORE STORAGE &TRANSPORT (Piling) | [35 empty] | 0%
C429 | CONC1240 | CONDITIONED ORE STORAGE & TRANSPORT (Piling) | [34 empty] | 0%
| CONDITIONED ORE STORAGE PILES | Tranport Material to site |  | 10% | 40714957.5 | 0.00119% | 2017-08-14: 0.00119% | 0%
| CONDITIONED ORE STORAGE PILES | Install and Final Inspection |  | 90% | 367803187.5 | 0.01075% | 2017-08-14: 0.01075% | 1.228e-08%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.5.2 CONDITIONED ORE STORAGE &TRANSPORT (RC Cons.) | [35 empty] | 0%
| CONC1241 | CONDITIONED ORE STORAGE & TRANSPORT (RC/Mech. Foundation) | [34 empty] | 0%
C430 | CONDITIONED ORE STORAGE REBAR | Tranport Material to site |  | 10% | 97510612.5 | 0.00285% | 2017-09-13: 0.00285% | 0%
| CONDITIONED ORE STORAGE REBAR | Install and Final Inspection |  | 90% | 876569085 | 0.02562% | 2017-09-13: 9.2e-06; 2017-10-13: 2.9e-06; 2017-11-12: 1.5e-06; 2017-12-12: 0.00596%; 2018-01-11: 0.01186%; 2018-02-10: 0.0081%; 2018-03-12: 0.00168%; 2018-05-11: 0.00042% | -0.00376%
0%
C431 | CONDITIONED ORE STORAGE CONCRETE | Tranport Material to site |  | 10% | 23607832.5 | 0.00069% | 2017-09-13: 0.00069% | 0%
| CONDITIONED ORE STORAGE CONCRETE | Install and Final Inspection |  | 90% | 212470492.5 | 0.00621% | 2017-09-13: 0.0008%; 2017-10-13: 7e-05%; 2017-11-12: 4e-05%; 2017-12-12: 0.00132%; 2018-01-11: 0.00266%; 2018-02-10: 0.00156%; 2018-03-12: 0.00116%; 2018-05-11: 0.0001% | -0.0015%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.6 Ore Mixing Equipment | [35 empty] | 0%
C434 | CONC1270 | ORE MIXING EQUIPMENT - Piling | [34 empty] | 0%
| CONDITIONED ORE STORAGE PILES | Tranport Material to site |  | 10% | 102642750 | 0.003% | 2017-08-14: 0.03001% | -0.02701%
| CONDITIONED ORE STORAGE PILES | Install and Final Inspection |  | 90% | 924126892.5 | 0.02701% | [30 empty] | 0.02701%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.6.14.2.1.6.2 Reductant Coal Storage Yard | [35 empty] | 0%
C454 | CONC1280 | Reductant Coal Storage Yard (RC) | [34 empty] | 0%
|  | Tranport Material to site |  | 10% | [32 empty] | 0%
|  | Install and Final Inspection |  | 90% | [32 empty] | 0%
0%
C455 | REDUCTANT COAL STORAGE REBAR | Tranport Material to site |  | 10% | 62269935 | 0.00182% | 2017-12-12: 0.00182% | 0%
| REDUCTANT COAL STORAGE REBAR | Install and Final Inspection |  | 90% | 559060845 | 0.01634% | 2017-12-12: 0.00394%; 2018-01-11: 0.00988%; 2018-02-10: 0.00202%; 2018-03-12: 0.00051% | -1e-05%
0%
C456 | REDUCTANT COAL STORAGE CONCRETE | Tranport Material to site |  | 10% | 15054270 | 0.00044% | 2017-12-12: 0.00044% | 0%
| REDUCTANT COAL STORAGE CONCRETE | Install and Final Inspection |  | 90% | 135488430 | 0.00396% | 2017-12-12: 0.00088%; 2018-01-11: 0.00229%; 2018-02-10: 0.00058%; 2018-03-12: 0.00021% | 0%
| CONC1290 | Reductant Coal Storage Yard (SS) | [34 empty] | 0%
C457 | CONC1300 | Reductant Coal Storage Yard (Roof & Siding) | [34 empty] | 0%
| REDUCTANT COAL STORAGE STEEL STRUCTURE & ROOF SIDING | Transport material to site |  | 10% | 161833402.5 | 0.00473% | 2018-03-12: 0.00473% | 0%
| REDUCTANT COAL STORAGE STEEL STRUCTURE & ROOF SIDING | Check elevation & orientation |  | 20% | 323666805 | 0.00946% | 2018-03-12: 0.001014%; 2018-04-11: 0.008446% | 0%
| REDUCTANT COAL STORAGE STEEL STRUCTURE & ROOF SIDING | Pre-assembly on the ground |  | 10% | 161833402.5 | 0.00473% | [30 empty] | 0.00473%
| REDUCTANT COAL STORAGE STEEL STRUCTURE & ROOF SIDING | Installation |  | 40% | 646649325 | 0.0189% | 2018-04-11: 0.006854%; 2018-05-11: 0.00606% | 0.005986%
| REDUCTANT COAL STORAGE STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 20% | 323666805 | 0.00946% | [30 empty] | 0.00946%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.6.14.2.1.6.3 Mixing Building | [35 empty] | 0%
| CONC1310 | Mixing Building (RC) | [34 empty] | 0%
C435 | ORE MIXING EQUIPMENT & DUST TREATMENT EQUIPMENT REBAR | Tranport Material to site |  | 10% | 46189237.5 | 0.00135% | 2017-11-12: 0.00094%; 2017-12-12: 0.00041% | 0%
| ORE MIXING EQUIPMENT & DUST TREATMENT EQUIPMENT REBAR | Install and Final Inspection |  | 90% | 417071707.5 | 0.01219% | 2017-12-12: 0.00175%; 2018-01-11: 0.00332%; 2018-02-10: 0.00446%; 2018-03-12: 0.00242%; 2018-05-11: 0.00024% | 0%
0%
C436 | ORE MIXING EQUIPMENT & DUST TREATMENT EQUIPMENT CONCRETE | Tranport Material to site |  | 10% | 12317130 | 0.00036% | 2017-11-12: 6e-05%; 2017-12-12: 0.0003% | 0%
| ORE MIXING EQUIPMENT & DUST TREATMENT EQUIPMENT CONCRETE | Install and Final Inspection |  | 90% | 109827742.5 | 0.00321% | 2017-12-12: 0.00033%; 2018-01-11: 0.00093%; 2018-02-10: 0.00077%; 2018-03-12: 0.00112%; 2018-05-11: 8e-05% | -2e-05%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.6.14.2.1.6.3.14.2.1.6.3.2 Mixing Building (SS) | [35 empty] | 0%
| CONC1320 | MIXING BUILDING (SS) - GL+3.0m,+6.0m,+9.0m | [34 empty] | 0%
| CONC1330 | MIXING BUILDING (SS) - GL+13.0m,+15.5m | [34 empty] | 0%
| CONC1340 | MIXING BUILDING (SS) - GL+18.0m,+21.0m, upper | [34 empty] | 0%
C437 | CONC1350 | Mixing Building (Roof & Siding) | [34 empty] | 0%
| ORE MIXING EQUIPMENT & DUST TREATMENT EQUIPMENT STEEL STRUCTURE & ROOF SIDING | Transport material to site |  | 10% | 292531837.5 | 0.00855% | [30 empty] | 0.00855%
| ORE MIXING EQUIPMENT & DUST TREATMENT EQUIPMENT STEEL STRUCTURE & ROOF SIDING | Check elevation & orientation |  | 20% | 584721532.5 | 0.01709% | [30 empty] | 0.01709%
| ORE MIXING EQUIPMENT & DUST TREATMENT EQUIPMENT STEEL STRUCTURE & ROOF SIDING | Pre-assembly on the ground |  | 10% | 292531837.5 | 0.00855% | [30 empty] | 0.00855%
| ORE MIXING EQUIPMENT & DUST TREATMENT EQUIPMENT STEEL STRUCTURE & ROOF SIDING | Installation |  | 40% | 1169785207.5 | 0.03419% | [30 empty] | 0.03419%
| ORE MIXING EQUIPMENT & DUST TREATMENT EQUIPMENT STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 20% | 584721532.5 | 0.01709% | [30 empty] | 0.01709%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.7 Dust Briquetting Equipment | [35 empty] | 0%
| CONC1360 | DUST BRIQUETTING BUILDING - Piling | [34 empty] | 0%
| CONC1370 | DUST BRIQUETTING BUILDING - RC | [34 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.7.14.2.1.7.3 Briquetting Building (SS) | [35 empty] | 0%
| CONC1380 | BRIQUETTING BUILDING (SS) - GL+7.5m,+11.5m, 12m | [34 empty] | 0%
| CONC1390 | BRIQUETTING BUILDING (SS) - GL+17m | [34 empty] | 0%
| CONC1400 | BRIQUETTING BUILDING (SS) - GL+21.5m | [34 empty] | 0%
| CONC1410 | BRIQUETTING BUILDING (SS) - Roof | [34 empty] | 0%
| CONC1420 | BRIQUETTING BUILDING (SS) - Roof & Siding | [34 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.8 Rotary Kiln Equipment | [35 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.8.14.2.1.8.1 Kiln Foundation | [35 empty] | 0%
C439 | CONC1430 | KILN FOUNDATION - Piling | [34 empty] | 0%
| ROTARY KILN & EXHAUST GAS TREATMENT EQUIPMENT PLIES | Tranport Material to site |  | 10% | 237789037.5 | 0.00695% | 2017-05-16: 0.004561%; 2017-06-15: 0.002389% | 0%
| ROTARY KILN & EXHAUST GAS TREATMENT EQUIPMENT PLIES | Install and Final Inspection |  | 90% | 2138390625 | 0.0625% | 2017-05-16: 0.04102%; 2017-06-15: 0.02148% | 0%
| CONC1440 | RC/Kiln Foundation | [34 empty] | 0%
C440 | ROTARY KILN & EXHAUST GAS TREATMENT EQUIPMENT REBAR | Tranport Material to site |  | 10% | 245316172.5 | 0.00717% | 2017-07-15: 0.00287%; 2017-08-14: 0.0043% | 0%
| ROTARY KILN & EXHAUST GAS TREATMENT EQUIPMENT REBAR | Install and Final Inspection |  | 90% | 2206476982.5 | 0.06449% | 2017-08-14: 0.00318%; 2017-09-13: 8.01e-05; 2017-10-13: 3.1e-05; 2017-11-12: 0.0001465; 2017-12-12: 0.00907%; 2018-01-11: 0.01538%; 2018-02-10: 0.01009%; 2018-03-12: 0.00014% | 0.00087%
0%
C441 | ROTARY KILN & EXHAUST GAS TREATMENT EQUIPMENT CONCRETE | Tranport Material to site |  | 10% | 84509197.5 | 0.00247% | 2017-08-14: 0.00247% | 0%
| ROTARY KILN & EXHAUST GAS TREATMENT EQUIPMENT CONCRETE | Install and Final Inspection |  | 90% | 761609205 | 0.02226% | 2017-08-14: 0.00229%; 2017-09-13: 1.28e-05; 2017-10-13: 1.35e-05; 2017-11-12: 5.06e-05; 2017-12-12: 0.00232%; 2018-01-11: 0.00552%; 2018-02-10: 0.00407%; 2018-03-12: 0.00018% | 0.00019%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.8.14.2.1.8.2 Burner Floor (GL+11.0m) | [35 empty] | 0%
| CONC1450 | BURNER FLOOR - Piling | [34 empty] | 0%
| CONC1460 | Burner Floor (GL+11.0m) | [34 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.8.14.2.1.8.3 Building Work for Kiln | [35 empty] | 0%
| CONC1470 | BUILDING WORK FOR KILN - Walk way & Stair | [34 empty] | 0%
| CONC1510 | Oil Pump unit Roof | [34 empty] | 0%
| CONC1500 | Drive Device Roof | [34 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.8.14.2.1.8.3.14.2.1.8.3.2 Kiln Shell Roof | [35 empty] | 0%
| CONC1480 | KILN SHELL ROOF - Steel Structure, 9m Floor | [34 empty] | 0%
C442 | CONC1490 | Roof | [34 empty] | 0%
| ROTARY KILN & EXHAUST GAS TREATMENT EQUIPMENT STEEL STRUCTURE & ROOF SIDING | Transport material to site |  | 10% | 602855085 | 0.01762% | [30 empty] | 0.01762%
| ROTARY KILN & EXHAUST GAS TREATMENT EQUIPMENT STEEL STRUCTURE & ROOF SIDING | Check elevation & orientation |  | 20% | 1205368027.5 | 0.03523% | [30 empty] | 0.03523%
| ROTARY KILN & EXHAUST GAS TREATMENT EQUIPMENT STEEL STRUCTURE & ROOF SIDING | Pre-assembly on the ground |  | 10% | 602855085 | 0.01762% | [30 empty] | 0.01762%
| ROTARY KILN & EXHAUST GAS TREATMENT EQUIPMENT STEEL STRUCTURE & ROOF SIDING | Installation |  | 40% | 2410736055 | 0.07046% | [30 empty] | 0.07046%
| ROTARY KILN & EXHAUST GAS TREATMENT EQUIPMENT STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 20% | 1205368027.5 | 0.03523% | [30 empty] | 0.03523%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.9 Scoop Feeder House | [35 empty] | 0%
| CONC1520 | Scoop Feeder Charge House | [34 empty] | 0%
| CONC1530 | Belt Conveyor | [34 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.9.14.2.1.9.3 Scoop Feeder Charge House (Hopper) SS | [35 empty] | 0%
| CONC1540 | Steel Structure | [34 empty] | 0%
| CONC1550 | Roof, Siding | [34 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.10 Exhaust Gas Treatment Equipment | [35 empty] | 0%
C459 | CONC1560 | Piling | [34 empty] | 0%
| BELT CONVEYOR / TRANSFER TOWER, GIRDER & SUPPORT PILES | Tranport Material to site |  | 0.1 | 122487015 | 0.00358% | 2017-08-14: 0.00358% | 0%
| BELT CONVEYOR / TRANSFER TOWER, GIRDER & SUPPORT PILES | Install and Final Inspection |  | 0.9 | 1103067420 | 0.03224% | 2017-08-14: 0.03224% | 3.683e-08%
| CONC1570 | Exhaust Gas Treatment Equipment (RC/Mech Foundation) | [34 empty] | 0%
C460 | BELT CONVEYOR / TRANSFER TOWER, GIRDER & SUPPORT REBAR | Tranport Material to site |  | 0.1 | 62269935 | 0.00182% | 2017-12-12: 0.00182% | 0%
| BELT CONVEYOR / TRANSFER TOWER, GIRDER & SUPPORT REBAR | Install and Final Inspection |  | 0.9 | 559060845 | 0.01634% | 2017-12-12: 0.00187%; 2018-01-11: 0.00738%; 2018-02-10: 0.00495%; 2018-03-12: 0.00134%; 2018-05-11: 0.00059% | 0.00021%
0%
C461 | BELT CONVEYOR / TRANSFER TOWER, GIRDER & SUPPORT CONCRETE | Tranport Material to site |  | 0.1 | 16422840 | 0.00048% | 2017-12-12: 0.00048% | 0%
| BELT CONVEYOR / TRANSFER TOWER, GIRDER & SUPPORT CONCRETE | Install and Final Inspection |  | 0.9 | 147121275 | 0.0043% | 2017-12-12: 0.00043%; 2018-01-11: 0.00181%; 2018-02-10: 0.00116%; 2018-03-12: 0.00039%; 2018-05-11: 0.00026% | 0.00025%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.10.14.2.1.10.3 Exhaust Gas Treatment Equipment (SS) | [35 empty] | 0%
| CONC1580 | GL+7.5m, +15.5m | [34 empty] | 0%
| CONC1590 | GL+7.0m, +7.5m, +12.5m | [34 empty] | 0%
| CONC1640 | GL2+7.0m,+12.5m (Dust Bin) | [34 empty] | 0%
| CONC1660 | Support (Chain Conveyor N1713, N1724) | [34 empty] | 0%
| CONC1670 | Support (Duct Support N1703 Fan) | [34 empty] | 0%
| CONC1600 | Floor +20.4m | [34 empty] | 0%
| CONC1610 | GL+25.5m, Roof | [34 empty] | 0%
| CONC1620 | GL+12.5m - Roof | [34 empty] | 0%
| CONC1650 | GL2+7.0m,+12.5m (Roof) | [34 empty] | 0%
| CONC1630 | Roof & Siding | [34 empty] | 0%
C462 | CONC1680 | Walkway EP - Stack | [34 empty] | 0%
| BELT CONVEYOR / TRANSFER TOWER, GIRDER & SUPPORT STEEL STRUCTURE & ROOF SIDING | Transport material to site |  | 10% | 392095305 | 0.01146% | 2018-04-11: 0.00019% | 0.01127%
| BELT CONVEYOR / TRANSFER TOWER, GIRDER & SUPPORT STEEL STRUCTURE & ROOF SIDING | Check elevation & orientation |  | 20% | 783848467.5 | 0.02291% | [30 empty] | 0.02291%
| BELT CONVEYOR / TRANSFER TOWER, GIRDER & SUPPORT STEEL STRUCTURE & ROOF SIDING | Pre-assembly on the ground |  | 10% | 392095305 | 0.01146% | [30 empty] | 0.01146%
| BELT CONVEYOR / TRANSFER TOWER, GIRDER & SUPPORT STEEL STRUCTURE & ROOF SIDING | Installation |  | 40% | 1567696935 | 0.04582% | [30 empty] | 0.04582%
| BELT CONVEYOR / TRANSFER TOWER, GIRDER & SUPPORT STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 20% | 783848467.5 | 0.02291% | [30 empty] | 0.02291%
0%
0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.11 Coal Firing Equipment (Storage) | [35 empty] | 0%
| CONC1690 | RC/ Mech. Foundation | [34 empty] | 0%
C445 | COAL FIRING EQUIPMENT REBAR | Tranport Material to site |  | 10% | 38662102.5 | 0.00113% | 2018-01-11: 0.00113% | 0%
| COAL FIRING EQUIPMENT REBAR | Install and Final Inspection |  | 90% | 347274637.5 | 0.01015% | 2018-01-11: 0.00391%; 2018-03-12: 0.00465%; 2018-04-11: 0.00084%; 2018-05-11: 0.00074% | 1e-05%
0%
C446 | COAL FIRING EQUIPMENT CONCRETE | Tranport Material to site |  | 10% | 10264275 | 0.0003% | 2017-12-12: 8e-05%; 2018-01-11: 0.00022% | 0%
| COAL FIRING EQUIPMENT CONCRETE | Install and Final Inspection |  | 90% | 91352047.5 | 0.00267% | 2018-01-11: 0.00075%; 2018-03-12: 0.00151%; 2018-04-11: 0.00018%; 2018-05-11: 0.00024% | -1e-05%
| CONC1700 | Steel Structure | [34 empty] | 0%
C447 | CONC1710 | Roof & Siding | [34 empty] | 0%
| COAL FIRING EQUIPMENT STEEL STRUCTURE & ROOF SIDING | Transport material to site |  | 10% | 141989137.5 | 0.00415% | [30 empty] | 0.00415%
| COAL FIRING EQUIPMENT STEEL STRUCTURE & ROOF SIDING | Check elevation & orientation |  | 20% | 283978275 | 0.0083% | [30 empty] | 0.0083%
| COAL FIRING EQUIPMENT STEEL STRUCTURE & ROOF SIDING | Pre-assembly on the ground |  | 10% | 141989137.5 | 0.00415% | [30 empty] | 0.00415%
| COAL FIRING EQUIPMENT STEEL STRUCTURE & ROOF SIDING | Installation |  | 40% | 567272265 | 0.01658% | [30 empty] | 0.01658%
| COAL FIRING EQUIPMENT STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 20% | 283978275 | 0.0083% | [30 empty] | 0.0083%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.12 Coal Grinding Buiding | [35 empty] | 0%
C444 | CONC1720 | COAL GRINDING BUILDING - Piling | [34 empty] | 0%
| COAL FIRING EQUIPMENT PILES | Tranport Material to site |  | 10% | 279872565 | 0.00818% | 2017-06-15: 0.00724%; 2017-07-15: 0.00094% | 0%
| COAL FIRING EQUIPMENT PILES | Install and Final Inspection |  | 90% | 2517826657.5 | 0.07359% | 2017-07-15: 0.01356%; 2017-08-14: 0.06004% | -8.395e-06%
| CONC1730 | RC/ Mech. Foundation | [34 empty] | 0%
C450 | FUEL COAL STORAGE REBAR | Tranport Material to site |  | 0.1 | 63296362.5 | 0.00185% | 2017-12-12: 0.00185% | 0%
| FUEL COAL STORAGE REBAR | Install and Final Inspection |  | 0.9 | 568298692.5 | 0.01661% | 2017-12-12: 0.00429%; 2018-01-11: 0.01089%; 2018-02-10: 0.00144% | -1e-05%
0%
C451 | FUEL COAL STORAGE CONCRETE | Tranport Material to site |  | 0.1 | 15054270 | 0.00044% | 2017-12-12: 0.00044% | 0%
| FUEL COAL STORAGE CONCRETE | Install and Final Inspection |  | 0.9 | 135488430 | 0.00396% | 2017-12-12: 0.00097%; 2018-01-11: 0.00257%; 2018-02-10: 0.00041% | 1e-05%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.12.14.2.1.12.3 Steel Structure | [35 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.12.14.2.1.12.3.14.2.1.12.3.1 Line D-C | [35 empty] | 0%
| CONC1740 | STEEL STRUCTURE LINE D-C - GL+12.6m, 19.6m, | [34 empty] | 0%
| CONC1750 | GL+26.6m | [34 empty] | 0%
| CONC1760 | Roof & Siding | [34 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.12.14.2.1.12.3.14.2.1.12.3.2 Line D-C-1 | [35 empty] | 0%
| CONC1770 | STEEL STRUCTURE LINE D-C-1 - GL+4m, 10.2m | [34 empty] | 0%
| CONC1780 | GL+16.7m | [34 empty] | 0%
| CONC1790 | Roof & Siding | [34 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.12.14.2.1.12.3.14.2.1.12.3.3 Line C-B | [35 empty] | 0%
| CONC1800 | STEEL STRUCTURE LINE C-B - SS (After H.A.G take-in) | [34 empty] | 0%
C452 | CONC1810 | Roof & Siding | [34 empty] | 0%
| FUEL COAL STORAGE STEEL STRUCTURE & ROOF SIDING | Transport material to site |  | 0.1 | 153279840 | 0.00448% | 2018-03-12: 0.00411%; 2018-04-11: 0.00037% | 0%
| FUEL COAL STORAGE STEEL STRUCTURE & ROOF SIDING | Check elevation & orientation |  | 0.2 | 306901822.5 | 0.00897% | 2018-04-11: 0.00558%; 2018-05-11: 0.00247% | 0.00092%
| FUEL COAL STORAGE STEEL STRUCTURE & ROOF SIDING | Pre-assembly on the ground |  | 0.1 | 153279840 | 0.00448% | [30 empty] | 0.00448%
| FUEL COAL STORAGE STEEL STRUCTURE & ROOF SIDING | Installation |  | 0.4 | 613803645 | 0.01794% | [30 empty] | 0.01794%
| FUEL COAL STORAGE STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 0.2 | 306901822.5 | 0.00897% | [30 empty] | 0.00897%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.13 Electrical Room | [35 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.13.14.2.1.13.1 Ore Drying Electrical Room - LSS-11 | [35 empty] | 0%
| CONC1820 | ORE DRYING ELECTRICAL ROOM - LSS-11 - RC Building | [34 empty] | 0%
| CONC1840 | Interior Work | [34 empty] | 0%
C410 | ELECTRICAL ROOM FOR ORE DRYER AREA REBAR | Tranport Material to site |  | 10% | 16080697.5 | 0.00047% | 2018-01-11: 0.00047% | 0%
| ELECTRICAL ROOM FOR ORE DRYER AREA REBAR | Install and Final Inspection |  | 90% | 143357707.5 | 0.00419% | 2018-01-11: 0.00126%; 2018-02-10: 0.00076%; 2018-03-12: 0.00014%; 2018-04-11: 0.00028%; 2018-05-11: 0.00027% | 0.00148%
0%
C411 | ELECTRICAL ROOM FOR ORE DRYER AREA CONCRETE | Tranport Material to site |  | 10% | 12317130 | 0.00036% | 2018-01-11: 0.00036% | 0%
| ELECTRICAL ROOM FOR ORE DRYER AREA CONCRETE | Install and Final Inspection |  | 90% | 109485600 | 0.0032% | 2018-01-11: 0.0009%; 2018-02-10: 0.00048%; 2018-03-12: 0.00025%; 2018-04-11: 0.00014%; 2018-05-11: 0.00029% | 0.00114%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.13.14.2.1.13.2 Mixing & Briquetting Electrical Room - LSS-12 | [35 empty] | 0%
| CONC1850 | MIXING & BRIQUETTING ELECTRICAL ROOM - LSS-12 - Reinforced Concrete | [34 empty] | 0%
| CONC1860 | Interior Work | [34 empty] | 0%
C413 | ELECTRICAL ROOM FOR ORE MIXING AREA INSIDE ORE MIXING AND BRIQUETT REBAR | Tranport Material to site |  | 10% | 13343557.5 | 0.00039% | [30 empty] | 0.00039%
| ELECTRICAL ROOM FOR ORE MIXING AREA INSIDE ORE MIXING AND BRIQUETT REBAR | Install and Final Inspection |  | 90% | 120776302.5 | 0.00353% | 2018-05-11: 0.00146% | 0.00207%
0%
C414 | ELECTRICAL ROOM FOR ORE MIXING AREA INSIDE ORE MIXING AND BRIQUETT CONCRETE | Tranport Material to site |  | 10% | 9579990 | 0.00028% | 2018-04-11: 0.00028% | 0%
| ELECTRICAL ROOM FOR ORE MIXING AREA INSIDE ORE MIXING AND BRIQUETT CONCRETE | Install and Final Inspection |  | 90% | 85193482.5 | 0.00249% | 2018-04-11: 0.00011%; 2018-05-11: 0.00095% | 0.00143%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.13.14.2.1.13.3 Rotary Kiln Electrical Room - LSS-13 | [35 empty] | 0%
| CONC1890 | ROTARY KILN - LSS-13 - Reinforced Concrete | [34 empty] | 0%
| CONC1910 | Interior Work | [34 empty] | 0%
C416 | ELECTRICAL ROOM FOR ROTARY KILN AREA AND COAL FIRING AREA REBAR | Tranport Material to site |  | 10% | 16080697.5 | 0.00047% | [30 empty] | 0.00047%
| ELECTRICAL ROOM FOR ROTARY KILN AREA AND COAL FIRING AREA REBAR | Install and Final Inspection |  | 90% | 146094847.5 | 0.00427% | 2018-02-10: 0.00227%; 2018-03-12: 0.00023%; 2018-05-11: 0.00291% | -0.00114%
0%
C417 | ELECTRICAL ROOM FOR ROTARY KILN AREA AND COAL FIRING AREA CONCRETE | Tranport Material to site |  | 10% | 10606417.5 | 0.00031% | [30 empty] | 0.00031%
| ELECTRICAL ROOM FOR ROTARY KILN AREA AND COAL FIRING AREA CONCRETE | Install and Final Inspection |  | 90% | 94773472.5 | 0.00277% | 2018-02-10: 0.00136%; 2018-03-12: 0.00016%; 2018-04-11: 0.00058%; 2018-05-11: 0.00134% | -0.00067%
| P3FH - 28 M.14.14.2.14.2.1.14.2.1.13.14.2.1.13.31 Coal Firing Electrical Room - LSS-14 | [35 empty] | 0%
| CONC2780 | COAL FIRING ELECTRICAL ROOM - LSS-14 - Reinforced Concrete | [34 empty] | 0%
| CONC2800 | Interior Work | [34 empty] | 0%
C416 | ELECTRICAL ROOM FOR ROTARY KILN AREA AND COAL FIRING AREA REBAR | Tranport Material to site |  | 10% | 16080697.5 | 0.00047% | [30 empty] | 0.00047%
| ELECTRICAL ROOM FOR ROTARY KILN AREA AND COAL FIRING AREA REBAR | Install and Final Inspection |  | 90% | 146094847.5 | 0.00427% | [30 empty] | 0.00427%
0%
C417 | ELECTRICAL ROOM FOR ROTARY KILN AREA AND COAL FIRING AREA CONCRETE | Tranport Material to site |  | 10% | 10606417.5 | 0.00031% | [30 empty] | 0.00031%
| ELECTRICAL ROOM FOR ROTARY KILN AREA AND COAL FIRING AREA CONCRETE | Install and Final Inspection |  | 90% | 94431330 | 0.00276% | [30 empty] | 0.00276%
| P3FH - 28 M.14.14.2.11.2.1 System 2 - Electric Smelting Furnace-Rev.1 | [35 empty] | 0%
| P3FH - 28 M.14.14.2.11.2.1.11.2.1.1 ESF & Refinery Building | [35 empty] | 0%
| P3FH - 28 M.14.14.2.11.2.1.11.2.1.1.11.2.1.1.1.1 Foundation | [35 empty] | 0%
C466 | SYSTEM-2-1120 | Piling on ESF Building, and Furnace | [34 empty] | 0%
| ESF BUILDING PILES | Tranport Material to site |  | 10% | 361644622.5 | 0.00409% | 2017-07-15: 0.00409% | 0%
| ESF BUILDING PILES | Install and Final Inspection |  | 90% | 3253433032.5 | 0.03682% | 2017-07-15: 0.02439%; 2017-08-14: 0.07867%; 2017-09-13: 0.02679%; 2017-12-12: 0.0002% | -0.09323%
| SYSTEM-2-1130 | Piling on Main Aisle column and Baghouse | [34 empty] | 0%
C471 | [36 empty] | 0%
| FURNACE FOUNDATION PILES | Tranport Material to site |  | 10% | 139936282.5 | 0.01057% | 2018-01-11: 0.01121% | -0.00064%
| FURNACE FOUNDATION PILES | Install and Final Inspection |  | 90% | 1259768685 | 0.09509% | [30 empty] | 0.09509%
| SYSTEM-2-1140 | RC Foundation on ESF Building | [34 empty] | 0%
C467 | ESF BUILDING REBAR | Tranport Material to site |  | 10% | 177229815 | 0.00518% | 2017-11-12: 0.00173%; 2017-12-12: 0.00345% | 0%
| ESF BUILDING REBAR | Install and Final Inspection |  | 90% | 1594384050 | 0.0466% | 2017-12-12: 0.01246%; 2018-01-11: 0.0007%; 2018-02-10: 0.00268%; 2018-03-12: 0.00054%; 2018-05-11: 0.01029% | 0.01993%
0%
C468 | ESF BUILDING CONCRETE | Tranport Material to site |  | 10% | 59190652.5 | 0.00173% | 2017-10-13: 6e-05%; 2017-11-12: 0.00018%; 2017-12-12: 0.00149% | 0%
| ESF BUILDING CONCRETE | Install and Final Inspection |  | 90% | 531005160 | 0.01552% | 2017-12-12: 0.00352%; 2018-01-11: 0.00085%; 2018-02-10: 0.00053%; 2018-03-12: 0.00026%; 2018-05-11: 0.00234% | 0.00802%
| SYSTEM-2-1170 | RC Foundation Main Aisle | [34 empty] | 0%
C472 | FURNACE FOUNDATION REBAR | Tranport Material to site |  | 10% | 40030672.5 | 0.00117% | 2017-10-13: 0.00117% | 0%
| FURNACE FOUNDATION REBAR | Install and Final Inspection |  | 90% | 358565340 | 0.01048% | 2017-10-13: 5e-07; 2017-11-12: 3.75e-05; 2018-02-10: 0.00332%; 2018-03-12: 0.00109%; 2018-04-11: 0.00171%; 2018-05-11: 8e-05% | 0.00048%
0%
C473 | FURNACE FOUNDATION CONCRETE | Tranport Material to site |  | 10% | 20186407.5 | 0.00059% | 2017-10-13: 5e-05%; 2017-11-12: 0.00054% | 0%
| FURNACE FOUNDATION CONCRETE | Install and Final Inspection |  | 90% | 180309097.5 | 0.00527% | 2017-11-12: 1.46e-05; 2018-01-11: 0.00012%; 2018-02-10: 0.00157%; 2018-03-12: 0.00032%; 2018-04-11: 0.00108%; 2018-05-11: 4e-05% | 0.00068%
| SYSTEM-2-1150 | Construct RC up to 2nd Floor | [34 empty] | 0%
| SYSTEM-2-1160 | RC Foundation on Furnace | [34 empty] | 0%
| P3FH - 28 M.14.14.2.11.2.1.11.2.1.1.11.2.1.1.1.2 Steel Structure and Siding ESF Building | [35 empty] | 0%
| SYSTEM-2-1180 | ESF Building SS Tapping Floor (Assembled Panels) | [34 empty] | 0%
| SYSTEM-2-1190 | ESF Building SS up to 3rd Floor | [34 empty] | 0%
| SYSTEM-2-1200 | ESF Building SS up to 4th Floor | [34 empty] | 0%
| SYSTEM-2-1210 | ESF Building SS up to El.44.000 | [34 empty] | 0%
| SYSTEM-2-1220 | ESF Building SS Roof (assembly 3 section) | [34 empty] | 0%
C469 | SYSTEM-2-1230 | Construct siding on Slag side | [34 empty] | 0%
| ESF BUILDING STEEL STRUCTURE & ROOF SIDING | Transport material to site |  | 10% | 946708297.5 | 0.02767% | 2018-05-11: 0.01422% | 0.01345%
| ESF BUILDING STEEL STRUCTURE & ROOF SIDING | Check elevation & orientation |  | 20% | 1893416595 | 0.05534% | [30 empty] | 0.05534%
| ESF BUILDING STEEL STRUCTURE & ROOF SIDING | Pre-assembly on the ground |  | 10% | 946708297.5 | 0.02767% | [30 empty] | 0.02767%
| ESF BUILDING STEEL STRUCTURE & ROOF SIDING | Installation |  | 40% | 3786833190 | 0.1107% | [30 empty] | 0.1107%
| ESF BUILDING STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 20% | 1893416595 | 0.05534% | [30 empty] | 0.05534%
| P3FH - 28 M.14.14.2.11.2.1.11.2.1.1.11.2.1.1.1.3 Steel Structure Main Aisle | [35 empty] | 0%
| SYSTEM-2-1240 | Survey and Marking | [34 empty] | 0%
| SYSTEM-2-1250 | Install Assembled Column on Main Aisle | [34 empty] | 0%
| SYSTEM-2-1260 | Install steel member each columns | [34 empty] | 0%
| SYSTEM-2-1270 | Lift complete panel roof (3Panels) | [34 empty] | 0%
| SYSTEM-2-1280 | Install Siding on Shot making side | [34 empty] | 0%
C476 | SYSTEM-2-1290 | Install Siding on Metal Side | [34 empty] | 0%
| TAPPING DECK STRUCTURE, SPRAY CHAMBER SUPPORT FOUNDATION, BAG HOUSE INLET DUCT SUPPORT, BAG HOUSE OUTLET DUCT SUPPORT STEEL STRUCTURE & ROOF SIDING | Transport material to site |  | 10% | 69797070 | 0.00204% | [30 empty] | 0.00204%
| TAPPING DECK STRUCTURE, SPRAY CHAMBER SUPPORT FOUNDATION, BAG HOUSE INLET DUCT SUPPORT, BAG HOUSE OUTLET DUCT SUPPORT STEEL STRUCTURE & ROOF SIDING | Check elevation & orientation |  | 20% | 139936282.5 | 0.00409% | [30 empty] | 0.00409%
| TAPPING DECK STRUCTURE, SPRAY CHAMBER SUPPORT FOUNDATION, BAG HOUSE INLET DUCT SUPPORT, BAG HOUSE OUTLET DUCT SUPPORT STEEL STRUCTURE & ROOF SIDING | Pre-assembly on the ground |  | 10% | 69797070 | 0.00204% | [30 empty] | 0.00204%
| TAPPING DECK STRUCTURE, SPRAY CHAMBER SUPPORT FOUNDATION, BAG HOUSE INLET DUCT SUPPORT, BAG HOUSE OUTLET DUCT SUPPORT STEEL STRUCTURE & ROOF SIDING | Installation |  | 40% | 279530422.5 | 0.00817% | [30 empty] | 0.00817%
| TAPPING DECK STRUCTURE, SPRAY CHAMBER SUPPORT FOUNDATION, BAG HOUSE INLET DUCT SUPPORT, BAG HOUSE OUTLET DUCT SUPPORT STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 20% | 139936282.5 | 0.00409% | [30 empty] | 0.00409%
| P3FH - 28 M.14.14.2.11.2.1.11.2.1.1.1 Electric Room & Transformer Room | [35 empty] | 0%
| SYSTEM-2-1300 | Electric Room LSS-21 & Transformer Room for Furnace | [34 empty] | 0%
C503 | ELECTRICAL ROOM FOR ESF AREA REBAR, CONCRETE, STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 100% | 162859830 | 0.00476% | [30 empty] | 0.00476%
| P3FH - 28 M.14.14.2.11.2.1.11.2.1.1.2 Hydraulic Room | [35 empty] | 0%
| SYSTEM-2-1310 | Hydraulic Unit Room | [34 empty] | 0%
| P3FH - 28 M.14.14.2.11.2.1.11.2.1.2 Hot Charge Crane | [35 empty] | 0%
| P3FH - 28 M.14.14.2.11.2.1.11.2.1.2.11.2.1.2.1 Container Car Pit | [35 empty] | 0%
| SYSTEM-2-1320 | Survey and Marking | [34 empty] | 0%
| SYSTEM-2-1330 | Construct Def.Bar for bottom | [34 empty] | 0%
| SYSTEM-2-1340 | Construct Reinf.Bar for Sideing | [34 empty] | 0%
| P3FH - 28 M.14.14.2.11.2.1.11.2.1.2.11.2.1.2.2 Control Room Container Car | [35 empty] | 0%
| SYSTEM-2-1350 | Survey and Marking | [34 empty] | 0%
| SYSTEM-2-1360 | Construct Building | [34 empty] | 0%
| SYSTEM-2-1370 | Painting | [34 empty] | 0%
C511 | CRANE CONTROL ROOM AT ESF BUILDING REBAR, CONCRETE, STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 100% | 88272765 | 0.00258% | [30 empty] | 0.00258%
| P3FH - 28 M.14.14.2.11.2.1.11.2.1.2.11.2.1.2.3 CCR for Kiln | [35 empty] | 0%
| SYSTEM-2-1380 | Survey and Marking | [34 empty] | 0%
| SYSTEM-2-1390 | Construct Steel Structure | [34 empty] | 0%
| SYSTEM-2-1400 | Contruct Cencrete block | [34 empty] | 0%
| SYSTEM-2-1410 | Construct Flooring | [34 empty] | 0%
| SYSTEM-2-1420 | Painting | [34 empty] | 0%
C507 | CENTRE CONTROL ROOM AT ESF BUILDING REBAR, CONCRETE, STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 100% | 256264732.5 | 0.00749% | [30 empty] | 0.00749%
| P3FH - 28 M.14.14.2.11.2.1.11.2.1.2.11.2.1.2.4 CCR for HCC | [35 empty] | 0%
| SYSTEM-2-1430 | Survey and Marking | [34 empty] | 0%
| SYSTEM-2-1440 | Construct Steel Structure | [34 empty] | 0%
| SYSTEM-2-1450 | Contruct Cencrete block | [34 empty] | 0%
| SYSTEM-2-1460 | Construct Flooring | [34 empty] | 0%
| SYSTEM-2-1470 | Painting | [34 empty] | 0%
| P3FH - 28 M.14.14.2.11.2.1.11.2.1.3 Slag Granulation | [35 empty] | 0%
| SYSTEM-2-1480 | Survey and Marking | [34 empty] | 0%
| SYSTEM-2-1490 | Construct base pond | [34 empty] | 0%
| SYSTEM-2-1500 | Construct wall Buaya River side | [34 empty] | 0%
| SYSTEM-2-1510 | Construct wall Slag side | [34 empty] | 0%
| SYSTEM-2-1520 | Construct wall Mountain side | [34 empty] | 0%
| SYSTEM-2-1530 | Construct wall rear | [34 empty] | 0%
C500 | MAIN SUBSTATION BUILDING REBAR | Tranport Material to site |  | 0.1 | 16080697.5 | 0.00047% | 2018-01-11: 0.00042% | 5e-05%
| MAIN SUBSTATION BUILDING REBAR | Install and Final Inspection |  | 0.9 | 145068420 | 0.00424% | 2018-02-10: 0.00285%; 2018-03-12: 0.00039%; 2018-04-11: 0.00032%; 2018-05-11: 0.00074% | -6e-05%
0%
C501 | MAIN SUBSTATION BUILDING CONCRETE | Tranport Material to site |  | 0.1 | 10948560 | 0.00032% | [30 empty] | 0.00032%
| MAIN SUBSTATION BUILDING CONCRETE | Install and Final Inspection |  | 0.9 | 98537040 | 0.00288% | 2018-02-10: 0.00145%; 2018-03-12: 0.00023%; 2018-04-11: 0.00023%; 2018-05-11: 0.00028% | 0.00069%
| P3FH - 28 M.14.14.2.11.2.1.11.2.1.4 Settling pond | [35 empty] | 0%
| SYSTEM-2-1550 | Construct Stone pitching from Road up to settling Pond | [34 empty] | 0%
| SYSTEM-2-1540 | Contruct RC up to Road | [34 empty] | 0%
C515 | EMERGENCY PIT REBAR, CONCRETE, STEEL STRUCTURE & ROOF SIDING | Install and Final Inspection |  | 100% | 35924962.5 | 0.00105% | [30 empty] | 0.00105%
| P3FH - 28 M.14.14.2.11.2.1.11.2.1.5 Ladle Preheating | [35 empty] | 0%
| SYSTEM-2-1560 | Foundation (Pre-Cast) | [34 empty] | 0%
| SYSTEM-2-1570 | Steel Structure (Assembled deck) | [34 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.3 System 3 - Refinery | [35 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.3.14.2.3.1.1 Desulphurizing Eq. | [35 empty] | 0%
| CONC2190 | Desulphurizing Eq. Foundation | [34 empty] | 0%
C529 | DESULPHURIZING EQ. REBAR | Tranport Material to site |  | 10% | 1368570 | 4e-05% | 2017-12-12: 4e-05% | 0%
| DESULPHURIZING EQ. REBAR | Install and Final Inspection |  | 90% | 13001415 | 0.00038% | 2017-12-12: 0.00011%; 2018-02-10: 0.0001%; 2018-03-12: 2e-05%; 2018-04-11: 2e-05%; 2018-05-11: 3e-05% | 0.0001%
0%
C530 | DESULPHURIZING EQ. CONCRETE | Tranport Material to site |  | 10% | 684285 | 2e-05% | 2017-12-12: 2e-05% | 0%
| DESULPHURIZING EQ. CONCRETE | Install and Final Inspection |  | 90% | 5816422.5 | 0.00017% | 2017-12-12: 5e-05%; 2018-02-10: 5e-05%; 2018-03-12: 1e-05%; 2018-04-11: 2e-05%; 2018-05-11: 1e-05% | 3e-05%
| P3FH - 28 M.14.14.2.14.2.3.14.2.3.1.2 Shotmaking | [35 empty] | 0%
C521 | CONC2099 | SHOT MAKING BUILDING - Piling | [34 empty] | 0%
| REFINING SHOT MAKING BUILDING PILES | Tranport Material to site |  | 10% | 8211420 | 0.00024% | 2017-08-14: 0.00024% | 0%
| REFINING SHOT MAKING BUILDING PILES | Install and Final Inspection |  | 90% | 74587065 | 0.00218% | 2017-08-14: 0.00218% | 0%
| CONC2210 | SHOT MAKING - Building (RC) | [34 empty] | 0%
| CONC2200 | SHOT MAKING EQ. - (RC Foundation) | [34 empty] | 0%
C522 | REFINING SHOT MAKING BUILDING REBAR | Tranport Material to site |  | 10% | 14369985 | 0.00042% | 2017-11-12: 0.00042% | 0%
| REFINING SHOT MAKING BUILDING REBAR | Install and Final Inspection |  | 90% | 129672007.5 | 0.00379% | 2017-11-12: 4.1e-06; 2017-12-12: 0.00064%; 2018-01-11: 0.00073%; 2018-02-10: 0.00024%; 2018-04-11: 0.00126%; 2018-05-11: 2e-05% | 0.00049%
0%
C523 | REFINING SHOT MAKING BUILDING CONCRETE | Tranport Material to site |  | 10% | 5816422.5 | 0.00017% | 2017-11-12: 0.00017% | 0%
| REFINING SHOT MAKING BUILDING CONCRETE | Install and Final Inspection |  | 90% | 50979232.5 | 0.00149% | 2017-11-12: 1.4e-06; 2017-12-12: 0.00024%; 2018-01-11: 0.00018%; 2018-02-10: 0.00019%; 2018-04-11: 0.00043%; 2018-05-11: 8e-05% | 0.00023%
| CONC2220 | SHOT MAKING - Building (SS) | [34 empty] | 0%
C524 | CONC2230 | Roof & Siding | [34 empty] | 0%
| REFINING SHOT MAKING BUILDING STEEL STRUCTURE & ROOF SIDING | Transport material to site |  | 10% | 38319960 | 0.00112% | [30 empty] | 0.00112%
| REFINING SHOT MAKING BUILDING STEEL STRUCTURE & ROOF SIDING | Check elevation & orientation |  | 20% | 76639920 | 0.00224% | [30 empty] | 0.00224%
| REFINING SHOT MAKING BUILDING STEEL STRUCTURE & ROOF SIDING | Pre-assembly on the ground |  | 10% | 38319960 | 0.00112% | [30 empty] | 0.00112%
| REFINING SHOT MAKING BUILDING STEEL STRUCTURE & ROOF SIDING | Installation |  | 40% | 153279840 | 0.00448% | [30 empty] | 0.00448%
| REFINING SHOT MAKING BUILDING STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 20% | 76639920 | 0.00224% | [30 empty] | 0.00224%
| P3FH - 28 M.14.14.2.14.2.3.14.2.3.1.3 Product Storage & Handling Crane Building | [35 empty] | 0%
C532 | CONC2240 | Desulphurizing Equipment Support & Foundation | [34 empty] | 0%
| DESULPHURIZING EQ. PILES | Tranport Material to site |  | 10% | 41399242.5 | 0.00121% | 2017-09-13: 0.00121% | 0%
| DESULPHURIZING EQ. PILES | Install and Final Inspection |  | 90% | 372935325 | 0.0109% | 2017-09-13: 0.000109 | 0%
| CONC2241 | Product Storage Foundation Building - RC Foundation | [34 empty] | 0%
| CONC2250 | Foundation for Rail of Container Car | [34 empty] | 0%
C533 | PRODUCT STORAGE BUILDING & HANDLING CRANE REBAR | Tranport Material to site |  | 10% | 23949975 | 0.0007% | 2018-01-11: 0.0007% | 0%
| PRODUCT STORAGE BUILDING & HANDLING CRANE REBAR | Install and Final Inspection |  | 90% | 216918345 | 0.00634% | 2018-01-11: 0.00096%; 2018-02-10: 0.00092%; 2018-03-12: 0.00146%; 2018-04-11: 0.00149% | 0.00151%
0%
C534 | PRODUCT STORAGE BUILDING & HANDLING CRANE CONCRETE | Tranport Material to site |  | 10% | 9237847.5 | 0.00027% | 2018-01-11: 0.00027% | 0%
| PRODUCT STORAGE BUILDING & HANDLING CRANE CONCRETE | Install and Final Inspection |  | 90% | 82114200 | 0.0024% | 2018-01-11: 0.00021%; 2018-02-10: 0.00017%; 2018-03-12: 0.00081%; 2018-04-11: 0.0001% | 0.00111%
| CONC2260 | Building for Product Storage (SS) | [34 empty] | 0%
C535 | CONC2270 | Roof & Siding | [34 empty] | 0%
| PRODUCT STORAGE BUILDING & HANDLING CRANE STEEL STRUCTURE & ROOF SIDING | Transport material to site |  | 10% | 124539870 | 0.00364% | [30 empty] | 0.00364%
| PRODUCT STORAGE BUILDING & HANDLING CRANE STEEL STRUCTURE & ROOF SIDING | Check elevation & orientation |  | 20% | 249079740 | 0.00728% | [30 empty] | 0.00728%
| PRODUCT STORAGE BUILDING & HANDLING CRANE STEEL STRUCTURE & ROOF SIDING | Pre-assembly on the ground |  | 10% | 124539870 | 0.00364% | [30 empty] | 0.00364%
| PRODUCT STORAGE BUILDING & HANDLING CRANE STEEL STRUCTURE & ROOF SIDING | Installation |  | 40% | 498843765 | 0.01458% | [30 empty] | 0.01458%
| PRODUCT STORAGE BUILDING & HANDLING CRANE STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 20% | 249079740 | 0.00728% | [30 empty] | 0.00728%
| P3FH - 28 M.14.14.2.14.2.3.14.2.3.1.4 Water Circulation System | [35 empty] | 0%
| CONC2280 | WATER CIRCULATION SYSTEM - Shot Return Water Pond | [34 empty] | 0%
| CONC2290 | Shot Cooling Pond | [34 empty] | 0%
| CONC2300 | Foundation for Equipment | [34 empty] | 0%
C550 | TURBO BLOWER FOUDATION, PUMP UNIT FOUNDATION REBAR, CONCRETE | Install and Final Inspection |  | 100% | 3421425 | 0.0001% | 2018-05-11: 5e-05% | 5e-05%
| P3FH - 28 M.14.14.2.14.2.3.14.2.1.13.31 Maintenance Deck for Ladle Preheating | [35 empty] | 0%
| A25610 | Foundation for Maintenance Deck | [34 empty] | 0%
| A25620 | Deck | [34 empty] | 0%
C544 | LADLE FOUNDATION, MAINTENANCE DECK FOR LADLE PREHAEATING REBAR | Tranport Material to site |  | 10% | 1368570 | 4e-05% | 2017-12-12: 4e-05% | 0%
| LADLE FOUNDATION, MAINTENANCE DECK FOR LADLE PREHAEATING REBAR | Install and Final Inspection |  | 90% | 11632845 | 0.00034% | 2017-12-12: 0.00022%; 2018-01-11: 6e-05%; 2018-02-10: 7e-05% | -1e-05%
0%
C545 | LADLE FOUNDATION, MAINTENANCE DECK FOR LADLE PREHAEATING CONCRETE | Tranport Material to site |  | 10% | 3421425 | 0.0001% | 2017-12-12: 0.0001% | 0%
| LADLE FOUNDATION, MAINTENANCE DECK FOR LADLE PREHAEATING CONCRETE | Install and Final Inspection |  | 90% | 29424255 | 0.00086% | 2018-01-11: 3e-05%; 2018-02-10: 5e-05% | 0.00078%
| P3FH - 28 M.14.14.2.14.2.3.14.2.1.13.311 Shot Making Electrical Room - LSS-31 | [35 empty] | 0%
| A25630 | Shot Making Electrical Room - LSS-31 - Reinforced Concrete | [34 empty] | 0%
| A25640 | Interior Work | [34 empty] | 0%
C537 | ELECTRICAL ROOM FOR SHOT MAKING AREA REBAR | Tranport Material to site |  | 10% | 7869277.5 | 0.00023% | 2018-01-11: 0.00023% | 0%
| ELECTRICAL ROOM FOR SHOT MAKING AREA REBAR | Install and Final Inspection |  | 90% | 71849925 | 0.0021% | 2018-01-11: 0.00043%; 2018-02-10: 0.00076%; 2018-03-12: 0.00018%; 2018-04-11: 0.0001% | 0.00063%
0%
C538 | ELECTRICAL ROOM FOR SHOT MAKING AREA CONCRETE | Tranport Material to site |  | 10% | 7869277.5 | 0.00023% | 2018-01-11: 0.00023% | 0%
| ELECTRICAL ROOM FOR SHOT MAKING AREA CONCRETE | Install and Final Inspection |  | 90% | 69797070 | 0.00204% | 2018-01-11: 0.0003%; 2018-02-10: 0.00064%; 2018-03-12: 0.00034%; 2018-05-11: 8e-05% | 0.00068%
0%
| P3FH - 28 M.14.14.2.14.2.4 System 4 - Utility Supply | [35 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.4.1 Pipeline & Piperack Foundation | [35 empty] | 0%
C593 | A25459 | Piling Pipe rack Foundation for Water, Air, Gas, Fuel | [34 empty] | 0%
| CABLE / PIPE RACK STRUCTURE PILES | Tranport Material to site |  | 10% | 185783377.5 | 0.00543% | 2017-12-12: 0.00543% | 0%
| CABLE / PIPE RACK STRUCTURE PILES | Install and Final Inspection |  | 90% | 1672392540 | 0.04888% | 2017-12-12: 0.04888% | 0%
| A25450 | Pipeline Foundation from Wayanof River & Sea | [34 empty] | 0%
C790 | PIPE SLEEPER RIVER WATER INTAKE REBAR | Tranport Material to site |  | 10% | 95115615 | 0.00278% | [30 empty] | 0.00278%
| PIPE SLEEPER RIVER WATER INTAKE REBAR | Install and Final Inspection |  | 90% | 857409105 | 0.02506% | 2018-03-12: 0.00421%; 2018-04-11: 0.00326%; 2018-05-11: 0.00112% | 0.01647%
0%
C791 | PIPE SLEEPER RIVER WATER INTAKE CONCRETE | Tranport Material to site |  | 10% | 24976402.5 | 0.00073% | [30 empty] | 0.00073%
| PIPE SLEEPER RIVER WATER INTAKE CONCRETE | Install and Final Inspection |  | 90% | 223761195 | 0.00654% | 2018-03-12: 0.00065%; 2018-04-11: 0.00078%; 2018-05-11: 0.00033% | 0.00478%
| A25460 | Pipe rack Foundation for Water, Air, Gas, Fuel | [34 empty] | 0%
C594 | CABLE / PIPE RACK STRUCTURE REBAR | Tranport Material to site |  | 10% | 20870692.5 | 0.00061% | 2018-01-11: 0.00039% | 0.00022%
| CABLE / PIPE RACK STRUCTURE REBAR | Install and Final Inspection |  | 90% | 187836232.5 | 0.00549% | 2018-02-10: 0.00059%; 2018-03-12: 0.00117%; 2018-04-11: 0.00189%; 2018-05-11: 0.00055% | 0.00129%
0%
C595 | CABLE / PIPE RACK STRUCTURE CONCRETE | Tranport Material to site |  | 10% | 5132137.5 | 0.00015% | 2018-01-11: 8e-05% | 7e-05%
| CABLE / PIPE RACK STRUCTURE CONCRETE | Install and Final Inspection |  | 90% | 45504952.5 | 0.00133% | 2018-02-10: 0.00012%; 2018-03-12: 0.00027%; 2018-04-11: 0.0004%; 2018-05-11: 0.00023% | 0.00031%
0%
0%
C596 | A25470 | Steel Structure & Pipe rack for Water, Air, Gas, Fuel | [34 empty] | 0%
| CABLE / PIPE RACK STRUCTURE STEEL STRUCTURE & ROOF SIDING | Transport material to site |  | 10% | 164912685 | 0.00482% | [30 empty] | 0.00482%
| CABLE / PIPE RACK STRUCTURE STEEL STRUCTURE & ROOF SIDING | Check elevation & orientation |  | 20% | 330167512.5 | 0.00965% | [30 empty] | 0.00965%
| CABLE / PIPE RACK STRUCTURE STEEL STRUCTURE & ROOF SIDING | Pre-assembly on the ground |  | 10% | 164912685 | 0.00482% | [30 empty] | 0.00482%
| CABLE / PIPE RACK STRUCTURE STEEL STRUCTURE & ROOF SIDING | Installation |  | 40% | 659992882.5 | 0.01929% | [30 empty] | 0.01929%
| CABLE / PIPE RACK STRUCTURE STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 20% | 330167512.5 | 0.00965% | [30 empty] | 0.00965%
| P3FH - 28 M.14.14.2.14.2.4.14.2.1.13.4 Main Substation Room | [35 empty] | 0%
| CONC1920 | MAIN SUBSTATION - Reinforced Concrete | [34 empty] | 0%
| CONC1940 | Interior Work | [34 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.4.14.2.1.13.41 Emergency Diesel Generator Room | [35 empty] | 0%
| CONC2750 | EMERGENCY DIESEL GENERATOR - Reinforced Concrete | [34 empty] | 0%
| CONC2770 | Interior Work | [34 empty] | 0%
C565 | EMERGENCY GENERATOR ROOM REBAR | Tranport Material to site |  | 10% | 15738555 | 0.00046% | [30 empty] | 0.00046%
| EMERGENCY GENERATOR ROOM REBAR | Install and Final Inspection |  | 90% | 140962710 | 0.00412% | 2018-03-12: 0.00151%; 2018-04-11: 0.00076%; 2018-05-11: 0.00108% | 0.00077%
0%
C566 | EMERGENCY GENERATOR ROOM CONCRETE | Tranport Material to site |  | 10% | 7527135 | 0.00022% | [30 empty] | 0.00022%
| EMERGENCY GENERATOR ROOM CONCRETE | Install and Final Inspection |  | 90% | 66375645 | 0.00194% | 2018-03-12: 0.00056%; 2018-04-11: 0.00038%; 2018-05-11: 0.00042% | 0.00058%
| P3FH - 28 M.14.14.2.14.2.4.14.2.4.1 Water Intake and Treatment System Equipment (4100) | [35 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.4.14.2.4.1.14.2.4.1.1 Raw Water Intake System | [35 empty] | 0%
C598 | CONC2349 | Raw Water Intake System_Piling for Clarifier Foundation | [34 empty] | 0%
| CLARIFIER & TANK FOUNDATION PILES | Tranport Material to site |  | 10% | 42767812.5 | 0.00125% | 2017-08-14: 0.00125% | 0%
| CLARIFIER & TANK FOUNDATION PILES | Install and Final Inspection |  | 90% | 384226027.5 | 0.01123% | 2017-08-14: 5.62e-05; 2017-09-13: 5.61e-05 | 0%
| CONC2340 | Raw Water Intake System_Raw Water Intake Pond (4100) | [34 empty] | 0%
C623 | INTAKE WATER POND (WAYANOF RIVER) REBAR | Tranport Material to site |  | 10% | 49610662.5 | 0.00145% | 2017-08-14: 0.00105%; 2017-09-13: 0.0004% | 0%
| INTAKE WATER POND (WAYANOF RIVER) REBAR | Install and Final Inspection |  | 90% | 445127392.5 | 0.01301% | 2017-09-13: 1.18e-05; 2017-10-13: 1.6e-06; 2017-11-12: 3.99e-05; 2017-12-12: 0.00213%; 2018-01-11: 0.00296%; 2018-02-10: 0.00211% | 0.00048%
0%
C624 | INTAKE WATER POND (WAYANOF RIVER) CONCRETE | Tranport Material to site |  | 10% | 15738555 | 0.00046% | 2017-09-13: 3.8e-06; 2017-10-13: 8e-05% | 0%
| INTAKE WATER POND (WAYANOF RIVER) CONCRETE | Install and Final Inspection |  | 90% | 141646995 | 0.00414% | 2017-11-12: 1.32e-05; 2017-12-12: 0.0008%; 2018-01-11: 0.00024%; 2018-02-10: 0.00153% | 0.00025%
| CONC2350 | Raw Water Intake System_Foundation for Clarifier | [34 empty] | 0%
C599 | SAND FILTER FOUNDATION REBAR | Tranport Material to site |  | 10% | 26687115 | 0.00078% | 2017-10-13: 0.0004%; 2017-11-12: 5e-05%; 2017-12-12: 0.0001%; 2018-01-11: 0.00023% | 0%
| SAND FILTER FOUNDATION REBAR | Install and Final Inspection |  | 90% | 239157607.5 | 0.00699% | 2018-01-11: 0.00179%; 2018-02-10: 4e-05%; 2018-03-12: 0.0036% | 0.00156%
0%
C600 | SAND FILTER FOUNDATION CONCRETE | Tranport Material to site |  | 10% | 45162810 | 0.00132% | 2017-10-13: 0.00012%; 2017-11-12: 3e-05%; 2018-01-11: 0.00045% | 0.00072%
| SAND FILTER FOUNDATION CONCRETE | Install and Final Inspection |  | 90% | 407149575 | 0.0119% | 2018-02-10: 4e-05%; 2018-03-12: 0.00068% | 0.01118%
| CONC2360 | Raw Water Intake System_Pump Room for Water Intake (RC) | [34 empty] | 0%
C581 | PUMP ROOM FOR WATER INTAKE (WAYANOF RIVER) REBAR | Tranport Material to site |  | 10% | 1710712.5 | 5e-05% | [30 empty] | 5e-05%
| PUMP ROOM FOR WATER INTAKE (WAYANOF RIVER) REBAR | Install and Final Inspection |  | 90% | 13685700 | 0.0004% | [30 empty] | 0.0004%
0%
C582 | PUMP ROOM FOR WATER INTAKE (WAYANOF RIVER) CONCRETE | Tranport Material to site |  | 10% | 684285 | 2e-05% | [30 empty] | 2e-05%
| PUMP ROOM FOR WATER INTAKE (WAYANOF RIVER) CONCRETE | Install and Final Inspection |  | 90% | 4789995 | 0.00014% | [30 empty] | 0.00014%
C583 | CONC3200 | Raw Water Intake System_Pump Room for Water Intake (SS & Roof Siding | [34 empty] | 0%
| PUMP ROOM FOR WATER INTAKE (WAYANOF RIVER) STEEL STRUCTURE & ROOF SIDNG | Transport material to site |  | 10% | 3763567.5 | 0.00011% | [30 empty] | 0.00011%
| PUMP ROOM FOR WATER INTAKE (WAYANOF RIVER) STEEL STRUCTURE & ROOF SIDNG | Check elevation & orientation |  | 20% | 7527135 | 0.00022% | [30 empty] | 0.00022%
| PUMP ROOM FOR WATER INTAKE (WAYANOF RIVER) STEEL STRUCTURE & ROOF SIDNG | Pre-assembly on the ground |  | 10% | 3763567.5 | 0.00011% | [30 empty] | 0.00011%
| PUMP ROOM FOR WATER INTAKE (WAYANOF RIVER) STEEL STRUCTURE & ROOF SIDNG | Installation |  | 40% | 14369985 | 0.00042% | [30 empty] | 0.00042%
| PUMP ROOM FOR WATER INTAKE (WAYANOF RIVER) STEEL STRUCTURE & ROOF SIDNG | Final inspection |  | 20% | 7527135 | 0.00022% | [30 empty] | 0.00022%
| P3FH - 28 M.14.14.2.14.2.4.14.2.4.1.14.2.4.1.1.14.2.4.1.1.1 Sump Pit | [35 empty] | 0%
| CONC2320 | Sump Pit_Temporary Rerouting River Flow | [34 empty] | 0%
| CONC2330 | Sump Pit_Sump Pit | [34 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.4.14.2.4.1.14.2.4.1.2 Filtration Receiving Water System | [35 empty] | 0%
| CONC2370 | Filtration_Receiving Water Pond (4110) | [34 empty] | 0%
C626 | RECEIVING WATER POND REBAR, CONCRETE | Tranport Material to site |  | 10% | 4105710 | 0.00012% | [30 empty] | 0.00012%
| RECEIVING WATER POND REBAR, CONCRETE | Install and Final Inspection |  | 90% | 37977817.5 | 0.00111% | 2018-02-10: 0.00032%; 2018-03-12: 0.00077%; 2018-05-11: 0.00013% | -0.00011%
| CONC2380 | Filtration_Filtered Water Pond (4113) | [34 empty] | 0%
C629 | FILTERED WATER POND REBAR, CONCRETE | Tranport Material to site |  | 10% | 4105710 | 0.00012% | [30 empty] | 0.00012%
| FILTERED WATER POND REBAR, CONCRETE | Install and Final Inspection |  | 90% | 37977817.5 | 0.00111% | 2018-02-10: 0.00032%; 2018-03-12: 0.00077%; 2018-05-11: 0.00013% | -0.00011%
| CONC2390 | Filtration_Pump Room (RC) | [34 empty] | 0%
C589 | PUMP ROOM (STR. & FDN.) REBAR, CONCRETE, STEEL STRUCTURE & ROOF SIDING | Tranport Material to site |  | 10% | 1710712.5 | 5e-05% | [30 empty] | 5e-05%
| PUMP ROOM (STR. & FDN.) REBAR, CONCRETE, STEEL STRUCTURE & ROOF SIDING | Install and Final Inspection |  | 90% | 16080697.5 | 0.00047% | [30 empty] | 0.00047%
| CONC2400 | Filtration_Foundation for Softener | [34 empty] | 0%
C616 | SOFTENER FOUNDATON, REBAR, CONCRETE | Tranport Material to site |  | 10% | 6842850 | 0.0002% | [30 empty] | 0.0002%
| SOFTENER FOUNDATON, REBAR, CONCRETE | Install and Final Inspection |  | 90% | 62269935 | 0.00182% | [30 empty] | 0.00182%
| CONC2391 | Filtration_Pump Room (SS & Roof Siding) | [34 empty] | 0%
0%
0%
0%
0%
0%
| CONC3210 | Filtration_Foundation for NaCl Tank | [34 empty] | 0%
C620 | NACL TANK FOUNDATION REBAR, CONCRETE | Tranport Material to site |  | 10% | 2737140 | 8e-05% | 2018-02-10: 1e-05% | 7e-05%
| NACL TANK FOUNDATION REBAR, CONCRETE | Install and Final Inspection |  | 90% | 23607832.5 | 0.00069% | 2018-03-12: 0.00076% | -7e-05%
| P3FH - 28 M.14.14.2.14.2.4.14.2.4.2 Water Circulation System | [35 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.4.14.2.4.2.14.2.4.2.1 Non-Softened Water Circulation System | [35 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.4.14.2.4.2.14.2.4.2.1.14.2.4.2.1.1 Non-Softened Water Tank (4202) | [35 empty] | 0%
| CONC2410 | NSW CIRCULATION SYSTEM_WATER TANK (4202) - Piling | [34 empty] | 0%
| CONC2420 | NSW CIRCULATION SYSTEM_WATER TANK (4202) - Foundation | [34 empty] | 0%
| CONC2430 | NSW CIRCULATION SYSTEM_WATER TANK (4202) - Steel Structure | [34 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.4.14.2.4.2.14.2.4.2.1.14.2.4.2.1.2 Non-Softened Water Pond | [35 empty] | 0%
C713 | CONC2470 | Piling for Cooling Tower Foundation (4205) | [34 empty] | 0%
| CONC3220 | Cooling Tower Foundation (4205) | [34 empty] | 0%
C714 | COOLING TOWER NON SOFTENED WATER FOUNDATION REBAR | Tranport Material to site |  | 10% | 39688530 | 0.00116% | [30 empty] | 0.00116%
| COOLING TOWER NON SOFTENED WATER FOUNDATION REBAR | Install and Final Inspection |  | 90% | 356512485 | 0.01042% | 2018-05-11: 0.01094% | -0.00052%
0%
C715 | COOLING TOWER NON SOFTENED WATER FOUNDATION CONCRETE | Tranport Material to site |  | 10% | 5816422.5 | 0.00017% | [30 empty] | 0.00017%
| COOLING TOWER NON SOFTENED WATER FOUNDATION CONCRETE | Install and Final Inspection |  | 90% | 50637090 | 0.00148% | 2018-05-11: 0.00156% | -8e-05%
| CONC2440 | NON SOFTENED WATER CIRCULATION SYSTEM_WATER POND - NSW Receiving Water Pond (RC) (4200) | [34 empty] | 0%
C632 | CIRCULATION WATER POND FOR COOPER COOLER REBAR | Tranport Material to site |  | 10% | 8211420 | 0.00024% | [30 empty] | 0.00024%
| CIRCULATION WATER POND FOR COOPER COOLER REBAR | Install and Final Inspection |  | 90% | 73218495 | 0.00214% | 2018-03-12: 0.00127%; 2018-04-11: 0.00097%; 2018-05-11: 0.00013% | -0.00023%
0%
C633 | CIRCULATION WATER POND FOR COOPER COOLER CONCRETE | Tranport Material to site |  | 10% | 3421425 | 0.0001% | 2018-02-10: 6e-05% | 4e-05%
| CIRCULATION WATER POND FOR COOPER COOLER CONCRETE | Install and Final Inspection |  | 90% | 29424255 | 0.00086% | 2018-03-12: 0.00035%; 2018-04-11: 0.00042%; 2018-05-11: 0.00013% | -4e-05%
| CONC2450 | NSW Return Water Pond (RC) (4203) | [34 empty] | 0%
C641 | NON SOFTENED WATER RETURN WATER POND REBAR | Tranport Material to site |  | 10% | 6500707.5 | 0.00019% | [30 empty] | 0.00019%
| NON SOFTENED WATER RETURN WATER POND REBAR | Install and Final Inspection |  | 90% | 57479940 | 0.00168% | 2018-03-12: 0.00099%; 2018-04-11: 0.00081%; 2018-05-11: 8e-05% | -0.0002%
0%
C642 | NON SOFTENED WATER RETURN WATER POND CONCRETE | Tranport Material to site |  | 10% | 2394997.5 | 7e-05% | 2018-02-10: 4e-05% | 3e-05%
| NON SOFTENED WATER RETURN WATER POND CONCRETE | Install and Final Inspection |  | 90% | 22923547.5 | 0.00067% | 2018-03-12: 0.00027%; 2018-04-11: 0.00034%; 2018-05-11: 9e-05% | -3e-05%
| CONC2460 | Pump Room (RC) | [34 empty] | 0%
0%
0%
0%
0%
0%
| P3FH - 28 M.14.14.2.14.2.4.14.2.4.2.14.2.4.2.2 Softened Water Circulation System Equipment | [35 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.4.14.2.4.2.14.2.4.2.2.14.2.4.2.2.1 Softened Water Tank (4212) | [35 empty] | 0%
C666 | CONC2480 | SOFTENED WATER TANK (4212) - Piling | [34 empty] | 0%
| HEAD TANKS SUPPORT & FOUNDATION PILES | Tranport Material to site |  | 10% | 53032087.5 | 0.00155% | 2017-08-14: 0.00155% | 0%
| HEAD TANKS SUPPORT & FOUNDATION PILES | Install and Final Inspection |  | 90% | 476262360 | 0.01392% | 2017-08-14: 0.01392% | 0%
| CONC2490 | SOFTENED WATER TANK (4212) - Foundation | [34 empty] | 0%
C667 | HEAD TANKS SUPPORT & FOUNDATION REBAR | Tranport Material to site |  | 10% | 11290702.5 | 0.00033% | 2017-08-14: 0.00033% | 0%
| HEAD TANKS SUPPORT & FOUNDATION REBAR | Install and Final Inspection |  | 90% | 100932037.5 | 0.00295% | 2017-08-14: 9.9e-06; 2017-09-13: 1.96e-05 | 0%
0%
C668 | HEAD TANKS SUPPORT & FOUNDATION CONCRETE | Tranport Material to site |  | 10% | 4105710 | 0.00012% | 2017-09-13: 0.00012% | 0%
| HEAD TANKS SUPPORT & FOUNDATION CONCRETE | Install and Final Inspection |  | 90% | 36609247.5 | 0.00107% | 2017-09-13: 8e-06; 2018-03-12: 0.00027% | 0%
C669 | CONC2500 | SOFTENED WATER TANK (4212) - Steel Structure | [34 empty] | 0%
| HEAD TANKS SUPPORT & FOUNDATION STEEL STRUTURE & ROOF SIDING | Transport material to site |  | 10% | 59190652.5 | 0.00173% | [30 empty] | 0.00173%
| HEAD TANKS SUPPORT & FOUNDATION STEEL STRUTURE & ROOF SIDING | Check elevation & orientation |  | 20% | 118723447.5 | 0.00347% | [30 empty] | 0.00347%
| HEAD TANKS SUPPORT & FOUNDATION STEEL STRUTURE & ROOF SIDING | Pre-assembly on the ground |  | 10% | 59190652.5 | 0.00173% | [30 empty] | 0.00173%
| HEAD TANKS SUPPORT & FOUNDATION STEEL STRUTURE & ROOF SIDING | Installation |  | 40% | 237446895 | 0.00694% | [30 empty] | 0.00694%
| HEAD TANKS SUPPORT & FOUNDATION STEEL STRUTURE & ROOF SIDING | Final inspection |  | 20% | 118723447.5 | 0.00347% | [30 empty] | 0.00347%
| P3FH - 28 M.14.14.2.14.2.4.14.2.4.2.14.2.4.2.2.14.2.4.2.2.2 Softened Water Tank for Cooper Cooler (4222) | [35 empty] | 0%
| CONC2510 | SOFTENED WATER TANK for COPPER COOLER (4222) - Piling | [34 empty] | 0%
| CONC2520 | SOFTENED WATER TANK for COPPER COOLER (4222) - Foundation | [34 empty] | 0%
| CONC2530 | SOFTENED WATER TANK for COPPER COOLER (4222) - Steel Structure | [34 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.4.14.2.4.2.14.2.4.2.2.14.2.4.2.2.3 Softened Water Pond Equipment | [35 empty] | 0%
| CONC2540 | SOFTENED WATER CIRCULATION SYST EQPT_WATER POND EQPT - SW Circulation Water Pond (RC) (4210) | [34 empty] | 0%
C635 | SHOT RETURN POND REBAR | Tranport Material to site |  | 10% | 52005660 | 0.00152% | 2017-12-12: 0.00152% | 0%
| SHOT RETURN POND REBAR | Install and Final Inspection |  | 90% | 468735225 | 0.0137% | 2017-12-12: 0.00751%; 2018-01-11: 0.00278%; 2018-02-10: 0.00116%; 2018-03-12: 0.0022%; 2018-05-11: 5e-05% | 0%
0%
C636 | SHOT RETURN POND CONCRETE | Tranport Material to site |  | 10% | 11974987.5 | 0.00035% | 2017-12-12: 0.00035% | 0%
| SHOT RETURN POND CONCRETE | Install and Final Inspection |  | 90% | 107090602.5 | 0.00313% | 2017-12-12: 0.00118%; 2018-01-11: 0.0008%; 2018-02-10: 0.00039%; 2018-03-12: 0.00055%; 2018-05-11: 0.00013% | 8e-05%
| CONC2550 | SW Return Water Pond (RC) (4213) | [34 empty] | 0%
C644 | SOFTENED WATER RETURN WATER POND REBAR | Tranport Material to site |  | 10% | 7184992.5 | 0.00021% | 2017-12-12: 0.00021% | 0%
| SOFTENED WATER RETURN WATER POND REBAR | Install and Final Inspection |  | 90% | 63638505 | 0.00186% | 2017-12-12: 0.00015%; 2018-01-11: 0.00081%; 2018-02-10: 0.00086%; 2018-05-11: 5e-05% | -1e-05%
0%
C645 | SOFTENED WATER RETURN WATER POND CONCRETE | Tranport Material to site |  | 10% | 2737140 | 8e-05% | 2017-12-12: 8e-05% | 0%
| SOFTENED WATER RETURN WATER POND CONCRETE | Install and Final Inspection |  | 90% | 24976402.5 | 0.00073% | 2018-01-11: 0.00035%; 2018-02-10: 0.0003%; 2018-05-11: 9e-05% | -1e-05%
C721 | CONC2570 | Piling for Cooling Tower Foundation (4215) | [34 empty] | 0%
| CONC2560 | Pump House (RC) | [34 empty] | 0%
| CONC3230 | Cooling Tower Foundation (4215) | [34 empty] | 0%
C663 | COOLING TOWER BASIN POND REBAR | Tranport Material to site |  | 10% | 104353462.5 | 0.00305% | [30 empty] | 0.00305%
| COOLING TOWER BASIN POND REBAR | Install and Final Inspection |  | 90% | 938496877.5 | 0.02743% | 2018-03-12: 0.01107%; 2018-04-11: 0.01375%; 2018-05-11: 0.00455% | -0.00194%
0%
C664 | COOLING TOWER BASIN POND CONCRETE | Tranport Material to site |  | 10% | 22923547.5 | 0.00067% | [30 empty] | 0.00067%
| COOLING TOWER BASIN POND CONCRETE | Install and Final Inspection |  | 90% | 204601215 | 0.00598% | 2018-03-12: 0.00371%; 2018-04-11: 0.00204%; 2018-05-11: 0.00074% | -0.00051%
| P3FH - 28 M.14.14.2.14.2.4.14.2.4.2.14.2.4.2.2.14.2.4.2.2.4 Softened Water Pond Equipment for Cooper Cooler | [35 empty] | 0%
| CONC2580 | SOFTENED _WATER CIRCULATION WATER POND EQPT FOR COOPER COOLER - SW Circulation Water Pond (RC) for Copper Cooler (4220) | [34 empty] | 0%
C638 | CIRCULATION WATER PIND FOR COPPER COOLER REBAR | Tranport Material to site |  | 10% | 12317130 | 0.00036% | 2017-12-12: 0.00036% | 0%
| CIRCULATION WATER PIND FOR COPPER COOLER REBAR | Install and Final Inspection |  | 90% | 109143457.5 | 0.00319% | 2017-12-12: 0.00018%; 2018-01-11: 0.00163%; 2018-02-10: 0.0013%; 2018-05-11: 8e-05% | 0%
0%
C639 | CIRCULATION WATER PIND FOR COPPER COOLER CONCRETE | Tranport Material to site |  | 10% | 4447852.5 | 0.00013% | 2017-12-12: 0.00013% | 0%
| CIRCULATION WATER PIND FOR COPPER COOLER CONCRETE | Install and Final Inspection |  | 90% | 41399242.5 | 0.00121% | 2017-12-12: 6e-05%; 2018-01-11: 0.00061%; 2018-02-10: 0.00039%; 2018-05-11: 0.00015% | 0%
0%
| CONC2590 | SW Return Water Pond (RC) for Copper Cooler (4223) | [34 empty] | 0%
C647 | SOFTENED WATER FOR COPPER COOLER RETURN POND REBAR | Tranport Material to site |  | 10% | 7184992.5 | 0.00021% | [30 empty] | 0.00021%
| SOFTENED WATER FOR COPPER COOLER RETURN POND REBAR | Install and Final Inspection |  | 90% | 64664932.5 | 0.00189% | 2018-03-12: 0.00131%; 2018-04-11: 0.00058%; 2018-05-11: 0.00022% | -0.00022%
0%
C648 | SOFTENED WATER FOR COPPER COOLER RETURN POND CONCRETE | Tranport Material to site |  | 10% | 3079282.5 | 9e-05% | 2018-02-10: 6e-05%; 2018-03-12: 0.00043%; 2018-04-11: 0.00033%; 2018-05-11: 0.00012% | -0.00085%
| SOFTENED WATER FOR COPPER COOLER RETURN POND CONCRETE | Install and Final Inspection |  | 90% | 29082112.5 | 0.00085% | [30 empty] | 0.00085%
C717 | CONC2610 | Piling for Cooling Tower Foundation (4225) | [34 empty] | 0%
| CONC2600 | Pump House (RC) | [34 empty] | 0%
| CONC3240 | Cooling Tower Foundation (4225) | [34 empty] | 0%
C718 | COOLING TOWER SOFTENED WATER COPPER COOLER FOUNDATION REBAR | Tranport Material to site |  | 10% | 66033502.5 | 0.00193% | [30 empty] | 0.00193%
| COOLING TOWER SOFTENED WATER COPPER COOLER FOUNDATION REBAR | Install and Final Inspection |  | 90% | 594301522.5 | 0.01737% | 2018-05-11: 0.01854% | -0.00117%
0%
C719 | COOLING TOWER SOFTENED WATER COPPER COOLER FOUNDATION CONCRETE | Tranport Material to site |  | 10% | 9579990 | 0.00028% | [30 empty] | 0.00028%
| COOLING TOWER SOFTENED WATER COPPER COOLER FOUNDATION CONCRETE | Install and Final Inspection |  | 90% | 84509197.5 | 0.00247% | 2018-05-11: 0.00268% | -0.00021%
| P3FH - 28 M.14.14.2.14.2.4.14.2.4.3 Compressed Air and Distribution System | [35 empty] | 0%
| CONC2620 | Air Compressor Room (RC) | [34 empty] | 0%
C575 | COMPRESSOR ROOM REBAR | Tranport Material to site |  | 10% | 15054270 | 0.00044% | [30 empty] | 0.00044%
| COMPRESSOR ROOM REBAR | Install and Final Inspection |  | 90% | 134462002.5 | 0.00393% | 2018-04-11: 0.00204%; 2018-05-11: 0.00026% | 0.00163%
0%
C576 | COMPRESSOR ROOM CONCRETE | Tranport Material to site |  | 10% | 15054270 | 0.00044% | [30 empty] | 0.00044%
| COMPRESSOR ROOM CONCRETE | Install and Final Inspection |  | 90% | 136514857.5 | 0.00399% | 2018-04-11: 0.00176%; 2018-05-11: 0.00031% | 0.00192%
| P3FH - 28 M.14.14.2.14.2.4.14.2.4.4 Fuel Oil Pumping and Distribution | [35 empty] | 0%
C679 | CONC2650 | IDO Tank Piling | [34 empty] | 0%
| HSD TANK FOUNDATION PILES | Tranport Material to site |  | 10% | 23607832.5 | 0.00069% | 2017-11-12: 0.00069% | 0%
| HSD TANK FOUNDATION PILES | Install and Final Inspection |  | 90% | 211444065 | 0.00618% | 2017-11-12: 6.18e-05 | 0%
C676 | CONC2630 | MFO Tank Foundation | [34 empty] | 0%
| MFO TANK FOUNDATION PILES | Tranport Material to site |  | 10% | 52689945 | 0.00154% | 2017-11-12: 0.00154% | 0%
| MFO TANK FOUNDATION PILES | Install and Final Inspection |  | 90% | 474893790 | 0.01388% | 2017-11-12: 0.0001388 | 0%
0%
C677 | MFO TANK FOUNDATION REBAR | Tranport Material to site |  | 10% | 18133552.5 | 0.00053% | [30 empty] | 0.00053%
| MFO TANK FOUNDATION REBAR | Install and Final Inspection |  | 90% | 163201972.5 | 0.00477% | 2018-02-10: 0.00071%; 2018-03-12: 2e-05%; 2018-04-11: 0.00059%; 2018-05-11: 0.00013% | 0.00332%
0%
C678 | MFO TANK FOUNDATION CONCRETE | Tranport Material to site |  | 10% | 2737140 | 8e-05% | [30 empty] | 8e-05%
| MFO TANK FOUNDATION CONCRETE | Install and Final Inspection |  | 90% | 23607832.5 | 0.00069% | 2018-02-10: 0.0001%; 2018-03-12: 1e-05%; 2018-04-11: 9e-05%; 2018-05-11: 2e-05% | 0.00047%
| CONC2640 | MFO Pump House | [34 empty] | 0%
C683 | MFO/HSD TRANSFER PUMP HOUSE REBAR | Tranport Material to site |  | 10% | 1368570 | 4e-05% | [30 empty] | 4e-05%
| MFO/HSD TRANSFER PUMP HOUSE REBAR | Install and Final Inspection |  | 90% | 10948560 | 0.00032% | [30 empty] | 0.00032%
0%
C684 | MFO/HSD TRANSFER PUMP HOUSE CONCRETE | Tranport Material to site |  | 10% | 3763567.5 | 0.00011% | [30 empty] | 0.00011%
| MFO/HSD TRANSFER PUMP HOUSE CONCRETE | Install and Final Inspection |  | 90% | 34898535 | 0.00102% | [30 empty] | 0.00102%
| CONC2660 | IDO Pump House | [34 empty] | 0%
C601 | PUMP ROOM FOR MFO/HSD TRANSFER REBAR | Tranport Material to site |  | 10% | 1368570 | 4e-05% | [30 empty] | 4e-05%
| PUMP ROOM FOR MFO/HSD TRANSFER REBAR | Install and Final Inspection |  | 90% | 10948560 | 0.00032% | [30 empty] | 0.00032%
0%
C602 | PUMP ROOM FOR MFO/HSD TRANSFER CONCRETE, STEEL STRUCTURE & ROOF SIDING | Tranport Material to site |  | 10% | 3763567.5 | 0.00011% | [30 empty] | 0.00011%
| PUMP ROOM FOR MFO/HSD TRANSFER CONCRETE, STEEL STRUCTURE & ROOF SIDING | Install and Final Inspection |  | 90% | 34898535 | 0.00102% | [30 empty] | 0.00102%
| CONC2651 | IDO Tank Foundation | [34 empty] | 0%
C680 | HSD TANK FOUNDATION REBAR | Tranport Material to site |  | 10% | 13343557.5 | 0.00039% | 2018-03-12: 0.00019% | 0.0002%
| HSD TANK FOUNDATION REBAR | Install and Final Inspection |  | 90% | 120776302.5 | 0.00353% | [30 empty] | 0.00353%
0%
C681 | HSD TANK FOUNDATION CONCRETE | Tranport Material to site |  | 10% | 2052855 | 6e-05% | [30 empty] | 6e-05%
| HSD TANK FOUNDATION CONCRETE | Install and Final Inspection |  | 90% | 17449267.5 | 0.00051% | 2018-03-12: 3e-05% | 0.00048%
| P3FH - 28 M.14.14.2.14.2.4.14.2.4.5 Sea Water Intake System | [35 empty] | 0%
C650 | CONC2670 | Piling Work | [34 empty] | 0%
| CONCRETE WORK FOR WATER INTAKE NEAR THE SEA PILES | Tranport Material to site |  | 10% | 51663517.5 | 0.00151% | [30 empty] | 0.00151%
| CONCRETE WORK FOR WATER INTAKE NEAR THE SEA PILES | Install and Final Inspection |  | 90% | 466340227.5 | 0.01363% | 2018-02-10: 0.01009%; 2018-03-12: 0.00505% | -0.00151%
| CONC2671 | Temporary Construction Method | [34 empty] | 0%
| CONC2672 | Sea Water Intake Pond (4900) | [34 empty] | 0%
C651 | CONCRETE WORK FOR WATER INTAKE NEAR THE SEA REBAR | Tranport Material to site |  | 10% | 262423297.5 | 0.00767% | [30 empty] | 0.00767%
| CONCRETE WORK FOR WATER INTAKE NEAR THE SEA REBAR | Install and Final Inspection |  | 90% | 2363178247.5 | 0.06907% | 2018-04-11: 0.05717%; 2018-05-11: 0.00194% | 0.00996%
0%
C652 | CONCRETE WORK FOR WATER INTAKE NEAR THE SEA CONCRETE | Tranport Material to site |  | 10% | 46873522.5 | 0.00137% | [30 empty] | 0.00137%
| CONCRETE WORK FOR WATER INTAKE NEAR THE SEA CONCRETE | Install and Final Inspection |  | 90% | 422888130 | 0.01236% | 2018-04-11: 0.00778%; 2018-05-11: 0.00039% | 0.00419%
0%
0%
C657 | SLAG GRANULATION POND REBAR | Tranport Material to site |  | 10% | 144041992.5 | 0.00421% | [30 empty] | 0.00421%
| SLAG GRANULATION POND REBAR | Install and Final Inspection |  | 90% | 1296720075 | 0.0379% | 2018-03-12: 0.01605%; 2018-04-11: 0.01681%; 2018-05-11: 0.00896% | -0.00392%
0%
C658 | SLAG GRANULATION POND CONCRETE | Tranport Material to site |  | 10% | 20528550 | 0.0006% | 2018-02-10: 0.00026% | 0.00034%
| SLAG GRANULATION POND CONCRETE | Install and Final Inspection |  | 90% | 184414807.5 | 0.00539% | 2018-03-12: 0.00098%; 2018-04-11: 0.00304%; 2018-05-11: 0.00164% | -0.00027%
0%
| CONC2680 | Pump House (RC) | [34 empty] | 0%
C585 | PUMP ROOM FOR WATER INTAKE (SEA) REBAR | Tranport Material to site |  | 10% | 2737140 | 8e-05% | [30 empty] | 8e-05%
| PUMP ROOM FOR WATER INTAKE (SEA) REBAR | Install and Final Inspection |  | 90% | 24634260 | 0.00072% | [30 empty] | 0.00072%
0%
C586 | PUMP ROOM FOR WATER INTAKE (SEA) CONCRETE | Tranport Material to site |  | 10% | 9237847.5 | 0.00027% | [30 empty] | 0.00027%
| PUMP ROOM FOR WATER INTAKE (SEA) CONCRETE | Install and Final Inspection |  | 90% | 81429915 | 0.00238% | [30 empty] | 0.00238%
| CONC2690 | Access Road | [34 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.4.14.2.4.5.1 Temporary Construction Method | [35 empty] | 0%
| P3FH - 28 M.14.14.2.14.2.4.14.2.4.6 Oxygen Plant | [35 empty] | 0%
| CONC2700 | Oxygen Plant - Foundation | [34 empty] | 0%
| CONC2710 | Oxygen Plant - Building | [34 empty] | 0%
C568 | OXYGENT PLANT BUILDING REBAR | Tranport Material to site |  | 10% | 12659272.5 | 0.00037% | [30 empty] | 0.00037%
| OXYGENT PLANT BUILDING REBAR | Install and Final Inspection |  | 90% | 114275595 | 0.00334% | [30 empty] | 0.00334%
| P3FH - 28 M.14.14.2.14.2.4.14.2.1.13.31 Utility Electrical Room - LSS-42 | [35 empty] | 0%
| A2080 | Utility Electrical Room - LSS-42 - Reinforced Concrete | [34 empty] | 0%
| A2090 | Interior Work | [34 empty] | 0%
C578 | ELECTRICAL ROOM FOR UTILITY REBAR | Tranport Material to site |  | 10% | 10264275 | 0.0003% | [30 empty] | 0.0003%
| ELECTRICAL ROOM FOR UTILITY REBAR | Install and Final Inspection |  | 90% | 93404902.5 | 0.00273% | 2018-03-12: 0.00055%; 2018-04-11: 8e-05%; 2018-05-11: 0.00023% | 0.00187%
| P3FH - 28 M.14.14.2.14.2.4.14.2.1.13.311 Oxygen Plant Electrical Room - LSS-43 | [35 empty] | 0%
| A2100 | Oxygen Plant Electrical Room - LSS-43 - Reinforced Concrete | [34 empty] | 0%
| A2110 | Interior Work | [34 empty] | 0%
C572 | OXYGENT PLANT EQ. SUPPORT & FOUNDATION REBAR | Tranport Material to site |  | 10% | 1368570 | 4e-05% | [30 empty] | 4e-05%
| OXYGENT PLANT EQ. SUPPORT & FOUNDATION REBAR | Install and Final Inspection |  | 90% | 11632845 | 0.00034% | 2018-03-12: 0.00042%; 2018-04-11: 0.0001% | -0.00018%
| P3FH - 28 M.14.14.2.14.2.4.14.2.1.13.3111 River Water Intake Electrical Room - LSS-44 | [35 empty] | 0%
| A2120 | River Water Intake Electrical Room - LSS-44 - Reinforced Concrete | [34 empty] | 0%
| A2130 | Interior Work | [34 empty] | 0%
C705 | ELECTRICAL ROOM FOR RIVER WATER INTAKE (No. 52) REBAR | Tranport Material to site |  | 10% | 11632845 | 0.00034% | [30 empty] | 0.00034%
| ELECTRICAL ROOM FOR RIVER WATER INTAKE (No. 52) REBAR | Install and Final Inspection |  | 90% | 104011320 | 0.00304% | 2018-02-10: 0.00102%; 2018-03-12: 0.00055%; 2018-04-11: 0.00042%; 2018-05-11: 0.00036% | 0.00069%
0%
C706 | ELECTRICAL ROOM FOR RIVER WATER INTAKE (No. 52) CONCRETE | Tranport Material to site |  | 10% | 5474280 | 0.00016% | [30 empty] | 0.00016%
| ELECTRICAL ROOM FOR RIVER WATER INTAKE (No. 52) CONCRETE | Install and Final Inspection |  | 90% | 48926377.5 | 0.00143% | 2018-02-10: 0.00017%; 2018-03-12: 8e-05%; 2018-04-11: 5e-05%; 2018-05-11: 1e-05% | 0.00112%
| P3FH - 28 M.14.14.2.14.2.4.14.2.1.13.31111 Sea Water Intake Electrical Room - LSS-45 | [35 empty] | 0%
| A2140 | Sea Water Intake Electrical Room - LSS-45 - Reinforced Concrete | [34 empty] | 0%
| A2150 | Interior Work | [34 empty] | 0%
C709 | ELECTRICAL ROOM FOR RIVER WATER INTAKE (No. 53) REBAR | Tranport Material to site |  | 10% | 11290702.5 | 0.00033% | [30 empty] | 0.00033%
| ELECTRICAL ROOM FOR RIVER WATER INTAKE (No. 53) REBAR | Install and Final Inspection |  | 90% | 99905610 | 0.00292% | 2018-03-12: 0.00161%; 2018-04-11: 0.0005% | 0.00081%
0%
C710 | ELECTRICAL ROOM FOR RIVER WATER INTAKE (No. 53) CONCRETE | Tranport Material to site |  | 10% | 5474280 | 0.00016% | [30 empty] | 0.00016%
| ELECTRICAL ROOM FOR RIVER WATER INTAKE (No. 53) CONCRETE | Install and Final Inspection |  | 90% | 48242092.5 | 0.00141% | 2018-03-12: 0.00024%; 2018-04-11: 6e-05%; 2018-05-11: 4e-05% | 0.00107%
| P3FH - 28 M.14.14.2.1 Non Process Building | [35 empty] | 0%
| P3FH - 28 M.14.14.2.1.2 Warehouse for Chemical | [35 empty] | 0%
| P3FH - 28 M.14.14.2.1.2.1 RC Foundation | [35 empty] | 0%
| CONC2810 | WAREHOUSE CHEMICAL - RC Foundation | [34 empty] | 0%
C786 | CHEMICAL WAREHOUSE REBAR | Tranport Material to site |  | 10% | 8553562.5 | 0.00025% | 2017-10-13: 0.00025% | 0%
| CHEMICAL WAREHOUSE REBAR | Install and Final Inspection |  | 90% | 76639920 | 0.00224% | 2017-10-13: 1.8e-05; 2017-12-12: 0.00036% | 8e-05%
0%
C787 | CHEMICAL WAREHOUSE CONCRETE | Tranport Material to site |  | 10% | 3421425 | 0.0001% | 2017-10-13: 0.0001% | 0%
| CHEMICAL WAREHOUSE CONCRETE | Install and Final Inspection |  | 90% | 31477110 | 0.00092% | 2017-10-13: 9e-07; 2017-11-12: 4e-07; 2017-12-12: 7e-05% | 0.00072%
| P3FH - 28 M.14.14.2.1.2.2 Steel Structure | [35 empty] | 0%
| CONC2820 | WAREHOUSE CHEMICAL - SS Erection | [34 empty] | 0%
C788 | CONC2830 | WAREHOUSE CHEMICAL - Roof & Cladding Installation | [34 empty] | 0%
| CHEMICAL WAREHOUSE STEEL STRUCTURE & ROOF SIDING | Transport material to site |  | 10% | 71849925 | 0.0021% | [30 empty] | 0.0021%
| CHEMICAL WAREHOUSE STEEL STRUCTURE & ROOF SIDING | Check elevation & orientation |  | 20% | 143699850 | 0.0042% | [30 empty] | 0.0042%
| CHEMICAL WAREHOUSE STEEL STRUCTURE & ROOF SIDING | Pre-assembly on the ground |  | 10% | 71849925 | 0.0021% | [30 empty] | 0.0021%
| CHEMICAL WAREHOUSE STEEL STRUCTURE & ROOF SIDING | Installation |  | 40% | 287057557.5 | 0.00839% | [30 empty] | 0.00839%
| CHEMICAL WAREHOUSE STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 20% | 143699850 | 0.0042% | [30 empty] | 0.0042%
| P3FH - 28 M.14.14.2.1.1 Warehouse for Mechanical | [35 empty] | 0%
| P3FH - 28 M.14.14.2.1.1.1 RC Foundation | [35 empty] | 0%
| CONC2890 | WAREHOUSE MECHANICAL - RC Foundation | [34 empty] | 0%
C731 |  | Tranport Material to site |  | 10% | 8553562.5 | 0.00025% | 2017-08-14: 0.00025% | 0%
|  | Install and Final Inspection |  | 90% | 76639920 | 0.00224% | 2017-08-14: 3.8e-06; 2017-09-13: 1.18e-05; 2017-10-13: 2.4e-06; 2017-11-12: 2e-06; 2017-12-12: 0.00016% | 8e-05%
0%
C732 |  | Tranport Material to site |  | 10% | 3421425 | 0.0001% | 2017-09-13: 0.0001% | 0%
|  | Install and Final Inspection |  | 90% | 31477110 | 0.00092% | 2017-09-13: 6e-07; 2017-10-13: 2e-07; 2017-11-12: 3e-07; 2017-12-12: 7e-05% | 0.00074%
| P3FH - 28 M.14.14.2.1.1.2 Steel Structure | [35 empty] | 0%
| CONC2900 | WAREHOUSE MECHANICAL - SS Erection | [34 empty] | 0%
C733 | CONC2910 | WAREHOUSE MECHANICAL - Roof & Cladding Installation | [34 empty] | 0%
| WAREHOUSE STEEL STRUCTURE & ROOF SIDING | Transport material to site |  | 10% | 71849925 | 0.0021% | [30 empty] | 0.0021%
| WAREHOUSE STEEL STRUCTURE & ROOF SIDING | Check elevation & orientation |  | 20% | 143699850 | 0.0042% | [30 empty] | 0.0042%
| WAREHOUSE STEEL STRUCTURE & ROOF SIDING | Pre-assembly on the ground |  | 10% | 71849925 | 0.0021% | [30 empty] | 0.0021%
| WAREHOUSE STEEL STRUCTURE & ROOF SIDING | Installation |  | 40% | 287057557.5 | 0.00839% | [30 empty] | 0.00839%
| WAREHOUSE STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 20% | 143699850 | 0.0042% | [30 empty] | 0.0042%
| P3FH - 28 M.14.14.2.1.3 Warehouse for Electrical | [35 empty] | 0%
| P3FH - 28 M.14.14.2.1.3.1 RC Foundation | [35 empty] | 0%
| CONC2840 | WAREHOUSE ELECTRICAL - RC Foundation | [34 empty] | 0%
C782 | ELECTRICAL & INSTRUMENT WAREHOUSE REBAR | Tranport Material to site |  | 10% | 8553562.5 | 0.00025% | 2017-10-13: 0.00025% | 0%
| ELECTRICAL & INSTRUMENT WAREHOUSE REBAR | Install and Final Inspection |  | 90% | 76639920 | 0.00224% | 2017-10-13: 1.8e-05; 2017-12-12: 0.00036% | 8e-05%
0%
C783 | ELECTRICAL & INSTRUMENT WAREHOUSE CONCRETE | Tranport Material to site |  | 10% | 3421425 | 0.0001% | 2017-10-13: 0.0001% | 0%
| ELECTRICAL & INSTRUMENT WAREHOUSE CONCRETE | Install and Final Inspection |  | 90% | 31477110 | 0.00092% | 2017-10-13: 9e-07; 2017-11-12: 3e-07; 2017-12-12: 7e-05% | 0.00073%
| P3FH - 28 M.14.14.2.1.3.2 Steel Structure | [35 empty] | 0%
| CONC2850 | WAREHOUSE ELECTRICAL- SS Erection | [34 empty] | 0%
C784 | CONC2860 | WAREHOUSE ELECTRICAL - Roof & Cladding Installation | [34 empty] | 0%
| ELECTRICAL & INSTRUMENT WAREHOUSE STEEL STRUCTURE & ROOF SIDING | Transport material to site |  | 10% | 71849925 | 0.0021% | [30 empty] | 0.0021%
| ELECTRICAL & INSTRUMENT WAREHOUSE STEEL STRUCTURE & ROOF SIDING | Check elevation & orientation |  | 20% | 143699850 | 0.0042% | [30 empty] | 0.0042%
| ELECTRICAL & INSTRUMENT WAREHOUSE STEEL STRUCTURE & ROOF SIDING | Pre-assembly on the ground |  | 10% | 71849925 | 0.0021% | [30 empty] | 0.0021%
| ELECTRICAL & INSTRUMENT WAREHOUSE STEEL STRUCTURE & ROOF SIDING | Installation |  | 40% | 287057557.5 | 0.00839% | [30 empty] | 0.00839%
| ELECTRICAL & INSTRUMENT WAREHOUSE STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 20% | 143699850 | 0.0042% | [30 empty] | 0.0042%
| P3FH - 28 M.14.14.2.1.7 Workshop for Heavy Equipment & Mechanical Maintenance | [35 empty] | 0%
| P3FH - 28 M.14.14.2.1.7.1 RC Foundation | [35 empty] | 0%
| CONC2870 | WORKSHOP MECHANICAL - RC Foundation | [34 empty] | 0%
C774 | MECHANICAL MAINTENANCE & HEAVY EQUIPMENT WORKSHOP REBAR | Tranport Material to site |  | 10% | 17449267.5 | 0.00051% | 2017-08-14: 0.00051% | 0%
| MECHANICAL MAINTENANCE & HEAVY EQUIPMENT WORKSHOP REBAR | Install and Final Inspection |  | 90% | 156016980 | 0.00456% | 2017-08-14: 7.4e-06; 2017-09-13: 3.33e-05 | 0.00049%
0%
C775 | MECHANICAL MAINTENANCE & HEAVY EQUIPMENT WORKSHOP CONCRETE | Tranport Material to site |  | 10% | 8895705 | 0.00026% | 2017-09-13: 0.00026% | 0%
| MECHANICAL MAINTENANCE & HEAVY EQUIPMENT WORKSHOP CONCRETE | Install and Final Inspection |  | 90% | 80403487.5 | 0.00235% | 2017-09-13: 4.5e-06; 2017-11-12: 6e-07; 2017-12-12: 8e-05% | 0.00176%
| P3FH - 28 M.14.14.2.1.7.2 Steel Structure | [35 empty] | 0%
| CONC2880 | WORKSHOP MECHANICAL - SS Erection | [34 empty] | 0%
C776 | CONC2920 | WORKSHOP MECHANICAL - Roof & Cladding Installation | [34 empty] | 0%
| MECHANICAL MAINTENANCE & HEAVY EQUIPMENT WORKSHOP STEEL STRUCTURE & ROOF SIDING | Transport material to site |  | 10% | 110512027.5 | 0.00323% | [30 empty] | 0.00323%
| MECHANICAL MAINTENANCE & HEAVY EQUIPMENT WORKSHOP STEEL STRUCTURE & ROOF SIDING | Check elevation & orientation |  | 20% | 221024055 | 0.00646% | [30 empty] | 0.00646%
| MECHANICAL MAINTENANCE & HEAVY EQUIPMENT WORKSHOP STEEL STRUCTURE & ROOF SIDING | Pre-assembly on the ground |  | 10% | 110512027.5 | 0.00323% | [30 empty] | 0.00323%
| MECHANICAL MAINTENANCE & HEAVY EQUIPMENT WORKSHOP STEEL STRUCTURE & ROOF SIDING | Installation |  | 40% | 442390252.5 | 0.01293% | [30 empty] | 0.01293%
| MECHANICAL MAINTENANCE & HEAVY EQUIPMENT WORKSHOP STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 20% | 221024055 | 0.00646% | [30 empty] | 0.00646%
| P3FH - 28 M.14.14.2.1.8 Workshop for Fabricant Machinary | [35 empty] | 0%
| P3FH - 28 M.14.14.2.1.8.1 RC Foundation | [35 empty] | 0%
| CONC2930 | WORKSHOP FABRICANT MACHINERY - RC Foundation | [34 empty] | 0%
C740 | WORKSHOP REBAR | Tranport Material to site |  | 10% | 25318545 | 0.00074% | 2017-08-14: 0.00074% | 0%
| WORKSHOP REBAR | Install and Final Inspection |  | 90% | 228209047.5 | 0.00667% | 2017-08-14: 1.87e-05; 2017-09-13: 2.43e-05; 2017-10-13: 2e-05 | 0.00037%
0%
C741 | WORKSHOP CONCRETE | Tranport Material to site |  | 10% | 26687115 | 0.00078% | 2017-08-14: 0.00078% | 0%
| WORKSHOP CONCRETE | Install and Final Inspection |  | 90% | 241210462.5 | 0.00705% | 2017-08-14: 1e-06; 2017-09-13: 6.9e-06; 2017-10-13: 8e-06; 2017-12-12: 0.00041% | 0.00505%
| P3FH - 28 M.14.14.2.1.8.2 Steel Structure | [35 empty] | 0%
| CONC2940 | WORKSHOP FABRICANT MACHINERY - SS Erection | [34 empty] | 0%
C742 | CONC2950 | WORKSHOP FABRICANT MACHINERY - Roof & Cladding Installation | [34 empty] | 0%
| WORKSHOP STEEL STRUCTURE & ROOF SIDING | Transport material to site |  | 10% | 146779132.5 | 0.00429% | [30 empty] | 0.00429%
| WORKSHOP STEEL STRUCTURE & ROOF SIDING | Check elevation & orientation |  | 20% | 293216122.5 | 0.00857% | [30 empty] | 0.00857%
| WORKSHOP STEEL STRUCTURE & ROOF SIDING | Pre-assembly on the ground |  | 10% | 146779132.5 | 0.00429% | [30 empty] | 0.00429%
| WORKSHOP STEEL STRUCTURE & ROOF SIDING | Installation |  | 40% | 586090102.5 | 0.01713% | [30 empty] | 0.01713%
| WORKSHOP STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 20% | 293216122.5 | 0.00857% | [30 empty] | 0.00857%
| P3FH - 28 M.14.14.2.1.9 Worshop for Electrical Maintenance and Control & Instrument | [35 empty] | 0%
| P3FH - 28 M.14.14.2.1.9.1 RC Foundation | [35 empty] | 0%
| CONC2960 | WORKSHOP E/I - RC Foundation | [34 empty] | 0%
C778 | ELECTRICAL MAINTENANCE & INSTRUMENT CONTROL WORKSHOP REBAR | Tranport Material to site |  | 10% | 13343557.5 | 0.00039% | 2017-08-14: 0.00039% | 0%
| ELECTRICAL MAINTENANCE & INSTRUMENT CONTROL WORKSHOP REBAR | Install and Final Inspection |  | 90% | 120092017.5 | 0.00351% | 2017-08-14: 9.1e-06; 2017-09-13: 1.83e-05; 2017-10-13: 5.8e-06 | 0.00019%
0%
C779 | ELECTRICAL MAINTENANCE & INSTRUMENT CONTROL WORKSHOP CONCRETE | Tranport Material to site |  | 10% | 6842850 | 0.0002% | 2017-09-13: 0.0002% | 0%
| ELECTRICAL MAINTENANCE & INSTRUMENT CONTROL WORKSHOP CONCRETE | Install and Final Inspection |  | 90% | 62269935 | 0.00182% | 2017-09-13: 1.9e-06; 2017-10-13: 2.9e-06; 2017-12-12: 0.00013%; 2018-02-10: 3e-05% | 0.00118%
| P3FH - 28 M.14.14.2.1.9.2 Steel Structure | [35 empty] | 0%
| CONC2970 | WORKSHOP E/I - SS Erection | [34 empty] | 0%
C780 | CONC2980 | WORKSHOP E/I - Roof & Cladding Installation | [34 empty] | 0%
| ELECTRICAL MAINTENANCE & INSTRUMENT CONTROL WORKSHOP STEEL STRUCTURE & ROOF SIDING | Transport material to site |  | 10% | 82114200 | 0.0024% | 2018-03-12: 0.0024% | 0%
| ELECTRICAL MAINTENANCE & INSTRUMENT CONTROL WORKSHOP STEEL STRUCTURE & ROOF SIDING | Check elevation & orientation |  | 20% | 164570542.5 | 0.00481% | 2018-03-12: 0.00087%; 2018-04-11: 0.00394% | 0%
| ELECTRICAL MAINTENANCE & INSTRUMENT CONTROL WORKSHOP STEEL STRUCTURE & ROOF SIDING | Pre-assembly on the ground |  | 10% | 82114200 | 0.0024% | 2018-04-11: 0.0024% | 0%
| ELECTRICAL MAINTENANCE & INSTRUMENT CONTROL WORKSHOP STEEL STRUCTURE & ROOF SIDING | Installation |  | 40% | 329141085 | 0.00962% | 2018-04-11: 0.00689% | 0.00273%
| ELECTRICAL MAINTENANCE & INSTRUMENT CONTROL WORKSHOP STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 20% | 164570542.5 | 0.00481% | 2018-05-11: 0.00401% | 0.0008%
| P3FH - 28 M.14.14.2.1.14 Administration Building | [35 empty] | 0%
| P3FH - 28 M.14.14.2.1.14.1 RC Building | [35 empty] | 0%
| CONC2990 | ADM BUILDING - RC Building | [34 empty] | 0%
C727 | ADMINISTRATION OFFICE BUILDING REBAR | Tranport Material to site |  | 10% | 27371400 | 0.0008% | 2017-08-14: 0.0008% | 0%
| ADMINISTRATION OFFICE BUILDING REBAR | Install and Final Inspection |  | 90% | 247369027.5 | 0.00723% | 2017-08-14: 1.48e-05; 2017-09-13: 3.4e-06; 2017-11-12: 3.08e-05; 2017-12-12: 0.00072%; 2018-03-12: 0.00088% | 0.00073%
0%
C728 | ADMINISTRATION OFFICE BUILDING CONCRETE | Tranport Material to site |  | 10% | 4447852.5 | 0.00013% | 2017-09-13: 4e-05%; 2017-10-13: 9e-05% | 0%
| ADMINISTRATION OFFICE BUILDING CONCRETE | Install and Final Inspection |  | 90% | 41399242.5 | 0.00121% | 2017-10-13: 1.5e-06; 2017-12-12: 0.00012%; 2018-01-11: 0.00062%; 2018-03-12: 0.00017% | 0.00015%
| P3FH - 28 M.14.14.2.1.14.4 Roofing | [35 empty] | 0%
C729 | CONC3010 | ADM BUILDING - Roofing Installation | [34 empty] | 0%
| ADMINISTRATION OFFICE BUILDING STEEL STRUCTURE & ROOF SIDING | Transport material to site |  | 10% | 28739970 | 0.00084% | [30 empty] | 0.00084%
| ADMINISTRATION OFFICE BUILDING STEEL STRUCTURE & ROOF SIDING | Check elevation & orientation |  | 20% | 57479940 | 0.00168% | [30 empty] | 0.00168%
| ADMINISTRATION OFFICE BUILDING STEEL STRUCTURE & ROOF SIDING | Pre-assembly on the ground |  | 10% | 28739970 | 0.00084% | [30 empty] | 0.00084%
| ADMINISTRATION OFFICE BUILDING STEEL STRUCTURE & ROOF SIDING | Installation |  | 40% | 115302022.5 | 0.00337% | [30 empty] | 0.00337%
| ADMINISTRATION OFFICE BUILDING STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 20% | 57479940 | 0.00168% | [30 empty] | 0.00168%
| P3FH - 28 M.14.14.2.1.14.3 Architectural | [35 empty] | 0%
| CONC3020 | ADM BUILDING - Interior & Architectural Installation | [34 empty] | 0%
| P3FH - 28 M.14.14.2.1.4 Laboratory for Ore Preparation | [35 empty] | 0%
| P3FH - 28 M.14.14.2.1.4.1 RC Building | [35 empty] | 0%
| CONC3030 | LAB for ORE PREP - RC Building | [34 empty] | 0%
C767 | ORE PREPARATION SAMPLE LABORATORY REBAR | Tranport Material to site |  | 10% | 22581405 | 0.00066% | 2018-01-11: 0.00066% | 0%
| ORE PREPARATION SAMPLE LABORATORY REBAR | Install and Final Inspection |  | 90% | 203574787.5 | 0.00595% | 2018-01-11: 0.00121%; 2018-02-10: 0.00085%; 2018-03-12: 0.00038% | 0.00351%
0%
C768 | ORE PREPARATION SAMPLE LABORATORY CONCRETE | Tranport Material to site |  | 10% | 14027842.5 | 0.00041% | 2018-01-11: 0.00041% | 0%
| ORE PREPARATION SAMPLE LABORATORY CONCRETE | Install and Final Inspection |  | 90% | 124539870 | 0.00364% | 2018-01-11: 0.00065%; 2018-02-10: 0.00048%; 2018-03-12: 0.00027% | 0.00224%
| P3FH - 28 M.14.14.2.1.4.3 Architectural | [35 empty] | 0%
| CONC3050 | LAB for ORE PREP - Interior & Architectural Installation | [34 empty] | 0%
| P3FH - 28 M.14.14.2.1.5 Laboratory for Instrument | [35 empty] | 0%
| P3FH - 28 M.14.14.2.1.5.1 RC Building | [35 empty] | 0%
| CONC3060 | LAB for INSTRUMENT - RC Building | [34 empty] | 0%
C736 | LABORATORY REBAR | Tranport Material to site |  | 10% | 24976402.5 | 0.00073% | 2018-01-11: 0.00073% | 0%
| LABORATORY REBAR | Install and Final Inspection |  | 90% | 224103337.5 | 0.00655% | 2018-01-11: 0.00219%; 2018-02-10: 0.00134%; 2018-03-12: 0.0009% | 0.00212%
0%
C737 | LABORATORY CONCRETE | Tranport Material to site |  | 10% | 3763567.5 | 0.00011% | 2018-01-11: 0.00011% | 0%
| LABORATORY CONCRETE | Install and Final Inspection |  | 90% | 35240677.5 | 0.00103% | 2018-01-11: 0.00034%; 2018-02-10: 0.00016%; 2018-03-12: 0.00019% | 0.00034%
| P3FH - 28 M.14.14.2.1.5.3 Architectural | [35 empty] | 0%
| CONC3070 | LAB for INSTRUMENT - Interior & Architectural Installation | [34 empty] | 0%
C738 | LABORATORY ARCHITECTURAL | Install and Final Inspection |  | 100% | 94089187.5 | 0.00275% | [30 empty] | 0.00275%
| P3FH - 28 M.14.14.2.1.6 Laboratory for Chemical | [35 empty] | 0%
| P3FH - 28 M.14.14.2.1.6.1 RC Building | [35 empty] | 0%
| CONC3080 | LAB for CHEMICAL - RC Building | [34 empty] | 0%
C764 | CHEMICAL LABORATORY REBAR | Tranport Material to site |  | 10% | 15396412.5 | 0.00045% | [30 empty] | 0.00045%
| CHEMICAL LABORATORY REBAR | Install and Final Inspection |  | 90% | 137541285 | 0.00402% | 2018-02-10: 0.00119%; 2018-03-12: 0.00067%; 2018-04-11: 0.00087% | 0.00129%
0%
C765 | CHEMICAL LABORATORY CONCRETE | Tranport Material to site |  | 10% | 9579990 | 0.00028% | 2018-01-11: 0.00024% | 4e-05%
| CHEMICAL LABORATORY CONCRETE | Install and Final Inspection |  | 90% | 86219910 | 0.00252% | 2018-02-10: 0.00042%; 2018-03-12: 0.00036%; 2018-04-11: 0.00065% | 0.00109%
| P3FH - 28 M.14.14.2.1.6.3 Architectural | [35 empty] | 0%
| CONC3090 | LAB for CHEMICAL - Interior & Architectural Installation | [34 empty] | 0%
| P3FH - 28 M.14.14.2.1.10 Fire Station House | [35 empty] | 0%
| P3FH - 28 M.14.14.2.1.10.1 RC Foundation/Building | [35 empty] | 0%
| P3FH - 28 M.14.14.2.1.10.1.1 RC Foundation for Equipment | [35 empty] | 0%
| CONC3130 | FIRE STATION - RC Foundation | [34 empty] | 0%
| P3FH - 28 M.14.14.2.1.10.1.2 RC Building | [35 empty] | 0%
| CONC3140 | FIRE STATION - RC Building | [34 empty] | 0%
C744 | FIRE STATION HAOUSE REBAR | Tranport Material to site |  | 10% | 9922132.5 | 0.00029% | 2017-10-13: 0.00029% | 0%
| FIRE STATION HAOUSE REBAR | Install and Final Inspection |  | 90% | 88957050 | 0.0026% | 2017-10-13: 0.00059%; 2017-11-12: 3.8e-06; 2017-12-12: 0.00094%; 2018-01-11: 0.00059%; 2018-04-11: 3e-05% | 7e-05%
0%
C745 | FIRE STATION HAOUSE CONCRETE | Tranport Material to site |  | 10% | 6500707.5 | 0.00019% | 2017-10-13: 0.00019% | 0%
| FIRE STATION HAOUSE CONCRETE | Install and Final Inspection |  | 90% | 59874937.5 | 0.00175% | 2017-10-13: 3.7e-06; 2017-11-12: 1.5e-06; 2017-12-12: 0.00018%; 2018-01-11: 0.00046%; 2018-04-11: 8e-05% | 0.00051%
0%
C748 | FIRE STATION SHELTER STEEL STRUCTURE & ROOF SIDING | Install and Final Inspection |  | 100% | 59532795 | 0.00174% | [30 empty] | 0.00174%
| P3FH - 28 M.14.14.2.1.10.3 Pump House | [35 empty] | 0%
| CONC3150 | FIRE STATION - Pump House | [34 empty] | 0%
C750 | PUMP HOUSE FOR FIRE STATION REBAR | Tranport Material to site |  | 10% | 5816422.5 | 0.00017% | [30 empty] | 0.00017%
| PUMP HOUSE FOR FIRE STATION REBAR | Install and Final Inspection |  | 90% | 52689945 | 0.00154% | [30 empty] | 0.00154%
0%
C751 | PUMP HOUSE FOR FIRE STATION CONCRETE | Tranport Material to site |  | 10% | 6158565 | 0.00018% | [30 empty] | 0.00018%
| PUMP HOUSE FOR FIRE STATION CONCRETE | Install and Final Inspection |  | 90% | 54742800 | 0.0016% | [30 empty] | 0.0016%
| P3FH - 28 M.14.14.2.1.13 Mosque | [35 empty] | 0%
| P3FH - 28 M.14.14.2.1.13.1 RC Building | [35 empty] | 0%
| CONC3100 | MOSQUE - RC Building | [34 empty] | 0%
C770 | MUSHOLLA REBAR | Tranport Material to site |  | 10% | 9922132.5 | 0.00029% | 2017-12-12: 0.00029% | 0%
| MUSHOLLA REBAR | Install and Final Inspection |  | 90% | 90325620 | 0.00264% | 2017-12-12: 0.00104%; 2018-01-11: 0.00124%; 2018-04-11: 8e-05% | 0.00028%
0%
C771 | MUSHOLLA CONCRETE | Tranport Material to site |  | 10% | 3421425 | 0.0001% | 2017-12-12: 0.0001% | 0%
| MUSHOLLA CONCRETE | Install and Final Inspection |  | 90% | 30450682.5 | 0.00089% | 2017-12-12: 0.00031%; 2018-01-11: 0.00042%; 2018-04-11: 2e-05% | 0.00014%
| P3FH - 28 M.14.14.2.1.13.4 Roofing | [35 empty] | 0%
C772 | CONC3120 | MOSQUE - Roofing Installation | [34 empty] | 0%
| MUSHOLLA STEEL STRUCTURE & ROOF SIDING | Transport material to site |  | 10% | 18133552.5 | 0.00053% | [30 empty] | 0.00053%
| MUSHOLLA STEEL STRUCTURE & ROOF SIDING | Check elevation & orientation |  | 20% | 36609247.5 | 0.00107% | [30 empty] | 0.00107%
| MUSHOLLA STEEL STRUCTURE & ROOF SIDING | Pre-assembly on the ground |  | 10% | 18133552.5 | 0.00053% | [30 empty] | 0.00053%
| MUSHOLLA STEEL STRUCTURE & ROOF SIDING | Installation |  | 40% | 73218495 | 0.00214% | [30 empty] | 0.00214%
| MUSHOLLA STEEL STRUCTURE & ROOF SIDING | Final inspection |  | 20% | 36609247.5 | 0.00107% | [30 empty] | 0.00107%
| P3FH - 28 M.14.14.2.1.13.3 Architectural | [35 empty] | 0%
| CONC3110 | MOSQUE- Interior & Architectural Installation | [34 empty] | 0%
| P3FH - 28 M.14.14.2.1.11 Gate House | [35 empty] | 0%
| P3FH - 28 M.14.14.2.1.11.1 RC Building | [35 empty] | 0%
| CONC3160 | GATE - RC Building | [34 empty] | 0%
C757 | GATE HOUSE REBAR | Tranport Material to site |  | 10% | 2394997.5 | 7e-05% | [30 empty] | 7e-05%
| GATE HOUSE REBAR | Install and Final Inspection |  | 90% | 21212835 | 0.00062% | [30 empty] | 0.00062%
0%
C758 | GATE HOUSE CONCRETE | Tranport Material to site |  | 10% | 4447852.5 | 0.00013% | [30 empty] | 0.00013%
| GATE HOUSE CONCRETE | Install and Final Inspection |  | 90% | 39346387.5 | 0.00115% | [30 empty] | 0.00115%
| P3FH - 28 M.14.14.2.1.11.3 Architectural | [35 empty] | 0%
| CONC3170 | GATE - Interior & Architectural Installation | [34 empty] | 0%
| P3FH - 28 M.14.14.2.1.12 Weight Bridge Building | [35 empty] | 0%
| P3FH - 28 M.14.14.2.1.12.1 RC Foundation/ Building | [35 empty] | 0%
| P3FH - 28 M.14.14.2.1.12.1.1 RC Foundation for Weight Bridge | [35 empty] | 0%
C735 | CONC3180 | WEIGHBRIDGE - Piling & RC Foundation | [34 empty] | 0%
|  | Tranport Material to site |  | 10% | 31819252.5 | 0.00093% | 2018-03-12: 0.00093% | 0%
|  | Install and Final Inspection |  | 90% | 287057557.5 | 0.00839% | 2018-03-12: 0.00839% | 0%
| P3FH - 28 M.14.14.2.1.12.1.2 RC Building | [35 empty] | 0%
| CONC3190 | WEIGHBRIDGE - RC Building | [34 empty] | 0%
C754 | WEIGHT BRIDGE & CONTROL ROOM REBAR | Tranport Material to site |  | 10% | 10264275 | 0.0003% | [30 empty] | 0.0003%
| WEIGHT BRIDGE & CONTROL ROOM REBAR | Install and Final Inspection |  | 90% | 91694190 | 0.00268% | 2018-04-11: 0.00179% | 0.00089%
0%
C755 | WEIGHT BRIDGE & CONTROL ROOM CONCRETE | Tranport Material to site |  | 10% | 5816422.5 | 0.00017% | [30 empty] | 0.00017%
| WEIGHT BRIDGE & CONTROL ROOM CONCRETE | Install and Final Inspection |  | 90% | 52689945 | 0.00154% | 2018-04-11: 0.00099% | 0.00055%
| P3FH - 28 M.14.14.2.2 Road, Drainage, Parking Area & Retaining Wall | [35 empty] | 0%
| P3FH - 28 M.14.14.2.2.5 Road | [35 empty] | 0%
| P3FH - 28 M.14.14.2.2.5.2 Lean Concrete | [35 empty] | 0%
| CONC-INFRA-1000 | ROAD - Lean Concrete | [34 empty] | 0%
C385 | ROAD & PAVEMENT CONCRETE | Tranport Material to site |  | 10% | 14027842.5 | 0.0042% | 2017-07-15: 0.0042% | 0%
| ROAD & PAVEMENT CONCRETE | Install and Final Inspection |  | 90% | 125908440 | 0.03776% | 2017-07-15: 0.00272%; 2017-08-14: 0.00116% | 0.03388%
| P3FH - 28 M.14.14.2.2.5.1 Rigid/FlexiblePavement | [35 empty] | 0%
| CONC-INFRA-1010 | ROAD - RIgid / Flexible Pavement | [34 empty] | 0%
C382 | ROAD & SIGN MARKIN CONCRETE | Tranport Material to site |  | 10% | 143699850 | 0.00041% | [30 empty] | 0.00041%
| ROAD & SIGN MARKIN CONCRETE | Install and Final Inspection |  | 90% | 1291930080 | 0.00368% | [30 empty] | 0.00368%
0%
C383 | ROAD & PAVEMENT REBAR | Tranport Material to site |  | 10% | 43109955 | 0.00126% | [30 empty] | 0.00126%
| ROAD & PAVEMENT REBAR | Install and Final Inspection |  | 90% | 386621025 | 0.0113% | [30 empty] | 0.0113%
| P3FH - 28 M.14.14.2.2.6 Drainage | [35 empty] | 0%
| CONC-INFRA-1040 | Drainage Work | [34 empty] | 0%
C368 | CONTROL BOX CONCRETE | Tranport Material to site |  | 10% | 117012735 | 0.00342% | 2018-02-10: 0.00025%; 2018-03-12: 0.00179%; 2018-04-11: 8e-05% | 0.0013%
| CONTROL BOX CONCRETE | Install and Final Inspection |  | 90% | 1052772472.5 | 0.03077% | [30 empty] | 0.03077%
0%
C369 | CONTROL BOX REBAR | Tranport Material to site |  | 10% | 180309097.5 | 0.00527% | 2018-02-10: 0.0004%; 2018-03-12: 0.003%; 2018-04-11: 0.0005% | 0.00137%
| CONTROL BOX REBAR | Install and Final Inspection |  | 90% | 1622097592.5 | 0.04741% | [30 empty] | 0.04741%
| P3FH - 28 M.14.14.2.2.3 Parking Area | [35 empty] | 0%
| P3FH - 28 M.14.14.2.2.3.2 Foundation & Floor | [35 empty] | 0%
| CONC-INFRA-1020 | PARKING AREA - Foundation & Floor | [34 empty] | 0%
C391 | PARKING & VEHICLE SHED CONCRETE | Tranport Material to site |  | 10% | 84167055 | 0.00246% | [30 empty] | 0.00246%
| PARKING & VEHICLE SHED CONCRETE | Install and Final Inspection |  | 90% | 755792782.5 | 0.02209% | [30 empty] | 0.02209%
0%
C392 | PARKING & VEHICLE SHED REBAR | Tranport Material to site |  | 10% | 27029257.5 | 0.00079% | [30 empty] | 0.00079%
| PARKING & VEHICLE SHED REBAR | Install and Final Inspection |  | 90% | 242921175 | 0.0071% | [30 empty] | 0.0071%
| P3FH - 28 M.14.14.2.2.3.1 Shelter | [35 empty] | 0%
| CONC-INFRA-1030 | PARKING AREA - Shelter | [34 empty] | 0%
C394 | TOILETS & OTHER SANITARY FACILITIES CONCRETE, REBAR | Tranport Material to site |  | 10% | 7869277.5 | 0.00023% | [30 empty] | 0.00023%
| TOILETS & OTHER SANITARY FACILITIES CONCRETE, REBAR | Install and Final Inspection |  | 90% | 71165640 | 0.00208% | [30 empty] | 0.00208%
| P3FH - 28 M.14.14.2.2.4 Retaining Wall | [35 empty] | 0%
| CONC-INFRA-1050 | Retaining Wall | [34 empty] | 0%
C397 | RETAINING WALL CONCRETE | Tranport Material to site |  | 10% | 126934867.5 | 0.00371% | 2017-09-13: 0.00371% | 0%
| RETAINING WALL CONCRETE | Install and Final Inspection |  | 90% | 1143440235 | 0.03342% | 2017-09-13: 0.0001558; 2017-10-13: 8.59e-05; 2017-11-12: 0.00849%; 2017-12-12: 0.00074% | 2e-05%
0%
C398 | RETAINING WALL REBAR | Tranport Material to site |  | 10% | 276451140 | 0.00808% | 2017-08-14: 0.00808% | 0%
| RETAINING WALL REBAR | Install and Final Inspection |  | 90% | 2488402402.5 | 0.07273% | 2017-08-14: 6.19e-05; 2017-09-13: 0.0003415; 2017-10-13: 0.0001236; 2017-11-12: 0.0001889; 2017-12-12: 0.00112% | 2e-05%
0%
C400 | GRASS LANDSCAPPING | Install and Final Inspection |  | 100% | 368145330 | 0.01076% | [30 empty] | 0.01076%
0%
0%
C402 | TRENCHES & DUCT SUPPORT CONCRETE, REBAR | Tranport Material to site |  | 10% | 9579990 | 0.00028% | [30 empty] | 0.00028%
| TRENCHES & DUCT SUPPORT CONCRETE, REBAR | Install and Final Inspection |  | 90% | 86562052.5 | 0.00253% | [30 empty] | 0.00253%
0%
C404 | TRENCHES & DUCT SUPPORT COMPACT SAND | Tranport Material to site |  | 10% | 95799900 | 0.0028% | [30 empty] | 0.0028%
| TRENCHES & DUCT SUPPORT COMPACT SAND | Install and Final Inspection |  | 90% | 861856957.5 | 0.02519% | [30 empty] | 0.02519%
0%
0%
| P3FH - 28 M. Mechanical Work |  |  |  | 221376803917.5008 | 6.47% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1484% | 0.05417% | 0.4056% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.862%
| P3FH - 28 M.14.14.3.14.3.1 System 1 - Ore Preparation | [35 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.1 Ore Receiving Equipment | [35 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.1.1 Shake Out Machine (1101) | [35 empty] | 0%
| CONM1000 | Shake Out Machine (1101) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.1.14.3.1.1.2 Belt Feeder (1102) | [35 empty] | 0%
| CONM1010 | BELT FEEDER - Anchoor & Mounting Drive Unit | [34 empty] | 0%
E18 | CONM1020 | Alignment | [34 empty] | 0%
|  | Transport material to site |  | 10% | 71849925 | 0.0021% | [30 empty] | 0.0021%
|  | Check elevation & orientation |  | 20% | 144041992.5 | 0.00421% | [30 empty] | 0.00421%
|  | Pre-assembly on the ground |  | 10% | 71849925 | 0.0021% | [30 empty] | 0.0021%
|  | Installation |  | 40% | 288426127.5 | 0.00843% | [30 empty] | 0.00843%
|  | Setting allignment |  | 10% | 71849925 | 0.0021% | [30 empty] | 0.0021%
|  | Final inspection |  | 10% | 71849925 | 0.0021% | [30 empty] | 0.0021%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.1.14.3.1.1.3 Belt Conveyor (Tunnel) - (1103) | [35 empty] | 0%
| CONM1030 | BELT CONVEYOR (TUNNEL) (1103) - Frame | [34 empty] | 0%
| CONM1040 | Carrier Roller | [34 empty] | 0%
| CONM1050 | Skirt | [34 empty] | 0%
| CONM1060 | Belt | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.1.14.3.1.1.4 Belt Conveyor (Girder) - (1103) | [35 empty] | 0%
| CONM1070 | BELT CONVEYOR (GIRDER) (1103) - Girder, Carrier Roller | [34 empty] | 0%
| CONM1080 | Head Part, Pulley, Drive | [34 empty] | 0%
E18 | CONM1090 | Belt Weigher (1103) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 71849925 | 0.0021% | [30 empty] | 0.0021%
|  | Check elevation & orientation |  | 20% | 144041992.5 | 0.00421% | [30 empty] | 0.00421%
|  | Pre-assembly on the ground |  | 10% | 71849925 | 0.0021% | [30 empty] | 0.0021%
|  | Installation |  | 40% | 288426127.5 | 0.00843% | [30 empty] | 0.00843%
|  | Setting allignment |  | 10% | 71849925 | 0.0021% | [30 empty] | 0.0021%
|  | Final inspection |  | 10% | 71849925 | 0.0021% | [30 empty] | 0.0021%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.1.2 CDPS - (1199) | [35 empty] | 0%
| CONM1100 | CDPS (1199) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.2 Ore Drying Equipment & Gas Treatment | [35 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.2.14.3.1.2.1 Rotary Dryer (Hood) - (1201) | [35 empty] | 0%
| CONM1110 | ROTARY DRYER(HOOD) - Inlet & outlet Hood (Lower Part) | [34 empty] | 0%
| CONM1120 | ROTARY DRYER(HOOD) - Inlet & outlet Hood (Upper Part) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.2.14.3.1.2.2 Rotary Dryer (Roller) - (1201) | [35 empty] | 0%
| CONM1150 | ROTARY DRYER(ROLLER) - Set Liner to bed | [34 empty] | 0%
| CONM1130 | Chipping & Padding | [34 empty] | 0%
| CONM1140 | Mounting & Pre-alignment bed | [34 empty] | 0%
| CONM1160 | Anchor grouting, Padding, Final Alignment | [34 empty] | 0%
| CONM1170 | Assemble Roller | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.2.14.3.1.2.3 Rotary Dryer (Shell) - (1201) | [35 empty] | 0%
| CONM1180 | ROTARY DRYER(SHELL) - Shell & Tyre Pre-assembly | [34 empty] | 0%
| CONM1190 | Shell Erection & centering | [34 empty] | 0%
| CONM1210 | Welding (No Rotation) | [34 empty] | 0%
| CONM1230 | Air Seal | [34 empty] | 0%
| CONM1220 | Cleaning, Lifter, cross plate | [34 empty] | 0%
| CONM1200 | UT test | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.2.14.3.1.2.4 Rotary Dryer (Girth Gear, Pinion) - (1201) | [35 empty] | 0%
| CONM1240 | ROTARY DRYER(GIRTH GEAR,PINION) - Putting Lower G.G | [34 empty] | 0%
| CONM1290 | Assemble Pinion | [34 empty] | 0%
| CONM1250 | Attach G.G | [34 empty] | 0%
| CONM1260 | Alignment G.G | [34 empty] | 0%
| CONM1270 | Drilling, Bolt | [34 empty] | 0%
| CONM1310 | Pre-Alignment Pinion, Reducer, Motor | [34 empty] | 0%
| CONM1300 | Tooth Contact (Rotated by Main Motor Min. Speed) | [34 empty] | 0%
| CONM1320 | Final Alignment | [34 empty] | 0%
| CONM1280 | G.G Cover | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.2.14.3.1.2.5 Gear Reducer & Main Motor - (1201) | [35 empty] | 0%
| CONM1330 | GEAR REDUCER & MAIN MOTOR - Main Motor Rotate Test (VVVF) | [34 empty] | 0%
E19 | CONM1340 | Final Alignment | [34 empty] | 0%
|  | Transport material to site |  | 10% | 218286915 | 0.00638% | 2018-03-12: 0.00638% | 0%
|  | Check elevation & orientation |  | 20% | 436231687.5 | 0.01275% | 2018-03-12: 0.01275% | 0%
|  | Pre-assembly on the ground |  | 10% | 218286915 | 0.00638% | 2018-03-12: 0.003509%; 2018-04-11: 0.002871% | 0%
|  | Installation |  | 40% | 872463375 | 0.0255% | 2018-04-11: 0.01487% | 0.01063%
|  | Setting allignment |  | 10% | 218286915 | 0.00638% | 2018-05-11: 0.00031% | 0.00607%
|  | Final inspection |  | 10% | 218286915 | 0.00638% | [30 empty] | 0.00638%
0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.2.1 Lub. Unit for Gear Reducer - (1202) | [35 empty] | 0%
| CONM1350 | Lub. Unit for Gear Reducer - (1202) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.2.2 Lub. Unit for Pinion & Thruster - (1203) | [35 empty] | 0%
| CONM1360 | Lub. Unit for Pinion & Thruster - (1203) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.2.14.3.1.2.8 Electrostatic Presipitator (1204) | [35 empty] | 0%
| CONM1370 | ELECTROSTATIC PRESIPITATOR - Support | [34 empty] | 0%
| CONM1380 | Pre-ass'y hopper | [34 empty] | 0%
| CONM1400 | Pre-ass'y Portal | [34 empty] | 0%
| CONM1440 | Pre-ass'y inlet & outlet | [34 empty] | 0%
| CONM1410 | Erection Portal & Alignment | [34 empty] | 0%
| CONM1420 | Stair | [34 empty] | 0%
| CONM1450 | Erection inlet & outlet | [34 empty] | 0%
| CONM1430 | Side casing of Inlet & welding | [34 empty] | 0%
| CONM1390 | Lift Up Hopper, welding, each plate | [34 empty] | 0%
| CONM1460 | Collecting Plate Alignment, rapping System | [34 empty] | 0%
| CONM1470 | Discharge Alignment, rapping System | [34 empty] | 0%
| CONM1480 | Hot Roof | [34 empty] | 0%
| CONM1500 | Insulation | [34 empty] | 0%
| CONM1490 | Outer Roof, TR, Whether Encloser | [34 empty] | 0%
| CONM1510 | Chain Conveyor | [34 empty] | 0%
E19 | CONM1520 | Rotary Valve | [34 empty] | 0%
|  | Transport material to site |  | 10% | 218286915 | 0.00638% | 2018-05-11: 0.00638% | 0%
|  | Check elevation & orientation |  | 20% | 436231687.5 | 0.01275% | 2018-05-11: 0.01275% | 0%
|  | Pre-assembly on the ground |  | 10% | 218286915 | 0.00638% | 2018-05-11: 0.00638% | 0%
|  | Installation |  | 40% | 872463375 | 0.0255% | 2018-05-11: 0.0255% | 0%
|  | Setting allignment |  | 10% | 218286915 | 0.00638% | 2018-05-11: 0.00638% | 0%
|  | Final inspection |  | 10% | 218286915 | 0.00638% | 2018-05-11: 0.00638% | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.2.14.3.1.2.9 Exhaust Fan - (1205) | [35 empty] | 0%
| CONM1530 | EXHAUST FAN - Fan | [34 empty] | 0%
| CONM1540 | Motor | [34 empty] | 0%
| CONM1550 | Duct (Fan-Stack) | [34 empty] | 0%
| CONM1560 | Duct (EP-Fan) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.2.14.3.1.2.10 Stack For Dryer - (1206) | [35 empty] | 0%
| CONM1570 | STACK FOR DRYER - Pre-ass'y | [34 empty] | 0%
| CONM1580 | Erection Bottom Part | [34 empty] | 0%
| CONM1590 | Erection Middle part | [34 empty] | 0%
| CONM1600 | Erection Top part | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.2.14.3.1.2.11 Chain Conveyor (Inclind) - (1207) | [35 empty] | 0%
| CONM1610 | CHAIN CONVEYOR (INCLIND) - Casing | [34 empty] | 0%
E19 | CONM1620 | Chain | [34 empty] | 0%
|  | Transport material to site |  | 10% | 218286915 | 0.00638% | [30 empty] | 0.00638%
|  | Check elevation & orientation |  | 20% | 436231687.5 | 0.01275% | [30 empty] | 0.01275%
|  | Pre-assembly on the ground |  | 10% | 218286915 | 0.00638% | [30 empty] | 0.00638%
|  | Installation |  | 40% | 872463375 | 0.0255% | [30 empty] | 0.0255%
|  | Setting allignment |  | 10% | 218286915 | 0.00638% | [30 empty] | 0.00638%
|  | Final inspection |  | 10% | 218286915 | 0.00638% | [30 empty] | 0.00638%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.2.14.3.1.2.12 Hot Air Generator - (1211) | [35 empty] | 0%
| CONM1630 | HOT AIR GENERATOR - Pre-ass'y casing Cone | [34 empty] | 0%
| CONM1640 | HOT AIR GENERATOR - Erection Cone | [34 empty] | 0%
| CONM1631 | HOT AIR GENERATOR - Pre-ass'y casing Middle | [34 empty] | 0%
| CONM1650 | HOT AIR GENERATOR - Erection middle part | [34 empty] | 0%
| CONM1632 | HOT AIR GENERATOR - Pre-ass'y casing Top Part | [34 empty] | 0%
| CONM1660 | HOT AIR GENERATOR - Erection top part | [34 empty] | 0%
| CONM1670 | HOT AIR GENERATOR - Man hole, burner, damper | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.2.14.3.1.2.12.14.3.1.2.12.6 Hot Air Generator (Refractory) | [35 empty] | 0%
| CONM1680 | HOT AIR GENERATOR(REFRACTORY) - Top cover - on the ground | [34 empty] | 0%
E19 | CONM1690 | Refractory | [34 empty] | 0%
|  | Transport material to site |  | 10% | 218286915 | 0.00638% | [30 empty] | 0.00638%
|  | Check elevation & orientation |  | 20% | 436231687.5 | 0.01275% | [30 empty] | 0.01275%
|  | Pre-assembly on the ground |  | 10% | 218286915 | 0.00638% | [30 empty] | 0.00638%
|  | Installation |  | 40% | 872463375 | 0.0255% | [30 empty] | 0.0255%
|  | Setting allignment |  | 10% | 218286915 | 0.00638% | [30 empty] | 0.00638%
|  | Final inspection |  | 10% | 218286915 | 0.00638% | [30 empty] | 0.00638%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.2.3 Pump Unit for HAG - (1212) | [35 empty] | 0%
| CONM1700 | Pump Unit for HAG - (1212) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.2.4 Valve Unit for Dryer - (1213) | [35 empty] | 0%
| CONM1710 | Valve Unit for Dryer - (1213) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.2.14.3.1.2.15 Combustion Air Fan for Dryer - (1214) | [35 empty] | 0%
| CONM1720 | COMBUSTION AIR FAN FOR DRYER - Fan | [34 empty] | 0%
| CONM1730 | Duct | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.2.14.3.1.2.16 Dilution Air Fan for Dryer - (1215) | [35 empty] | 0%
| CONM1740 | DILUTION AIR FAN FOR DRYER - Fan | [34 empty] | 0%
| CONM1750 | Duct | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.2.5 CDPS - (1299) | [35 empty] | 0%
| CONM1760 | CDPS ( Duct Dryer-EP) - (1299) | [34 empty] | 0%
| CONM1770 | CDPS (Insulation) - (1299) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.3 Dryer EP Dust Bin Room | [35 empty] | 0%
| CONM1780 | Dust Hopper | [34 empty] | 0%
| CONM1790 | Pneumatic Conveyor | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.3.14.3.1.3.3 Roots Blower | [35 empty] | 0%
| CONM1800 | Roots Blower | [34 empty] | 0%
| CONM1810 | Silencer | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.4 Pulverized Coal Feeding for Dryer | [35 empty] | 0%
| CONM1840 | Pulverized Coal Bin for Dryer HAG | [34 empty] | 0%
| CONM1850 | Loop Feeder | [34 empty] | 0%
| CONM1860 | Pneumatic Conveyor | [34 empty] | 0%
| CONM1870 | Roots Blower | [34 empty] | 0%
| CONM1880 | Bag Filter | [34 empty] | 0%
| CONM1820 | Cyclone | [34 empty] | 0%
| CONM1890 | Rotary Valve | [34 empty] | 0%
| CONM1830 | Rotary Valve | [34 empty] | 0%
| CONM1900 | Fan for Bag Filter | [34 empty] | 0%
E19 | CONM1910 | CDPS | [34 empty] | 0%
|  | Transport material to site |  | 10% | 218286915 | 0.00638% | [30 empty] | 0.00638%
|  | Check elevation & orientation |  | 20% | 436231687.5 | 0.01275% | [30 empty] | 0.01275%
|  | Pre-assembly on the ground |  | 10% | 218286915 | 0.00638% | [30 empty] | 0.00638%
|  | Installation |  | 40% | 872463375 | 0.0255% | [30 empty] | 0.0255%
|  | Setting allignment |  | 10% | 218286915 | 0.00638% | [30 empty] | 0.00638%
|  | Final inspection |  | 10% | 218286915 | 0.00638% | [30 empty] | 0.00638%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.5 Conditioned Ore Storage & Transport Conditioned Ore | [35 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.5.1 Conditoned Ore Storage | [35 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.5.1.1 Crusher (Impeller Breaker) - (1301) | [35 empty] | 0%
| CONM1920 | Crusher (Impeller Breaker) - (1301) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.5.1.14.3.1.5.2 Belt Conveyor - (1303) | [35 empty] | 0%
| CONM1930 | BELT CONVEYOR (1303) - Transfer Tower, BC | [34 empty] | 0%
| CONM1940 | Skirt | [34 empty] | 0%
| CONM1950 | Belt | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.5.1.14.3.1.5.3 Belt Conveyor- (1302) | [35 empty] | 0%
| CONM1960 | BELT CONVEYOR (1302) - Belt Conveyor | [34 empty] | 0%
| CONM1970 | Belt | [34 empty] | 0%
| CONM1980 | Drive | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.5.1.2 Two Way Chute - (1304) | [35 empty] | 0%
E20 | CONM1990 | Two Way Chute - (1304) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 77324205 | 0.00226% | [30 empty] | 0.00226%
|  | Check elevation & orientation |  | 20% | 154648410 | 0.00452% | [30 empty] | 0.00452%
|  | Pre-assembly on the ground |  | 10% | 77324205 | 0.00226% | [30 empty] | 0.00226%
|  | Installation |  | 40% | 309296820 | 0.00904% | [30 empty] | 0.00904%
|  | Setting allignment |  | 10% | 77324205 | 0.00226% | [30 empty] | 0.00226%
|  | Final inspection |  | 10% | 77324205 | 0.00226% | [30 empty] | 0.00226%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.5.2 Transport Conditioned Ore | [35 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.5.2.14.3.1.5.5 Loading Hopper - (1306) | [35 empty] | 0%
| CONM2000 | LOADING HOPPER - Hopper | [34 empty] | 0%
| CONM2010 | Hand rail, etc | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.5.2.14.3.1.5.6 Belt Feeder - (1307) | [35 empty] | 0%
| CONM2020 | Belt Feeder | [34 empty] | 0%
| CONM2030 | Drive Unit | [34 empty] | 0%
| CONM2040 | Alignment | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.5.2.14.3.1.5.7 Belt Conveyor - (1308) | [35 empty] | 0%
| CONM2050 | BELT CONVEYOR (1308) - BC | [34 empty] | 0%
| CONM2060 | Drive Unit | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.5.2.1 Two Way Chute - (1309) | [35 empty] | 0%
| CONM2070 | Two Way Chute - (1309) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.5.2.14.3.1.5.9 Belt Conveyor (Reversible) - (1310) | [35 empty] | 0%
| CONM2080 | BELT CONVEYOR (REVERSIBLE) (1310) - BC | [34 empty] | 0%
| CONM2090 | Belt | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.5.2.2 CDPS - (1399) | [35 empty] | 0%
E20 | CONM2100 | CDPS | [34 empty] | 0%
|  | Transport material to site |  | 10% | 77324205 | 0.00226% | [30 empty] | 0.00226%
|  | Check elevation & orientation |  | 20% | 154648410 | 0.00452% | [30 empty] | 0.00452%
|  | Pre-assembly on the ground |  | 10% | 77324205 | 0.00226% | [30 empty] | 0.00226%
|  | Installation |  | 40% | 309296820 | 0.00904% | [30 empty] | 0.00904%
|  | Setting allignment |  | 10% | 77324205 | 0.00226% | [30 empty] | 0.00226%
|  | Final inspection |  | 10% | 77324205 | 0.00226% | [30 empty] | 0.00226%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.6 Ore Mixing Equipment | [35 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.6.14.3.1.6.1 Conditioned Ore Bin - (1401AB) | [35 empty] | 0%
| CONM2110 | CONDITIONED ORE BIN - Mounting | [34 empty] | 0%
| CONM2120 | Cone | [34 empty] | 0%
| CONM2130 | Lining | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.6.1 Weighing Feeder - (1402) | [35 empty] | 0%
| CONM2140 | Weighing Feeder for Conditioned Ore | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.6.14.3.1.6.3 Belt Conveyor - (1403) | [35 empty] | 0%
| CONM2150 | BELT CONVEYOR - BC | [34 empty] | 0%
| CONM2160 | Drive Unit | [34 empty] | 0%
| CONM2170 | Belt | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.6.14.3.1.6.4 Belt Conveyor - (1404) | [35 empty] | 0%
| CONM2180 | BELT CONVEYOR - 1 : BC | [34 empty] | 0%
| CONM2190 | Drive Unit | [34 empty] | 0%
| CONM2200 | Belt | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.6.14.3.1.6.5 Conditioned Ore Bin for Briquetting - (1411) | [35 empty] | 0%
| CONM2210 | CONDITIONED ORE BIN FOR BRIQUETTING - Mounting | [34 empty] | 0%
| CONM2220 | Cone | [34 empty] | 0%
E21 | CONM2230 | Lining | [34 empty] | 0%
|  | Transport material to site |  | 10% | 97168470 | 0.00284% | [30 empty] | 0.00284%
|  | Check elevation & orientation |  | 20% | 194679082.5 | 0.00569% | [30 empty] | 0.00569%
|  | Pre-assembly on the ground |  | 10% | 97168470 | 0.00284% | [30 empty] | 0.00284%
|  | Installation |  | 40% | 389358165 | 0.01138% | [30 empty] | 0.01138%
|  | Setting allignment |  | 10% | 97168470 | 0.00284% | [30 empty] | 0.00284%
|  | Final inspection |  | 10% | 97168470 | 0.00284% | [30 empty] | 0.00284%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.6.2 Weighing Feeder - (1412) | [35 empty] | 0%
| CONM2240 | Weighing Feeder for Conditioned Ore | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.6.3 Loading Hopper (in Coal Storage yard) - (1421) | [35 empty] | 0%
| CONM2250 | Loading Hopper (in Reductant Coal sto. yard) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.6.4 Grizzly Feeder - (1422) | [35 empty] | 0%
| CONM2260 | Grizzly Feeder | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.6.5 Belt Conveyor - (1423) | [35 empty] | 0%
| CONM2270 | Belt Conveyor | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.6.6 Two Way Chute - (1424) | [35 empty] | 0%
| CONM2280 | Two Way Chute | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.6.14.3.1.6.11 Reductant Coal Bin - (1431) | [35 empty] | 0%
| CONM2290 | REDUCTANT COAL BIN - Mounting | [34 empty] | 0%
| CONM2300 | Cone | [34 empty] | 0%
| CONM2310 | Lining | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.6.7 Weighing Feeder - (1432) | [35 empty] | 0%
| CONM2320 | Weighing Feeder for Reduction Coal | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.6.8 CDPS - (1499) | [35 empty] | 0%
E21 | CONM2330 | CDPS | [34 empty] | 0%
|  | Transport material to site |  | 10% | 97168470 | 0.00284% | [30 empty] | 0.00284%
|  | Check elevation & orientation |  | 20% | 194336940 | 0.00568% | [30 empty] | 0.00568%
|  | Pre-assembly on the ground |  | 10% | 97168470 | 0.00284% | [30 empty] | 0.00284%
|  | Installation |  | 40% | 389358165 | 0.01138% | [30 empty] | 0.01138%
|  | Setting allignment |  | 10% | 97168470 | 0.00284% | [30 empty] | 0.00284%
|  | Final inspection |  | 10% | 97168470 | 0.00284% | [30 empty] | 0.00284%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7 Dust Briquetting Equipment | [35 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7.1 Cyclone - (1501) | [35 empty] | 0%
| CONM2340 | Cyclone for Dryer Dust - (1501) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7.2 Rotary Valve - (1502) | [35 empty] | 0%
| CONM2350 | Rotary Valve - (1502) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7.14.3.1.7.3 Dryer Dust Bin for Briquetting - (1503) | [35 empty] | 0%
| CONM2360 | DRYER DUST FOR BRIQUETTING - (1503) - Mounting | [34 empty] | 0%
| CONM2370 | Deck | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7.3 Loop Feeder - (1504) | [35 empty] | 0%
| CONM2380 | Loop Feeder for Dryer Dust - (1504) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7.4 Bag Filter for Dryer Dust - (1505) | [35 empty] | 0%
| CONM2390 | BAG FILTER FOR DRYER DUST - (1505) - Pre-assembly | [34 empty] | 0%
| CONM2400 | Mounting | [34 empty] | 0%
E22 | CONM2410 | Accessories, bag | [34 empty] | 0%
|  | Transport material to site |  | 10% | 73218495 | 0.00214% | [30 empty] | 0.00214%
|  | Check elevation & orientation |  | 20% | 146436990 | 0.00428% | [30 empty] | 0.00428%
|  | Pre-assembly on the ground |  | 10% | 73218495 | 0.00214% | [30 empty] | 0.00214%
|  | Installation |  | 40% | 292189695 | 0.00854% | [30 empty] | 0.00854%
|  | Setting allignment |  | 10% | 73218495 | 0.00214% | [30 empty] | 0.00214%
|  | Final inspection |  | 10% | 73218495 | 0.00214% | [30 empty] | 0.00214%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7.15 Rotary Valve - (1506) | [35 empty] | 0%
| CONM2420 | Rotary Valve for Bag filter - (1506) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7.14.3.1.7.5 Bag filter Fan - (1507) | [35 empty] | 0%
| CONM2430 | Bag filter Fan - (1507) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7.5 Cyclone - (1511) | [35 empty] | 0%
| CONM2440 | Cyclone for Kiln Dust - (1511) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7.13 Rotary Valve - (1512) | [35 empty] | 0%
| CONM2450 | Rotary Valve - (1512) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7.14.3.1.7.10 Kiln Dust Bin for Briquetting - (1513) | [35 empty] | 0%
| CONM2460 | KILN DUST BIN FOR BRIQUETTING - (1513) - Mounting | [34 empty] | 0%
| CONM2470 | Deck | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7.6 Loop Feeder - (1514) | [35 empty] | 0%
| CONM2480 | Loop Feeder Kiln Dust - (1514) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7.14.3.1.7.12 Bag filter for Kiln Dust - (1515) | [35 empty] | 0%
| CONM2490 | BAG FILTER KILN DUST - (1515) - Pre-assembly | [34 empty] | 0%
| CONM2500 | Mounting | [34 empty] | 0%
| CONM2510 | Accessories, bag | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7.7 Rotary Valve - (1516) | [35 empty] | 0%
| CONM2520 | Rotary Valve for Bag Filter - (1516) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7.8 Bag Filter Fan - (1517) | [35 empty] | 0%
| CONM2530 | Bag filter Fan - (1517) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7.14.3.1.7.15 Pug mill - (1521) | [35 empty] | 0%
| CONM2540 | PUG MILL - (1521) - Mounting | [34 empty] | 0%
| CONM2550 | Piping, Drive | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7.9 Water Tank - (1522) | [35 empty] | 0%
| CONM2560 | Water Tank - (1522) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7.10 Water Pump - (1523) | [35 empty] | 0%
| CONM2570 | Water Pump - (1523) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7.14.3.1.7.18 Screw Conveyor - (1524) | [35 empty] | 0%
| CONM2580 | SCREW CONVEYOR - (1524) - Rail | [34 empty] | 0%
| CONM2590 | Screw Conveyor - (1524) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7.14.3.1.7.19 Rod mill - (1525) | [35 empty] | 0%
| CONM2600 | ROD MILL - (1525) - Base Frame | [34 empty] | 0%
| CONM2610 | Pre-assembly Shell, Trunion, G/G, Bearing | [34 empty] | 0%
| CONM2620 | Mounting on base frame | [34 empty] | 0%
| CONM2630 | Inching | [34 empty] | 0%
| CONM2640 | Pinion & Tooth Contact | [34 empty] | 0%
| CONM2650 | Final Alignment | [34 empty] | 0%
| CONM2660 | Piping | [34 empty] | 0%
E22 | CONM2670 | Rod Charge | [34 empty] | 0%
|  | Transport material to site |  | 10% | 73218495 | 0.00214% | [30 empty] | 0.00214%
|  | Check elevation & orientation |  | 20% | 146436990 | 0.00428% | [30 empty] | 0.00428%
|  | Pre-assembly on the ground |  | 10% | 73218495 | 0.00214% | [30 empty] | 0.00214%
|  | Installation |  | 40% | 292189695 | 0.00854% | [30 empty] | 0.00854%
|  | Setting allignment |  | 10% | 73218495 | 0.00214% | [30 empty] | 0.00214%
|  | Final inspection |  | 10% | 73218495 | 0.00214% | [30 empty] | 0.00214%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7.11 Chain Conveyor - (1526) | [35 empty] | 0%
| CONM2680 | Chain Conveyor - (1526) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7.14.3.1.7.21 Mixed Dust Bin for Briquetting - (1531) | [35 empty] | 0%
| CONM2690 | MIXED DUST BIN FOR BRIQUETTING - (1531) - Mounting | [34 empty] | 0%
| CONM2700 | Hopper Lining | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7.12 Weighing Feeder - (1532) | [35 empty] | 0%
| CONM2710 | Weighing Feeder for Briquetting - (1532) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7.14.3.1.7.23 Briquetting Machine - (1533) | [35 empty] | 0%
| CONM2720 | BRIQUETTING MACHINE - (1533) - Put in body | [34 empty] | 0%
| CONM2730 | Accessories | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.7.14 CDPS - (1599) | [35 empty] | 0%
| CONM2740 | CDPS - (1599) - Hoist, chute, duct | [34 empty] | 0%
|  | Transport material to site |  | 10% | 73218495 | 0.00214% | [30 empty] | 0.00214%
|  | Check elevation & orientation |  | 20% | 146436990 | 0.00428% | [30 empty] | 0.00428%
|  | Pre-assembly on the ground |  | 10% | 73218495 | 0.00214% | [30 empty] | 0.00214%
|  | Installation |  | 40% | 292531837.5 | 0.00855% | [30 empty] | 0.00855%
|  | Setting allignment |  | 10% | 73218495 | 0.00214% | [30 empty] | 0.00214%
|  | Final inspection |  | 10% | 73218495 | 0.00214% | [30 empty] | 0.00214%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8 Rotary Kiln Equipment | [35 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.14.3.1.8.1 Rotary Kiln (Charging Hood) - (1601) | [35 empty] | 0%
| CONM2750 | CHARGING HOOD - Lower Part | [34 empty] | 0%
| CONM2760 | Upper Part | [34 empty] | 0%
| CONM2770 | Air Seal | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.14.3.1.8.2 Rotary Kiln (Combustion Hood) - (1601) | [35 empty] | 0%
| CONM2780 | COMBUSTION HOOD - Lower Part | [34 empty] | 0%
| CONM2790 | Upper Part | [34 empty] | 0%
| CONM2800 | Air Seal Duct | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.14.3.1.8.3 Rotary Kiln (Roller Bed) - (1601) | [35 empty] | 0%
| CONM2810 | ROLLER BED - Chipping | [34 empty] | 0%
| CONM2830 | Set liner to bed | [34 empty] | 0%
| CONM2820 | Install Roller Bed & Pre-alignment | [34 empty] | 0%
| CONM2840 | Anchoor grout | [34 empty] | 0%
| CONM2850 | Final alignment bed | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.1 Rotary Kiln (Roller) - (1601) | [35 empty] | 0%
E23 | CONM2860 | Rotary Kiln (Roller Assembling) - (1601) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 438284542.5 | 0.01281% | 2018-03-12: 0.01281% | 0%
|  | Check elevation & orientation |  | 20% | 876569085 | 0.02562% | 2018-03-12: 0.02562% | 0%
|  | Pre-assembly on the ground |  | 10% | 438284542.5 | 0.01281% | 2018-03-12: 0.01281% | 0%
|  | Installation |  | 40% | 1753822455 | 0.05126% | 2018-03-12: 0.05126% | 0%
|  | Setting allignment |  | 10% | 438284542.5 | 0.01281% | 2018-03-12: 0.01281% | 0%
|  | Final inspection |  | 10% | 438284542.5 | 0.01281% | 2018-03-12: 0.01048% | 0.002327%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.14.3.1.8.5 Rotary Kiln (Shell) - (1601) | [35 empty] | 0%
| CONM2870 | SHELL - Pre-assembly Shell | [34 empty] | 0%
| CONM2880 | Pre-assembly Tyre | [34 empty] | 0%
| CONM2890 | Mounting Shell & Centering | [34 empty] | 0%
| CONM2900 | Welding Shell (No Rotation) | [34 empty] | 0%
| CONM2910 | Cleaning Inside | [34 empty] | 0%
| CONM2920 | UT Test | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.14.3.1.8.7 Rotary Kiln (Girth Gear) - (1601) | [35 empty] | 0%
| CONM2970 | Girth Gear on Foundation | [34 empty] | 0%
| CONM2980 | Setting Up | [34 empty] | 0%
| CONM2990 | Alignment Girth Gear | [34 empty] | 0%
| CONM3000 | Girth Gear Hole | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.14.3.1.8.6 Rotary kiln (Pinion) - (1601) | [35 empty] | 0%
| CONM2930 | Pinion Bed | [34 empty] | 0%
| CONM2940 | Pinion Pre-setting | [34 empty] | 0%
| CONM2950 | Preparation for rotating (Lub, panel, cable) | [34 empty] | 0%
E23 | CONM2960 | Tooth Contact | [34 empty] | 0%
|  | Transport material to site |  | 10% | 438284542.5 | 0.01281% | 2018-04-11: 0.01281% | 0%
|  | Check elevation & orientation |  | 20% | 876569085 | 0.02562% | 2018-04-11: 0.01098% | 0.01464%
|  | Pre-assembly on the ground |  | 10% | 438284542.5 | 0.01281% | 2018-05-11: 0.01281% | 0%
|  | Installation |  | 40% | 1753822455 | 0.05126% | 2018-05-11: 0.0404% | 0.01086%
|  | Setting allignment |  | 10% | 438284542.5 | 0.01281% | [30 empty] | 0.01281%
|  | Final inspection |  | 10% | 438284542.5 | 0.01281% | [30 empty] | 0.01281%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.14.3.1.8.8 Main Gear Reducer - (1602) | [35 empty] | 0%
| CONM3010 | MAIN GEAR REDUCER - Mounting Reducer | [34 empty] | 0%
| CONM3020 | Pre-alignment | [34 empty] | 0%
| CONM3030 | Final Alignment | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.14.3.1.8.9 Inching Device - (1603) | [35 empty] | 0%
| CONM3040 | INCHING DEVICE - Mounting Inching Device | [34 empty] | 0%
| CONM3050 | Pre-alignment | [34 empty] | 0%
| CONM3060 | Final Alignment | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.14.3.1.8.10 Main Motor - (1601) | [35 empty] | 0%
| CONM3070 | MAIN MOTOR - Mounting Main Motor | [34 empty] | 0%
| CONM3080 | Pre-alignment | [34 empty] | 0%
| CONM3090 | Final Alignment | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.14.3.1.8.13 Lub. Unit for Thruster & Pinion - (1604) | [35 empty] | 0%
| CONM3120 | LUB. UNIT FOR THRUSTER&PINION - Lub. Unit | [34 empty] | 0%
| CONM3130 | Piping | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.9 Rotary Kiln (Castable & Refractory) - (1601) | [35 empty] | 0%
| CONM3100 | Anchoor Castable Installation - (1601) | [34 empty] | 0%
| CONM3110 | Refractory Installation - (1601) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.14.3.1.8.14 Hydraulic Unit for Thruster - (1605) | [35 empty] | 0%
| CONM3140 | HYDRAULIC UNIT FOR THRUSTER - Lub. Unit | [34 empty] | 0%
E23 | CONM3150 | Piping | [34 empty] | 0%
|  | Transport material to site |  | 10% | 438284542.5 | 0.01281% | [30 empty] | 0.01281%
|  | Check elevation & orientation |  | 20% | 876569085 | 0.02562% | [30 empty] | 0.02562%
|  | Pre-assembly on the ground |  | 10% | 438284542.5 | 0.01281% | [30 empty] | 0.01281%
|  | Installation |  | 40% | 1753822455 | 0.05126% | [30 empty] | 0.05126%
|  | Setting allignment |  | 10% | 438284542.5 | 0.01281% | [30 empty] | 0.01281%
|  | Final inspection |  | 10% | 438284542.5 | 0.01281% | [30 empty] | 0.01281%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.14.3.1.8.16 Kiln Burner - (1611) | [35 empty] | 0%
| CONM3180 | KILN BURNER - Castable | [34 empty] | 0%
| CONM3170 | Kiln Burner | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.2 Cooling Fan - (1606) | [35 empty] | 0%
| CONM3160 | Cooling Fan - (1606) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.4 Burner Hanger - (1612) | [35 empty] | 0%
| CONM3190 | Burner Hanger - (1612) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.5 Pump Unit for Kiln - (1613) | [35 empty] | 0%
| CONM3200 | Pump Unit for Kiln - (1613) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.3 Valve Unit for Kiln - (1614) | [35 empty] | 0%
E23 | CONM3210 | Valve Unit for Kiln - (1614) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 438284542.5 | 0.01281% | [30 empty] | 0.01281%
|  | Check elevation & orientation |  | 20% | 876569085 | 0.02562% | [30 empty] | 0.02562%
|  | Pre-assembly on the ground |  | 10% | 438284542.5 | 0.01281% | [30 empty] | 0.01281%
|  | Installation |  | 40% | 1753822455 | 0.05126% | [30 empty] | 0.05126%
|  | Setting allignment |  | 10% | 438284542.5 | 0.01281% | [30 empty] | 0.01281%
|  | Final inspection |  | 10% | 438284542.5 | 0.01281% | [30 empty] | 0.01281%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.14.3.1.8.20 Primary Air Fan - (1615) | [35 empty] | 0%
| CONM3220 | Primary Air Fan - (1615) | [34 empty] | 0%
| CONM3230 | Duct | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.14.3.1.8.21 Secondary Air Fan - (1616) | [35 empty] | 0%
| CONM3240 | Secondary Air Fan - (1616) | [34 empty] | 0%
| CONM3250 | Duct | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.14.3.1.8.22 Clinker Pusher - (1621) | [35 empty] | 0%
| CONM3260 | CLINKER PUSHER - (1621) - Crusher | [34 empty] | 0%
| CONM3270 | Piping & Flushing | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.6 Rotary Valve for Inlet Hood - (1631) | [35 empty] | 0%
| CONM3280 | Rotary Valve for Inlet Hood - (1631) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.7 Double Flap Damper for Inlet Hood - (1632) | [35 empty] | 0%
| CONM3290 | Double Flap Damper for Inlet Hood - (1632) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.14.3.1.8.25 Hoist - (1641) | [35 empty] | 0%
| CONM3300 | HOIST - (1641) - Beam | [34 empty] | 0%
| CONM3310 | Hoist - (1641) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.8.8 CDPS - (1699) | [35 empty] | 0%
E23 | CONM6552 | CDPS - (1699) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 438284542.5 | 0.01281% | [30 empty] | 0.01281%
|  | Check elevation & orientation |  | 20% | 876569085 | 0.02562% | [30 empty] | 0.02562%
|  | Pre-assembly on the ground |  | 10% | 438284542.5 | 0.01281% | [30 empty] | 0.01281%
|  | Installation |  | 40% | 1753822455 | 0.05126% | [30 empty] | 0.05126%
|  | Setting allignment |  | 10% | 438284542.5 | 0.01281% | [30 empty] | 0.01281%
|  | Final inspection |  | 10% | 438284542.5 | 0.01281% | [30 empty] | 0.01281%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.9 Scoop Feeder Charge House (Hopper) | [35 empty] | 0%
| CONM3320 | Belt Conveyor | [34 empty] | 0%
| CONM3350 | Reductant Coal Bin for Scoop Feeder | [34 empty] | 0%
| CONM3430 | Slip Ring | [34 empty] | 0%
| CONM3360 | Weighing Feeder for Reduction Coal | [34 empty] | 0%
| CONM3370 | Scoop Feeder (Casing) | [34 empty] | 0%
| CONM3380 | Air port (SUS) | [34 empty] | 0%
| CONM3330 | Belt Conveyor | [34 empty] | 0%
| CONM3390 | Scoop Feeder (Bucket) | [34 empty] | 0%
| CONM3400 | Duct | [34 empty] | 0%
| CONM3410 | Scoop Feeder Fan | [34 empty] | 0%
| CONM3420 | Air Port Fan | [34 empty] | 0%
| CONM3440 | CDPS | [34 empty] | 0%
E23 | CONM3340 | Belt Conveyor | [34 empty] | 0%
|  | Transport material to site |  | 10% | 438284542.5 | 0.01281% | [30 empty] | 0.01281%
|  | Check elevation & orientation |  | 20% | 876569085 | 0.02562% | [30 empty] | 0.02562%
|  | Pre-assembly on the ground |  | 10% | 438284542.5 | 0.01281% | [30 empty] | 0.01281%
|  | Installation |  | 40% | 1753822455 | 0.05126% | [30 empty] | 0.05126%
|  | Setting allignment |  | 10% | 438284542.5 | 0.01281% | [30 empty] | 0.01281%
|  | Final inspection |  | 10% | 438284542.5 | 0.01281% | [30 empty] | 0.01281%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.10 Exhaust Gas Treatment Equipment | [35 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.10.1 Hexa Cyclone (1701) | [35 empty] | 0%
| CONM3450 | Hexa Cyclone | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.10.14.3.1.10.2 Electrostatic Precipitator (1702) | [35 empty] | 0%
| CONM3460 | ELECTROSTATIC PRECIPITATOR - Support | [34 empty] | 0%
| CONM3470 | Pre-ass'y hopper | [34 empty] | 0%
| CONM3500 | Pre-ass'y Portal | [34 empty] | 0%
| CONM3540 | Pre-ass'y inlet & outlet | [34 empty] | 0%
| CONM3480 | Temp. setting | [34 empty] | 0%
| CONM3510 | Erection Portal & Alignment | [34 empty] | 0%
| CONM3550 | Erection inlet & outlet | [34 empty] | 0%
| CONM3520 | Stair | [34 empty] | 0%
| CONM3530 | Side casing | [34 empty] | 0%
| CONM3490 | Lift Up Hopper, welding, each plate | [34 empty] | 0%
| CONM3560 | Collecting Plate Alignment | [34 empty] | 0%
| CONM3580 | Discharge Alignment | [34 empty] | 0%
| CONM3570 | Rapping System | [34 empty] | 0%
| CONM3590 | Rapping System | [34 empty] | 0%
| CONM3600 | Hot Roof | [34 empty] | 0%
| CONM3610 | Outer Roof, TR, Whether Encloser | [34 empty] | 0%
E24 | CONM3620 | Insulation | [34 empty] | 0%
|  | Transport material to site |  | 10% | 670257157.5 | 0.01959% | 2018-04-11: 0.00518% | 0.01441%
|  | Check elevation & orientation |  | 20% | 1340514315 | 0.03918% | [30 empty] | 0.03918%
|  | Pre-assembly on the ground |  | 10% | 670257157.5 | 0.01959% | [30 empty] | 0.01959%
|  | Installation |  | 40% | 2681370772.5 | 0.07837% | 2018-05-11: 0.05728% | 0.02109%
|  | Setting allignment |  | 10% | 670257157.5 | 0.01959% | [30 empty] | 0.01959%
|  | Final inspection |  | 10% | 670257157.5 | 0.01959% | [30 empty] | 0.01959%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.10.14.3.1.10.3 Exhaust Fan (1703) | [35 empty] | 0%
| CONM3630 | EXHAUST FAN - Fan, Motor | [34 empty] | 0%
| CONM3640 | Duct (Fan-EP/Fan Stack) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.10.9 Kiln Dust Bin (1721) | [35 empty] | 0%
| CONM3750 | Kiln Dust Bin (1721) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.10.5 Chain Conveyor for EP Dust (1715) | [35 empty] | 0%
| CONM3740 | Chain Conveyor for EP Dust (1715) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.10.14.3.1.10.4 Stack (1704) | [35 empty] | 0%
| CONM3660 | STACK - Padding | [34 empty] | 0%
| CONM3691 | STACK - Pre-ass'y on the ground | [34 empty] | 0%
| CONM3670 | STACK - Lower Part | [34 empty] | 0%
| CONM3680 | STACK - Middle Part | [34 empty] | 0%
| CONM3700 | STACK - Refractory (Castable Work) | [34 empty] | 0%
E24 | CONM3690 | STACK - Top Part | [34 empty] | 0%
|  | Transport material to site |  | 10% | 335299650 | 0.0098% | [30 empty] | 0.0098%
|  | Check elevation & orientation |  | 20% | 670257157.5 | 0.01959% | [30 empty] | 0.01959%
|  | Pre-assembly on the ground |  | 10% | 335299650 | 0.0098% | [30 empty] | 0.0098%
|  | Installation |  | 40% | 1340001101.25 | 0.03917% | [30 empty] | 0.03917%
|  | Setting allignment |  | 10% | 335299650 | 0.0098% | [30 empty] | 0.0098%
|  | Final inspection |  | 10% | 335299650 | 0.0098% | [30 empty] | 0.0098%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.10.2 Rotary Valve (1712) | [35 empty] | 0%
| CONM3710 | Rotary Valve | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.10.3 Chain Conveyor for Kiln Dust (1713) | [35 empty] | 0%
| CONM3720 | Chain Conveyor for Kiln Dust (1713) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.10.4 Chain Conveyor for EP Dust (1714) | [35 empty] | 0%
| CONM3730 | Chain Conveyor for EP Dust (1714) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.10.6 Pneumatic Conveyor (1722) | [35 empty] | 0%
| CONM3760 | Pneumatic Conveyor (1722) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.10.7 Roots Blower (1723) | [35 empty] | 0%
| CONM3770 | Roots Blower (1723) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.10.8 CDPS (1799) | [35 empty] | 0%
E24 | CONM3780 | CDPS (1799) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 335299650 | 0.0098% | [30 empty] | 0.0098%
|  | Check elevation & orientation |  | 20% | 670257157.5 | 0.01959% | [30 empty] | 0.01959%
|  | Pre-assembly on the ground |  | 10% | 335299650 | 0.0098% | [30 empty] | 0.0098%
|  | Installation |  | 40% | 1340001101.25 | 0.03917% | [30 empty] | 0.03917%
|  | Setting allignment |  | 10% | 335299650 | 0.0098% | [30 empty] | 0.0098%
|  | Final inspection |  | 10% | 335299650 | 0.0098% | [30 empty] | 0.0098%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.11 Coal Storage and Transport | [35 empty] | 0%
| CONM3790 | Loading hopper (1801) | [34 empty] | 0%
| CONM3800 | Grizzly Feeder (1802) | [34 empty] | 0%
| CONM3810 | Magnet Separator (1803) | [34 empty] | 0%
| CONM3820 | Belt Conveyor (1804) | [34 empty] | 0%
| CONM3830 | Metal Detector (1805) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12 Coal Grinding Building | [35 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.1 Raw Coal Bin (1811) | [35 empty] | 0%
| CONM3840 | Fuel Coal Bin (1811) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.2 Coal Weigher (1812) | [35 empty] | 0%
| CONM3850 | Coal Weigher (1812) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.14.3.1.12.3 Coal Grinding Mill / Mill Body (1813) | [35 empty] | 0%
| CONM3860 | MILL BODY - - Chipping, Padding | [34 empty] | 0%
| CONM3870 | Reducer Base Frame | [34 empty] | 0%
| CONM3880 | Reducer , Wind Box | [34 empty] | 0%
| CONM3890 | Shell, armer ring | [34 empty] | 0%
| CONM3900 | Arm | [34 empty] | 0%
| CONM3910 | Table Roller | [34 empty] | 0%
| CONM3920 | Clasifier | [34 empty] | 0%
| CONM3930 | Inlet chute | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.14.3.1.12.4 Hydraulic unit & Piping (1814) | [35 empty] | 0%
| CONM3940 | HYDRAULIC UNIT & PIPING - Hydraulic Unit | [34 empty] | 0%
| CONM3950 | Piping, Flushing | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.14.3.1.12.5 Lub. Unit for Coal Mill Reducer (1815) | [35 empty] | 0%
| CONM3960 | LUB UNIT FOR COAL MILL REDUCER - Unit | [34 empty] | 0%
| CONM3970 | Piping, Flushing | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.14.3.1.12.6 Air Seal Fan for Coal Mill (1816) | [35 empty] | 0%
| CONM3980 | AIR SEAL FAN FOR COAL MILL - Fan | [34 empty] | 0%
| CONM3990 | Piping | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.14.3.1.12.7 Grease unit for classifier (1817) | [35 empty] | 0%
| CONM4000 | GREASE UNIT FOR CLASSIFIER - Unit | [34 empty] | 0%
| CONM4010 | Piping, Flushing | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.14.3.1.12.8 Bag Filter for Coal Mill (1818) | [35 empty] | 0%
| CONM4020 | BAG FILTER FOR COAL MILL - Structure | [34 empty] | 0%
| CONM4030 | Hopper | [34 empty] | 0%
| CONM4050 | Pre-ass'y solenoid valve | [34 empty] | 0%
| CONM4040 | Casing | [34 empty] | 0%
| CONM4060 | Bag & cover | [34 empty] | 0%
| CONM4070 | Insulation | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.14.3.1.12.9 Coal Mill Exhaust Fan (1819) | [35 empty] | 0%
| CONM4080 | COAL MILL EXHAUST FAN - Fan, Damper | [34 empty] | 0%
| CONM4090 | Silencer | [34 empty] | 0%
| CONM4100 | Duct (Fan-BF) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.14.3.1.12.10 Hot Air Generator for Coal Mill (1821) | [35 empty] | 0%
| CONM4110 | HOT OIL GENERATOR FOR COAL MILL - Mounting casing | [34 empty] | 0%
| CONM4120 | Alignment | [34 empty] | 0%
E25 | CONM4130 | Insulation | [34 empty] | 0%
|  | Transport material to site |  | 10% | 173466247.5 | 0.00507% | [30 empty] | 0.00507%
|  | Check elevation & orientation |  | 20% | 346590352.5 | 0.01013% | [30 empty] | 0.01013%
|  | Pre-assembly on the ground |  | 10% | 173466247.5 | 0.00507% | [30 empty] | 0.00507%
|  | Installation |  | 40% | 693180705 | 0.02026% | [30 empty] | 0.02026%
|  | Setting allignment |  | 10% | 173466247.5 | 0.00507% | [30 empty] | 0.00507%
|  | Final inspection |  | 10% | 173466247.5 | 0.00507% | [30 empty] | 0.00507%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.3 Oil Pump Unit for HAG (1822) | [35 empty] | 0%
| CONM4140 | Oil Pump Unit for HAG (1822) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.4 Valve Unit (1823) | [35 empty] | 0%
E25 | CONM4150 | Valve Unit for Coal Mill HAG (1823) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 864936240 | 0.02528% | [30 empty] | 0.02528%
|  | Check elevation & orientation |  | 20% | 1729530337.5 | 0.05055% | [30 empty] | 0.05055%
|  | Pre-assembly on the ground |  | 10% | 864936240 | 0.02528% | [30 empty] | 0.02528%
|  | Installation |  | 40% | 3458376390 | 0.1011% | [30 empty] | 0.1011%
|  | Setting allignment |  | 10% | 864936240 | 0.02528% | [30 empty] | 0.02528%
|  | Final inspection |  | 10% | 864936240 | 0.02528% | [30 empty] | 0.02528%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.5 Mixing Chamber (1826) | [35 empty] | 0%
| CONM4200 | Mixing Chamber (1826) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.14.3.1.12.13 Combustion Fan for Coal Mill HAG (1824) | [35 empty] | 0%
| CONM4160 | COMBUSTION FAN FOR COAL MILL HAG - Fan | [34 empty] | 0%
| CONM4170 | Duct | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.14.3.1.12.14 Dilution Fan for Coal Mill HAG (1825) | [35 empty] | 0%
| CONM4180 | DILUTION FAN FOR COAL MILL HAG - Fan | [34 empty] | 0%
| CONM4190 | Duct | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.6 Limestone Hopper (1827) | [35 empty] | 0%
| CONM4210 | Limestone Hopper for Coal Mill (1827) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.14.3.1.12.17 Chain Hoist (1828) | [35 empty] | 0%
| CONM4220 | HOIST - Hoist Beam | [34 empty] | 0%
E25 | CONM4230 | Hoist | [34 empty] | 0%
|  | Transport material to site |  | 10% | 173466247.5 | 0.00507% | [30 empty] | 0.00507%
|  | Check elevation & orientation |  | 20% | 346590352.5 | 0.01013% | [30 empty] | 0.01013%
|  | Pre-assembly on the ground |  | 10% | 173466247.5 | 0.00507% | [30 empty] | 0.00507%
|  | Installation |  | 40% | 693180705 | 0.02026% | [30 empty] | 0.02026%
|  | Setting allignment |  | 10% | 173466247.5 | 0.00507% | [30 empty] | 0.00507%
|  | Final inspection |  | 10% | 173466247.5 | 0.00507% | [30 empty] | 0.00507%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.7 Rotary Valve (1831) | [35 empty] | 0%
| CONM4240 | Rotary Valve for Bag Filter (1831) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.8 Screw Conveyor for PV Coal (1832) | [35 empty] | 0%
| CONM4250 | Screw Conveyor for PV Coal (1832) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.9 Screw Conveyor for PV Coal (1833) | [35 empty] | 0%
| CONM4260 | Screw Conveyor for PV Coal (1833) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.14.3.1.12.21 Pulverized Coal Bin (1841) | [35 empty] | 0%
| CONM4270 | PULVERIZED COAL BIN - Mounting | [34 empty] | 0%
| CONM4280 | Deck | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.10 Auto Feeder (1842) | [35 empty] | 0%
| CONM4290 | Auto Feeder for Dryer HAG (1842) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.11 Pneumatic Conveyor for Dryer (1843) | [35 empty] | 0%
| CONM4300 | Pneumatic Conveyor for Dryer HAG (1843) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.12 Roots Blower (1844) | [35 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.14.3.1.12.25 Pulverized Coal Bin for Kiln (1851) | [35 empty] | 0%
| CONM4320 | PULVIRIZED COAL BIN FOR KILN - Mounting | [34 empty] | 0%
| CONM4330 | Deck | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.13 Auto Feeder (1852) | [35 empty] | 0%
| CONM4340 | Loop Feeder for Kiln (1852) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.14 Pneumatic Conveyor for Kiln (1853) | [35 empty] | 0%
| CONM4350 | Pneumatic Conveyor for Kiln (1853) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.15 Roots Blower (1854) | [35 empty] | 0%
| CONM4310 | Roots Blower for Dryer HAG (1854) | [34 empty] | 0%
| CONM4360 | Roots Blower for Kiln (1854) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.12.14.3.1.12.29 CDPS (1899) | [35 empty] | 0%
| CONM4370 | CDPS - Mixing chamber, Duct, Deck | [34 empty] | 0%
| CONM4380 | Mill-B/F | [34 empty] | 0%
E25 | CONM4390 | Insulation | [34 empty] | 0%
|  | Transport material to site |  | 10% | 173466247.5 | 0.00507% | [30 empty] | 0.00507%
|  | Check elevation & orientation |  | 20% | 346590352.5 | 0.01013% | [30 empty] | 0.01013%
|  | Pre-assembly on the ground |  | 10% | 173466247.5 | 0.00507% | [30 empty] | 0.00507%
|  | Installation |  | 40% | 693180705 | 0.02026% | [30 empty] | 0.02026%
|  | Setting allignment |  | 10% | 173466247.5 | 0.00507% | [30 empty] | 0.00507%
|  | Final inspection |  | 10% | 173466247.5 | 0.00507% | [30 empty] | 0.00507%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.13 Surge Hopper Equipment | [35 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.13.14.3.1.13.1 Surge Hopper (2101) | [35 empty] | 0%
| CONM4400 | SURGE HOPPER - Structure | [34 empty] | 0%
| CONM4410 | Walkway & Stair | [34 empty] | 0%
E26 | CONM4420 | Castable | [34 empty] | 0%
|  | Transport material to site |  | 10% | 148489845 | 0.00434% | [30 empty] | 0.00434%
|  | Check elevation & orientation |  | 20% | 296637547.5 | 0.00867% | [30 empty] | 0.00867%
|  | Pre-assembly on the ground |  | 10% | 148489845 | 0.00434% | [30 empty] | 0.00434%
|  | Installation |  | 40% | 592590810 | 0.01732% | [30 empty] | 0.01732%
|  | Setting allignment |  | 10% | 148489845 | 0.00434% | [30 empty] | 0.00434%
|  | Final inspection |  | 10% | 148489845 | 0.00434% | [30 empty] | 0.00434%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.13.14.3.1.13.2 Gate (2102) | [35 empty] | 0%
| CONM4430 | Gate | [34 empty] | 0%
| CONM4440 | Cover | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.13.1 Cyclone (2103) | [35 empty] | 0%
| CONM4450 | Cyclone (2103) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.13.2 Induced Fan (2104) | [35 empty] | 0%
| CONM4460 | Fan for Cyclone (2104) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.1.14.3.1.13.3 CDPS (2199) | [35 empty] | 0%
| CONM4470 | CDPS (2199) | [34 empty] | 0%
E26 | CONM4480 | CDPS (Insulation) - (2199) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 148489845 | 0.00434% | [30 empty] | 0.00434%
|  | Check elevation & orientation |  | 20% | 296637547.5 | 0.00867% | [30 empty] | 0.00867%
|  | Pre-assembly on the ground |  | 10% | 148489845 | 0.00434% | [30 empty] | 0.00434%
|  | Installation |  | 40% | 592932952.5 | 0.01733% | [30 empty] | 0.01733%
|  | Setting allignment |  | 10% | 148489845 | 0.00434% | [30 empty] | 0.00434%
|  | Final inspection |  | 10% | 148489845 | 0.00434% | [30 empty] | 0.00434%
| P3FH - 28 M.14.14.3.11.3.1 System 2 - Electric Smelting Furnace-Rev.1 | [35 empty] | 0%
E170 | P3FH - 28 M.14.14.3.11.3.1.11.3.1.1 Electrical Smelting Furnace Equipment | [35 empty] | 0%
|  | Transport material to site |  | 10% | 662730022.5 | 0.01937% | [30 empty] | 0.01937%
|  | Check elevation & orientation |  | 20% | 1325460045 | 0.03874% | [30 empty] | 0.03874%
|  | Pre-assembly on the ground |  | 10% | 662730022.5 | 0.01937% | [30 empty] | 0.01937%
|  | Installation |  | 40% | 2651604375 | 0.0775% | [30 empty] | 0.0775%
|  | Setting allignment |  | 10% | 662730022.5 | 0.01937% | [30 empty] | 0.01937%
|  | Final inspection |  | 10% | 662730022.5 | 0.01937% | [30 empty] | 0.01937%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.1.11.3.1.1.1 Furnace Body & Refractory | [35 empty] | 0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.1.11.3.1.1.1.11.3.1.1.1.1 Furnace Shell | [35 empty] | 0%
| SYSTEM-2-1580 | Grillage Beams Installation | [34 empty] | 0%
| SYSTEM-2-1590 | Bottom Plate Installation | [34 empty] | 0%
| SYSTEM-2-1600 | Lower shell Installation | [34 empty] | 0%
E161 | SYSTEM-2-1610 | Upper Shell Installation | [34 empty] | 0%
|  | Transport material to site |  | 10% | 1121543115 | 0.03278% | 2018-05-11: 0.03278% | 0%
|  | Check elevation & orientation |  | 20% | 2243086230 | 0.06556% | 2018-05-11: 0.06556% | 0%
|  | Pre-assembly on the ground |  | 10% | 1121543115 | 0.03278% | 2018-05-11: 0.03278% | 0%
|  | Installation |  | 40% | 4486172460 | 0.1311% | 2018-05-11: 0.09524% | 0.03588%
|  | Setting allignment |  | 10% | 1121543115 | 0.03278% | [30 empty] | 0.03278%
|  | Final inspection |  | 10% | 1121543115 | 0.03278% | [30 empty] | 0.03278%
0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.1.11.3.1.1.1.11.3.1.1.1.2 Furnace Refractory (24 Hrs) | [35 empty] | 0%
| SYSTEM-2-1620 | Bottom skeuwback bricks installation | [34 empty] | 0%
| SYSTEM-2-1630 | Furnace refractory heart | [34 empty] | 0%
| SYSTEM-2-1640 | Lowershell refractory and cooler block | [34 empty] | 0%
| SYSTEM-2-1650 | Slag and Tapping Block | [34 empty] | 0%
| SYSTEM-2-1660 | Inserting module | [34 empty] | 0%
E161 | SYSTEM-2-1670 | Upper Refractory | [34 empty] | 0%
|  | Transport material to site |  | 10% | 3950035162.5 | 0.1154% | [30 empty] | 0.1154%
|  | Check elevation & orientation |  | 20% | 7899728182.5 | 0.2309% | [30 empty] | 0.2309%
|  | Pre-assembly on the ground |  | 10% | 3950035162.5 | 0.1154% | [30 empty] | 0.1154%
|  | Installation |  | 40% | 15798772080 | 0.4618% | [30 empty] | 0.4618%
|  | Setting allignment |  | 10% | 3950035162.5 | 0.1154% | [30 empty] | 0.1154%
|  | Final inspection |  | 10% | 3950035162.5 | 0.1154% | [30 empty] | 0.1154%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.1.11.3.1.1.2 Suspension Roof (24 Hrs) | [35 empty] | 0%
| SYSTEM-2-1680 | Main Beams Support | [34 empty] | 0%
| SYSTEM-2-1690 | Secondary and Tertiery | [34 empty] | 0%
| SYSTEM-2-1700 | Inner Delta beams | [34 empty] | 0%
| SYSTEM-2-1710 | Built Temporary support sus bricks | [34 empty] | 0%
| SYSTEM-2-1720 | Install Opening holes | [34 empty] | 0%
| SYSTEM-2-1730 | Install Off Takes | [34 empty] | 0%
| SYSTEM-2-1740 | Install Bricks area II | [34 empty] | 0%
| SYSTEM-2-1750 | Install Bricks area II | [34 empty] | 0%
| SYSTEM-2-1760 | Install Bricks area III | [34 empty] | 0%
| SYSTEM-2-1770 | Install Bricks area IV | [34 empty] | 0%
| SYSTEM-2-1780 | Install kaowoll | [34 empty] | 0%
E161 | SYSTEM-2-1790 | Install Supporting Ring Brick | [34 empty] | 0%
|  | Transport material to site |  | 10% | 4011962955 | 0.1173% | [30 empty] | 0.1173%
|  | Check elevation & orientation |  | 20% | 8023583767.5 | 0.2345% | [30 empty] | 0.2345%
|  | Pre-assembly on the ground |  | 10% | 4011962955 | 0.1173% | [30 empty] | 0.1173%
|  | Installation |  | 40% | 16046825392.5 | 0.469% | [30 empty] | 0.469%
|  | Setting allignment |  | 10% | 4011962955 | 0.1173% | [30 empty] | 0.1173%
|  | Final inspection |  | 10% | 4011962955 | 0.1173% | [30 empty] | 0.1173%
E166 | P3FH - 28 M.14.14.3.11.3.1.14.3.2.5 Cooling System | [35 empty] | 0%
| CONM6562 | FURNACE ROOF COOLING FAN (2241) | [34 empty] | 0%
| CONM6572 | FURNACE BOTTOM COOLING FAN (2242) | [34 empty] | 0%
| CONM6582 | FURNACE LOWER SHELL COOLING SYSTEM (2243) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 33187822.5 | 0.00097% | [30 empty] | 0.00097%
|  | Check elevation & orientation |  | 20% | 66375645 | 0.00194% | [30 empty] | 0.00194%
|  | Pre-assembly on the ground |  | 10% | 33187822.5 | 0.00097% | [30 empty] | 0.00097%
|  | Installation |  | 40% | 133435575 | 0.0039% | [30 empty] | 0.0039%
|  | Setting allignment |  | 10% | 33187822.5 | 0.00097% | [30 empty] | 0.00097%
|  | Final inspection |  | 10% | 33187822.5 | 0.00097% | [30 empty] | 0.00097%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.2 Electrode Installation | [35 empty] | 0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.2.11.3.1.2.1 Electrodes | [35 empty] | 0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.2.11.3.1.2.1.11.3.1.2.1.1 Assembly | [35 empty] | 0%
| SYSTEM-2-1800 | Built Frame | [34 empty] | 0%
| SYSTEM-2-1810 | Install supporting cylinder bottom part | [34 empty] | 0%
| SYSTEM-2-1820 | Install Contact clamp | [34 empty] | 0%
| SYSTEM-2-1830 | Install Clamping ring | [34 empty] | 0%
| SYSTEM-2-1840 | Install Protection Ring | [34 empty] | 0%
| SYSTEM-2-1850 | Set up bush tubes and bracing | [34 empty] | 0%
| SYSTEM-2-1860 | Set up cooling pipes | [34 empty] | 0%
| SYSTEM-2-1870 | Install Sealing Cylinder | [34 empty] | 0%
| SYSTEM-2-1880 | Set Up Hydraulic pipes | [34 empty] | 0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.2.11.3.1.2.1.11.3.1.2.1.2 Electrode Installation | [35 empty] | 0%
E163 |  | Electrode Equipment | [34 empty] | 0%
|  | Transport material to site |  | 10% | 392095305 | 0.01146% | [30 empty] | 0.01146%
|  | Check elevation & orientation |  | 20% | 784190610 | 0.02292% | [30 empty] | 0.02292%
|  | Pre-assembly on the ground |  | 10% | 392095305 | 0.01146% | [30 empty] | 0.01146%
|  | Installation |  | 40% | 1568039077.5 | 0.04583% | [30 empty] | 0.04583%
|  | Setting allignment |  | 10% | 392095305 | 0.01146% | [30 empty] | 0.01146%
|  | Final inspection |  | 10% | 392095305 | 0.01146% | [30 empty] | 0.01146%
E168 |  | Electrode Suspension Devices ( Main Hydraulic System ) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
|  | Check elevation & orientation |  | 20% | 17107125 | 0.0005% | [30 empty] | 0.0005%
|  | Pre-assembly on the ground |  | 10% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
|  | Installation |  | 40% | 33529965 | 0.00098% | [30 empty] | 0.00098%
|  | Setting allignment |  | 10% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
|  | Final inspection |  | 10% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
E172 |  | Electrode Movement Equipment & Auxiliary | [34 empty] | 0%
|  | Transport material to site |  | 10% | 483447352.5 | 0.01413% | [30 empty] | 0.01413%
|  | Check elevation & orientation |  | 20% | 967236847.5 | 0.02827% | [30 empty] | 0.02827%
|  | Pre-assembly on the ground |  | 10% | 483447352.5 | 0.01413% | [30 empty] | 0.01413%
|  | Installation |  | 40% | 1934815837.5 | 0.05655% | [30 empty] | 0.05655%
|  | Setting allignment |  | 10% | 483447352.5 | 0.01413% | [30 empty] | 0.01413%
|  | Final inspection |  | 10% | 483447352.5 | 0.01413% | [30 empty] | 0.01413%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.2.11.3.1.2.1.11.3.1.2.1.2.11.3.1.2.1.2.1 Electrode 1 | [35 empty] | 0%
| SYSTEM-2-1890 | Install supporting cylinder upper part complete with hoisting | [34 empty] | 0%
| SYSTEM-2-1900 | Opening roof furnace as sequence | [34 empty] | 0%
| SYSTEM-2-1910 | Lift Electrode No.1, lower in and sit on temporary steel beam | [34 empty] | 0%
| SYSTEM-2-1920 | Install hoisting support cylinder | [34 empty] | 0%
| SYSTEM-2-1930 | Lift Electrode 1 and install Hoisting cylinder on york | [34 empty] | 0%
| SYSTEM-2-1940 | Install purlin and furnace roof | [34 empty] | 0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.2.11.3.1.2.1.11.3.1.2.1.2.11.3.1.2.1.2.2 Electrode 2 | [35 empty] | 0%
| SYSTEM-2-1950 | Install supporting cylinder upper part complete with hoisting | [34 empty] | 0%
| SYSTEM-2-1960 | Opening roof furnace as sequence | [34 empty] | 0%
| SYSTEM-2-1970 | Lift Electrode No.2, lower in and sit on temporary steel beam | [34 empty] | 0%
| SYSTEM-2-1980 | Install hoisting support cylinder | [34 empty] | 0%
| SYSTEM-2-1990 | Lift Electrode 2 and install Hoisting cylinder on york | [34 empty] | 0%
| SYSTEM-2-2000 | Install purlin and furnace roof | [34 empty] | 0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.2.11.3.1.2.1.11.3.1.2.1.2.11.3.1.2.1.2.3 Electrode 3 | [35 empty] | 0%
| SYSTEM-2-2010 | Install supporting cylinder upper part complete with hoisting | [34 empty] | 0%
| SYSTEM-2-2020 | Opening roof furnace as sequence | [34 empty] | 0%
| SYSTEM-2-2030 | Lift Electrode No.3, lower in and sit on temporary steel beam | [34 empty] | 0%
| SYSTEM-2-2040 | Install hoisting support cylinder | [34 empty] | 0%
| SYSTEM-2-2050 | Lift Electrode 3 and install Hoisting cylinder on york | [34 empty] | 0%
| SYSTEM-2-2060 | Install purlin and furnace roof | [34 empty] | 0%
| SYSTEM-2-2070 | Install Electrode Gland | [34 empty] | 0%
| SYSTEM-2-2080 | Install Ring Brick | [34 empty] | 0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.2.11.3.1.2.2 HPU Installation | [35 empty] | 0%
| SYSTEM-2-2090 | Install group of accumulator | [34 empty] | 0%
| SYSTEM-2-2100 | Install PMG and oil tank | [34 empty] | 0%
| SYSTEM-2-2110 | Install Valve racks | [34 empty] | 0%
| SYSTEM-2-2120 | Construct hydraulic pipe tubes | [34 empty] | 0%
| SYSTEM-2-2130 | Construct Hydraulic pipe tubes on electrode component | [34 empty] | 0%
| SYSTEM-2-2140 | Construct Hydrotesting | [34 empty] | 0%
| SYSTEM-2-2150 | Contruct Flushing | [34 empty] | 0%
| SYSTEM-2-2160 | Construct Chemical Clining | [34 empty] | 0%
| SYSTEM-2-2170 | Construct Pacivation | [34 empty] | 0%
| SYSTEM-2-2180 | Reinstatement of pipe lines | [34 empty] | 0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.2.11.3.1.2.3 Bush Tubes Installation | [35 empty] | 0%
| SYSTEM-2-2190 | Build scaffolding | [34 empty] | 0%
| SYSTEM-2-2200 | Survey and marking | [34 empty] | 0%
| SYSTEM-2-2210 | Install new steel support | [34 empty] | 0%
| SYSTEM-2-2220 | Assembly bush tube on 2nd floor | [34 empty] | 0%
| SYSTEM-2-2230 | Lift assembled bush tubes on line 1 | [34 empty] | 0%
| SYSTEM-2-2240 | Assembly bush tube on 2nd floor | [34 empty] | 0%
| SYSTEM-2-2250 | Lift assembled bush tubes on line 2 | [34 empty] | 0%
| SYSTEM-2-2260 | Assembly bush tube on 2nd floor | [34 empty] | 0%
| SYSTEM-2-2270 | Lift assembled bush tubes on line 3 | [34 empty] | 0%
| SYSTEM-2-2280 | Install cable gland on transformer | [34 empty] | 0%
| SYSTEM-2-2290 | Install cable gland on electrode | [34 empty] | 0%
| SYSTEM-2-2300 | Construct Cooling water lines from pipe header to Electrode | [34 empty] | 0%
| SYSTEM-2-2310 | Hydrotesting, flushing and reinstatement | [34 empty] | 0%
E178 | P3FH - 28 M.14.14.3.11.3.1.11.3.1.2.11.3.1.2.4 Paste Hoist | [35 empty] | 0%
| SYSTEM-2-2320 | Construct spiro hoist beam | [34 empty] | 0%
| SYSTEM-2-2330 | Install hoist beam on hoist well | [34 empty] | 0%
| SYSTEM-2-2340 | Install hoist device | [34 empty] | 0%
| SYSTEM-2-2350 | Install pasta hoist | [34 empty] | 0%
| SYSTEM-2-2360 | Power on pasta hoist | [34 empty] | 0%
|  | Transport material to site |  | 10% | 3079282.5 | 9e-05% | [30 empty] | 9e-05%
|  | Check elevation & orientation |  | 20% | 6158565 | 0.00018% | [30 empty] | 0.00018%
|  | Pre-assembly on the ground |  | 10% | 3079282.5 | 9e-05% | [30 empty] | 9e-05%
|  | Installation |  | 40% | 13001415 | 0.00038% | [30 empty] | 0.00038%
|  | Setting allignment |  | 10% | 3079282.5 | 9e-05% | [30 empty] | 9e-05%
|  | Final inspection |  | 10% | 3079282.5 | 9e-05% | [30 empty] | 9e-05%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.2.11.3.1.2.5 Electrode Casing and Pasta | [35 empty] | 0%
| SYSTEM-2-2370 | Install Electrode casing each electrode and tip cone | [34 empty] | 0%
| SYSTEM-2-2380 | Filling Pasta | [34 empty] | 0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.3 Hot Charge Equipment | [35 empty] | 0%
E155 | P3FH - 28 M.14.14.3.11.3.1.11.3.1.3.11.3.1.3.1 Container Car | [35 empty] | 0%
| SYSTEM-2-2390 | Survey and marking | [34 empty] | 0%
| SYSTEM-2-2400 | Install Railways | [34 empty] | 0%
| SYSTEM-2-2410 | Set completed install TX Car | [34 empty] | 0%
| SYSTEM-2-2420 | Install Stoppers | [34 empty] | 0%
| SYSTEM-2-2430 | Install Electrict power | [34 empty] | 0%
| SYSTEM-2-2440 | Install instrument | [34 empty] | 0%
| SYSTEM-2-2450 | Testing and Balancing | [34 empty] | 0%
|  | Transport material to site |  | 10% | 108117030 | 0.00316% | [30 empty] | 0.00316%
|  | Check elevation & orientation |  | 20% | 216234060 | 0.00632% | [30 empty] | 0.00632%
|  | Pre-assembly on the ground |  | 10% | 108117030 | 0.00316% | [30 empty] | 0.00316%
|  | Installation |  | 40% | 431783835 | 0.01262% | [30 empty] | 0.01262%
|  | Setting allignment |  | 10% | 108117030 | 0.00316% | [30 empty] | 0.00316%
|  | Final inspection |  | 10% | 108117030 | 0.00316% | [30 empty] | 0.00316%
E156 | P3FH - 28 M.14.14.3.11.3.1.11.3.1.3.11.3.1.3.2 Container Shaft | [35 empty] | 0%
| SYSTEM-2-2460 | Survey and marking | [34 empty] | 0%
| SYSTEM-2-2470 | Pre Assembly Hoist well section 1 | [34 empty] | 0%
| SYSTEM-2-2480 | Pre Assembly Hoist well section 2 | [34 empty] | 0%
| SYSTEM-2-2490 | Lift assembly Hoist well section 1 | [34 empty] | 0%
| SYSTEM-2-2500 | lift assembly Hoist well section 2 | [34 empty] | 0%
|  | Transport material to site |  | 10% | 214865490 | 0.00628% | [30 empty] | 0.00628%
|  | Check elevation & orientation |  | 20% | 429388837.5 | 0.01255% | [30 empty] | 0.01255%
|  | Pre-assembly on the ground |  | 10% | 214865490 | 0.00628% | [30 empty] | 0.00628%
|  | Installation |  | 40% | 858777675 | 0.0251% | [30 empty] | 0.0251%
|  | Setting allignment |  | 10% | 214865490 | 0.00628% | [30 empty] | 0.00628%
|  | Final inspection |  | 10% | 214865490 | 0.00628% | [30 empty] | 0.00628%
0%
E157 | P3FH - 28 M.14.14.3.11.3.1.11.3.1.3.11.3.1.3.3 Hot Charge Crane | [35 empty] | 0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.3.11.3.1.3.3.11.3.1.3.3.1 Moving Parts | [35 empty] | 0%
| SYSTEM-2-2510 | Survey and marking | [34 empty] | 0%
| SYSTEM-2-2520 | Install Girder complete with base plate | [34 empty] | 0%
| SYSTEM-2-2530 | Survey for distance | [34 empty] | 0%
| SYSTEM-2-2540 | Install railways | [34 empty] | 0%
| SYSTEM-2-2550 | Install Transversing beams | [34 empty] | 0%
| SYSTEM-2-2560 | Install Travelling beams | [34 empty] | 0%
| SYSTEM-2-2570 | Diagonal check and tigthening | [34 empty] | 0%
| SYSTEM-2-2580 | Install Hoist and Cage | [34 empty] | 0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.3.11.3.1.3.3.11.3.1.3.3.2 Electrict and Control | [35 empty] | 0%
| SYSTEM-2-2590 | Install Fiston Cable on Travelling | [34 empty] | 0%
| SYSTEM-2-2600 | Install De-coder and FO Cables | [34 empty] | 0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.3.1 Load Test | [35 empty] | 0%
| SYSTEM-2-2610 | Load Tes | [34 empty] | 0%
|  | Transport material to site |  | 10% | 182361952.5 | 0.00533% | [30 empty] | 0.00533%
|  | Check elevation & orientation |  | 20% | 364723905 | 0.01066% | [30 empty] | 0.01066%
|  | Pre-assembly on the ground |  | 10% | 182361952.5 | 0.00533% | [30 empty] | 0.00533%
|  | Installation |  | 40% | 730132095 | 0.02134% | [30 empty] | 0.02134%
|  | Setting allignment |  | 10% | 182361952.5 | 0.00533% | [30 empty] | 0.00533%
|  | Final inspection |  | 10% | 182361952.5 | 0.00533% | [30 empty] | 0.00533%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.4 Furnace Charging Equipment | [35 empty] | 0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.4.11.3.1.4.1 Top Bin & Top Bin Cover (2137) | [35 empty] | 0%
E154 |  | Top Bin | [34 empty] | 0%
|  | Transport material to site |  | 10% | 146094847.5 | 0.00427% | [30 empty] | 0.00427%
|  | Check elevation & orientation |  | 20% | 292189695 | 0.00854% | [30 empty] | 0.00854%
|  | Pre-assembly on the ground |  | 10% | 146094847.5 | 0.00427% | [30 empty] | 0.00427%
|  | Installation |  | 40% | 585063675 | 0.0171% | [30 empty] | 0.0171%
|  | Setting allignment |  | 10% | 146094847.5 | 0.00427% | [30 empty] | 0.00427%
|  | Final inspection |  | 10% | 146094847.5 | 0.00427% | [30 empty] | 0.00427%
E158 |  | Top Bin Cover | [34 empty] | 0%
| SYSTEM-2-2620 | Survey and marking | [34 empty] | 0%
| SYSTEM-2-2630 | Lift and place Bin No, 1, 2, 3 | [34 empty] | 0%
| SYSTEM-2-2640 | Lift and place Bin No, 4, 5, 6 | [34 empty] | 0%
| SYSTEM-2-2650 | Lift and place Bin No, 7, 8, 9, 10 | [34 empty] | 0%
| SYSTEM-2-2660 | Install Castable on Bins | [34 empty] | 0%
| SYSTEM-2-2670 | Install buffer plates each bins | [34 empty] | 0%
| SYSTEM-2-2680 | Install Top Bin Cover (2121) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 385594597.5 | 0.01127% | [30 empty] | 0.01127%
|  | Check elevation & orientation |  | 20% | 771189195 | 0.02254% | [30 empty] | 0.02254%
|  | Pre-assembly on the ground |  | 10% | 385594597.5 | 0.01127% | [30 empty] | 0.01127%
|  | Installation |  | 40% | 1542378390 | 0.04508% | [30 empty] | 0.04508%
|  | Setting allignment |  | 10% | 385594597.5 | 0.01127% | [30 empty] | 0.01127%
|  | Final inspection |  | 10% | 385594597.5 | 0.01127% | [30 empty] | 0.01127%
E159 | P3FH - 28 M.14.14.3.11.3.1.11.3.1.4.11.3.1.4.2 Charging Tube (2138) | [35 empty] | 0%
| SYSTEM-2-2690 | Assembly Section Feed Tube | [34 empty] | 0%
| SYSTEM-2-2700 | Lift and put on 3rd floor and Hang for Bin 1 | [34 empty] | 0%
| SYSTEM-2-2710 | Lift and put on 3rd floor and Hang for Bin 2 | [34 empty] | 0%
| SYSTEM-2-2720 | Lift and put on 3rd floor and Hang for Bin 3 | [34 empty] | 0%
| SYSTEM-2-2730 | Lift and put on 3rd floor and Hang for Bin 4 | [34 empty] | 0%
| SYSTEM-2-2740 | Lift and put on 3rd floor and Hang for Bin 5 | [34 empty] | 0%
| SYSTEM-2-2750 | Lift and put on 3rd floor and Hang for Bin 6 | [34 empty] | 0%
| SYSTEM-2-2760 | Lift and put on 3rd floor and Hang for Bin 7 | [34 empty] | 0%
| SYSTEM-2-2770 | Lift and put on 3rd floor and Hang for Bin 8 | [34 empty] | 0%
| SYSTEM-2-2780 | Complete Install section Elbow and Expansion Joint on Bin 1 | [34 empty] | 0%
| SYSTEM-2-2790 | Complete Install section Elbow and Expansion Joint on Bin 2 | [34 empty] | 0%
| SYSTEM-2-2800 | Complete Install section Elbow and Expansion Joint on Bin 3 | [34 empty] | 0%
| SYSTEM-2-2810 | Complete Install section Elbow and Expansion Joint on Bin 4 | [34 empty] | 0%
| SYSTEM-2-2820 | Complete Install section Elbow and Expansion Joint on Bin 5 | [34 empty] | 0%
| SYSTEM-2-2830 | Complete Install section Elbow and Expansion Joint on Bin 6 | [34 empty] | 0%
| SYSTEM-2-2840 | Complete Install section Elbow and Expansion Joint on Bin 7 | [34 empty] | 0%
| SYSTEM-2-2850 | Complete Install section Elbow and Expansion Joint on Bin 8 | [34 empty] | 0%
| SYSTEM-2-2860 | Complete Install section Elbow and Expansion Joint on Bin 9 | [34 empty] | 0%
|  | Transport material to site |  | 10% | 190573372.5 | 0.00557% | [30 empty] | 0.00557%
|  | Check elevation & orientation |  | 20% | 381488887.5 | 0.01115% | [30 empty] | 0.01115%
|  | Pre-assembly on the ground |  | 10% | 190573372.5 | 0.00557% | [30 empty] | 0.00557%
|  | Installation |  | 40% | 763319917.5 | 0.02231% | [30 empty] | 0.02231%
|  | Setting allignment |  | 10% | 190573372.5 | 0.00557% | [30 empty] | 0.00557%
|  | Final inspection |  | 10% | 190573372.5 | 0.00557% | [30 empty] | 0.00557%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.4.3 Screw Conveyor (2134) | [35 empty] | 0%
| SYSTEM-2-4219 | Install Platform | [34 empty] | 0%
| SYSTEM-2-4220 | Install Screw Conveyor | [34 empty] | 0%
| SYSTEM-2-4230 | Install Component | [34 empty] | 0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.4.5 Multi Cyclone (2136) | [35 empty] | 0%
| SYSTEM-2-4240 | Install Multi Cyclone Support | [34 empty] | 0%
| SYSTEM-2-4250 | Install Cyclone | [34 empty] | 0%
| SYSTEM-2-4260 | Install Duct (2199) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.4.1 Bag Filter (2132) | [35 empty] | 0%
| SYSTEM-2-4170 | Install Bag Filter Casing | [34 empty] | 0%
| SYSTEM-2-4180 | Install Retainer | [34 empty] | 0%
| SYSTEM-2-4190 | Insulation (2199) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.4.2 Fan (2133) | [35 empty] | 0%
| SYSTEM-2-4200 | Install Fan | [34 empty] | 0%
| SYSTEM-2-4210 | Duct (2199) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.4.4 Air Compressor (2135) | [35 empty] | 0%
| SYSTEM-2-4270 | Install Air Compressor | [34 empty] | 0%
| SYSTEM-2-4280 | Alignment | [34 empty] | 0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.4.6 Duct, Stack, & Support (2199) | [35 empty] | 0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.5 Ladle Preheating | [35 empty] | 0%
| SYSTEM-2-2870 | Ladle & Accessories | [34 empty] | 0%
| SYSTEM-2-2880 | Blower Installation | [34 empty] | 0%
E169 | P3FH - 28 M.14.14.3.11.3.1.11.3.1.6 TMT Installation (Clay Gun only) | [35 empty] | 0%
| SYSTEM-2-2890 | Install Stand up Body | [34 empty] | 0%
| SYSTEM-2-2900 | Install clay gun Arm | [34 empty] | 0%
| SYSTEM-2-2910 | Install Hydraulic System | [34 empty] | 0%
| SYSTEM-2-2920 | Install Monorail for Drill Machine | [34 empty] | 0%
| SYSTEM-2-2921 | Install Slag Stopper (2233) | [34 empty] | 0%
| SYSTEM-2-2922 | Install Mud Kneader (2234) | [34 empty] | 0%
| SYSTEM-2-2930 | Testing and Pickling | [34 empty] | 0%
|  | Transport material to site |  | 10% | 19159980 | 0.00056% | [30 empty] | 0.00056%
|  | Check elevation & orientation |  | 20% | 38319960 | 0.00112% | [30 empty] | 0.00112%
|  | Pre-assembly on the ground |  | 10% | 19159980 | 0.00056% | [30 empty] | 0.00056%
|  | Installation |  | 40% | 76297777.5 | 0.00223% | [30 empty] | 0.00223%
|  | Setting allignment |  | 10% | 19159980 | 0.00056% | [30 empty] | 0.00056%
|  | Final inspection |  | 10% | 19159980 | 0.00056% | [30 empty] | 0.00056%
E179 | P3FH - 28 M.14.14.3.11.3.1.11.3.1.7 Slag Granulation System Equipment | [35 empty] | 0%
| SYSTEM-2-2940 | Install Base support | [34 empty] | 0%
| SYSTEM-2-2950 | Install Boshes with Body | [34 empty] | 0%
| SYSTEM-2-2960 | Install Nozzle tip | [34 empty] | 0%
|  | Transport material to site |  | 10% | 48242092.5 | 0.00141% | [30 empty] | 0.00141%
|  | Check elevation & orientation |  | 20% | 96484185 | 0.00282% | [30 empty] | 0.00282%
|  | Pre-assembly on the ground |  | 10% | 48242092.5 | 0.00141% | [30 empty] | 0.00141%
|  | Installation |  | 40% | 192626227.5 | 0.00563% | [30 empty] | 0.00563%
|  | Setting allignment |  | 10% | 48242092.5 | 0.00141% | [30 empty] | 0.00141%
|  | Final inspection |  | 10% | 48242092.5 | 0.00141% | [30 empty] | 0.00141%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.8 Off Gas Furnace Treatment System | [35 empty] | 0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.8.11.3.1.8.1 Refractory Lined Duct Mountain Stack (2413) | [35 empty] | 0%
| SYSTEM-2-2970 | Install Refractory Line Duct Sec.4 with support | [34 empty] | 0%
| SYSTEM-2-2980 | Install Refractory Line Duct Sec.3 | [34 empty] | 0%
| SYSTEM-2-2990 | Install Refractory Line Duct Sec.2 | [34 empty] | 0%
| SYSTEM-2-3000 | Install Refractory Line Duct Sec.1 | [34 empty] | 0%
| SYSTEM-2-3010 | Install Refractory Line Duct Sec.5 | [34 empty] | 0%
| SYSTEM-2-3020 | Install Refractory Line Duct Sec.6 | [34 empty] | 0%
| SYSTEM-2-3030 | Install Refractory Line Duct Sec.7 (branch) | [34 empty] | 0%
| SYSTEM-2-3040 | Install Refractory Line Duct Sec.8 | [34 empty] | 0%
| SYSTEM-2-3050 | Install Refractory Line Duct Sec.9 | [34 empty] | 0%
| SYSTEM-2-3060 | Install Refractory Line Duct Sec.10 | [34 empty] | 0%
| SYSTEM-2-3070 | Install Refractory Line Duct Sec.11 | [34 empty] | 0%
| SYSTEM-2-3080 | Install Refractory Line Duct Sec.12 | [34 empty] | 0%
E174 | SYSTEM-2-3090 | Install Emergency stack | [34 empty] | 0%
|  | Transport material to site |  | 10% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
|  | Check elevation & orientation |  | 20% | 379778175 | 0.0111% | [30 empty] | 0.0111%
|  | Pre-assembly on the ground |  | 10% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
|  | Installation |  | 40% | 759214207.5 | 0.02219% | [30 empty] | 0.02219%
|  | Setting allignment |  | 10% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
|  | Final inspection |  | 10% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.8.11.3.1.8.2 Sea Stack (2413) | [35 empty] | 0%
| SYSTEM-2-3100 | Install Refractory Line Duct Sec.A | [34 empty] | 0%
| SYSTEM-2-3110 | Install Refractory Line Duct Sec.B | [34 empty] | 0%
| SYSTEM-2-3120 | Install Refractory Line Duct Sec.C | [34 empty] | 0%
| SYSTEM-2-3130 | Install Refractory Line Duct Sec.D | [34 empty] | 0%
| SYSTEM-2-3140 | Install Refractory Line Duct Sec.E | [34 empty] | 0%
| SYSTEM-2-3150 | Install Refractory Line Duct Sec.F | [34 empty] | 0%
| SYSTEM-2-3160 | Install Refractory Line Duct Sec.G | [34 empty] | 0%
| SYSTEM-2-3170 | Install Refractory Line Duct Sec.H | [34 empty] | 0%
| SYSTEM-2-3180 | Install Refractory Line Duct Sec.I | [34 empty] | 0%
| SYSTEM-2-3190 | Install Refractory Line Duct Sec.A | [34 empty] | 0%
E174 | SYSTEM-2-3200 | Install Emergency stack | [34 empty] | 0%
|  | Transport material to site |  | 10% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
|  | Check elevation & orientation |  | 20% | 379778175 | 0.0111% | [30 empty] | 0.0111%
|  | Pre-assembly on the ground |  | 10% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
|  | Installation |  | 40% | 759214207.5 | 0.02219% | [30 empty] | 0.02219%
|  | Setting allignment |  | 10% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
|  | Final inspection |  | 10% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.8.11.3.1.8.3 Spray Chamber (2405) | [35 empty] | 0%
| SYSTEM-2-3210 | Install Spray Chamber Support | [34 empty] | 0%
| SYSTEM-2-3220 | Install bottom Cone | [34 empty] | 0%
| SYSTEM-2-3230 | Install Spray Chamber body | [34 empty] | 0%
| SYSTEM-2-3240 | Install Spray Chamber Head | [34 empty] | 0%
| SYSTEM-2-3250 | Install Castable inside body | [34 empty] | 0%
E174 | SYSTEM-2-3260 | Install explotion doors | [34 empty] | 0%
|  | Transport material to site |  | 10% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
|  | Check elevation & orientation |  | 20% | 379778175 | 0.0111% | [30 empty] | 0.0111%
|  | Pre-assembly on the ground |  | 10% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
|  | Installation |  | 40% | 759214207.5 | 0.02219% | [30 empty] | 0.02219%
|  | Setting allignment |  | 10% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
|  | Final inspection |  | 10% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.8.11.3.1.8.4 Baghouse (2401) | [35 empty] | 0%
| SYSTEM-2-3270 | Install Assembed Portal up to El.6 | [34 empty] | 0%
| SYSTEM-2-3280 | Install Steel Structure in between | [34 empty] | 0%
| SYSTEM-2-3290 | Install Dust Bins | [34 empty] | 0%
| SYSTEM-2-3300 | Install Assembed Portal up to El.12 | [34 empty] | 0%
| SYSTEM-2-3310 | Install Steel Structure in between | [34 empty] | 0%
| SYSTEM-2-3320 | Install Assembly Dirty, Pulse jet, Clean Compartment 1 | [34 empty] | 0%
| SYSTEM-2-3330 | Install Assembly Dirty, Pulse jet, Clean Compartment 2 | [34 empty] | 0%
| SYSTEM-2-3340 | Install Assembly Dirty, Pulse jet, Clean Compartment 3 | [34 empty] | 0%
| SYSTEM-2-3350 | Install Assembly Dirty, Pulse jet, Clean Compartment 4 | [34 empty] | 0%
| SYSTEM-2-3360 | Install Assembly Dirty, Pulse jet, Clean Compartment 5 | [34 empty] | 0%
| SYSTEM-2-3370 | Install Assembly Dirty, Pulse jet, Clean Compartment 6 | [34 empty] | 0%
| SYSTEM-2-3380 | Install Inlet Duct complete with dampers | [34 empty] | 0%
| SYSTEM-2-3390 | Install Air reciever | [34 empty] | 0%
| SYSTEM-2-3400 | Install Outlet Duct | [34 empty] | 0%
| SYSTEM-2-3410 | Install Poppet Dampers | [34 empty] | 0%
E160 | SYSTEM-2-3420 | Install Trunk duct from Spray Chamber | [34 empty] | 0%
|  | Transport material to site |  | 10% | 152937697.5 | 0.00447% | [30 empty] | 0.00447%
|  | Check elevation & orientation |  | 20% | 305875395 | 0.00894% | [30 empty] | 0.00894%
|  | Pre-assembly on the ground |  | 10% | 152937697.5 | 0.00447% | [30 empty] | 0.00447%
|  | Installation |  | 40% | 611750790 | 0.01788% | [30 empty] | 0.01788%
|  | Setting allignment |  | 10% | 152937697.5 | 0.00447% | [30 empty] | 0.00447%
|  | Final inspection |  | 10% | 152937697.5 | 0.00447% | [30 empty] | 0.00447%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.8.1 Smoke Hood (2411) | [35 empty] | 0%
| SYSTEM-2-4110 | Install Smoke Hood Support | [34 empty] | 0%
| SYSTEM-2-4120 | Install Smoke Hood | [34 empty] | 0%
E174 | SYSTEM-2-4130 | Install Smoke Hood Duct | [34 empty] | 0%
|  | Transport material to site |  | 10% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
|  | Check elevation & orientation |  | 20% | 379778175 | 0.0111% | [30 empty] | 0.0111%
|  | Pre-assembly on the ground |  | 10% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
|  | Installation |  | 40% | 759214207.5 | 0.02219% | [30 empty] | 0.02219%
|  | Setting allignment |  | 10% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
|  | Final inspection |  | 10% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.8.3 Ladle Hood (2414) | [35 empty] | 0%
| SYSTEM-2-4140 | Install Ladle Hood Support | [34 empty] | 0%
| SYSTEM-2-4150 | Install Ladle Hood | [34 empty] | 0%
E174 | SYSTEM-2-4160 | Install Ladle Hood Duct | [34 empty] | 0%
|  | Transport material to site |  | 10% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
|  | Check elevation & orientation |  | 20% | 379778175 | 0.0111% | [30 empty] | 0.0111%
|  | Pre-assembly on the ground |  | 10% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
|  | Installation |  | 40% | 759214207.5 | 0.02219% | [30 empty] | 0.02219%
|  | Setting allignment |  | 10% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
|  | Final inspection |  | 10% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.8.2 Tempering Purge Air Fan (2404) | [35 empty] | 0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.9 Exhaust Gas Stack and ID Fan | [35 empty] | 0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.9.11.3.1.10 ID Fan (2412) | [35 empty] | 0%
| SYSTEM-2-3460 | Install Padding Plate | [34 empty] | 0%
| SYSTEM-2-3470 | Install Bottom Casing | [34 empty] | 0%
| SYSTEM-2-3480 | Install Bearing | [34 empty] | 0%
| SYSTEM-2-3490 | Install Impeller and cones | [34 empty] | 0%
| SYSTEM-2-3500 | Install Upper casing | [34 empty] | 0%
| SYSTEM-2-3510 | Install Gear Box | [34 empty] | 0%
| SYSTEM-2-3520 | Install Motor | [34 empty] | 0%
| SYSTEM-2-3530 | Install outlet duct, Guiletine gate, exp.joint | [34 empty] | 0%
| SYSTEM-2-3540 | Install Inlet Duct spool | [34 empty] | 0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.9.1 Control Damper for Exhaust Gas (2403) | [35 empty] | 0%
| SYSTEM-2-4100 | Install Control Damper | [34 empty] | 0%
| P3FH - 28 M.14.14.3.11.3.1.11.3.1.9.11.3.1.9.1 Exhaust Gas Stack (Has been castabled) (2402) | [35 empty] | 0%
| SYSTEM-2-3429 | Pre-assembly | [34 empty] | 0%
| SYSTEM-2-3430 | Install Padding Plate | [34 empty] | 0%
| SYSTEM-2-3440 | Install 1st Section | [34 empty] | 0%
E174 | SYSTEM-2-3450 | Install 2nd Section complete with Platform | [34 empty] | 0%
|  | Transport material to site |  | 10% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
|  | Check elevation & orientation |  | 20% | 379778175 | 0.0111% | [30 empty] | 0.0111%
|  | Pre-assembly on the ground |  | 10% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
|  | Installation |  | 40% | 758872065 | 0.02218% | [30 empty] | 0.02218%
|  | Setting allignment |  | 10% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
|  | Final inspection |  | 10% | 189889087.5 | 0.00555% | [30 empty] | 0.00555%
0%
0%
E162 | P3FH - 28 M.14.14.3.11.3.1.1 Other Auxiliary | [35 empty] | 0%
| CONM6592 | WORKING DECK for electrode (2701) | [34 empty] | 0%
| CONM6602 | TAPPING DECK (2702) | [34 empty] | 0%
| CONM6612 | TAPPING RUNNER (2703) | [34 empty] | 0%
| CONM6622 | HEAT PREVENTION BOARD for Tapping Runner (2704) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 31477110 | 0.00092% | [30 empty] | 0.00092%
|  | Check elevation & orientation |  | 20% | 63296362.5 | 0.00185% | [30 empty] | 0.00185%
|  | Pre-assembly on the ground |  | 10% | 31477110 | 0.00092% | [30 empty] | 0.00092%
|  | Installation |  | 40% | 126934867.5 | 0.00371% | [30 empty] | 0.00371%
|  | Setting allignment |  | 10% | 31477110 | 0.00092% | [30 empty] | 0.00092%
|  | Final inspection |  | 10% | 31477110 | 0.00092% | [30 empty] | 0.00092%
0%
| P3FH - 28 M.14.14.3.14.3.3 System 3 - Refinery | [35 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.3.14.3.3.1 Deshulphurizing Equipment | [35 empty] | 0%
E33 | CONM5450 | Shifting Device & Swinging Part (3118 A/B) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 14369985 | 0.00042% | [30 empty] | 0.00042%
|  | Check elevation & orientation |  | 20% | 28739970 | 0.00084% | [30 empty] | 0.00084%
|  | Pre-assembly on the ground |  | 10% | 14369985 | 0.00042% | [30 empty] | 0.00042%
|  | Installation |  | 40% | 58164225 | 0.0017% | [30 empty] | 0.0017%
|  | Setting allignment |  | 10% | 14369985 | 0.00042% | [30 empty] | 0.00042%
|  | Final inspection |  | 10% | 14369985 | 0.00042% | [30 empty] | 0.00042%
E31 | CONM5430 | Stirrer Unit (3112 A/B) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 8211420 | 0.00024% | [30 empty] | 0.00024%
|  | Check elevation & orientation |  | 20% | 16080697.5 | 0.00047% | [30 empty] | 0.00047%
|  | Pre-assembly on the ground |  | 10% | 8211420 | 0.00024% | [30 empty] | 0.00024%
|  | Installation |  | 40% | 31819252.5 | 0.00093% | [30 empty] | 0.00093%
|  | Setting allignment |  | 10% | 8211420 | 0.00024% | [30 empty] | 0.00024%
|  | Final inspection |  | 10% | 8211420 | 0.00024% | [30 empty] | 0.00024%
E32 | CONM5440 | Lifting Device (3115 A/B) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 14712127.5 | 0.00043% | [30 empty] | 0.00043%
|  | Check elevation & orientation |  | 20% | 29424255 | 0.00086% | [30 empty] | 0.00086%
|  | Pre-assembly on the ground |  | 10% | 14712127.5 | 0.00043% | [30 empty] | 0.00043%
|  | Installation |  | 40% | 58506367.5 | 0.00171% | [30 empty] | 0.00171%
|  | Setting allignment |  | 10% | 14712127.5 | 0.00043% | [30 empty] | 0.00043%
|  | Final inspection |  | 10% | 14712127.5 | 0.00043% | [30 empty] | 0.00043%
E34 | CONM5460 | Hoist (3134 A/B) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 3421425 | 0.0001% | [30 empty] | 0.0001%
|  | Check elevation & orientation |  | 20% | 6842850 | 0.0002% | [30 empty] | 0.0002%
|  | Pre-assembly on the ground |  | 10% | 3421425 | 0.0001% | [30 empty] | 0.0001%
|  | Installation |  | 40% | 13685700 | 0.0004% | [30 empty] | 0.0004%
|  | Setting allignment |  | 10% | 3421425 | 0.0001% | [30 empty] | 0.0001%
|  | Final inspection |  | 10% | 3421425 | 0.0001% | [30 empty] | 0.0001%
E35 | CONM5470 | Exhaust Gas Duct and Stack (3199 A/B) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 9237847.5 | 0.00027% | [30 empty] | 0.00027%
|  | Check elevation & orientation |  | 20% | 18133552.5 | 0.00053% | [30 empty] | 0.00053%
|  | Pre-assembly on the ground |  | 10% | 9237847.5 | 0.00027% | [30 empty] | 0.00027%
|  | Installation |  | 40% | 36267105 | 0.00106% | [30 empty] | 0.00106%
|  | Setting allignment |  | 10% | 9237847.5 | 0.00027% | [30 empty] | 0.00027%
|  | Final inspection |  | 10% | 9237847.5 | 0.00027% | [30 empty] | 0.00027%
E36 | CONM5480 | Work Stage (xxxx) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 56111370 | 0.00164% | [30 empty] | 0.00164%
|  | Check elevation & orientation |  | 20% | 111880597.5 | 0.00327% | [30 empty] | 0.00327%
|  | Pre-assembly on the ground |  | 10% | 56111370 | 0.00164% | [30 empty] | 0.00164%
|  | Installation |  | 40% | 223761195 | 0.00654% | [30 empty] | 0.00654%
|  | Setting allignment |  | 10% | 56111370 | 0.00164% | [30 empty] | 0.00164%
|  | Final inspection |  | 10% | 56111370 | 0.00164% | [30 empty] | 0.00164%
| P3FH - 28 M.14.14.3.14.3.3.14.3.3.2 Shot Making Equipment | [35 empty] | 0%
| CONM5490 | Steel Structure | [34 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.3.14.3.3.2.14.3.3.2.2 Granulation Section | [35 empty] | 0%
| CONM5500 | GRANULATION SECTION - Deck for Ladle Tilting Machine (3511/) | [34 empty] | 0%
| CONM5520 | Hydraulic Oil Pump Unit (3514) | [34 empty] | 0%
E40 | CONM5550 | Shot making Tank (3531) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 82798485 | 0.00242% | 2018-04-11: 0.00242% | 0%
|  | Check elevation & orientation |  | 20% | 165254827.5 | 0.00483% | 2018-04-11: 0.00483% | 0%
|  | Pre-assembly on the ground |  | 10% | 82798485 | 0.00242% | 2018-04-11: 0.00021% | 0.00221%
|  | Installation |  | 40% | 330509655 | 0.00966% | 2018-05-11: 0.00188% | 0.00778%
|  | Setting allignment |  | 10% | 82798485 | 0.00242% | [30 empty] | 0.00242%
|  | Final inspection |  | 10% | 82798485 | 0.00242% | [30 empty] | 0.00242%
| CONM5540 | Hydraulic Cylinder (3513) | [34 empty] | 0%
E37 | CONM5510 | Ladle Tilting Machine (3511) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 79377060 | 0.00232% | [30 empty] | 0.00232%
|  | Check elevation & orientation |  | 20% | 159096262.5 | 0.00465% | [30 empty] | 0.00465%
|  | Pre-assembly on the ground |  | 10% | 79377060 | 0.00232% | [30 empty] | 0.00232%
|  | Installation |  | 40% | 318534667.5 | 0.00931% | [30 empty] | 0.00931%
|  | Setting allignment |  | 10% | 79377060 | 0.00232% | [30 empty] | 0.00232%
|  | Final inspection |  | 10% | 79377060 | 0.00232% | [30 empty] | 0.00232%
E41 | CONM5570 | No.1 Net Conveyor (3532) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 19502122.5 | 0.00057% | [30 empty] | 0.00057%
|  | Check elevation & orientation |  | 20% | 39004245 | 0.00114% | [30 empty] | 0.00114%
|  | Pre-assembly on the ground |  | 10% | 19502122.5 | 0.00057% | [30 empty] | 0.00057%
|  | Installation |  | 40% | 77324205 | 0.00226% | [30 empty] | 0.00226%
|  | Setting allignment |  | 10% | 19502122.5 | 0.00057% | [30 empty] | 0.00057%
|  | Final inspection |  | 10% | 19502122.5 | 0.00057% | [30 empty] | 0.00057%
E39 | CONM5560 | Spray head (3532) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 684285 | 2e-05% | [30 empty] | 2e-05%
|  | Check elevation & orientation |  | 20% | 1368570 | 4e-05% | [30 empty] | 4e-05%
|  | Pre-assembly on the ground |  | 10% | 684285 | 2e-05% | [30 empty] | 2e-05%
|  | Installation |  | 40% | 2052855 | 6e-05% | [30 empty] | 6e-05%
|  | Setting allignment |  | 10% | 684285 | 2e-05% | [30 empty] | 2e-05%
|  | Final inspection |  | 10% | 684285 | 2e-05% | [30 empty] | 2e-05%
E38 | CONM5530 | Runner (3515) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 11632845 | 0.00034% | [30 empty] | 0.00034%
|  | Check elevation & orientation |  | 20% | 23265690 | 0.00068% | [30 empty] | 0.00068%
|  | Pre-assembly on the ground |  | 10% | 11632845 | 0.00034% | [30 empty] | 0.00034%
|  | Installation |  | 40% | 46873522.5 | 0.00137% | [30 empty] | 0.00137%
|  | Setting allignment |  | 10% | 11632845 | 0.00034% | [30 empty] | 0.00034%
|  | Final inspection |  | 10% | 11632845 | 0.00034% | [30 empty] | 0.00034%
E42 | CONM5580 | Jet Water Pump (3533) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 2737140 | 8e-05% | [30 empty] | 8e-05%
|  | Check elevation & orientation |  | 20% | 5474280 | 0.00016% | [30 empty] | 0.00016%
|  | Pre-assembly on the ground |  | 10% | 2737140 | 8e-05% | [30 empty] | 8e-05%
|  | Installation |  | 40% | 10948560 | 0.00032% | [30 empty] | 0.00032%
|  | Setting allignment |  | 10% | 2737140 | 8e-05% | [30 empty] | 8e-05%
|  | Final inspection |  | 10% | 2737140 | 8e-05% | [30 empty] | 8e-05%
| P3FH - 28 M.14.14.3.14.3.3.14.3.3.2.14.3.3.2.3 Drying Section | [35 empty] | 0%
E43 | CONM5590 | DRYING SECTION - Surge Hopper (3541) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 9922132.5 | 0.00029% | [30 empty] | 0.00029%
|  | Check elevation & orientation |  | 20% | 19844265 | 0.00058% | [30 empty] | 0.00058%
|  | Pre-assembly on the ground |  | 10% | 9922132.5 | 0.00029% | [30 empty] | 0.00029%
|  | Installation |  | 40% | 40030672.5 | 0.00117% | [30 empty] | 0.00117%
|  | Setting allignment |  | 10% | 9922132.5 | 0.00029% | [30 empty] | 0.00029%
|  | Final inspection |  | 10% | 9922132.5 | 0.00029% | [30 empty] | 0.00029%
E44 | CONM5600 | No.2 Net Conveyor (3542) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 20528550 | 0.0006% | [30 empty] | 0.0006%
|  | Check elevation & orientation |  | 20% | 41399242.5 | 0.00121% | [30 empty] | 0.00121%
|  | Pre-assembly on the ground |  | 10% | 20528550 | 0.0006% | [30 empty] | 0.0006%
|  | Installation |  | 40% | 82798485 | 0.00242% | [30 empty] | 0.00242%
|  | Setting allignment |  | 10% | 20528550 | 0.0006% | [30 empty] | 0.0006%
|  | Final inspection |  | 10% | 20528550 | 0.0006% | [30 empty] | 0.0006%
E49 | CONM5650 | Trommel (3551) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
|  | Check elevation & orientation |  | 20% | 16764982.5 | 0.00049% | [30 empty] | 0.00049%
|  | Pre-assembly on the ground |  | 10% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
|  | Installation |  | 40% | 33529965 | 0.00098% | [30 empty] | 0.00098%
|  | Setting allignment |  | 10% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
|  | Final inspection |  | 10% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
E45 | CONM5610 | Hot Stove (3543) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 3421425 | 0.0001% | [30 empty] | 0.0001%
|  | Check elevation & orientation |  | 20% | 6842850 | 0.0002% | [30 empty] | 0.0002%
|  | Pre-assembly on the ground |  | 10% | 3421425 | 0.0001% | [30 empty] | 0.0001%
|  | Installation |  | 40% | 13685700 | 0.0004% | [30 empty] | 0.0004%
|  | Setting allignment |  | 10% | 3421425 | 0.0001% | [30 empty] | 0.0001%
|  | Final inspection |  | 10% | 3421425 | 0.0001% | [30 empty] | 0.0001%
E47 | CONM5630 | Hot Gas Circulation Fan (3545) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 1368570 | 4e-05% | [30 empty] | 4e-05%
|  | Check elevation & orientation |  | 20% | 2394997.5 | 7e-05% | [30 empty] | 7e-05%
|  | Pre-assembly on the ground |  | 10% | 1368570 | 4e-05% | [30 empty] | 4e-05%
|  | Installation |  | 40% | 4447852.5 | 0.00013% | [30 empty] | 0.00013%
|  | Setting allignment |  | 10% | 1368570 | 4e-05% | [30 empty] | 4e-05%
|  | Final inspection |  | 10% | 1368570 | 4e-05% | [30 empty] | 4e-05%
E46 | CONM5620 | Burner Dilution Fan (3544) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Check elevation & orientation |  | 20% | 1710712.5 | 5e-05% | [30 empty] | 5e-05%
|  | Pre-assembly on the ground |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Installation |  | 40% | 2737140 | 8e-05% | [30 empty] | 8e-05%
|  | Setting allignment |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Final inspection |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
E50 | CONM5660 | Soundproof Box (3552) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 11632845 | 0.00034% | [30 empty] | 0.00034%
|  | Check elevation & orientation |  | 20% | 23265690 | 0.00068% | [30 empty] | 0.00068%
|  | Pre-assembly on the ground |  | 10% | 11632845 | 0.00034% | [30 empty] | 0.00034%
|  | Installation |  | 40% | 47215665 | 0.00138% | [30 empty] | 0.00138%
|  | Setting allignment |  | 10% | 11632845 | 0.00034% | [30 empty] | 0.00034%
|  | Final inspection |  | 10% | 11632845 | 0.00034% | [30 empty] | 0.00034%
E48 | CONM5640 | Ducting (3546) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 15054270 | 0.00044% | [30 empty] | 0.00044%
|  | Check elevation & orientation |  | 20% | 29766397.5 | 0.00087% | [30 empty] | 0.00087%
|  | Pre-assembly on the ground |  | 10% | 15054270 | 0.00044% | [30 empty] | 0.00044%
|  | Installation |  | 40% | 59190652.5 | 0.00173% | [30 empty] | 0.00173%
|  | Setting allignment |  | 10% | 15054270 | 0.00044% | [30 empty] | 0.00044%
|  | Final inspection |  | 10% | 15054270 | 0.00044% | [30 empty] | 0.00044%
| P3FH - 28 M.14.14.3.14.3.3.14.3.3.2.14.3.3.2.4 Product Handling Section | [35 empty] | 0%
| CONM5670 | PRODUCT HANDLING SECTION - Rail for Container Car (3561/) | [34 empty] | 0%
E52 | CONM5680 | Container Car (3561) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
|  | Check elevation & orientation |  | 20% | 16764982.5 | 0.00049% | [30 empty] | 0.00049%
|  | Pre-assembly on the ground |  | 10% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
|  | Installation |  | 40% | 32845680 | 0.00096% | [30 empty] | 0.00096%
|  | Setting allignment |  | 10% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
|  | Final inspection |  | 10% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
E51 | CONM5690 | Container (3562) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 20528550 | 0.0006% | [30 empty] | 0.0006%
|  | Check elevation & orientation |  | 20% | 41399242.5 | 0.00121% | [30 empty] | 0.00121%
|  | Pre-assembly on the ground |  | 10% | 20528550 | 0.0006% | [30 empty] | 0.0006%
|  | Installation |  | 40% | 83140627.5 | 0.00243% | [30 empty] | 0.00243%
|  | Setting allignment |  | 10% | 20528550 | 0.0006% | [30 empty] | 0.0006%
|  | Final inspection |  | 10% | 20528550 | 0.0006% | [30 empty] | 0.0006%
| P3FH - 28 M.14.14.3.14.3.3.14.3.3.2.14.3.3.2.5 Water Circulation Section | [35 empty] | 0%
E53 | CONM5700 | WATER CIRCULATION SECTION - Shot Cooling Pump (3571) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 6158565 | 0.00018% | 2018-05-11: 0.00018% | 0%
|  | Check elevation & orientation |  | 20% | 11974987.5 | 0.00035% | 2018-05-11: 0.00035% | 0%
|  | Pre-assembly on the ground |  | 10% | 6158565 | 0.00018% | 2018-05-11: 0.00018% | 0%
|  | Installation |  | 40% | 23949975 | 0.0007% | [30 empty] | 0.0007%
|  | Setting allignment |  | 10% | 6158565 | 0.00018% | [30 empty] | 0.00018%
|  | Final inspection |  | 10% | 6158565 | 0.00018% | [30 empty] | 0.00018%
E55 | CONM5720 | Cooling Tower Feed Pump (3573) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 6158565 | 0.00018% | 2018-05-11: 0.00018% | 0%
|  | Check elevation & orientation |  | 20% | 11974987.5 | 0.00035% | 2018-05-11: 0.00035% | 0%
|  | Pre-assembly on the ground |  | 10% | 6158565 | 0.00018% | 2018-05-11: 0.00018% | 0%
|  | Installation |  | 40% | 23949975 | 0.0007% | [30 empty] | 0.0007%
|  | Setting allignment |  | 10% | 6158565 | 0.00018% | [30 empty] | 0.00018%
|  | Final inspection |  | 10% | 6158565 | 0.00018% | [30 empty] | 0.00018%
E54 | CONM5710 | Cooling Tower (3572) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 9237847.5 | 0.00027% | 2018-05-11: 0.00027% | 0%
|  | Check elevation & orientation |  | 20% | 18475695 | 0.00054% | 2018-05-11: 0.00054% | 0%
|  | Pre-assembly on the ground |  | 10% | 9237847.5 | 0.00027% | 2018-05-11: 0.00027% | 0%
|  | Installation |  | 40% | 36267105 | 0.00106% | 2018-05-11: 0.00031% | 0.00075%
|  | Setting allignment |  | 10% | 9237847.5 | 0.00027% | [30 empty] | 0.00027%
|  | Final inspection |  | 10% | 9237847.5 | 0.00027% | [30 empty] | 0.00027%
| P3FH - 28 M.14.14.3.14.3.3.14.3.3.3 Crane, Ladles, Ladle Preheating & Ladle Heating Equipment | [35 empty] | 0%
E56 | CONM5730 | Transport material to site |  | 10% | 74929207.5 | 0.00219% | [30 empty] | 0.00219%
|  | Check elevation & orientation |  | 20% | 149516272.5 | 0.00437% | [30 empty] | 0.00437%
|  | Pre-assembly on the ground |  | 10% | 74929207.5 | 0.00219% | [30 empty] | 0.00219%
|  | Installation |  | 40% | 298690402.5 | 0.00873% | [30 empty] | 0.00873%
|  | Setting allignment |  | 10% | 74929207.5 | 0.00219% | [30 empty] | 0.00219%
|  | Final inspection |  | 10% | 74929207.5 | 0.00219% | [30 empty] | 0.00219%
0%
E66 | CONM5830 | Casting Storage Crane (3661) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 19502122.5 | 0.00057% | [30 empty] | 0.00057%
|  | Check elevation & orientation |  | 20% | 39004245 | 0.00114% | [30 empty] | 0.00114%
|  | Pre-assembly on the ground |  | 10% | 19502122.5 | 0.00057% | [30 empty] | 0.00057%
|  | Installation |  | 40% | 78692775 | 0.0023% | [30 empty] | 0.0023%
|  | Setting allignment |  | 10% | 19502122.5 | 0.00057% | [30 empty] | 0.00057%
|  | Final inspection |  | 10% | 19502122.5 | 0.00057% | [30 empty] | 0.00057%
E59 | CONM5760 | Hanger (3644) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 29424255 | 0.00086% | [30 empty] | 0.00086%
|  | Check elevation & orientation |  | 20% | 58848510 | 0.00172% | [30 empty] | 0.00172%
|  | Pre-assembly on the ground |  | 10% | 29424255 | 0.00086% | [30 empty] | 0.00086%
|  | Installation |  | 40% | 117012735 | 0.00342% | [30 empty] | 0.00342%
|  | Setting allignment |  | 10% | 29424255 | 0.00086% | [30 empty] | 0.00086%
|  | Final inspection |  | 10% | 29424255 | 0.00086% | [30 empty] | 0.00086%
E60 | CONM5770 | Service Tank (3601) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 1368570 | 4e-05% | [30 empty] | 4e-05%
|  | Check elevation & orientation |  | 20% | 3079282.5 | 9e-05% | [30 empty] | 9e-05%
|  | Pre-assembly on the ground |  | 10% | 1368570 | 4e-05% | [30 empty] | 4e-05%
|  | Installation |  | 40% | 6500707.5 | 0.00019% | [30 empty] | 0.00019%
|  | Setting allignment |  | 10% | 1368570 | 4e-05% | [30 empty] | 4e-05%
|  | Final inspection |  | 10% | 1368570 | 4e-05% | [30 empty] | 4e-05%
E61 | CONM5780 | Pump Unit (3602) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 1368570 | 4e-05% | [30 empty] | 4e-05%
|  | Check elevation & orientation |  | 20% | 2737140 | 8e-05% | [30 empty] | 8e-05%
|  | Pre-assembly on the ground |  | 10% | 1368570 | 4e-05% | [30 empty] | 4e-05%
|  | Installation |  | 40% | 5816422.5 | 0.00017% | [30 empty] | 0.00017%
|  | Setting allignment |  | 10% | 1368570 | 4e-05% | [30 empty] | 4e-05%
|  | Final inspection |  | 10% | 1368570 | 4e-05% | [30 empty] | 4e-05%
E57 | CONM5740 | Ladle (3641) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 129672007.5 | 0.00379% | [30 empty] | 0.00379%
|  | Check elevation & orientation |  | 20% | 259686157.5 | 0.00759% | [30 empty] | 0.00759%
|  | Pre-assembly on the ground |  | 10% | 129672007.5 | 0.00379% | [30 empty] | 0.00379%
|  | Installation |  | 40% | 519372315 | 0.01518% | [30 empty] | 0.01518%
|  | Setting allignment |  | 10% | 129672007.5 | 0.00379% | [30 empty] | 0.00379%
|  | Final inspection |  | 10% | 129672007.5 | 0.00379% | [30 empty] | 0.00379%
E58 | CONM5750 | Slag Pot (3643) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 6842850 | 0.0002% | [30 empty] | 0.0002%
|  | Check elevation & orientation |  | 20% | 13343557.5 | 0.00039% | [30 empty] | 0.00039%
|  | Pre-assembly on the ground |  | 10% | 6842850 | 0.0002% | [30 empty] | 0.0002%
|  | Installation |  | 40% | 26687115 | 0.00078% | [30 empty] | 0.00078%
|  | Setting allignment |  | 10% | 6842850 | 0.0002% | [30 empty] | 0.0002%
|  | Final inspection |  | 10% | 6842850 | 0.0002% | [30 empty] | 0.0002%
E63 | CONM5790 | Burner (3604) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
|  | Check elevation & orientation |  | 20% | 684285 | 2e-05% | [30 empty] | 2e-05%
|  | Pre-assembly on the ground |  | 10% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
|  | Installation |  | 40% | 1710712.5 | 5e-05% | [30 empty] | 5e-05%
|  | Setting allignment |  | 10% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
|  | Final inspection |  | 10% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
| CONM5810 | Ladle Preheating Unit (3606A) | [34 empty] | 0%
E64 | CONM5800 | Blower (3605) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 1710712.5 | 5e-05% | [30 empty] | 5e-05%
|  | Check elevation & orientation |  | 20% | 3079282.5 | 9e-05% | [30 empty] | 9e-05%
|  | Pre-assembly on the ground |  | 10% | 1710712.5 | 5e-05% | [30 empty] | 5e-05%
|  | Installation |  | 40% | 5816422.5 | 0.00017% | [30 empty] | 0.00017%
|  | Setting allignment |  | 10% | 1710712.5 | 5e-05% | [30 empty] | 5e-05%
|  | Final inspection |  | 10% | 1710712.5 | 5e-05% | [30 empty] | 5e-05%
E65 | CONM5820 | Ladle Heating Unit (3606B) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 13685700 | 0.0004% | [30 empty] | 0.0004%
|  | Check elevation & orientation |  | 20% | 27029257.5 | 0.00079% | [30 empty] | 0.00079%
|  | Pre-assembly on the ground |  | 10% | 13685700 | 0.0004% | [30 empty] | 0.0004%
|  | Installation |  | 40% | 53716372.5 | 0.00157% | [30 empty] | 0.00157%
|  | Setting allignment |  | 10% | 13685700 | 0.0004% | [30 empty] | 0.0004%
|  | Final inspection |  | 10% | 13685700 | 0.0004% | [30 empty] | 0.0004%
E68 | P3FH - 28 M.14.14.3.14.3.4 System 4 - Utility Supply | [35 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.4.14.3.4.1 Water Intake and Treatment System Equipment | [35 empty] | 0%
E69 | P3FH - 28 M.14.14.3.14.3.4.14.3.4.1.14.3.4.1.1 Raw Water Intake System 4100 | [35 empty] | 0%
E72 | CONM5850 | RAW WATER INTAKE SYTEM_Clarifier (4103) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 45504952.5 | 0.00133% | [30 empty] | 0.00133%
|  | Check elevation & orientation |  | 20% | 91009905 | 0.00266% | [30 empty] | 0.00266%
|  | Pre-assembly on the ground |  | 10% | 45504952.5 | 0.00133% | [30 empty] | 0.00133%
|  | Installation |  | 40% | 181677667.5 | 0.00531% | [30 empty] | 0.00531%
|  | Setting allignment |  | 10% | 45504952.5 | 0.00133% | [30 empty] | 0.00133%
|  | Final inspection |  | 10% | 45504952.5 | 0.00133% | [30 empty] | 0.00133%
E71 | CONM5840 | RAW WATER INTAKE SYSTEM_Intake Pump (4102 - 1 / 2) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
|  | Check elevation & orientation |  | 20% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Pre-assembly on the ground |  | 10% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
|  | Installation |  | 40% | 2394997.5 | 7e-05% | [30 empty] | 7e-05%
|  | Setting allignment |  | 10% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
|  | Final inspection |  | 10% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
E73 | CONM5860 | RAW WATER INTAKE SYSTEM_Transfer Pump (4104 - 1 / 2) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 2737140 | 8e-05% | [30 empty] | 8e-05%
|  | Check elevation & orientation |  | 20% | 5132137.5 | 0.00015% | [30 empty] | 0.00015%
|  | Pre-assembly on the ground |  | 10% | 2737140 | 8e-05% | [30 empty] | 8e-05%
|  | Installation |  | 40% | 9922132.5 | 0.00029% | [30 empty] | 0.00029%
|  | Setting allignment |  | 10% | 2737140 | 8e-05% | [30 empty] | 8e-05%
|  | Final inspection |  | 10% | 2737140 | 8e-05% | [30 empty] | 8e-05%
E75 | CONM5870 | RAW WATER INTAKE SYSTEM_No. 1 Dosing Tank (4105 - 1) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 1710712.5 | 5e-05% | [30 empty] | 5e-05%
|  | Check elevation & orientation |  | 20% | 3421425 | 0.0001% | [30 empty] | 0.0001%
|  | Pre-assembly on the ground |  | 10% | 1710712.5 | 5e-05% | [30 empty] | 5e-05%
|  | Installation |  | 40% | 6500707.5 | 0.00019% | [30 empty] | 0.00019%
|  | Setting allignment |  | 10% | 1710712.5 | 5e-05% | [30 empty] | 5e-05%
|  | Final inspection |  | 10% | 1710712.5 | 5e-05% | [30 empty] | 5e-05%
E76 | CONM5880 | RAW WATER INTAKE SYSTEM_Dosing Pump for No. 1 Tank (4106 - 1) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Check elevation & orientation |  | 20% | 2052855 | 6e-05% | [30 empty] | 6e-05%
|  | Pre-assembly on the ground |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Installation |  | 40% | 4447852.5 | 0.00013% | [30 empty] | 0.00013%
|  | Setting allignment |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Final inspection |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
E77 | CONM5890 | RAW WATER INTAKE SYSTEM_No. 2 Dosing Tank (4105 - 2) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 0 | 0% | [30 empty] | 0%
|  | Check elevation & orientation |  | 20% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
|  | Pre-assembly on the ground |  | 10% | 0 | 0% | [30 empty] | 0%
|  | Installation |  | 40% | 684285 | 2e-05% | [30 empty] | 2e-05%
|  | Setting allignment |  | 10% | 0 | 0% | [30 empty] | 0%
|  | Final inspection |  | 10% | 0 | 0% | [30 empty] | 0%
E78 | CONM5900 | RAW WATER INTAKE SYSTEM_Dosing Pump for No. 2 Tank (4106 - 2) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 0 | 0% | [30 empty] | 0%
|  | Check elevation & orientation |  | 20% | 0 | 0% | [30 empty] | 0%
|  | Pre-assembly on the ground |  | 10% | 0 | 0% | [30 empty] | 0%
|  | Installation |  | 40% | 684285 | 2e-05% | [30 empty] | 2e-05%
|  | Setting allignment |  | 10% | 0 | 0% | [30 empty] | 0%
|  | Final inspection |  | 10% | 0 | 0% | [30 empty] | 0%
| P3FH - 28 M.14.14.3.14.3.4.14.3.4.1.14.3.4.1.2 Filtration Receiving Water System 4100 | [35 empty] | 0%
E83 | CONM5920 | FILTRATION RECEIVING WATER SYSTEM_Sand Filter (4112 - 1 / 2) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 26002830 | 0.00076% | [30 empty] | 0.00076%
|  | Check elevation & orientation |  | 20% | 52005660 | 0.00152% | [30 empty] | 0.00152%
|  | Pre-assembly on the ground |  | 10% | 26002830 | 0.00076% | [30 empty] | 0.00076%
|  | Installation |  | 40% | 104011320 | 0.00304% | [30 empty] | 0.00304%
|  | Setting allignment |  | 10% | 26002830 | 0.00076% | [30 empty] | 0.00076%
|  | Final inspection |  | 10% | 26002830 | 0.00076% | [30 empty] | 0.00076%
E86 | CONM5940 | FILTRATION RECEIVING WATER SYSTEM - Softener (4115 ) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 15054270 | 0.00044% | [30 empty] | 0.00044%
|  | Check elevation & orientation |  | 20% | 29766397.5 | 0.00087% | [30 empty] | 0.00087%
|  | Pre-assembly on the ground |  | 10% | 15054270 | 0.00044% | [30 empty] | 0.00044%
|  | Installation |  | 40% | 58848510 | 0.00172% | [30 empty] | 0.00172%
|  | Setting allignment |  | 10% | 15054270 | 0.00044% | [30 empty] | 0.00044%
|  | Final inspection |  | 10% | 15054270 | 0.00044% | [30 empty] | 0.00044%
E81 | CONM5910 | FILTRATION RECEIVING WATER SYSTEM_Receiving Water Pump (4111 - 1 / 2) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 684285 | 2e-05% | [30 empty] | 2e-05%
|  | Check elevation & orientation |  | 20% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Pre-assembly on the ground |  | 10% | 684285 | 2e-05% | [30 empty] | 2e-05%
|  | Installation |  | 40% | 1710712.5 | 5e-05% | [30 empty] | 5e-05%
|  | Setting allignment |  | 10% | 684285 | 2e-05% | [30 empty] | 2e-05%
|  | Final inspection |  | 10% | 684285 | 2e-05% | [30 empty] | 2e-05%
E84 | CONM5930 | FILTRATION RECEIVING WATER SYSTEM_Filtered Water Pump (4114 - 1) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 684285 | 2e-05% | [30 empty] | 2e-05%
|  | Check elevation & orientation |  | 20% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Pre-assembly on the ground |  | 10% | 684285 | 2e-05% | [30 empty] | 2e-05%
|  | Installation |  | 40% | 1710712.5 | 5e-05% | [30 empty] | 5e-05%
|  | Setting allignment |  | 10% | 684285 | 2e-05% | [30 empty] | 2e-05%
|  | Final inspection |  | 10% | 684285 | 2e-05% | [30 empty] | 2e-05%
E87 | CONM5950 | FILTRATION RECEIVING WATER SYSTEM_NaCl Tank (4116) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 2052855 | 6e-05% | [30 empty] | 6e-05%
|  | Check elevation & orientation |  | 20% | 4105710 | 0.00012% | [30 empty] | 0.00012%
|  | Pre-assembly on the ground |  | 10% | 2052855 | 6e-05% | [30 empty] | 6e-05%
|  | Installation |  | 40% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
|  | Setting allignment |  | 10% | 2052855 | 6e-05% | [30 empty] | 6e-05%
|  | Final inspection |  | 10% | 2052855 | 6e-05% | [30 empty] | 6e-05%
| P3FH - 28 M.14.14.3.14.3.4.14.3.4.2 Water Circulation System | [35 empty] | 0%
E89 | P3FH - 28 M.14.14.3.14.3.4.14.3.4.2.14.3.4.2.1 Non-Softened Water Circulation System Equipment 4200 | [35 empty] | 0%
E92 | CONM5970 | NSW - Head Tank (4202) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 63296362.5 | 0.00185% | [30 empty] | 0.00185%
|  | Check elevation & orientation |  | 20% | 126592725 | 0.0037% | [30 empty] | 0.0037%
|  | Pre-assembly on the ground |  | 10% | 63296362.5 | 0.00185% | [30 empty] | 0.00185%
|  | Installation |  | 40% | 253527592.5 | 0.00741% | [30 empty] | 0.00741%
|  | Setting allignment |  | 10% | 63296362.5 | 0.00185% | [30 empty] | 0.00185%
|  | Final inspection |  | 10% | 63296362.5 | 0.00185% | [30 empty] | 0.00185%
E90 | CONM5960 | NSW - Circulation Pump (4201 - 1 / 2) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 2737140 | 8e-05% | [30 empty] | 8e-05%
|  | Check elevation & orientation |  | 20% | 5474280 | 0.00016% | [30 empty] | 0.00016%
|  | Pre-assembly on the ground |  | 10% | 2737140 | 8e-05% | [30 empty] | 8e-05%
|  | Installation |  | 40% | 10948560 | 0.00032% | [30 empty] | 0.00032%
|  | Setting allignment |  | 10% | 2737140 | 8e-05% | [30 empty] | 8e-05%
|  | Final inspection |  | 10% | 2737140 | 8e-05% | [30 empty] | 8e-05%
E93 | CONM5980 | NSW - Return Water Pump (4204 - 1 / 2) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 1368570 | 4e-05% | [30 empty] | 4e-05%
|  | Check elevation & orientation |  | 20% | 2737140 | 8e-05% | [30 empty] | 8e-05%
|  | Pre-assembly on the ground |  | 10% | 1368570 | 4e-05% | [30 empty] | 4e-05%
|  | Installation |  | 40% | 4789995 | 0.00014% | [30 empty] | 0.00014%
|  | Setting allignment |  | 10% | 1368570 | 4e-05% | [30 empty] | 4e-05%
|  | Final inspection |  | 10% | 1368570 | 4e-05% | [30 empty] | 4e-05%
E95 | CONM5990 | NSW - Cooling Tower (4205) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 6842850 | 0.0002% | [30 empty] | 0.0002%
|  | Check elevation & orientation |  | 20% | 13343557.5 | 0.00039% | [30 empty] | 0.00039%
|  | Pre-assembly on the ground |  | 10% | 6842850 | 0.0002% | [30 empty] | 0.0002%
|  | Installation |  | 40% | 26344972.5 | 0.00077% | [30 empty] | 0.00077%
|  | Setting allignment |  | 10% | 6842850 | 0.0002% | [30 empty] | 0.0002%
|  | Final inspection |  | 10% | 6842850 | 0.0002% | [30 empty] | 0.0002%
E97 | P3FH - 28 M.14.14.3.14.3.4.14.3.4.2.14.3.4.2.2 Softened Water Circulation System Equipment | [35 empty] | 0%
E100 | CONM6010 | SW - Head Tank (4212) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 63296362.5 | 0.00185% | [30 empty] | 0.00185%
|  | Check elevation & orientation |  | 20% | 126592725 | 0.0037% | [30 empty] | 0.0037%
|  | Pre-assembly on the ground |  | 10% | 63296362.5 | 0.00185% | [30 empty] | 0.00185%
|  | Installation |  | 40% | 253527592.5 | 0.00741% | [30 empty] | 0.00741%
|  | Setting allignment |  | 10% | 63296362.5 | 0.00185% | [30 empty] | 0.00185%
|  | Final inspection |  | 10% | 63296362.5 | 0.00185% | [30 empty] | 0.00185%
E98 | CONM6000 | SW - Circulation Pump (4211 - 1 / 2) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 2737140 | 8e-05% | [30 empty] | 8e-05%
|  | Check elevation & orientation |  | 20% | 5474280 | 0.00016% | [30 empty] | 0.00016%
|  | Pre-assembly on the ground |  | 10% | 2737140 | 8e-05% | [30 empty] | 8e-05%
|  | Installation |  | 40% | 10948560 | 0.00032% | [30 empty] | 0.00032%
|  | Setting allignment |  | 10% | 2737140 | 8e-05% | [30 empty] | 8e-05%
|  | Final inspection |  | 10% | 2737140 | 8e-05% | [30 empty] | 8e-05%
E101 | CONM6020 | SW - Return Water Pump (4214 - 1 / 2) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 2052855 | 6e-05% | [30 empty] | 6e-05%
|  | Check elevation & orientation |  | 20% | 3763567.5 | 0.00011% | [30 empty] | 0.00011%
|  | Pre-assembly on the ground |  | 10% | 2052855 | 6e-05% | [30 empty] | 6e-05%
|  | Installation |  | 40% | 7184992.5 | 0.00021% | [30 empty] | 0.00021%
|  | Setting allignment |  | 10% | 2052855 | 6e-05% | [30 empty] | 6e-05%
|  | Final inspection |  | 10% | 2052855 | 6e-05% | [30 empty] | 6e-05%
E104 | CONM6040 | SW - Inline Filter (4216) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
|  | Check elevation & orientation |  | 20% | 684285 | 2e-05% | [30 empty] | 2e-05%
|  | Pre-assembly on the ground |  | 10% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
|  | Installation |  | 40% | 684285 | 2e-05% | [30 empty] | 2e-05%
|  | Setting allignment |  | 10% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
|  | Final inspection |  | 10% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
E103 | CONM6030 | SW - Cooling Tower (4215) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 22239262.5 | 0.00065% | [30 empty] | 0.00065%
|  | Check elevation & orientation |  | 20% | 44478525 | 0.0013% | [30 empty] | 0.0013%
|  | Pre-assembly on the ground |  | 10% | 22239262.5 | 0.00065% | [30 empty] | 0.00065%
|  | Installation |  | 40% | 89641335 | 0.00262% | [30 empty] | 0.00262%
|  | Setting allignment |  | 10% | 22239262.5 | 0.00065% | [30 empty] | 0.00065%
|  | Final inspection |  | 10% | 22239262.5 | 0.00065% | [30 empty] | 0.00065%
E106 | P3FH - 28 M.14.14.3.14.3.4.14.3.4.2.14.3.4.2.3 Softened Water Circulation System Equipment for Copper Cooler | [35 empty] | 0%
E109 | CONM6060 | SW FOR COOPER COOLER - Head Tank (4222) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 63296362.5 | 0.00185% | [30 empty] | 0.00185%
|  | Check elevation & orientation |  | 20% | 126592725 | 0.0037% | [30 empty] | 0.0037%
|  | Pre-assembly on the ground |  | 10% | 63296362.5 | 0.00185% | [30 empty] | 0.00185%
|  | Installation |  | 40% | 253527592.5 | 0.00741% | [30 empty] | 0.00741%
|  | Setting allignment |  | 10% | 63296362.5 | 0.00185% | [30 empty] | 0.00185%
|  | Final inspection |  | 10% | 63296362.5 | 0.00185% | [30 empty] | 0.00185%
E107 | CONM6050 | SW FOR COOPER COOLER - Circulation Pump (4221 - 1 / 2) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 2052855 | 6e-05% | [30 empty] | 6e-05%
|  | Check elevation & orientation |  | 20% | 4105710 | 0.00012% | [30 empty] | 0.00012%
|  | Pre-assembly on the ground |  | 10% | 2052855 | 6e-05% | [30 empty] | 6e-05%
|  | Installation |  | 40% | 8895705 | 0.00026% | [30 empty] | 0.00026%
|  | Setting allignment |  | 10% | 2052855 | 6e-05% | [30 empty] | 6e-05%
|  | Final inspection |  | 10% | 2052855 | 6e-05% | [30 empty] | 6e-05%
E110 | CONM6070 | SW FOR COOPER COOLER - Return Water Pump (4224 - 1 / 2) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 2052855 | 6e-05% | [30 empty] | 6e-05%
|  | Check elevation & orientation |  | 20% | 3763567.5 | 0.00011% | [30 empty] | 0.00011%
|  | Pre-assembly on the ground |  | 10% | 2052855 | 6e-05% | [30 empty] | 6e-05%
|  | Installation |  | 40% | 7184992.5 | 0.00021% | [30 empty] | 0.00021%
|  | Setting allignment |  | 10% | 2052855 | 6e-05% | [30 empty] | 6e-05%
|  | Final inspection |  | 10% | 2052855 | 6e-05% | [30 empty] | 6e-05%
E113 | CONM6090 | SW FOR COOPER COOLER - Inline Filter (4226) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
|  | Check elevation & orientation |  | 20% | 684285 | 2e-05% | [30 empty] | 2e-05%
|  | Pre-assembly on the ground |  | 10% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
|  | Installation |  | 40% | 684285 | 2e-05% | [30 empty] | 2e-05%
|  | Setting allignment |  | 10% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
|  | Final inspection |  | 10% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
E112 | CONM6080 | SW FOR COOPER COOLER - Cooling Tower (4225) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 22239262.5 | 0.00065% | [30 empty] | 0.00065%
|  | Check elevation & orientation |  | 20% | 44478525 | 0.0013% | [30 empty] | 0.0013%
|  | Pre-assembly on the ground |  | 10% | 22239262.5 | 0.00065% | [30 empty] | 0.00065%
|  | Installation |  | 40% | 89641335 | 0.00262% | [30 empty] | 0.00262%
|  | Setting allignment |  | 10% | 22239262.5 | 0.00065% | [30 empty] | 0.00065%
|  | Final inspection |  | 10% | 22239262.5 | 0.00065% | [30 empty] | 0.00065%
E115 | P3FH - 28 M.14.14.3.14.3.4.14.3.4.3 Compressed Air and Distribution System | [35 empty] | 0%
E116 | CONM6100 | Air Compressor for Ore Preparation System (4701 - 1/2) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 11290702.5 | 0.00033% | [30 empty] | 0.00033%
|  | Check elevation & orientation |  | 20% | 22581405 | 0.00066% | [30 empty] | 0.00066%
|  | Pre-assembly on the ground |  | 10% | 11290702.5 | 0.00033% | [30 empty] | 0.00033%
|  | Installation |  | 40% | 44478525 | 0.0013% | [30 empty] | 0.0013%
|  | Setting allignment |  | 10% | 11290702.5 | 0.00033% | [30 empty] | 0.00033%
|  | Final inspection |  | 10% | 11290702.5 | 0.00033% | [30 empty] | 0.00033%
E117 | CONM6110 | Main Receiver Tank (4702) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 3421425 | 0.0001% | [30 empty] | 0.0001%
|  | Check elevation & orientation |  | 20% | 6842850 | 0.0002% | [30 empty] | 0.0002%
|  | Pre-assembly on the ground |  | 10% | 3421425 | 0.0001% | [30 empty] | 0.0001%
|  | Installation |  | 40% | 13001415 | 0.00038% | [30 empty] | 0.00038%
|  | Setting allignment |  | 10% | 3421425 | 0.0001% | [30 empty] | 0.0001%
|  | Final inspection |  | 10% | 3421425 | 0.0001% | [30 empty] | 0.0001%
E118 | CONM6120 | Air Receiver Tank (4703 - 1) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 16764982.5 | 0.00049% | [30 empty] | 0.00049%
|  | Check elevation & orientation |  | 20% | 33529965 | 0.00098% | [30 empty] | 0.00098%
|  | Pre-assembly on the ground |  | 10% | 16764982.5 | 0.00049% | [30 empty] | 0.00049%
|  | Installation |  | 40% | 66717787.5 | 0.00195% | [30 empty] | 0.00195%
|  | Setting allignment |  | 10% | 16764982.5 | 0.00049% | [30 empty] | 0.00049%
|  | Final inspection |  | 10% | 16764982.5 | 0.00049% | [30 empty] | 0.00049%
E126 | CONM6220 | Air Receiver Tank (4706) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Check elevation & orientation |  | 20% | 2394997.5 | 7e-05% | [30 empty] | 7e-05%
|  | Pre-assembly on the ground |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Installation |  | 40% | 4789995 | 0.00014% | [30 empty] | 0.00014%
|  | Setting allignment |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Final inspection |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
E127 | CONM6240 | Air Receiver Tank (4708 - 1/2) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Check elevation & orientation |  | 20% | 2394997.5 | 7e-05% | [30 empty] | 7e-05%
|  | Pre-assembly on the ground |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Installation |  | 40% | 4789995 | 0.00014% | [30 empty] | 0.00014%
|  | Setting allignment |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Final inspection |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
| CONM6130 | Air Receiver Tank (4703 - 2) | [34 empty] | 0%
E128 | CONM6250 | Air Receiver Tank (4709 - 1) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Check elevation & orientation |  | 20% | 2394997.5 | 7e-05% | [30 empty] | 7e-05%
|  | Pre-assembly on the ground |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Installation |  | 40% | 4789995 | 0.00014% | [30 empty] | 0.00014%
|  | Setting allignment |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Final inspection |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
E120 | CONM6180 | Air Dryer for Gas Treatment Instrument (4704 - 2) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 0 | 0% | [30 empty] | 0%
|  | Check elevation & orientation |  | 20% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
|  | Pre-assembly on the ground |  | 10% | 0 | 0% | [30 empty] | 0%
|  | Installation |  | 40% | 684285 | 2e-05% | [30 empty] | 2e-05%
|  | Setting allignment |  | 10% | 0 | 0% | [30 empty] | 0%
|  | Final inspection |  | 10% | 0 | 0% | [30 empty] | 0%
E124 | CONM6210 | Air Compressor for - Type ESF & Refinery System (4705 - 1/2) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 9237847.5 | 0.00027% | [30 empty] | 0.00027%
|  | Check elevation & orientation |  | 20% | 18475695 | 0.00054% | [30 empty] | 0.00054%
|  | Pre-assembly on the ground |  | 10% | 9237847.5 | 0.00027% | [30 empty] | 0.00027%
|  | Installation |  | 40% | 37635675 | 0.0011% | [30 empty] | 0.0011%
|  | Setting allignment |  | 10% | 9237847.5 | 0.00027% | [30 empty] | 0.00027%
|  | Final inspection |  | 10% | 9237847.5 | 0.00027% | [30 empty] | 0.00027%
E123 | CONM6230 | Air Compressor for - Type Mud Gun (4707 - 1/2) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 2394997.5 | 7e-05% | [30 empty] | 7e-05%
|  | Check elevation & orientation |  | 20% | 4789995 | 0.00014% | [30 empty] | 0.00014%
|  | Pre-assembly on the ground |  | 10% | 2394997.5 | 7e-05% | [30 empty] | 7e-05%
|  | Installation |  | 40% | 8895705 | 0.00026% | [30 empty] | 0.00026%
|  | Setting allignment |  | 10% | 2394997.5 | 7e-05% | [30 empty] | 7e-05%
|  | Final inspection |  | 10% | 2394997.5 | 7e-05% | [30 empty] | 7e-05%
| CONM6140 | Air Receiver Tank (4703 - 3) | [34 empty] | 0%
E121 | CONM6190 | Air Dryer for Instrument for Kiln (4704 - 3) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 0 | 0% | [30 empty] | 0%
|  | Check elevation & orientation |  | 20% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
|  | Pre-assembly on the ground |  | 10% | 0 | 0% | [30 empty] | 0%
|  | Installation |  | 40% | 684285 | 2e-05% | [30 empty] | 2e-05%
|  | Setting allignment |  | 10% | 0 | 0% | [30 empty] | 0%
|  | Final inspection |  | 10% | 0 | 0% | [30 empty] | 0%
E122 | CONM6200 | Air Dryer for De-S System and other (4704 - 4) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 0 | 0% | [30 empty] | 0%
|  | Check elevation & orientation |  | 20% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
|  | Pre-assembly on the ground |  | 10% | 0 | 0% | [30 empty] | 0%
|  | Installation |  | 40% | 684285 | 2e-05% | [30 empty] | 2e-05%
|  | Setting allignment |  | 10% | 0 | 0% | [30 empty] | 0%
|  | Final inspection |  | 10% | 0 | 0% | [30 empty] | 0%
E129 | CONM6260 | Air Dryer for ESF and Instrument Air (4711 - 1) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
|  | Check elevation & orientation |  | 20% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
|  | Pre-assembly on the ground |  | 10% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
|  | Installation |  | 40% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
|  | Setting allignment |  | 10% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
|  | Final inspection |  | 10% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
| CONM6150 | Air Receiver Tank (4703 - 4) | [34 empty] | 0%
| CONM6160 | Air Receiver Tank (4703 - 5) | [34 empty] | 0%
E119 | CONM6170 | Air Receiver Tank (4703 - 6) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 3421425 | 0.0001% | [30 empty] | 0.0001%
|  | Check elevation & orientation |  | 20% | 6842850 | 0.0002% | [30 empty] | 0.0002%
|  | Pre-assembly on the ground |  | 10% | 3421425 | 0.0001% | [30 empty] | 0.0001%
|  | Installation |  | 40% | 13001415 | 0.00038% | [30 empty] | 0.00038%
|  | Setting allignment |  | 10% | 3421425 | 0.0001% | [30 empty] | 0.0001%
|  | Final inspection |  | 10% | 3421425 | 0.0001% | [30 empty] | 0.0001%
E132 | P3FH - 28 M.14.14.3.14.3.4.14.3.4.4 Fuel Oil Pumping and Distribution System | [35 empty] | 0%
E133 | CONM6300 | MFO Feed Pump (4302 - 1 / 2) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Check elevation & orientation |  | 20% | 1710712.5 | 5e-05% | [30 empty] | 5e-05%
|  | Pre-assembly on the ground |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Installation |  | 40% | 3079282.5 | 9e-05% | [30 empty] | 9e-05%
|  | Setting allignment |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Final inspection |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
E137 | CONM6320 | HSD Feed Pump (4401 - 1 / 2) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Check elevation & orientation |  | 20% | 1710712.5 | 5e-05% | [30 empty] | 5e-05%
|  | Pre-assembly on the ground |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Installation |  | 40% | 3079282.5 | 9e-05% | [30 empty] | 9e-05%
|  | Setting allignment |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Final inspection |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
| CONM6310 | MFO Transfer Pump (4303 - 1 / 2) | [34 empty] | 0%
| CONM6330 | HSD Transfer Pump (4403 - 1 / 2) | [34 empty] | 0%
E135 | CONM6270 | MFO Service Tank for Dryer HAG (4401) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Check elevation & orientation |  | 20% | 1710712.5 | 5e-05% | [30 empty] | 5e-05%
|  | Pre-assembly on the ground |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Installation |  | 40% | 3421425 | 0.0001% | [30 empty] | 0.0001%
|  | Setting allignment |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Final inspection |  | 10% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
| CONM6280 | MFO Service Tank for Kiln (4402) | [34 empty] | 0%
| CONM6290 | HSD Service Tank for Coal Mill HAG (4403) | [34 empty] | 0%
E140 | P3FH - 28 M.14.14.3.14.3.4.14.3.4.5 Sea Water Intake System | [35 empty] | 0%
E141 | CONM6340 | Sea water intake pump (4901 - 1/2/3) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 2737140 | 8e-05% | [30 empty] | 8e-05%
|  | Check elevation & orientation |  | 20% | 5132137.5 | 0.00015% | [30 empty] | 0.00015%
|  | Pre-assembly on the ground |  | 10% | 2737140 | 8e-05% | [30 empty] | 8e-05%
|  | Installation |  | 40% | 9922132.5 | 0.00029% | [30 empty] | 0.00029%
|  | Setting allignment |  | 10% | 2737140 | 8e-05% | [30 empty] | 8e-05%
|  | Final inspection |  | 10% | 2737140 | 8e-05% | [30 empty] | 8e-05%
E143 | CONM6350 | Sea water intake pump (4901 - 4) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 162517687.5 | 0.00475% | [30 empty] | 0.00475%
|  | Check elevation & orientation |  | 20% | 325035375 | 0.0095% | [30 empty] | 0.0095%
|  | Pre-assembly on the ground |  | 10% | 162517687.5 | 0.00475% | [30 empty] | 0.00475%
|  | Installation |  | 40% | 649728607.5 | 0.01899% | [30 empty] | 0.01899%
|  | Setting allignment |  | 10% | 162517687.5 | 0.00475% | [30 empty] | 0.00475%
|  | Final inspection |  | 10% | 162517687.5 | 0.00475% | [30 empty] | 0.00475%
E150 | P3FH - 28 M.14.14.3.14.3.4.14.3.4.6 Oxygen Plant | [35 empty] | 0%
| CONM6360 | Nitrogen Buffer Vessel | [34 empty] | 0%
| CONM6420 | Heat Exchanger | [34 empty] | 0%
| CONM6370 | Oxygen Buffer Vessel | [34 empty] | 0%
| CONM6430 | Precooling Unit | [34 empty] | 0%
| CONM6440 | Purification Unit Vessel | [34 empty] | 0%
| CONM6450 | Air Filter | [34 empty] | 0%
| CONM6380 | Compressor | [34 empty] | 0%
| CONM6460 | Electric Heater | [34 empty] | 0%
| CONM6470 | Moisture Separator | [34 empty] | 0%
| CONM6390 | Nitrogen Compressor | [34 empty] | 0%
| CONM6480 | Cold Box | [34 empty] | 0%
| CONM6400 | Oxygen Compressor | [34 empty] | 0%
| CONM6410 | Turbine | [34 empty] | 0%
| CONM6490 | Pump | [34 empty] | 0%
|  | Transport material to site |  | 10% | 125908440 | 0.00368% | [30 empty] | 0.00368%
|  | Check elevation & orientation |  | 20% | 252159022.5 | 0.00737% | [30 empty] | 0.00737%
|  | Pre-assembly on the ground |  | 10% | 125908440 | 0.00368% | [30 empty] | 0.00368%
|  | Installation |  | 40% | 504318045 | 0.01474% | [30 empty] | 0.01474%
|  | Setting allignment |  | 10% | 125908440 | 0.00368% | [30 empty] | 0.00368%
|  | Final inspection |  | 10% | 125908440 | 0.00368% | [30 empty] | 0.00368%
| P3FH - 28 M.14.14.3.14.3.4.10 Fire Water System | [35 empty] | 0%
| A25560 | Fabrication for Fire Water Tank - (4801) | [34 empty] | 0%
| A25570 | Intallation for Fire Water Tank - (4801) | [34 empty] | 0%
| A25580 | Intallation for Fire Water Pump - (4802 A/B) | [34 empty] | 0%
| A25590 | Intallation for Jockey Pump - (4803) | [34 empty] | 0%
| P3FH - 28 M.14.14.3.1 Non Process Building | [35 empty] | 0%
| P3FH - 28 M.14.14.3.1.14 Administration Building | [35 empty] | 0%
| A25500 | AC, Ventilation Fan, Supply Fan, & others mechanical work | [34 empty] | 0%
| P3FH - 28 M.14.14.3.1.4 Laboratory for Ore Preparation | [35 empty] | 0%
| A25510 | AC, Ventilation Fan, Supply Fan, & others mechanical work | [34 empty] | 0%
| P3FH - 28 M.14.14.3.1.5 Laboratory for Instrument | [35 empty] | 0%
| A25520 | AC, Ventilation Fan, Supply Fan, & others mechanical work | [34 empty] | 0%
| P3FH - 28 M.14.14.3.1.6 Laboratory for Chemical | [35 empty] | 0%
| A25530 | AC, Ventilation Fan, Supply Fan, & others mechanical work | [34 empty] | 0%
| P3FH - 28 M.14.14.3.1.12 Weight Bridge Building | [35 empty] | 0%
| A25550 | Load Cell Installation | [34 empty] | 0%
| A25600 | Platform Installation | [34 empty] | 0%
| P3FH - 28 M.14.14.3.1.1 Fire Fighting House | [35 empty] | 0%
| A25540 | AC, Ventilation Fan, Supply Fan, & others mechanical work | [34 empty] | 0%
0%
E2 | P3FH - 28 M. Piping Work |  |  |  | 51600905422.5 | 1.508% | [30 empty] | 1.508% | bar: 2017-02-15 to 2019-07-05
E4 | [36 empty] | 0%
|  | Transport material to site |  | 10% | 612435075 | 0.0179% | [30 empty] | 0.0179%
|  | Check elevation & orientation |  | 20% | 1224870150 | 0.0358% | [30 empty] | 0.0358%
|  | Pre-assembly on the ground |  | 10% | 612435075 | 0.0179% | [30 empty] | 0.0179%
|  | Installation |  | 40% | 2449740300 | 0.0716% | [30 empty] | 0.0716%
|  | Setting allignment |  | 10% | 612435075 | 0.0179% | [30 empty] | 0.0179%
|  | Final inspection |  | 10% | 612435075 | 0.0179% | [30 empty] | 0.0179%
| P3FH - 28 M.14.14.41.11.4.1 System 2 - Electric Smelting Furnace | [35 empty] | 0%
| P3FH - 28 M.14.14.41.11.4.1.11.4.1.1 Piping & Support (221099) | [35 empty] | 0%
| P3FH - 28 M.14.14.41.11.4.1.11.4.1.1.11.4.1.1.1 Furnace Water Circulation | [35 empty] | 0%
| A24680 | Install Main supply ring pipe header | [34 empty] | 0%
| A24700 | Install pipe Headers (6 set) | [34 empty] | 0%
| A24710 | Install return boshes (6 Set) | [34 empty] | 0%
| A24720 | Install Supply and Return lines area 1 | [34 empty] | 0%
| A24730 | Install Supply and Return lines area 2 | [34 empty] | 0%
| A24740 | Install Supply and Return lines area 3 | [34 empty] | 0%
| A24750 | Install Supply and Return lines area 4 | [34 empty] | 0%
| A24760 | Install pipe nozzles on cooler block | [34 empty] | 0%
| A24690 | Install Main return ring pipe header | [34 empty] | 0%
| A24770 | Install Flexible Joint | [34 empty] | 0%
| A24780 | Service test and Flushing Area 1 ( 5 set) | [34 empty] | 0%
| A24790 | Service test and Flushing Area 2 ( 5 set) | [34 empty] | 0%
| A24800 | Service test and Flushing Area 3 ( 5 set) | [34 empty] | 0%
| A24810 | Service test and Flushing Area 4 ( 5 set) | [34 empty] | 0%
E6 | A24820 | Reinstatemet of pipe spool | [34 empty] | 0%
|  | Transport material to site |  | 10% | 292189695 | 0.00854% | [30 empty] | 0.00854%
|  | Check elevation & orientation |  | 20% | 584721532.5 | 0.01709% | [30 empty] | 0.01709%
|  | Pre-assembly on the ground |  | 10% | 292189695 | 0.00854% | [30 empty] | 0.00854%
|  | Installation |  | 40% | 1169614136.25 | 0.03418% | [30 empty] | 0.03418%
|  | Setting allignment |  | 10% | 292189695 | 0.00854% | [30 empty] | 0.00854%
|  | Final inspection |  | 10% | 292189695 | 0.00854% | [30 empty] | 0.00854%
| P3FH - 28 M.14.14.41.11.4.1.11.4.1.1.11.4.1.1.2 Furnace Spry Body | [35 empty] | 0%
| A24830 | Install Main Spry header | [34 empty] | 0%
| A24840 | Install Spry Nozzles | [34 empty] | 0%
E6 | A24850 | Install Water Tray and screen | [34 empty] | 0%
|  | Transport material to site |  | 10% | 292189695 | 0.00854% | [30 empty] | 0.00854%
|  | Check elevation & orientation |  | 20% | 584721532.5 | 0.01709% | [30 empty] | 0.01709%
|  | Pre-assembly on the ground |  | 10% | 292189695 | 0.00854% | [30 empty] | 0.00854%
|  | Installation |  | 40% | 1169614136.25 | 0.03418% | [30 empty] | 0.03418%
|  | Setting allignment |  | 10% | 292189695 | 0.00854% | [30 empty] | 0.00854%
|  | Final inspection |  | 10% | 292189695 | 0.00854% | [30 empty] | 0.00854%
| P3FH - 28 M.14.14.41.11.4.1.11.4.1.1.11.4.1.1.3 Electrode Cooling | [35 empty] | 0%
| A24860 | Install Supply and Return lines area 1 | [34 empty] | 0%
| A24870 | Install Supply and Return lines area 2 | [34 empty] | 0%
| A24880 | Install Supply and Return lines area 3 | [34 empty] | 0%
| A24890 | Install Flexible hoses | [34 empty] | 0%
| A24900 | Service test and Flushing Area 1 ( 5 set) | [34 empty] | 0%
| A24910 | Service test and Flushing Area 2 ( 5 set) | [34 empty] | 0%
| A24920 | Service test and Flushing Area 3 ( 5 set) | [34 empty] | 0%
E6 | A24930 | Reinstatemet of pipe spool | [34 empty] | 0%
|  | Transport material to site |  | 10% | 292189695 | 0.00854% | [30 empty] | 0.00854%
|  | Check elevation & orientation |  | 20% | 584721532.5 | 0.01709% | [30 empty] | 0.01709%
|  | Pre-assembly on the ground |  | 10% | 292189695 | 0.00854% | [30 empty] | 0.00854%
|  | Installation |  | 40% | 1169614136.25 | 0.03418% | [30 empty] | 0.03418%
|  | Setting allignment |  | 10% | 292189695 | 0.00854% | [30 empty] | 0.00854%
|  | Final inspection |  | 10% | 292189695 | 0.00854% | [30 empty] | 0.00854%
| P3FH - 28 M.14.14.41.11.4.1.11.4.1.2 Baghouse Spray lances | [35 empty] | 0%
| A24940 | Install pipe racks (4 Set) | [34 empty] | 0%
| A24950 | Install Supply line from Tie-Point | [34 empty] | 0%
E6 | A24960 | Install Dischard line to spray lance ( 4 set) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 292189695 | 0.00854% | [30 empty] | 0.00854%
|  | Check elevation & orientation |  | 20% | 584721532.5 | 0.01709% | [30 empty] | 0.01709%
|  | Pre-assembly on the ground |  | 10% | 292189695 | 0.00854% | [30 empty] | 0.00854%
|  | Installation |  | 40% | 1169614136.25 | 0.03418% | [30 empty] | 0.03418%
|  | Setting allignment |  | 10% | 292189695 | 0.00854% | [30 empty] | 0.00854%
|  | Final inspection |  | 10% | 292189695 | 0.00854% | [30 empty] | 0.00854%
0%
E9 | P3FH - 28 M.14.14.41.14.4.2 System 3 - Refinery | [35 empty] | 0%
| A24970 | Pipe Spool Fabrication | [34 empty] | 0%
| A24980 | Pipe Spool & Fittings Installation | [34 empty] | 0%
| A24990 | Painting | [34 empty] | 0%
|  | Transport material to site |  | 10% | 94089187.5 | 0.00275% | [30 empty] | 0.00275%
|  | Check elevation & orientation |  | 20% | 188520517.5 | 0.00551% | [30 empty] | 0.00551%
|  | Pre-assembly on the ground |  | 10% | 94089187.5 | 0.00275% | [30 empty] | 0.00275%
|  | Installation |  | 40% | 377383177.5 | 0.01103% | [30 empty] | 0.01103%
|  | Setting allignment |  | 10% | 94089187.5 | 0.00275% | [30 empty] | 0.00275%
|  | Final inspection |  | 10% | 94089187.5 | 0.00275% | [30 empty] | 0.00275%
E11 | P3FH - 28 M.14.14.41.14.4.3 System 4 - Utility Supply | [35 empty] | 0%
| P3FH - 28 M.14.14.41.14.4.3.14.4.3.1 Raw Water Intake | [35 empty] | 0%
|  | Transport material to site |  | 10% | 1983742215 | 0.05798% | [30 empty] | 0.05798%
|  | Check elevation & orientation |  | 20% | 3967142287.5 | 0.1159% | [30 empty] | 0.1159%
|  | Pre-assembly on the ground |  | 10% | 1983742215 | 0.05798% | [30 empty] | 0.05798%
|  | Installation |  | 40% | 7933600290 | 0.2319% | [30 empty] | 0.2319%
|  | Setting allignment |  | 10% | 1983742215 | 0.05798% | [30 empty] | 0.05798%
|  | Final inspection |  | 10% | 1983742215 | 0.05798% | [30 empty] | 0.05798%
E79 | P3FH - 28 M.14.14.41.14.4.3.14.4.3.1.1 Pipe & Support (4107) River Water Intake Area | [35 empty] | 0%
| A24610 | Pipe Spool Fabrication | [34 empty] | 0%
| A25000 | Pipe Spool & Fittings Installation | [34 empty] | 0%
| A25020 | Flushing | [34 empty] | 0%
| A25010 | Painting | [34 empty] | 0%
|  | Transport material to site |  | 10% | 285688987.5 | 0.00835% | [30 empty] | 0.00835%
|  | Check elevation & orientation |  | 20% | 571035832.5 | 0.01669% | [30 empty] | 0.01669%
|  | Pre-assembly on the ground |  | 10% | 285688987.5 | 0.00835% | [30 empty] | 0.00835%
|  | Installation |  | 40% | 1141729522.5 | 0.03337% | [30 empty] | 0.03337%
|  | Setting allignment |  | 10% | 285688987.5 | 0.00835% | [30 empty] | 0.00835%
|  | Final inspection |  | 10% | 285688987.5 | 0.00835% | [30 empty] | 0.00835%
E80 | P3FH - 28 M.14.14.41.14.4.3.14.4.3.1.2 Piping (4108) Water Intake to Filtered Water Pond | [35 empty] | 0%
| A25030 | Stringing Pipe | [34 empty] | 0%
| A25040 | Pipe & Fittings Installation | [34 empty] | 0%
| A25060 | Flushing | [34 empty] | 0%
| A25050 | Painting | [34 empty] | 0%
|  | Transport material to site |  | 10% | 5132137.5 | 0.00015% | [30 empty] | 0.00015%
|  | Check elevation & orientation |  | 20% | 10606417.5 | 0.00031% | [30 empty] | 0.00031%
|  | Pre-assembly on the ground |  | 10% | 5132137.5 | 0.00015% | [30 empty] | 0.00015%
|  | Installation |  | 40% | 21212835 | 0.00062% | [30 empty] | 0.00062%
|  | Setting allignment |  | 10% | 5132137.5 | 0.00015% | [30 empty] | 0.00015%
|  | Final inspection |  | 10% | 5132137.5 | 0.00015% | [30 empty] | 0.00015%
E88 | P3FH - 28 M.14.14.41.14.4.3.14.4.3.1.3 Piping (4119) Water Filtered Pond to Circulation Water Pond | [35 empty] | 0%
| A25070 | Stringing Pipe | [34 empty] | 0%
| A25080 | Pipe & Fittings Installation | [34 empty] | 0%
| A25100 | Flushing | [34 empty] | 0%
| A25090 | Painting | [34 empty] | 0%
|  | Transport material to site |  | 10% | 3763567.5 | 0.00011% | [30 empty] | 0.00011%
|  | Check elevation & orientation |  | 20% | 7184992.5 | 0.00021% | [30 empty] | 0.00021%
|  | Pre-assembly on the ground |  | 10% | 3763567.5 | 0.00011% | [30 empty] | 0.00011%
|  | Installation |  | 40% | 13685700 | 0.0004% | [30 empty] | 0.0004%
|  | Setting allignment |  | 10% | 3763567.5 | 0.00011% | [30 empty] | 0.00011%
|  | Final inspection |  | 10% | 3763567.5 | 0.00011% | [30 empty] | 0.00011%
| P3FH - 28 M.14.14.41.14.4.3.14.4.3.2 Water Circulation System | [35 empty] | 0%
E96 | P3FH - 28 M.14.14.41.14.4.3.14.4.3.2.1 Piping and Support for NSW (4209) | [35 empty] | 0%
| A24620 | Pipe Spool Fabrication | [34 empty] | 0%
| A25110 | Pipe Spool & Fittings Installation | [34 empty] | 0%
| A25130 | Flushing | [34 empty] | 0%
| A25120 | Painting | [34 empty] | 0%
|  | Transport material to site |  | 10% | 9237847.5 | 0.00027% | [30 empty] | 0.00027%
|  | Check elevation & orientation |  | 20% | 18133552.5 | 0.00053% | [30 empty] | 0.00053%
|  | Pre-assembly on the ground |  | 10% | 9237847.5 | 0.00027% | [30 empty] | 0.00027%
|  | Installation |  | 40% | 36267105 | 0.00106% | [30 empty] | 0.00106%
|  | Setting allignment |  | 10% | 9237847.5 | 0.00027% | [30 empty] | 0.00027%
|  | Final inspection |  | 10% | 9237847.5 | 0.00027% | [30 empty] | 0.00027%
E105 | P3FH - 28 M.14.14.41.14.4.3.14.4.3.2.2 Piping and Support for SW (4219) | [35 empty] | 0%
| A25140 | Pipe Spool Fabrication | [34 empty] | 0%
| A25150 | Pipe Spool & Fittings Installation | [34 empty] | 0%
| A25170 | Flushing | [34 empty] | 0%
| A25160 | Painting | [34 empty] | 0%
|  | Transport material to site |  | 10% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
|  | Check elevation & orientation |  | 20% | 17107125 | 0.0005% | [30 empty] | 0.0005%
|  | Pre-assembly on the ground |  | 10% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
|  | Installation |  | 40% | 34214250 | 0.001% | [30 empty] | 0.001%
|  | Setting allignment |  | 10% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
|  | Final inspection |  | 10% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
E114 | P3FH - 28 M.14.14.41.14.4.3.14.4.3.2.3 Piping and Support for SW Copper Cooler (4229) | [35 empty] | 0%
| A25180 | Pipe Spool Fabrication | [34 empty] | 0%
| A25190 | Pipe Spool & Fittings Installation | [34 empty] | 0%
| A25210 | Flushing | [34 empty] | 0%
| A25200 | Painting | [34 empty] | 0%
|  | Transport material to site |  | 10% | 701392125 | 0.0205% | [30 empty] | 0.0205%
|  | Check elevation & orientation |  | 20% | 1402784250 | 0.041% | [30 empty] | 0.041%
|  | Pre-assembly on the ground |  | 10% | 701392125 | 0.0205% | [30 empty] | 0.0205%
|  | Installation |  | 40% | 2804884215 | 0.08198% | [30 empty] | 0.08198%
|  | Setting allignment |  | 10% | 701392125 | 0.0205% | [30 empty] | 0.0205%
|  | Final inspection |  | 10% | 701392125 | 0.0205% | [30 empty] | 0.0205%
E131 | P3FH - 28 M.14.14.41.14.4.3.14.4.3.3 Compressed Air and Distribution System | [35 empty] | 0%
| A24630 | Pipe Spool Fabrication | [34 empty] | 0%
| A25220 | Pipe Spool & Fittings Installation | [34 empty] | 0%
| A25240 | Flushing | [34 empty] | 0%
| A25230 | Insulation | [34 empty] | 0%
|  | Transport material to site |  | 10% | 121802730 | 0.00356% | [30 empty] | 0.00356%
|  | Check elevation & orientation |  | 20% | 243605460 | 0.00712% | [30 empty] | 0.00712%
|  | Pre-assembly on the ground |  | 10% | 121802730 | 0.00356% | [30 empty] | 0.00356%
|  | Installation |  | 40% | 487210920 | 0.01424% | [30 empty] | 0.01424%
|  | Setting allignment |  | 10% | 121802730 | 0.00356% | [30 empty] | 0.00356%
|  | Final inspection |  | 10% | 121802730 | 0.00356% | [30 empty] | 0.00356%
| P3FH - 28 M.14.14.41.14.4.3.14.4.3.4 Fuel Oil Pumping and Distribution | [35 empty] | 0%
E136 | P3FH - 28 M.14.14.41.14.4.3.14.4.3.4.1 Piping & Support for MFO Fuel (4319) | [35 empty] | 0%
| A25250 | Pipe Spool Fabrication | [34 empty] | 0%
| A25260 | Pipe Spool & Fittings Installation | [34 empty] | 0%
| A25280 | Flushing | [34 empty] | 0%
| A25270 | Insulation | [34 empty] | 0%
|  | Transport material to site |  | 10% | 82456342.5 | 0.00241% | [30 empty] | 0.00241%
|  | Check elevation & orientation |  | 20% | 164912685 | 0.00482% | [30 empty] | 0.00482%
|  | Pre-assembly on the ground |  | 10% | 82456342.5 | 0.00241% | [30 empty] | 0.00241%
|  | Installation |  | 40% | 329483227.5 | 0.00963% | [30 empty] | 0.00963%
|  | Setting allignment |  | 10% | 82456342.5 | 0.00241% | [30 empty] | 0.00241%
|  | Final inspection |  | 10% | 82456342.5 | 0.00241% | [30 empty] | 0.00241%
E139 | P3FH - 28 M.14.14.41.14.4.3.14.4.3.4.2 Piping & Support for HSD Fuel (4419) | [35 empty] | 0%
| A25290 | Pipe Spool Fabrication | [34 empty] | 0%
| A25300 | Pipe Spool & Fittings Installation | [34 empty] | 0%
| A25320 | Flushing | [34 empty] | 0%
| A25310 | Insulation | [34 empty] | 0%
| P3FH - 28 M.14.14.41.14.4.3.14.4.3.5 Sea Water Intake System | [35 empty] | 0%
| A24640 | Stringing pipe | [34 empty] | 0%
| A25330 | Pipe & Fittings Installation | [34 empty] | 0%
| A25350 | Flushing | [34 empty] | 0%
| A25340 | Painting | [34 empty] | 0%
| P3FH - 28 M.14.14.41.14.4.3.14.4.3.6 Steam Supply System | [35 empty] | 0%
| A24650 | Pipe Spool Fabrication | [34 empty] | 0%
| A25360 | Pipe Spool & Fittings Installation | [34 empty] | 0%
| A25380 | Flushing | [34 empty] | 0%
| A25370 | Insulation | [34 empty] | 0%
| P3FH - 28 M.14.14.41.14.4.3.14.4.3.7 O2 & N2 | [35 empty] | 0%
| P3FH - 28 M.14.14.41.14.4.3.14.4.3.7.1 Pipe & Support for O2 | [35 empty] | 0%
| A24660 | Pipe Spool Fabrication | [34 empty] | 0%
| A25390 | Pipe Spool & Fittings Installation | [34 empty] | 0%
| A25410 | Flushing | [34 empty] | 0%
| A25400 | Insulation | [34 empty] | 0%
| P3FH - 28 M.14.14.41.14.4.3.14.4.3.7.2 Pipe & Support for N2 | [35 empty] | 0%
| A24670 | Pipe Spool Fabrication | [34 empty] | 0%
| A25420 | Pipe Spool & Fittings Installation | [34 empty] | 0%
| A25440 | Flushing | [34 empty] | 0%
| A25430 | Insulation | [34 empty] | 0%
|  | Transport material to site |  | 10% | 83140627.5 | 0.00243% | [30 empty] | 0.00243%
|  | Check elevation & orientation |  | 20% | 165939112.5 | 0.00485% | [30 empty] | 0.00485%
|  | Pre-assembly on the ground |  | 10% | 83140627.5 | 0.00243% | [30 empty] | 0.00243%
|  | Installation |  | 40% | 331536082.5 | 0.00969% | [30 empty] | 0.00969%
|  | Setting allignment |  | 10% | 83140627.5 | 0.00243% | [30 empty] | 0.00243%
|  | Final inspection |  | 10% | 83140627.5 | 0.00243% | [30 empty] | 0.00243%
0%
| P3FH - 28 M. Electrical & Instrument Work |  |  |  | 46530011430 | 1.36% | [30 empty] | 1.36% | bar: 2017-02-15 to 2019-07-05
| P3FH - 28 M.14.1.1 System 1 - Ore Preparation | [35 empty] | 0%
| P3FH - 28 M.14.1.1.1 Raw Ore Storage Building | [35 empty] | 0%
| CONEI-1100-1020 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
E199 | CONEI-1100-1021 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
|  | Transport material to site |  | 10% | 134462002.5 | 0.00393% | [30 empty] | 0.00393%
|  | Check elevation & orientation |  | 20% | 269266147.5 | 0.00787% | [30 empty] | 0.00787%
|  | Pre-assembly on the ground |  | 10% | 134462002.5 | 0.00393% | [30 empty] | 0.00393%
|  | Installation |  | 40% | 538532295 | 0.01574% | [30 empty] | 0.01574%
|  | Setting allignment |  | 10% | 134462002.5 | 0.00393% | [30 empty] | 0.00393%
|  | Final inspection |  | 10% | 134462002.5 | 0.00393% | [30 empty] | 0.00393%
E201 | CONEI-1100-1000 | Earthing & Grounding | [34 empty] | 0%
|  | Transport material to site |  | 10% | 111538455 | 0.00326% | [30 empty] | 0.00326%
|  | Check elevation & orientation |  | 20% | 223076910 | 0.00652% | [30 empty] | 0.00652%
|  | Pre-assembly on the ground |  | 10% | 111538455 | 0.00326% | [30 empty] | 0.00326%
|  | Installation |  | 40% | 446153820 | 0.01304% | [30 empty] | 0.01304%
|  | Setting allignment |  | 10% | 111538455 | 0.00326% | [30 empty] | 0.00326%
|  | Final inspection |  | 10% | 111538455 | 0.00326% | [30 empty] | 0.00326%
E195 | CONEI-1100-1010 | Lighting System Installation | [34 empty] | 0%
|  | Transport material to site |  | 10% | 60901365 | 0.00178% | [30 empty] | 0.00178%
|  | Check elevation & orientation |  | 20% | 121802730 | 0.00356% | [30 empty] | 0.00356%
|  | Pre-assembly on the ground |  | 10% | 60901365 | 0.00178% | [30 empty] | 0.00178%
|  | Installation |  | 40% | 243605460 | 0.00712% | [30 empty] | 0.00712%
|  | Setting allignment |  | 10% | 60901365 | 0.00178% | [30 empty] | 0.00178%
|  | Final inspection |  | 10% | 60901365 | 0.00178% | [30 empty] | 0.00178%
E192 | CONEI-1100-1030 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
|  | Transport material to site |  | 10% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
|  | Check elevation & orientation |  | 20% | 17107125 | 0.0005% | [30 empty] | 0.0005%
|  | Pre-assembly on the ground |  | 10% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
|  | Installation |  | 40% | 33529965 | 0.00098% | [30 empty] | 0.00098%
|  | Setting allignment |  | 10% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
|  | Final inspection |  | 10% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
E196 | CONEI-1100-1022 | Power, Control & Instrument Cables Pulling & Laying | [34 empty] | 0%
|  | Transport material to site |  | 10% | 577878682.5 | 0.01689% | [30 empty] | 0.01689%
|  | Check elevation & orientation |  | 20% | 1155757365 | 0.03378% | [30 empty] | 0.03378%
|  | Pre-assembly on the ground |  | 10% | 577878682.5 | 0.01689% | [30 empty] | 0.01689%
|  | Installation |  | 40% | 2310830445 | 0.06754% | [30 empty] | 0.06754%
|  | Setting allignment |  | 10% | 577878682.5 | 0.01689% | [30 empty] | 0.01689%
|  | Final inspection |  | 10% | 577878682.5 | 0.01689% | [30 empty] | 0.01689%
| CONEI-1100-1009 | Lightning Protection | [34 empty] | 0%
| CONEI-1100-1060 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.1.2 Ore Drying Structure | [35 empty] | 0%
| CONEI-1200-1020 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-1200-1021 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-1200-1000 | Earthing & Grounding | [34 empty] | 0%
| CONEI-1200-1030 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-1200-1040 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-1200-1022 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-1200-1060 | Cable Termination | [34 empty] | 0%
| CONEI-1200-1010 | Lighting System Installation | [34 empty] | 0%
| CONEI-1200-1009 | Lightning Protection | [34 empty] | 0%
| P3FH - 28 M.14.1.1.3 Dryer EP Dust Bin Room | [35 empty] | 0%
| CONEI-1210-1020 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-1210-1030 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-1210-1000 | Earthing & Grounding | [34 empty] | 0%
| CONEI-1210-1010 | Lighting System Installation | [34 empty] | 0%
| CONEI-1210-1050 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-1210-1060 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-1210-1040 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-1210-1070 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.1.4 Conditioned Ore Storage Building | [35 empty] | 0%
| P3FH - 28 M.14.1.1.4.1 Conditioned Ore Storage | [35 empty] | 0%
| CONEI-1300-1080 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-1300-1081 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-1300-1000 | Lightning & Grounding | [34 empty] | 0%
| CONEI-1300-1070 | Lighting System Installation | [34 empty] | 0%
| CONEI-1300-1090 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-1300-1110 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-1300-1100 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-1300-1120 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.1.4.2 Transfer Conditoned Ore | [35 empty] | 0%
| CONEI-1300-1020 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-1300-1021 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-1300-1010 | Lighting System Installation | [34 empty] | 0%
| CONEI-1300-1030 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-1300-1040 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-1300-1050 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-1300-1009 | Lightning & Grounding | [34 empty] | 0%
| CONEI-1300-1060 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.1.5 Ore Mixing | [35 empty] | 0%
| CONEI-1400-1020 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-1400-1030 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-1400-1000 | Lightning & Grounding | [34 empty] | 0%
| CONEI-1400-1010 | Lighting System Installation | [34 empty] | 0%
| CONEI-1400-1040 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-1400-1060 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-1400-1050 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-1400-1070 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.1.10 Dust Treatment Building | [35 empty] | 0%
| CONEI-1500-1020 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-1500-1030 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-1500-1000 | Lightning & Grounding | [34 empty] | 0%
| CONEI-1500-1010 | Lighting System Installation | [34 empty] | 0%
| CONEI-1500-1040 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-1500-1060 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-1500-1050 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-1500-1070 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.1.6 Rotary Kiln Structure | [35 empty] | 0%
| CONEI-1600-1020 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-1600-1021 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-1600-1000 | Lightning & Grounding | [34 empty] | 0%
| CONEI-1600-1010 | Lighting System Installation | [34 empty] | 0%
| CONEI-1600-1030 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-1600-1050 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-1600-1040 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-1600-1060 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.1.11 Scoop Feeder Charge | [35 empty] | 0%
| CONEI-1610-1020 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-1610-1021 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-1610-1000 | Lightning & Grounding | [34 empty] | 0%
| CONEI-1610-1010 | Lighting System Installation | [34 empty] | 0%
| CONEI-1610-1030 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-1610-1040 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-1610-1050 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-1610-1060 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.1.7 Exhaust Gas Structure | [35 empty] | 0%
| CONEI-1700-1020 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-1700-1021 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-1700-1000 | Lightning & Grounding | [34 empty] | 0%
| CONEI-1700-1010 | Lighting System Installation | [34 empty] | 0%
| CONEI-1700-1030 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-1700-1040 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-1700-1050 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-1700-1060 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.1.9 Fuel Coal Storage & Reductant Coal Storage Building | [35 empty] | 0%
| CONEI-1820-1090 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-1820-1100 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-1820-1070 | Lightning & Grounding | [34 empty] | 0%
| CONEI-1820-1080 | Lighting System Installation | [34 empty] | 0%
| CONEI-1820-1110 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-1820-1120 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-1820-1130 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-1820-1140 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.1.8 Coal Firing Building | [35 empty] | 0%
| CONEI-1820-1020 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-1820-1021 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-1820-1000 | Lightning & Grounding | [34 empty] | 0%
| CONEI-1820-1010 | Lighting System Installation | [34 empty] | 0%
| CONEI-1820-1030 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-1820-1040 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-1820-1050 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-1820-1060 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.1.12 Electrical Room for Ore Dryer Area (LSS-11) | [35 empty] | 0%
| CONEI-LSS11-1020 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-LSS11-1021 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-LSS11-1000 | Earthing & Grounding | [34 empty] | 0%
| CONEI-LSS11-1050 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-LSS11-1009 | Lightning Protection | [34 empty] | 0%
| CONEI-LSS11-1022 | Lighting System Installation | [34 empty] | 0%
| CONEI-LSS11-1030 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
E191 | CONEI-LSS11-1070 | MV Switchgear 6.6kV Installation (MVP11) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 1331276467.5 | 0.03891% | [30 empty] | 0.03891%
|  | Check elevation & orientation |  | 20% | 2662552935 | 0.07782% | [30 empty] | 0.07782%
|  | Pre-assembly on the ground |  | 10% | 1331276467.5 | 0.03891% | [30 empty] | 0.03891%
|  | Installation |  | 40% | 5325790155 | 0.1557% | [30 empty] | 0.1557%
|  | Setting allignment |  | 10% | 1331276467.5 | 0.03891% | [30 empty] | 0.03891%
|  | Final inspection |  | 10% | 1331276467.5 | 0.03891% | [30 empty] | 0.03891%
| CONEI-LSS11-1120 | Transformer for RD 1600kVA Installation (TR 11) | [34 empty] | 0%
| CONEI-LSS11-1080 | Load Center Installation (LVP11) | [34 empty] | 0%
| CONEI-LSS11-1090 | Motor Control Center Installation (MCC11-1) | [34 empty] | 0%
| CONEI-LSS11-1130 | Transformer for Dryer EP 500kVA Installation (TR 12) | [34 empty] | 0%
| CONEI-LSS11-1100 | Motor Control Center Installation (MCC11-2) | [34 empty] | 0%
| CONEI-LSS11-1110 | Motor Control Center Installation (MCC11-3) | [34 empty] | 0%
| CONEI-LSS11-1140 | Other Panel (UPS 11, LCP, ITV, PCS 11, DCS) | [34 empty] | 0%
| CONEI-LSS11-1040 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-LSS11-1150 | Control Room (Display, Printer, Station) | [34 empty] | 0%
| CONEI-LSS11-1151 | Telecommunication System Installation | [34 empty] | 0%
| CONEI-LSS11-1152 | Paging System Installation | [34 empty] | 0%
| CONEI-LSS11-1153 | Siren System Installation | [34 empty] | 0%
| CONEI-LSS11-1154 | Fire Protection & Detection System Installation | [34 empty] | 0%
| CONEI-LSS11-1160 | Tie-in & Interconnection | [34 empty] | 0%
| P3FH - 28 M.14.1.1.13 Electrical Room for Mixing & Briquetting (LSS-12) | [35 empty] | 0%
| CONEI-LSS12-1020 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-LSS12-1021 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-LSS12-1000 | Lightning & Grounding | [34 empty] | 0%
| CONEI-LSS12-1022 | Lighting System Installation | [34 empty] | 0%
| CONEI-LSS12-1050 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-LSS12-1030 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-LSS12-1070 | MV Switchgear 6.6kV Installation (MVP12) | [34 empty] | 0%
| CONEI-LSS12-1120 | Transformer for Mixing & Briquetting 1000kVA (TR 13) | [34 empty] | 0%
| CONEI-LSS12-1080 | Load Center Installation (LVP12) | [34 empty] | 0%
| CONEI-LSS12-1090 | Motor Control Center Installation for Mixing (MCC12-1) | [34 empty] | 0%
| CONEI-LSS12-1130 | Other Panel for Mixing & Briquetting (UPS 12, LCP, ITV, PCS 12, DCS) | [34 empty] | 0%
| CONEI-LSS12-1100 | Motor Control Center Installation for Rod Mill (MCC12-2) | [34 empty] | 0%
| CONEI-LSS12-1110 | Motor Control Center Installation for Briquetting (MCC12-3) | [34 empty] | 0%
| CONEI-LSS12-1040 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-LSS12-1140 | Control Room (Display, Printer, Station) | [34 empty] | 0%
| CONEI-LSS12-1141 | Telecommunication System Installation | [34 empty] | 0%
| CONEI-LSS12-1142 | Paging System Installation | [34 empty] | 0%
| CONEI-LSS12-1143 | Siren System Installation | [34 empty] | 0%
| CONEI-LSS12-1144 | Fire Protection & Detection System Installation | [34 empty] | 0%
| CONEI-LSS12-1160 | Tie in & Interconnection | [34 empty] | 0%
| P3FH - 28 M.14.1.1.14 Electrical Room for Rotary Kiln (LSS-13) | [35 empty] | 0%
| CONEI-LSS13-1020 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-LSS13-1021 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-LSS13-1000 | Earthing & Grounding | [34 empty] | 0%
| CONEI-LSS13-1050 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-LSS13-1001 | Lightning Protection | [34 empty] | 0%
| CONEI-LSS13-1022 | Lighting System Installation | [34 empty] | 0%
| CONEI-LSS13-1030 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-LSS13-1070 | MV Switchgear 6.6kV Installation (MVP13) | [34 empty] | 0%
| CONEI-LSS13-1210 | Transformer for Rotary Kiln & EP 1600kVA (TR 14) | [34 empty] | 0%
| CONEI-LSS13-1160 | Load Center Installation (LVP13) | [34 empty] | 0%
| CONEI-LSS13-1180 | Motor Control Center Installation for Rotary Kiln (MCC13-1) | [34 empty] | 0%
| CONEI-LSS13-1190 | Motor Control Center Installation for Burner Combustion (MCC13-2) | [34 empty] | 0%
| CONEI-LSS13-1200 | Motor Control Center Installation for Dust Treatment (MCC13-3) | [34 empty] | 0%
| CONEI-LSS13-1220 | Other Panel for Rotary Kiln (UPS 13, Inverter Panel MVI-01/02, ITV, PCS 13, DCS) | [34 empty] | 0%
| CONEI-LSS13-1040 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-LSS13-1240 | Control Room (Display, Printer, Station) | [34 empty] | 0%
| CONEI-LSS13-1241 | Telecommunication System Installation | [34 empty] | 0%
| CONEI-LSS13-1242 | Paging System Installation | [34 empty] | 0%
| CONEI-LSS13-1243 | Siren System Installation | [34 empty] | 0%
| CONEI-LSS13-1244 | Fire Protection & Detection System Installation | [34 empty] | 0%
| CONEI-LSS13-1250 | Tie-in & Interconnection | [34 empty] | 0%
| P3FH - 28 M.14.1.1.15 Electrical Room for Coal Firing (LSS-14) | [35 empty] | 0%
| CONEI-LSS14-1020 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-LSS14-1021 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-LSS14-1000 | Earthing & Grounding | [34 empty] | 0%
| CONEI-LSS14-1050 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-LSS14-1001 | Lightning Protection | [34 empty] | 0%
| CONEI-LSS14-1022 | Lighting System Installation | [34 empty] | 0%
| CONEI-LSS14-1030 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-LSS14-1070 | MV Switchgear 6.6kV Installation (MVP14) | [34 empty] | 0%
| CONEI-LSS14-1100 | Transformer for Coal Firing 800kVA Installation (TR14) | [34 empty] | 0%
| CONEI-LSS14-1080 | Load Center Installation (LVP14) | [34 empty] | 0%
| CONEI-LSS14-1090 | Motor Control Center for Coal Firing (MCC14-1) | [34 empty] | 0%
| CONEI-LSS14-1110 | Other Panel for Coal firing (UPS 14, ITV, LCP, PCS 14, DCS) | [34 empty] | 0%
| CONEI-LSS14-1040 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-LSS14-1120 | Control Room (Display, Printer, Station) | [34 empty] | 0%
| CONEI-LSS14-1121 | Telecommunication System Installation | [34 empty] | 0%
| CONEI-LSS14-1122 | Paging System Installation | [34 empty] | 0%
| CONEI-LSS14-1123 | Siren System Installation | [34 empty] | 0%
| CONEI-LSS14-1140 | Siren System Installation | [34 empty] | 0%
| CONEI-LSS14-1130 | Tie-in & Interconnection | [34 empty] | 0%
| P3FH - 28 M.14.1.1.16 Surge Bin Equipment | [35 empty] | 0%
| CONEI-2100-1020 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-2100-1030 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-2100-1040 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-2100-1050 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-2100-1060 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-2100-1070 | Cable Termination | [34 empty] | 0%
E200 | [36 empty] | 0%
|  | Transport material to site |  | 10% | 110512027.5 | 0.00323% | [30 empty] | 0.00323%
|  | Check elevation & orientation |  | 20% | 220681912.5 | 0.00645% | [30 empty] | 0.00645%
|  | Pre-assembly on the ground |  | 10% | 110512027.5 | 0.00323% | [30 empty] | 0.00323%
|  | Installation |  | 40% | 441021682.5 | 0.01289% | [30 empty] | 0.01289%
|  | Setting allignment |  | 10% | 110512027.5 | 0.00323% | [30 empty] | 0.00323%
|  | Final inspection |  | 10% | 110512027.5 | 0.00323% | [30 empty] | 0.00323%
0%
E267 | [36 empty] | 0%
|  | Transport material to site |  | 10% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
|  | Check elevation & orientation |  | 20% | 1026427.5 | 3e-05% | [30 empty] | 3e-05%
|  | Pre-assembly on the ground |  | 10% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
|  | Installation |  | 40% | 2394997.5 | 7e-05% | [30 empty] | 7e-05%
|  | Setting allignment |  | 10% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
|  | Final inspection |  | 10% | 342142.5 | 1e-05% | [30 empty] | 1e-05%
0%
| P3FH - 28 M.14.1.11.5.1 System 2 - Electric Smelting Furnace-Rev.1 | [35 empty] | 0%
| P3FH - 28 M.14.1.11.5.1.9 ESF Building | [35 empty] | 0%
| A1750 | Install Cable Tray & Conduit | [34 empty] | 0%
E222 | A1370 | Lightning & Grounding | [34 empty] | 0%
|  | Transport material to site |  | 10% | 21212835 | 0.00062% | [30 empty] | 0.00062%
|  | Check elevation & orientation |  | 20% | 42083527.5 | 0.00123% | [30 empty] | 0.00123%
|  | Pre-assembly on the ground |  | 10% | 21212835 | 0.00062% | [30 empty] | 0.00062%
|  | Installation |  | 40% | 83482770 | 0.00244% | [30 empty] | 0.00244%
|  | Setting allignment |  | 10% | 21212835 | 0.00062% | [30 empty] | 0.00062%
|  | Final inspection |  | 10% | 21212835 | 0.00062% | [30 empty] | 0.00062%
| A1850 | Lighting Installation | [34 empty] | 0%
| A1380 | Lighting Panel & Local Panel Installation | [34 empty] | 0%
| A1390 | Instrument Device Equipment | [34 empty] | 0%
| A1400 | Power, Control & Instrument Cables | [34 empty] | 0%
| A1410 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.11.5.1.1 Trafo Room | [35 empty] | 0%
| A1760 | Furnace Transformer (include Test) | [34 empty] | 0%
| P3FH - 28 M.14.1.11.5.1.2 Electrode System | [35 empty] | 0%
| A1770 | Electrical Work for Electrode System | [34 empty] | 0%
| P3FH - 28 M.14.1.11.5.1.3 Hot Charge System | [35 empty] | 0%
| A1790 | Electrical Work for TX car | [34 empty] | 0%
| A1800 | Electrical Work for HCC | [34 empty] | 0%
| P3FH - 28 M.14.1.11.5.1.4 Furnace Charging System | [35 empty] | 0%
| A1810 | Electrical Work for Cover Bin | [34 empty] | 0%
| P3FH - 28 M.14.1.11.5.1.5 Tapping System | [35 empty] | 0%
| A1840 | Clay gun | [34 empty] | 0%
| P3FH - 28 M.14.1.11.5.1.6 Ladle Preheating | [35 empty] | 0%
| A1830 | Laddle preheating | [34 empty] | 0%
| P3FH - 28 M.14.1.11.5.1.7 Electric Room for ESF (LSS-21) | [35 empty] | 0%
E214 | A1420 | Lighting System Installation | [34 empty] | 0%
|  | Transport material to site |  | 10% | 13343557.5 | 0.00039% | [30 empty] | 0.00039%
|  | Check elevation & orientation |  | 20% | 27029257.5 | 0.00079% | [30 empty] | 0.00079%
|  | Pre-assembly on the ground |  | 10% | 13343557.5 | 0.00039% | [30 empty] | 0.00039%
|  | Installation |  | 40% | 54400657.5 | 0.00159% | [30 empty] | 0.00159%
|  | Setting allignment |  | 10% | 13343557.5 | 0.00039% | [30 empty] | 0.00039%
|  | Final inspection |  | 10% | 13343557.5 | 0.00039% | [30 empty] | 0.00039%
| A1660 | Motor Control Center for Electric Furnace-1 (MCC21-1) | [34 empty] | 0%
| A1670 | Motor Control Center for Electric Furnace-2 (MCC21-2) | [34 empty] | 0%
E220 | A1430 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
|  | Transport material to site |  | 10% | 98194897.5 | 0.00287% | [30 empty] | 0.00287%
|  | Check elevation & orientation |  | 20% | 196389795 | 0.00574% | [30 empty] | 0.00574%
|  | Pre-assembly on the ground |  | 10% | 98194897.5 | 0.00287% | [30 empty] | 0.00287%
|  | Installation |  | 40% | 392437447.5 | 0.01147% | [30 empty] | 0.01147%
|  | Setting allignment |  | 10% | 98194897.5 | 0.00287% | [30 empty] | 0.00287%
|  | Final inspection |  | 10% | 98194897.5 | 0.00287% | [30 empty] | 0.00287%
E207 | A1620 | MV Switchgear 6.6kV Installation (MVP21) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 32503537.5 | 0.00095% | [30 empty] | 0.00095%
|  | Check elevation & orientation |  | 20% | 65007075 | 0.0019% | [30 empty] | 0.0019%
|  | Pre-assembly on the ground |  | 10% | 32503537.5 | 0.00095% | [30 empty] | 0.00095%
|  | Installation |  | 40% | 130014150 | 0.0038% | [30 empty] | 0.0038%
|  | Setting allignment |  | 10% | 32503537.5 | 0.00095% | [30 empty] | 0.00095%
|  | Final inspection |  | 10% | 32503537.5 | 0.00095% | [30 empty] | 0.00095%
| A1640 | Load Center (LVP21) | [34 empty] | 0%
| A1690 | Transformer for ESF 1250 kVA Installation (TR 21) | [34 empty] | 0%
E270 | A1450 | Instrument Device Equipment | [34 empty] | 0%
|  | Transport material to site |  | 10% | 75271350 | 0.0022% | [30 empty] | 0.0022%
|  | Check elevation & orientation |  | 20% | 150542700 | 0.0044% | [30 empty] | 0.0044%
|  | Pre-assembly on the ground |  | 10% | 75271350 | 0.0022% | [30 empty] | 0.0022%
|  | Installation |  | 40% | 301085400 | 0.0088% | [30 empty] | 0.0088%
|  | Setting allignment |  | 10% | 75271350 | 0.0022% | [30 empty] | 0.0022%
|  | Final inspection |  | 10% | 75271350 | 0.0022% | [30 empty] | 0.0022%
TANDA TANYA | A1460 | Power, Control & Instrument Cables | [34 empty] | 0%
|  | Transport material to site |  | 10% | 249079740 | 0.00728% | [30 empty] | 0.00728%
|  | Check elevation & orientation |  | 20% | 497817337.5 | 0.01455% | [30 empty] | 0.01455%
|  | Pre-assembly on the ground |  | 10% | 249079740 | 0.00728% | [30 empty] | 0.00728%
|  | Installation |  | 40% | 995634675 | 0.0291% | [30 empty] | 0.0291%
|  | Setting allignment |  | 10% | 249079740 | 0.00728% | [30 empty] | 0.00728%
|  | Final inspection |  | 10% | 249079740 | 0.00728% | [30 empty] | 0.00728%
| A1710 | DC Battery & Charger for MVP201 Installation (DC21) | [34 empty] | 0%
E281 | A1440 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
|  | Transport material to site |  | 10% | 4447852.5 | 0.00013% | [30 empty] | 0.00013%
|  | Check elevation & orientation |  | 20% | 9237847.5 | 0.00027% | [30 empty] | 0.00027%
|  | Pre-assembly on the ground |  | 10% | 4447852.5 | 0.00013% | [30 empty] | 0.00013%
|  | Installation |  | 40% | 18817837.5 | 0.00055% | [30 empty] | 0.00055%
|  | Setting allignment |  | 10% | 4447852.5 | 0.00013% | [30 empty] | 0.00013%
|  | Final inspection |  | 10% | 4447852.5 | 0.00013% | [30 empty] | 0.00013%
E215 | A1720 | Uninterupted Power Supply for ESF (UPS 21) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 4447852.5 | 0.00013% | [30 empty] | 0.00013%
|  | Check elevation & orientation |  | 20% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
|  | Pre-assembly on the ground |  | 10% | 4447852.5 | 0.00013% | [30 empty] | 0.00013%
|  | Installation |  | 40% | 16422840 | 0.00048% | [30 empty] | 0.00048%
|  | Setting allignment |  | 10% | 4447852.5 | 0.00013% | [30 empty] | 0.00013%
|  | Final inspection |  | 10% | 4447852.5 | 0.00013% | [30 empty] | 0.00013%
| A1470 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.11.5.1.8 HPU Electrode Room | [35 empty] | 0%
| A1780 | HPU Electrode | [34 empty] | 0%
| P3FH - 28 M.14.1.11.5.1.11.6.1 Electric Smelting Furnace Instrument | [35 empty] | 0%
| A1860 | Central control room | [34 empty] | 0%
| A1880 | Furnace vesel | [34 empty] | 0%
| A1870 | PLC Panels | [34 empty] | 0%
| A1890 | Electrodes | [34 empty] | 0%
| A1900 | TX car, HCC and Top Bins | [34 empty] | 0%
| A1920 | Laddle preheating | [34 empty] | 0%
E221 | A1930 | Clay Gun | [34 empty] | 0%
0%
|  | Transport material to site |  | 10% | 49610662.5 | 0.00145% | [30 empty] | 0.00145%
|  | Check elevation & orientation |  | 20% | 98879182.5 | 0.00289% | [30 empty] | 0.00289%
|  | Pre-assembly on the ground |  | 10% | 49610662.5 | 0.00145% | [30 empty] | 0.00145%
|  | Installation |  | 40% | 197074080 | 0.00576% | [30 empty] | 0.00576%
|  | Setting allignment |  | 10% | 49610662.5 | 0.00145% | [30 empty] | 0.00145%
|  | Final inspection |  | 10% | 49610662.5 | 0.00145% | [30 empty] | 0.00145%
0%
E273 | [36 empty] | 0%
|  | Transport material to site |  | 10% | 241552605 | 0.00706% | [30 empty] | 0.00706%
|  | Check elevation & orientation |  | 20% | 483447352.5 | 0.01413% | [30 empty] | 0.01413%
|  | Pre-assembly on the ground |  | 10% | 241552605 | 0.00706% | [30 empty] | 0.00706%
|  | Installation |  | 40% | 967236847.5 | 0.02827% | [30 empty] | 0.02827%
|  | Setting allignment |  | 10% | 241552605 | 0.00706% | [30 empty] | 0.00706%
|  | Final inspection |  | 10% | 241552605 | 0.00706% | [30 empty] | 0.00706%
0%
| P3FH - 28 M.14.1.7 System 3 - Refinery-Rev.1 | [35 empty] | 0%
| P3FH - 28 M.14.1.7.3 Deshulpurizing Equipment | [35 empty] | 0%
| A1960 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| A1950 | Lighting System Installation | [34 empty] | 0%
| A1990 | Power, Control & Instrument Cables | [34 empty] | 0%
| A1970 | Lighting Panel & Local Panel Installation | [34 empty] | 0%
| A1980 | Instrument Device Equipment | [34 empty] | 0%
| A1940 | Lightning & Grounding | [34 empty] | 0%
| A2000 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.7.4 Shotmaking Equipment | [35 empty] | 0%
| A2030 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| A2020 | Lighting System Installation | [34 empty] | 0%
| A2060 | Power, Control & Instrument Cables | [34 empty] | 0%
| A2040 | Lighting Panel & Local Panel Installation | [34 empty] | 0%
| A2050 | Instrument Device Equipment | [34 empty] | 0%
| A2010 | Lightning & Grounding | [34 empty] | 0%
| A2070 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.7.1 Product Storage Building | [35 empty] | 0%
| A1500 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| A1490 | Lighting System Installation | [34 empty] | 0%
| A1530 | Power, Control & Instrument Cables | [34 empty] | 0%
| A1510 | Lighting Panel & Local Panel Installation | [34 empty] | 0%
| A1520 | Instrument Device Equipment | [34 empty] | 0%
| A1480 | Lightning & Grounding | [34 empty] | 0%
| A1540 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.7.5 Water Circulation System | [35 empty] | 0%
| A25670 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| A25660 | Lighting System Installation | [34 empty] | 0%
| A25700 | Power, Control & Instrument Cables | [34 empty] | 0%
| A25680 | Lighting Panel & Local Panel Installation | [34 empty] | 0%
| A25690 | Instrument Device Equipment | [34 empty] | 0%
| A25650 | Lightning & Grounding | [34 empty] | 0%
| A25710 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.7.2 Electrical Room for Shot Making at GF ESF Building (LSS-31) | [35 empty] | 0%
E239 | A1570 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
|  | Transport material to site |  | 10% | 49610662.5 | 0.00145% | [30 empty] | 0.00145%
|  | Check elevation & orientation |  | 20% | 99563467.5 | 0.00291% | [30 empty] | 0.00291%
|  | Pre-assembly on the ground |  | 10% | 49610662.5 | 0.00145% | [30 empty] | 0.00145%
|  | Installation |  | 40% | 199126935 | 0.00582% | [30 empty] | 0.00582%
|  | Setting allignment |  | 10% | 49610662.5 | 0.00145% | [30 empty] | 0.00145%
|  | Final inspection |  | 10% | 49610662.5 | 0.00145% | [30 empty] | 0.00145%
E233 | A1560 | Lighting System Installation | [34 empty] | 0%
|  | Transport material to site |  | 10% | 2052855 | 6e-05% | [30 empty] | 6e-05%
|  | Check elevation & orientation |  | 20% | 3763567.5 | 0.00011% | [30 empty] | 0.00011%
|  | Pre-assembly on the ground |  | 10% | 2052855 | 6e-05% | [30 empty] | 6e-05%
|  | Installation |  | 40% | 6842850 | 0.0002% | [30 empty] | 0.0002%
|  | Setting allignment |  | 10% | 2052855 | 6e-05% | [30 empty] | 6e-05%
|  | Final inspection |  | 10% | 2052855 | 6e-05% | [30 empty] | 6e-05%
TANDA TANYA | A1600 | Power, Control & Instrument Cables | [34 empty] | 0%
|  | Transport material to site |  | 10% | 40714957.5 | 0.00119% | [30 empty] | 0.00119%
|  | Check elevation & orientation |  | 20% | 81429915 | 0.00238% | [30 empty] | 0.00238%
|  | Pre-assembly on the ground |  | 10% | 40714957.5 | 0.00119% | [30 empty] | 0.00119%
|  | Installation |  | 40% | 162859830 | 0.00476% | [30 empty] | 0.00476%
|  | Setting allignment |  | 10% | 40714957.5 | 0.00119% | [30 empty] | 0.00119%
|  | Final inspection |  | 10% | 40714957.5 | 0.00119% | [30 empty] | 0.00119%
E227 | A1630 | MV Switchgear 6.6kV Installation (MVP31) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 24292117.5 | 0.00071% | [30 empty] | 0.00071%
|  | Check elevation & orientation |  | 20% | 48584235 | 0.00142% | [30 empty] | 0.00142%
|  | Pre-assembly on the ground |  | 10% | 24292117.5 | 0.00071% | [30 empty] | 0.00071%
|  | Installation |  | 40% | 97852755 | 0.00286% | [30 empty] | 0.00286%
|  | Setting allignment |  | 10% | 24292117.5 | 0.00071% | [30 empty] | 0.00071%
|  | Final inspection |  | 10% | 24292117.5 | 0.00071% | [30 empty] | 0.00071%
E230 | A1580 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
|  | Transport material to site |  | 10% | 2394997.5 | 7e-05% | [30 empty] | 7e-05%
|  | Check elevation & orientation |  | 20% | 4789995 | 0.00014% | [30 empty] | 0.00014%
|  | Pre-assembly on the ground |  | 10% | 2394997.5 | 7e-05% | [30 empty] | 7e-05%
|  | Installation |  | 40% | 10264275 | 0.0003% | [30 empty] | 0.0003%
|  | Setting allignment |  | 10% | 2394997.5 | 7e-05% | [30 empty] | 7e-05%
|  | Final inspection |  | 10% | 2394997.5 | 7e-05% | [30 empty] | 7e-05%
| A1650 | Load Center (LVP31) | [34 empty] | 0%
E278 | A1590 | Instrument Device Equipment | [34 empty] | 0%
|  | Transport material to site |  | 10% | 10606417.5 | 0.00031% | [30 empty] | 0.00031%
|  | Check elevation & orientation |  | 20% | 21212835 | 0.00062% | [30 empty] | 0.00062%
|  | Pre-assembly on the ground |  | 10% | 10606417.5 | 0.00031% | [30 empty] | 0.00031%
|  | Installation |  | 40% | 41741385 | 0.00122% | [30 empty] | 0.00122%
|  | Setting allignment |  | 10% | 10606417.5 | 0.00031% | [30 empty] | 0.00031%
|  | Final inspection |  | 10% | 10606417.5 | 0.00031% | [30 empty] | 0.00031%
| A1680 | Motor Control Center for Refining (MCC31) | [34 empty] | 0%
| A1700 | Transformer for Refining 1250kVA Installation (TR 31) | [34 empty] | 0%
E234 | A1730 | Uninterupted Power Supply for Refining (UPS 31) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 3079282.5 | 9e-05% | [30 empty] | 9e-05%
|  | Check elevation & orientation |  | 20% | 6158565 | 0.00018% | [30 empty] | 0.00018%
|  | Pre-assembly on the ground |  | 10% | 3079282.5 | 9e-05% | [30 empty] | 9e-05%
|  | Installation |  | 40% | 13001415 | 0.00038% | [30 empty] | 0.00038%
|  | Setting allignment |  | 10% | 3079282.5 | 9e-05% | [30 empty] | 9e-05%
|  | Final inspection |  | 10% | 3079282.5 | 9e-05% | [30 empty] | 9e-05%
| A1740 | Process Control System Inst'l (PCS 31) | [34 empty] | 0%
E241 | A1550 | Lightning & Grounding | [34 empty] | 0%
|  | Transport material to site |  | 10% | 15738555 | 0.00046% | [30 empty] | 0.00046%
|  | Check elevation & orientation |  | 20% | 31477110 | 0.00092% | [30 empty] | 0.00092%
|  | Pre-assembly on the ground |  | 10% | 15738555 | 0.00046% | [30 empty] | 0.00046%
|  | Installation |  | 40% | 62612077.5 | 0.00183% | [30 empty] | 0.00183%
|  | Setting allignment |  | 10% | 15738555 | 0.00046% | [30 empty] | 0.00046%
|  | Final inspection |  | 10% | 15738555 | 0.00046% | [30 empty] | 0.00046%
| A1610 | Cable Termination | [34 empty] | 0%
E240 | [36 empty] | 0%
|  | Transport material to site |  | 10% | 32503537.5 | 0.00095% | [30 empty] | 0.00095%
|  | Check elevation & orientation |  | 20% | 65007075 | 0.0019% | [30 empty] | 0.0019%
|  | Pre-assembly on the ground |  | 10% | 32503537.5 | 0.00095% | [30 empty] | 0.00095%
|  | Installation |  | 40% | 129329865 | 0.00378% | [30 empty] | 0.00378%
|  | Setting allignment |  | 10% | 32503537.5 | 0.00095% | [30 empty] | 0.00095%
|  | Final inspection |  | 10% | 32503537.5 | 0.00095% | [30 empty] | 0.00095%
0%
TANDA TANYA | [36 empty] | 0%
|  | Transport material to site |  | 10% | 49952805 | 0.00146% | [30 empty] | 0.00146%
|  | Check elevation & orientation |  | 20% | 99905610 | 0.00292% | [30 empty] | 0.00292%
|  | Pre-assembly on the ground |  | 10% | 49952805 | 0.00146% | [30 empty] | 0.00146%
|  | Installation |  | 40% | 199126935 | 0.00582% | [30 empty] | 0.00582%
|  | Setting allignment |  | 10% | 49952805 | 0.00146% | [30 empty] | 0.00146%
|  | Final inspection |  | 10% | 49952805 | 0.00146% | [30 empty] | 0.00146%
0%
| P3FH - 28 M.14.1.2 System 4 - Utility Supply-Rev.1 | [35 empty] | 0%
| P3FH - 28 M.14.1.2.7 Main Substation | [35 empty] | 0%
E258 | CONEI-MAIN-1007 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
|  | Transport material to site |  | 10% | 147121275 | 0.0043% | [30 empty] | 0.0043%
|  | Check elevation & orientation |  | 20% | 293900407.5 | 0.00859% | [30 empty] | 0.00859%
|  | Pre-assembly on the ground |  | 10% | 147121275 | 0.0043% | [30 empty] | 0.0043%
|  | Installation |  | 40% | 587116530 | 0.01716% | [30 empty] | 0.01716%
|  | Setting allignment |  | 10% | 147121275 | 0.0043% | [30 empty] | 0.0043%
|  | Final inspection |  | 10% | 147121275 | 0.0043% | [30 empty] | 0.0043%
E260 | CONEI-MAIN-1125 | Lightning & Grounding | [34 empty] | 0%
|  | Transport material to site |  | 10% | 193652655 | 0.00566% | [30 empty] | 0.00566%
|  | Check elevation & orientation |  | 20% | 387305310 | 0.01132% | [30 empty] | 0.01132%
|  | Pre-assembly on the ground |  | 10% | 193652655 | 0.00566% | [30 empty] | 0.00566%
|  | Installation |  | 40% | 774610620 | 0.02264% | [30 empty] | 0.02264%
|  | Setting allignment |  | 10% | 193652655 | 0.00566% | [30 empty] | 0.00566%
|  | Final inspection |  | 10% | 193652655 | 0.00566% | [30 empty] | 0.00566%
| CONEI-MAIN-1008 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
TANDA TANYA | CONEI-MAIN-1009 | Power, Control & Instrument Cables Pulling & Laying | [34 empty] | 0%
|  | Transport material to site |  | 10% | 234025470 | 0.00684% | [30 empty] | 0.00684%
|  | Check elevation & orientation |  | 20% | 468050940 | 0.01368% | [30 empty] | 0.01368%
|  | Pre-assembly on the ground |  | 10% | 234025470 | 0.00684% | [30 empty] | 0.00684%
|  | Installation |  | 40% | 935759737.5 | 0.02735% | [30 empty] | 0.02735%
|  | Setting allignment |  | 10% | 234025470 | 0.00684% | [30 empty] | 0.00684%
|  | Final inspection |  | 10% | 234025470 | 0.00684% | [30 empty] | 0.00684%
E245 | CONEI-MAIN-1010 | Lighting System Installation | [34 empty] | 0%
|  | Transport material to site |  | 10% | 92378475 | 0.0027% | [30 empty] | 0.0027%
|  | Check elevation & orientation |  | 20% | 185099092.5 | 0.00541% | [30 empty] | 0.00541%
|  | Pre-assembly on the ground |  | 10% | 92378475 | 0.0027% | [30 empty] | 0.0027%
|  | Installation |  | 40% | 370540327.5 | 0.01083% | [30 empty] | 0.01083%
|  | Setting allignment |  | 10% | 92378475 | 0.0027% | [30 empty] | 0.0027%
|  | Final inspection |  | 10% | 92378475 | 0.0027% | [30 empty] | 0.0027%
| CONEI-MAIN-1070 | MV Switchgear Installation 30kV Installation (MVP401) | [34 empty] | 0%
TANDA TANYA | CONEI-MAIN-1080 | MV Switchgear Installation 6.6kV Installation (MVP41) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 114617737.5 | 0.00335% | [30 empty] | 0.00335%
|  | Check elevation & orientation |  | 20% | 228893332.5 | 0.00669% | [30 empty] | 0.00669%
|  | Pre-assembly on the ground |  | 10% | 114617737.5 | 0.00335% | [30 empty] | 0.00335%
|  | Installation |  | 40% | 457102380 | 0.01336% | [30 empty] | 0.01336%
|  | Setting allignment |  | 10% | 114617737.5 | 0.00335% | [30 empty] | 0.00335%
|  | Final inspection |  | 10% | 114617737.5 | 0.00335% | [30 empty] | 0.00335%
| CONEI-MAIN-1090 | Neutral Grounding Resistor Installation (NGR41) | [34 empty] | 0%
| CONEI-MAIN-1100 | Load Center Installation (LVP41) | [34 empty] | 0%
| CONEI-MAIN-1126 | Cable Termination | [34 empty] | 0%
| CONEI-MAIN-1110 | Power Transformer 30/6.6 kV 17500 kVA (TR MV401) | [34 empty] | 0%
| CONEI-MAIN-1120 | Power Transformer 30/4.6 kV 100 kVA (TR 41) | [34 empty] | 0%
TANDA TANYA | CONEI-MAIN-1030 | Lighting Panel & Local Panel Installation | [34 empty] | 0%
|  | Transport material to site |  | 10% | 28739970 | 0.00084% | [30 empty] | 0.00084%
|  | Check elevation & orientation |  | 20% | 57479940 | 0.00168% | [30 empty] | 0.00168%
|  | Pre-assembly on the ground |  | 10% | 28739970 | 0.00084% | [30 empty] | 0.00084%
|  | Installation |  | 40% | 114617737.5 | 0.00335% | [30 empty] | 0.00335%
|  | Setting allignment |  | 10% | 28739970 | 0.00084% | [30 empty] | 0.00084%
|  | Final inspection |  | 10% | 28739970 | 0.00084% | [30 empty] | 0.00084%
E253 | CONEI-MAIN-1121 | DC Battery and Charger for MVP401 Installation (DC41) | [34 empty] | 0%
|  | Transport material to site |  | 10% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
|  | Check elevation & orientation |  | 20% | 17107125 | 0.0005% | [30 empty] | 0.0005%
|  | Pre-assembly on the ground |  | 10% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
|  | Installation |  | 40% | 33529965 | 0.00098% | [30 empty] | 0.00098%
|  | Setting allignment |  | 10% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
|  | Final inspection |  | 10% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
TANDA TANYA | CONEI-MAIN-1040 | Instrument Device Equipment | [34 empty] | 0%
|  | Transport material to site |  | 10% | 17107125 | 0.0005% | [30 empty] | 0.0005%
|  | Check elevation & orientation |  | 20% | 34214250 | 0.001% | [30 empty] | 0.001%
|  | Pre-assembly on the ground |  | 10% | 17107125 | 0.0005% | [30 empty] | 0.0005%
|  | Installation |  | 40% | 68086357.5 | 0.00199% | [30 empty] | 0.00199%
|  | Setting allignment |  | 10% | 17107125 | 0.0005% | [30 empty] | 0.0005%
|  | Final inspection |  | 10% | 17107125 | 0.0005% | [30 empty] | 0.0005%
| P3FH - 28 M.14.1.2.16 Central Control Room (CCR) | [35 empty] | 0%
| CONEI-CCR-1001 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-CCR-1008 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-CCR-1010 | Lighting System Installation | [34 empty] | 0%
E299 | CONEI-CCR-1090 | Telecommunication System Installation | [34 empty] | 0%
|  | Transport material to site |  | 10% | 4447852.5 | 0.00013% | [30 empty] | 0.00013%
|  | Check elevation & orientation |  | 20% | 8553562.5 | 0.00025% | [30 empty] | 0.00025%
|  | Pre-assembly on the ground |  | 10% | 4447852.5 | 0.00013% | [30 empty] | 0.00013%
|  | Installation |  | 40% | 16764982.5 | 0.00049% | [30 empty] | 0.00049%
|  | Setting allignment |  | 10% | 4447852.5 | 0.00013% | [30 empty] | 0.00013%
|  | Final inspection |  | 10% | 4447852.5 | 0.00013% | [30 empty] | 0.00013%
| CONEI-CCR-1100 | Siren System Installation | [34 empty] | 0%
E294 | CONEI-CCR-1110 | ITV Sytem Installation | [34 empty] | 0%
|  | Transport material to site |  | 10% | 28055685 | 0.00082% | [30 empty] | 0.00082%
|  | Check elevation & orientation |  | 20% | 55769227.5 | 0.00163% | [30 empty] | 0.00163%
|  | Pre-assembly on the ground |  | 10% | 28055685 | 0.00082% | [30 empty] | 0.00082%
|  | Installation |  | 40% | 111196312.5 | 0.00325% | [30 empty] | 0.00325%
|  | Setting allignment |  | 10% | 28055685 | 0.00082% | [30 empty] | 0.00082%
|  | Final inspection |  | 10% | 28055685 | 0.00082% | [30 empty] | 0.00082%
| CONEI-CCR-1030 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-CCR-1040 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-CCR-1009 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-CCR-1070 | Uninterupted Power Supply for CCR system-1 (UPS 10) | [34 empty] | 0%
| CONEI-CCR-1080 | Uninterupted Power Supply for CCR ESF&Utility (UPS 22) | [34 empty] | 0%
| CONEI-CCR-1120 | Process Control System Ins'l (PCS 10) | [34 empty] | 0%
| CONEI-CCR-1126 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.2.11 Emergency Generator Room | [35 empty] | 0%
| CONEI-EDG-1001 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-EDG-1008 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-EDG-1041 | Lightning & Grounding | [34 empty] | 0%
| CONEI-EDG-1010 | Lighting System Installation | [34 empty] | 0%
| CONEI-EDG-1009 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-EDG-1030 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-EDG-1040 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-EDG-1060 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.2.11.8 Install EDG41 | [35 empty] | 0%
| A25480 | EDG Installation (EDG 41) | [34 empty] | 0%
| A25490 | Emergency Power Distribution Panel Installation (DPE 41) | [34 empty] | 0%
| P3FH - 28 M.14.1.2.6 Utility (LSS-42) | [35 empty] | 0%
| CONEI-LSS42-1001 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-LSS42-1008 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-LSS42-1151 | Lightning & Grounding | [34 empty] | 0%
| CONEI-LSS42-1010 | Lighting System Installation | [34 empty] | 0%
| CONEI-LSS42-1009 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-LSS42-1070 | MV Switchgear 6.6kV Installation (MVP42) | [34 empty] | 0%
| CONEI-LSS42-1080 | Load Center (LVP42) | [34 empty] | 0%
| CONEI-LSS42-1090 | Load Center (LVP43) | [34 empty] | 0%
| CONEI-LSS42-1100 | Motor Control Center for Utility (Water, Oil) - (MCC42) | [34 empty] | 0%
| CONEI-LSS42-1110 | Transformer for Utility-1 1600kVA (TR 42) | [34 empty] | 0%
| CONEI-LSS42-1150 | Process Control System Inst'l (PCS 42) | [34 empty] | 0%
| CONEI-LSS42-1120 | Transformer for Utility-2 1000kVA (TR 43) | [34 empty] | 0%
| CONEI-LSS42-1030 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-LSS42-1130 | Transformer for Oxygen Plant 400kVA (TR 44) | [34 empty] | 0%
| CONEI-LSS42-1040 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-LSS42-1140 | Uninterupted Power Supply for Utility (UPS 42) | [34 empty] | 0%
| CONEI-LSS42-1152 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.2.3 Oxygen Plant (LSS-43) | [35 empty] | 0%
| CONEI-LSS43-1001 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-LSS43-1008 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-LSS43-1091 | Lightning & Grounding | [34 empty] | 0%
| CONEI-LSS43-1010 | Lighting System Installation | [34 empty] | 0%
| CONEI-LSS43-1009 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-LSS43-1070 | Motor Control Center for Oxygen Plant (MCC43) | [34 empty] | 0%
| CONEI-LSS43-1080 | Uninterupted Power Supply for Oxygen Plant (UPS 43) | [34 empty] | 0%
| CONEI-LSS43-1030 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-LSS43-1040 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-LSS43-1090 | Process Control System Inst'l (PCS 43) | [34 empty] | 0%
| CONEI-LSS43-1092 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.2.4 River Water Intake (LSS-44) | [35 empty] | 0%
| CONEI-LSS44-1001 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-LSS44-1008 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-LSS44-1091 | Lightning & Grounding | [34 empty] | 0%
| CONEI-LSS44-1010 | Lighting System Installation | [34 empty] | 0%
| CONEI-LSS44-1009 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-LSS44-1070 | MV Switchgear 6.6kV (MVP43) | [34 empty] | 0%
| CONEI-LSS44-1030 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-LSS44-1080 | Load Center (LVP44) | [34 empty] | 0%
| CONEI-LSS44-1040 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-LSS44-1090 | Transformer for River water intake 400kVA (TR 45) | [34 empty] | 0%
| CONEI-LSS44-1092 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.2.5 Sea Water Intake (LSS-45) | [35 empty] | 0%
| CONEI-LSS45-1001 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-LSS45-1008 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-LSS45-1091 | Lightning & Grounding | [34 empty] | 0%
| CONEI-LSS45-1010 | Lighting System Installation | [34 empty] | 0%
| CONEI-LSS45-1009 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-LSS45-1070 | MV Switchgear 6.6kV (MVP45) | [34 empty] | 0%
| CONEI-LSS45-1080 | Load Center (LVP45) | [34 empty] | 0%
| CONEI-LSS45-1090 | Tranformer for Sea water intake 100kVA (TR 46) | [34 empty] | 0%
| CONEI-LSS45-1030 | Distribution Panel, Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-LSS45-1040 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-LSS45-1092 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.2.8 River Water Intake System | [35 empty] | 0%
| CONEI-SYS4-1000 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-SYS4-1010 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-SYS4-1030 | Lighting System Installation | [34 empty] | 0%
| CONEI-SYS4-1020 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-SYS4-1080 | Telecommunication System Installation | [34 empty] | 0%
| CONEI-SYS4-1090 | Siren System Installation | [34 empty] | 0%
| CONEI-SYS4-1100 | ITV Sytem Installation | [34 empty] | 0%
| CONEI-SYS4-1040 | Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-SYS4-1050 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-SYS4-1120 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.2.9 Circulation Water System | [35 empty] | 0%
| CONEI-SYS4-1139 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-SYS4-1140 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-SYS4-1171 | Lighting System Installation | [34 empty] | 0%
| CONEI-SYS4-1170 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-SYS4-1190 | Telecommunication System Installation | [34 empty] | 0%
| CONEI-SYS4-1200 | Siren System Installation | [34 empty] | 0%
| CONEI-SYS4-1210 | ITV Sytem Installation | [34 empty] | 0%
| CONEI-SYS4-1150 | Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-SYS4-1160 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-SYS4-1211 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.2.1 Sea Water Intake System | [35 empty] | 0%
| CONEI-SEA-1000 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-SEA-1010 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-SEA-1016 | Lighting System Installation | [34 empty] | 0%
| CONEI-SEA-1015 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-SEA-1080 | Telecommunication System Installation | [34 empty] | 0%
| CONEI-SEA-1090 | Siren System Installation | [34 empty] | 0%
| CONEI-SEA-1100 | ITV Sytem Installation | [34 empty] | 0%
| CONEI-SEA-1020 | Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-SEA-1021 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-SEA-1120 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.2.2 Compressed Air & Distribution System | [35 empty] | 0%
| CONEI-AIR-1000 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-AIR-1010 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-AIR-1016 | Lighting System Installation | [34 empty] | 0%
| CONEI-AIR-1015 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-AIR-1060 | Telecommunication System Installation | [34 empty] | 0%
| CONEI-AIR-1070 | Siren System Installation | [34 empty] | 0%
| CONEI-AIR-1080 | ITV Sytem Installation | [34 empty] | 0%
| CONEI-AIR-1020 | Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-AIR-1030 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-AIR-1090 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.2.12 Fuel Oil Pumping and Distribution System | [35 empty] | 0%
| CONEI-FUEL-1000 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-FUEL-1010 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-FUEL-1030 | Lighting System Installation | [34 empty] | 0%
| CONEI-FUEL-1020 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-FUEL-1060 | Telecommunication System Installation | [34 empty] | 0%
| CONEI-FUEL-1070 | Siren System Installation | [34 empty] | 0%
| CONEI-FUEL-1080 | ITV Sytem Installation | [34 empty] | 0%
| CONEI-FUEL-1040 | Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-FUEL-1050 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-FUEL-1090 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.2.13 Oxygen Plant | [35 empty] | 0%
| CONEI-O2N2-1000 | Cable Ladder, Tray, and Conduit Fabrication | [34 empty] | 0%
| CONEI-O2N2-1010 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-O2N2-1030 | Lighting System Installation | [34 empty] | 0%
| CONEI-O2N2-1020 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-O2N2-1060 | Telecommunication System Installation | [34 empty] | 0%
| CONEI-O2N2-1070 | Siren System Installation | [34 empty] | 0%
| CONEI-O2N2-1080 | ITV Sytem Installation | [34 empty] | 0%
| CONEI-O2N2-1040 | Lighting Panel & Local Panel Installation | [34 empty] | 0%
| CONEI-O2N2-1050 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-O2N2-1090 | Cable Termination | [34 empty] | 0%
E259 | [36 empty] | 0%
|  | Transport material to site |  | 10% | 224103337.5 | 0.00655% | [30 empty] | 0.00655%
|  | Check elevation & orientation |  | 20% | 447864532.5 | 0.01309% | [30 empty] | 0.01309%
|  | Pre-assembly on the ground |  | 10% | 224103337.5 | 0.00655% | [30 empty] | 0.00655%
|  | Installation |  | 40% | 895386922.5 | 0.02617% | [30 empty] | 0.02617%
|  | Setting allignment |  | 10% | 224103337.5 | 0.00655% | [30 empty] | 0.00655%
|  | Final inspection |  | 10% | 224103337.5 | 0.00655% | [30 empty] | 0.00655%
0%
TANDA TANYA | [36 empty] | 0%
|  | Transport material to site |  | 10% | 119407732.5 | 0.00349% | [30 empty] | 0.00349%
|  | Check elevation & orientation |  | 20% | 238815465 | 0.00698% | [30 empty] | 0.00698%
|  | Pre-assembly on the ground |  | 10% | 119407732.5 | 0.00349% | [30 empty] | 0.00349%
|  | Installation |  | 40% | 476946645 | 0.01394% | [30 empty] | 0.01394%
|  | Setting allignment |  | 10% | 119407732.5 | 0.00349% | [30 empty] | 0.00349%
|  | Final inspection |  | 10% | 119407732.5 | 0.00349% | [30 empty] | 0.00349%
0%
| P3FH - 28 M.14.1.3 Non Process Building-Rev.1 | [35 empty] | 0%
| P3FH - 28 M.14.1.3.1 Administration Building | [35 empty] | 0%
| CONEI-ADM-1001 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-ADM-1050 | Lightning & Grounding | [34 empty] | 0%
| CONEI-ADM-1010 | Lighting System Installation | [34 empty] | 0%
| CONEI-ADM-1002 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-ADM-1030 | Panel Installation | [34 empty] | 0%
| CONEI-ADM-1040 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-ADM-1060 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.3.2 Warehouse | [35 empty] | 0%
| CONEI-WRHS-1001 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-WRHS-1050 | Lightning & Grounding | [34 empty] | 0%
| CONEI-WRHS-1010 | Lighting System Installation | [34 empty] | 0%
| CONEI-WRHS-1002 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-WRHS-1030 | Local Panel Installation | [34 empty] | 0%
| CONEI-WRHS-1040 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-WRHS-1060 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.3.3 Laboratory | [35 empty] | 0%
| CONEI-LAB-1001 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-LAB-1050 | Lightning & Grounding | [34 empty] | 0%
| CONEI-LAB-1010 | Lighting System Installation | [34 empty] | 0%
| CONEI-LAB-1002 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-LAB-1030 | Local Panel Installation | [34 empty] | 0%
| CONEI-LAB-1040 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-LAB-1060 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.3.4 Workshop | [35 empty] | 0%
| CONEI-WRKS-1001 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-WRKS-1050 | Lightning & Grounding | [34 empty] | 0%
| CONEI-WRKS-1010 | Lighting System Installation | [34 empty] | 0%
| CONEI-WRKS-1002 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-WRKS-1030 | Local Panel Installation | [34 empty] | 0%
| CONEI-WRKS-1040 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-WRKS-1060 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.3.5 Fire Station House | [35 empty] | 0%
| CONEI-FIRE-1001 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-FIRE-1050 | Lightning & Grounding | [34 empty] | 0%
| CONEI-FIRE-1010 | Lighting System Installation | [34 empty] | 0%
| CONEI-FIRE-1002 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-FIRE-1030 | Local Panel Installation | [34 empty] | 0%
| CONEI-FIRE-1040 | Instrument Device Equipment | [34 empty] | 0%
TANDA TANYA | CONEI-FIRE-1060 | Cable Termination | [34 empty] | 0%
|  | Transport material to site |  | 10% | 85877767.5 | 0.00251% | [30 empty] | 0.00251%
|  | Check elevation & orientation |  | 20% | 171755535 | 0.00502% | [30 empty] | 0.00502%
|  | Pre-assembly on the ground |  | 10% | 85877767.5 | 0.00251% | [30 empty] | 0.00251%
|  | Installation |  | 40% | 343511070 | 0.01004% | [30 empty] | 0.01004%
|  | Setting allignment |  | 10% | 85877767.5 | 0.00251% | [30 empty] | 0.00251%
|  | Final inspection |  | 10% | 85877767.5 | 0.00251% | [30 empty] | 0.00251%
| P3FH - 28 M.14.1.3.6 Gate House | [35 empty] | 0%
| CONEI-GATE-1001 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-GATE-1050 | Lightning & Grounding | [34 empty] | 0%
| CONEI-GATE-1010 | Lighting System Installation | [34 empty] | 0%
| CONEI-GATE-1002 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-GATE-1030 | Local Panel Installation | [34 empty] | 0%
| CONEI-GATE-1040 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-GATE-1060 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.3.7 Mosque | [35 empty] | 0%
| CONEI-MOSQUE-1001 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-MOSQUE-1050 | Lightning & Grounding | [34 empty] | 0%
| CONEI-MOSQUE-1010 | Lighting System Installation | [34 empty] | 0%
| CONEI-MOSQUE-1002 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-MOSQUE-1030 | Local Panel Installation | [34 empty] | 0%
| CONEI-MOSQUE-1040 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-MOSQUE-1060 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.3.8 Weight Bridge Building | [35 empty] | 0%
| CONEI-WBRG-1001 | Cable Ladder, Tray, and Conduit Installation | [34 empty] | 0%
| CONEI-WBRG-1050 | Lightning & Grounding | [34 empty] | 0%
| CONEI-WBRG-1010 | Lighting System Installation | [34 empty] | 0%
| CONEI-WBRG-1002 | Power, Control & Instrument Cables | [34 empty] | 0%
| CONEI-WBRG-1030 | Local Panel Installation | [34 empty] | 0%
| CONEI-WBRG-1040 | Instrument Device Equipment | [34 empty] | 0%
| CONEI-WBRG-1060 | Cable Termination | [34 empty] | 0%
| P3FH - 28 M.14.1.6 Road & Parking Area-Rev.1 | [35 empty] | 0%
| CONEI-INFRA-1010 | Lighting System Installation | [34 empty] | 0%
| CONEI-INFRA-1020 | Lighting Panel Installation | [34 empty] | 0%
| CONEI-INFRA-1030 | Cables | [34 empty] | 0%
| CONEI-INFRA-1040 | Cable Termination | [34 empty] | 0%
0%
| P3FH - 28 M. Insurance |  |  |  | 71579974567.5 | 2.092% | 0.0343% | 0.0343% | 0.0343% | 0.0343% | 0.0343% | 0.343% | 0.03813% | 0.0379% | 0.1925% | 0.01608% | 0.01608% | 0.01608% | 0.01608% | 0.01608% | 0.03884% | 0.04255% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.147%
G2 |  | 0 |  | 100% | 35205094680 | 1.029% | 2017-02-15: 0.0343%; 2017-03-17: 0.0343%; 2017-04-16: 0.0343%; 2017-05-16: 0.0343%; 2017-06-15: 0.0343%; 2017-07-15: 0.343%; 2017-08-14: 0.0343%; 2017-09-13: 0.0343%; 2017-10-13: 0.1886%; 2017-11-12: 0.01225%; 2017-12-12: 0.01225%; 2018-01-11: 0.01225%; 2018-02-10: 0.01225%; 2018-03-12: 0.01225%; 2018-04-11: 0.01225%; 2018-05-11: 0.01225% | 0.1715%
0%
G2 |  | 0 |  | 100% | 36374879887.5 | 1.063% | 2017-02-15: 0%; 2017-03-17: 0%; 2017-04-16: 0%; 2017-05-16: 0%; 2017-06-15: 0%; 2017-07-15: 0%; 2017-08-14: 0.00383%; 2017-09-13: 0.0036%; 2017-10-13: 0.00383%; 2017-11-12: 0.00383%; 2017-12-12: 0.00383%; 2018-01-11: 0.00383%; 2018-02-10: 0.00383%; 2018-03-12: 0.00383%; 2018-04-11: 0.02659%; 2018-05-11: 0.0303% | 0.9758%
0%
0%
| P3FH - 28 M. Commissioning |  |  |  | 57075527565 | 1.668% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5296% | 0.5296% | 0.5296% | 0% | 0% | 0.07926%
| P3FH - 28 M. Commissioning |  |  |  | 2711821455 | 0.07926% | [30 empty] | 0.07926% | bar: 2017-02-15 to 2019-07-05
E305 | P3FH - 28 M.15.1 Commissioning - System 1 | [35 empty] | 0
|  |  |  | 50% | 339063217.5 | 0.00991% | [30 empty] | 9.91e-05
|  |  |  | 40% | 271319002.5 | 0.00793% | [30 empty] | 7.93e-05
|  |  |  | 10% | 67744215 | 0.00198% | [30 empty] | 1.98e-05
| P3FH - 28 M.15.1.2 Ore Receiving Equipment | [35 empty] | 0
| P3FH - 28 M.15.1.2.1 No Load Test | [35 empty] | 0
| PRECOM-1100-1000 | Ore Receiving Equipment - No Load Test | [34 empty] | 0
| P3FH - 28 M.15.1.2.2 Load Test & PT | [35 empty] | 0
| COM-1100-1000 | Ore Receiving Equipment - Load Test & PT | [34 empty] | 0
| P3FH - 28 M.15.1.15.1.2 Ore Drying Equipment & Gas Treatment | [35 empty] | 0
| P3FH - 28 M.15.1.15.1.2.1 No Load Test | [35 empty] | 0
| PRECOM-1200-1000 | Ore Drying Equipment & Gas Treatment - No Load Test | [34 empty] | 0
| P3FH - 28 M.15.1.15.1.2.2 Load Test & PT | [35 empty] | 0
| COM-1200-1000 | Dryer - H.A.G Test | [34 empty] | 0
| COM-1200-1010 | Drying Castable ( 88 hours) | [34 empty] | 0
| COM-1200-1020 | Ore Dryer - Load & Storage / PT | [34 empty] | 0
| P3FH - 28 M.15.1.3 Dryer EP Dust Bin Equipment | [35 empty] | 0
| P3FH - 28 M.15.1.3.1 No Load Test | [35 empty] | 0
| PRECOM-1210-1000 | Dryer EP Dust Bin Room - No Load Test | [34 empty] | 0
| P3FH - 28 M.15.1.3.2 Load Test & PT | [35 empty] | 0
| COM-1210-1000 | Dryer EP Dust Bin Room (Transport to N1500) | [34 empty] | 0
| P3FH - 28 M.15.1.15.1.4 Pulverized Coal Feeding for Dryer | [35 empty] | 0
| P3FH - 28 M.15.1.15.1.4.1 No Load Test | [35 empty] | 0
| PRECOM-1220-1000 | PV Coal Feeding for Dryer - No Load Test | [34 empty] | 0
| P3FH - 28 M.15.1.15.1.4.2 Load Test & PT | [35 empty] | 0
| COM-1220-1000 | PV Coal Feeding for Dryer - H.A.G Test | [34 empty] | 0
| COM-1220-1010 | PV Coal Feeding for Dryer - Load & Storage / PT | [34 empty] | 0
| P3FH - 28 M.15.1.5 Conditioned Ore Storage & Transport Conditioned Ore | [35 empty] | 0
| P3FH - 28 M.15.1.5.15.1.5 Conditioned Ore Storage | [35 empty] | 0
| P3FH - 28 M.15.1.5.15.1.5.1 No Load Test | [35 empty] | 0
| PRECOM-1300-1000 | Conditioned Ore Storage - No Load Test | [34 empty] | 0
| P3FH - 28 M.15.1.5.15.1.5.2 Load Test & PT | [35 empty] | 0
| COM-1320-1000 | Conditioned Ore Storage - Load Test | [34 empty] | 0
| COM-1320-1010 | Conditioned Ore Storage - Storage | [34 empty] | 0
| P3FH - 28 M.15.1.5.15.1.6 Transport Conditioned Ore | [35 empty] | 0
| P3FH - 28 M.15.1.5.15.1.6.1 No Load Test | [35 empty] | 0
| PRECOM-1310-1000 | Transport Conditioned Ore - No Load Test | [34 empty] | 0
| P3FH - 28 M.15.1.5.15.1.6.2 Load Test & PT | [35 empty] | 0
| COM-1310-1000 | Transport Conditioned Ore - Load Test & PT | [34 empty] | 0
| P3FH - 28 M.15.1.15.1.7 Ore Mixing Equipment | [35 empty] | 0
| P3FH - 28 M.15.1.15.1.7.1 No Load Test | [35 empty] | 0
| PRECOM-1400-1000 | Ore Mixing - No Load Test Indoor | [34 empty] | 0
| PRECOM-1400-1010 | Ore Mixing - No Load Test BC | [34 empty] | 0
| P3FH - 28 M.15.1.15.1.7.2 Load Test & PT | [35 empty] | 0
| COM-1400-1000 | Ore Mixing - Receiving Materials to Hopper | [34 empty] | 0
| COM-1400-1010 | Ore Mixing - Weighing Feeder Calculation Test | [34 empty] | 0
| COM-1400-1020 | Ore Mixing - Load Test & PT | [34 empty] | 0
| P3FH - 28 M.15.1.15.1.8 Dust Briquetting Equipment | [35 empty] | 0
| P3FH - 28 M.15.1.15.1.8.1 No Load Test | [35 empty] | 0
| PRECOM-1500-1000 | Dust Briquetting - No Load Test | [34 empty] | 0
| P3FH - 28 M.15.1.15.1.8.2 Load Test & PT | [35 empty] | 0
| COM-1500-1000 | Dust Briquetting - Receiving Dryer Dust | [34 empty] | 0
| COM-1500-1010 | Dust Briquetting - Briquetting Test | [34 empty] | 0
| P3FH - 28 M.15.1.4 Rotary Kiln Equipment | [35 empty] | 0
| P3FH - 28 M.15.1.4.1 No Load Test | [35 empty] | 0
| PRECOM-1600-1000 | Rotary Kiln - No Load Test | [34 empty] | 0
| P3FH - 28 M.15.1.4.2 Load Test & PT | [35 empty] | 0
| COM-1600-1000 | Rotary Kiln - Load Test | [34 empty] | 0
| COM-1600-1010 | Rotary Kiln - PT | [34 empty] | 0
| P3FH - 28 M.15.1.8 Scoop Feeder Equipment | [35 empty] | 0
| P3FH - 28 M.15.1.8.1 No Load Test | [35 empty] | 0
| PRECOM-1610-1000 | Scoop Feeder - No Load Test | [34 empty] | 0
| P3FH - 28 M.15.1.8.2 Load Test & PT | [35 empty] | 0
| COM-1610-1000 | Scoop Feeder - Load Test | [34 empty] | 0
| P3FH - 28 M.15.1.6 Exhaust Gas Treatment Equipment | [35 empty] | 0
| P3FH - 28 M.15.1.6.1 No Load Test | [35 empty] | 0
| PRECOM-1700-1000 | Exhaust Gas Treatment - No Load Test | [34 empty] | 0
| P3FH - 28 M.15.1.6.2 Load Test & PT | [35 empty] | 0
| COM-1700-1000 | Exhaust Gas Treatment - Load Test & PT | [34 empty] | 0
| P3FH - 28 M.15.1.15.1.12 Coal Firing Equipment | [35 empty] | 0
| P3FH - 28 M.15.1.15.1.12.1 No Load Test | [35 empty] | 0
| PRECOM-1820-1000 | Coal Firing - No Load Test | [34 empty] | 0
| P3FH - 28 M.15.1.15.1.12.2 Load Test & PT | [35 empty] | 0
| COM-1820-1000 | Coal Firing - HAG Test | [34 empty] | 0
| COM-1820-1010 | Coal Firing - Load Test by Limestone | [34 empty] | 0
| COM-1820-1020 | Coal Firing - Load Test by Coal / PT | [34 empty] | 0
| P3FH - 28 M.15.1.7 Surge Hopper Equipment | [35 empty] | 0
| P3FH - 28 M.15.1.7.1 No Load Test | [35 empty] | 0
| PRECOM-2100-1000 | Surge Hopper Equipment - No Load Test | [34 empty] | 0
| P3FH - 28 M.15.1.7.2 Load Test & PT | [35 empty] | 0
| COM-2100-1000 | Surge Hopper Equipment - Load Test / PT | [34 empty] | 0
E305 | P3FH - 28 M.15.2 Commissioning - System 2 | [35 empty] | 0
|  |  |  | 50% | 339063217.5 | 0.00991% | [30 empty] | 9.91e-05
|  |  |  | 40% | 271319002.5 | 0.00793% | [30 empty] | 7.93e-05
|  |  |  | 10% | 67744215 | 0.00198% | [30 empty] | 1.98e-05
| P3FH - 28 M.15.2.14.7.2 ESF - Calcine Transfer | [35 empty] | 0
| P3FH - 28 M.15.2.14.7.2.1 No Load Test ESF - Calcine Transfer | [35 empty] | 0
| PRECOM-2200-1000 | Hot Charge Crane | [34 empty] | 0
| PRECOM-2200-1050 | Slag Granulation System | [34 empty] | 0
| PRECOM-2200-1040 | Off Gas System | [34 empty] | 0
| PRECOM-2200-1010 | Furnace Charging System | [34 empty] | 0
| PRECOM-2200-1020 | Tapping Equipment | [34 empty] | 0
| PRECOM-2200-1030 | Cooling System | [34 empty] | 0
| P3FH - 28 M.15.2.14.7.2.2 Load Test ESF - Calcine Transfer | [35 empty] | 0
| COM-2200-1000 | System 2 - ESF-Calcine Transfer | [34 empty] | 0
| P3FH - 28 M.15.2.1 ESF - Crucible | [35 empty] | 0
| P3FH - 28 M.15.2.1.2 Load Test ESF - Crucible | [35 empty] | 0
| COM-2300-1000 | System 2 - ESF-Crucible | [34 empty] | 0
E305 | P3FH - 28 M.15.3 Commissioning - System 3 | [35 empty] | 0
|  |  |  | 50% | 339063217.5 | 0.00991% | [30 empty] | 9.91e-05
|  |  |  | 40% | 270976860 | 0.00792% | [30 empty] | 7.92e-05
|  |  |  | 10% | 67744215 | 0.00198% | [30 empty] | 1.98e-05
| P3FH - 28 M.15.3.1 No Load Test | [35 empty] | 0
| PRECOM-3000-1000 | System 3 - Refinery | [34 empty] | 0
| P3FH - 28 M.15.3.2 Load Test | [35 empty] | 0
| COM-3000-1000 | System 3 - Refinery | [34 empty] | 0
E305 | P3FH - 28 M.15.4 Commissioning - System 4 | [35 empty] | 0
|  |  |  | 50% | 339063217.5 | 0.00991% | [30 empty] | 9.91e-05
|  |  |  | 40% | 270976860 | 0.00792% | [30 empty] | 7.92e-05
|  |  |  | 10% | 67744215 | 0.00198% | [30 empty] | 1.98e-05
| P3FH - 28 M.15.4.1 No Load Test | [35 empty] | 0
| PRECOM-4000-1000 | System 4 - Utility Supply | [34 empty] | 0
| P3FH - 28 M.15.4.2 Load Test | [35 empty] | 0
| COM-4000-1000 | System 4 - Utility Supply | [34 empty] | 0
| P3FH - 28 M. Spare Part |  |  |  | 54363706110 | 1.589% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5296% | 0.5296% | 0.5296% | 0% | 0% | 0
0
|  |  | Sparepart | 100% | 54363706110 | 1.589% | 2019-03-07: 0.0052964; 2019-04-06: 0.0052964; 2019-05-06: 0.0052964 | 0
0
0
| PROGRESS PLAN PER MONTH |  |  |  | 3.4214e+12 | 100% | 0.2999% | 0.8859% | 0.45% | 2.519% | 3.695% | 4.423% | 4.609% | 4.501% | 3.917% | 5.511% | 4.057% | 4.804% | 6.799% | 7.56% | 6.77% | 4.462% | 5.196% | 5.992% | 5.406% | 6.382% | 3.702% | 3.513% | 1.597% | 0.3439% | 0.1923% | 0.7091% | 0.7057% | 0.7302% | 0.1754% | 0.09412%
| ACCUMULATED PROGRESS PLAN PER MONTH |  |  |  |  | 0% | 0.2999% | 1.186% | 1.636% | 4.155% | 7.85% | 12.27% | 16.88% | 21.38% | 25.3% | 30.81% | 34.87% | 39.67% | 46.47% | 54.03% | 60.8% | 65.26% | 70.46% | 76.45% | 81.86% | 88.24% | 91.94% | 95.45% | 97.05% | 97.39% | 97.59% | 98.29% | 99% | 99.73% | 99.91% | 100%
| PROGRESS REALIZATION PER MONTH | [5 empty] | 2017-02-15: 3.746%; 2017-03-17: 1.279%; 2017-04-16: 2.839%; 2017-05-16: 0.8986%; 2017-06-15: 1.59%; 2017-07-15: 2.803%; 2017-08-14: 3.494%; 2017-09-13: 5.604%; 2017-10-13: 3.512%; 2017-11-12: 4.788%; 2017-12-12: 6.504%; 2018-01-11: 3.202%; 2018-02-10: 6.211%; 2018-03-12: 7.145%; 2018-04-11: 4.695%; 2018-05-11: 2.663%; 2018-06-10: 5.643% | -0.66617
| ACCUMULATED PROGRESS REALIZATION PER MONTH |  |  |  |  | 0% | 2017-02-15: 3.746%; 2017-03-17: 5.025%; 2017-04-16: 7.864%; 2017-05-16: 8.762%; 2017-06-15: 10.35%; 2017-07-15: 13.16%; 2017-08-14: 16.65%; 2017-09-13: 22.25%; 2017-10-13: 25.77%; 2017-11-12: 30.55%; 2017-12-12: 37.06%; 2018-01-11: 40.26%; 2018-02-10: 46.47%; 2018-03-12: 53.62%; 2018-04-11: 58.31%; 2018-05-11: 60.97%; 2018-06-10: 66.62% | -5.0743
| DEVIATION | [5 empty] | 2017-02-15: 3.446%; 2017-03-17: 3.839%; 2017-04-16: 6.228%; 2017-05-16: 4.608%; 2017-06-15: 2.503%; 2017-07-15: 0.8826%; 2017-08-14: -0.232%; 2017-09-13: 0.8707%; 2017-10-13: 0.466%; 2017-11-12: -0.2575%; 2017-12-12: 2.19%; 2018-01-11: 0.5883%; 2018-02-10: 0.0004082%; 2018-03-12: -0.4148%; 2018-04-11: -2.489%; 2018-05-11: -4.289%; 2018-06-10: -3.841%
P3FH-PM-9000-PRG-1001C
3421425000000
[6 empty] | 100% | 2017-02-15: 3.591%
0
Note on G2190: ANDRY: diambil dari total bobot procurement sistem 3 x 25%
Note on G3074: ANDRY: diambil dari % pekerjaan pipa total sistem 3
Note on E3075: ANDRY: tidak ada PO, sehingga 20%+60%

## Sheet1
Back up Evident Progress Commercial September 2017
No | Uraian | Progress | PIC |  | Bentuk Eviden / Back up Dokumen
A | Project Management & Engineering
A.1 | Project Managemen | 3.333% | HO Jkt | Sabar/Bayu | Kontrak sewa kantor jakarta, gaji karyawan unprice, bukti pembayaran air, listrik, internet (unprice)
A.2 | Temporary Facility
1 | Mess | 3.333% | HO Jkt | Sabar/Bayu | Kontrak sewa mess jkt & site camp
2 | Internet | 3.333% | HO Jkt | Sabar/Bayu | bukti pembayaran internet site office (unprice)
3 | Electricity Distribution | 3.333% | HO Jkt | Sabar/Bayu | bukti pembayaran listrik (unprice)
4 | Water Distribution | 3.333% | HO Jkt | Sabar/Bayu | bukti pembayaran air (unprice)
5 | Camp | 25% | SO Buli | Pak Teguh | BA Penyelesaian Pekerjaan + foto
6 | Site Office | 50% | SO Buli | Pak Teguh | BA Penyelesaian Pekerjaan + foto
7 | Workshop | 50% | SO Buli | Pak Teguh | BA Penyelesaian Pekerjaan + foto
8 | Acces Road | 100% | SO Buli | Pak Teguh | BA Penyelesaian Pekerjaan, Perhitungan Progress + foto
9 | Temporary Fencing | 70% | SO Buli | Pak Teguh | BA Penyelesaian Pekerjaan, Perhitungan Progress + foto
A.3 | Engineering | 11.15% | HO Jkt | Adrian | Transmittal documen/drawing approved, approved as note dan approved as not ke approved
B | Procurement & Transportation
B.1 | Material Onshore Equipment
1 | Feed Pump for MFO & HSD | 20% | HO Jkt | Proc./Dita | Purchase Order - PO/LOI ke vendor yg telah ditanda tangani (wika & vendor) un price
2 | MV Switchgear 6.6 kV | 20% | HO Jkt | Proc./Dita | Purchase Order - PO/LOI ke vendor yg telah ditanda tangani (wika & vendor) un price
3 | Power Transformer 6.6 / 0.4 kV | 20% | HO Jkt | Proc./Dita | Purchase Order - PO/LOI ke vendor yg telah ditanda tangani (wika & vendor) un price
4 | Valve Piping | 20% | HO Jkt | Proc./Dita | Purchase Order - PO/LOI ke vendor yg telah ditanda tangani (wika & vendor) un price
5 | Remaining Rebar | 80% | SO Buli | Mat.Con/Syafrudin | Dokumen Shipment dan Material Receiving Report + photo
6 | Remaining Pile (pancang terendam) | 11.28% | SO Buli | Mat.Con/Syafrudin | MOM/Surat & lokasi penggunaan material pancang terendam
7 | Furnace Shell & Roof | 20% | HO Jkt | Proc./Dita | Purchase Order - PO/LOI ke vendor yg telah ditanda tangani (wika & vendor) un price
C | Construction
C.1 | Construction Work
1 | Site Clearing & Ground Improvement | 10% | SO Buli | Pak Teguh | BA Penyelesaian Pekerjaan, Perhitungan Progress + foto
2 | Piling Work-ESF Bldg, Surge hopper dll |  | SO Buli | Pak Teguh | Inspection Report, perhitungan progress, gambar dan foto
3 | Rebar Work-kiln, dryer, non proces dll |  | SO Buli | Pak Teguh | Inspection Report, perhitungan progress, gambar dan foto
4 | Concrete Work-kiln, dryer, non proces dll |  | SO Buli | Pak Teguh | Inspection Report, perhitungan progress, gambar dan foto
C.2 | Insurance & Others fee
1 | Asuransi BPJS dan Asuransi lainnya | 3.333% | HO Jkt | Sabar/Bayu | bukti pembayaran polis asuransi